# PROJECT MANAGEMENT PLAN (PMP)

PROYEK P-FNE-08: ADVANCED & AUTONOMOUS ENTERPRISE
SUPER ERP FARM NATION ENTERPRISE (FNE)

## BAB 1: PENDAHULUAN

### 1.1. TUJUAN DOKUMEN

Dokumen Project Management Plan (PMP) ini disusun dengan tujuan:

- Memberikan panduan komprehensif untuk seluruh siklus hidup proyek P-FNE-08, mulai dari inisiasi, perencanaan, pelaksanaan, pengendalian, hingga penutupan.

- Menjadi acuan utama bagi seluruh tim proyek dalam menjalankan tugas dan tanggung jawab masing-masing, serta menjadi referensi dalam pengambilan keputusan.

- Memastikan ketercapaian tujuan proyek sesuai dengan ruang lingkup, jadwal, biaya, dan mutu yang telah ditetapkan.

- Mengintegrasikan seluruh area manajemen (lingkup, waktu, biaya, mutu, sumber daya, komunikasi, risiko, pengadaan, dan stakeholder) dalam satu dokumen yang terkoordinasi.

- Menyediakan mekanisme pengendalian yang jelas untuk memantau kemajuan proyek dan melakukan tindakan korektif jika diperlukan.

- Menjadi alat komunikasi antara tim proyek, sponsor, steering committee, dan seluruh stakeholder terkait.

### 1.2. GAMBARAN UMUM PROYEK

#### 1.2.1. Identitas Proyek

| Aspek | Rincian |
| --- | --- |
| Nama Proyek | P-FNE-08: Advanced & Autonomous Enterprise |
| Nama Singkat | P-FNE-08 atau Autonomus Enterprise |
| Program | Super ERP Farm Nation Enterprise (FNE) |
| Status | Proyek Baru |
| Lokasi | [Lokasi Tim Pengembangan] |

#### 1.2.2. Deskripsi Proyek

Proyek P-FNE-08 merupakan puncak dari ekosistem Super ERP Farm Nation Enterprise, yang menghubungkan dunia fisik dengan dunia digital melalui Internet of Things (IoT) dan menciptakan representasi digital (Digital Twin) dari seluruh operasi perusahaan. Proyek ini memungkinkan simulasi berbagai skenario bisnis, optimasi otomatis, dan pengambilan keputusan yang didukung oleh kecerdasan buatan secara real-time.

Proyek ini mengintegrasikan 8 proyek turunan FNE ke dalam satu ekosistem digital yang kohesif dengan pendekatan modular, API-first, event-driven, dan cloud-native.

#### 1.2.3. Tujuan Utama Proyek

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | IoT Integration | Mengintegrasikan perangkat IoT (sensor dan aktual) untuk monitoring real-time dan kontrol perangkat. |
| 2 | Digital Twin | Membangun Digital Twin dari aset dan proses bisnis kritis (Farm, Machine, Warehouse) yang tersinkronisasi dengan data aktual. |
| 3 | Simulation Engine | Menyediakan kemampuan simulasi dan what-if analysis untuk 5 use case kritis (Crop Yield, Production Capacity, Inventory, Supply Chain Disruption, Expansion). |
| 4 | Optimasi Otonom | Mengoptimalkan proses bisnis secara otomatis berbasis data real-time dengan rule engine dan AI. |
| 5 | Enterprise Otonom | Mewujudkan enterprise yang adaptif dan otonom (sebagian) dengan human-in-the-loop untuk keputusan berisiko tinggi. |

#### 1.2.4. Ruang Lingkup Singkat

| Komponen | Lingkup |
| --- | --- |
| IoT Integration | Device registration, telemetry ingestion, threshold alert, command sending, device health monitoring, IoT dashboard |
| Digital Twin | Twin creation (3 jenis), state synchronization, historical state, what-if analysis, twin viewer |
| Simulation Engine | Scenario management, 5 use case simulasi, optimization module, scenario comparison, simulation workbench |
| Autonomous | Rule engine, recommendation generator, approval handler, action executor, feedback loop |
| Dashboard | IoT dashboard, Digital Twin dashboard, Simulation dashboard, Autonomy dashboard |
| Reporting | 12 jenis laporan (IoT, Twin, Simulation, Autonomy, System) |
| Integration | ERP connector (P-FNE-01 s.d P-FNE-07), AI/ML Service integration, external API (Weather) |

#### 1.2.5. Durasi dan Tim

| Aspek | Rincian |
| --- | --- |
| Durasi Estimasi | 4-5 bulan (20 minggu) |
| Jumlah Tim | 12-14 orang |
| Komposisi Tim | 1 PM, 1 BA, 2 IoT Engineer, 2 Backend Twin, 2 Backend Simulation, 2 Backend Autonomous, 2 Frontend, 1 Data Scientist, 1 QA, 1 DevOps |
| Ketergantungan | P-FNE-01 (Foundation), P-FNE-07 (Intelligence Platform), P-FNE-02 s.d P-FNE-06 (Data Sources) |

#### 1.2.6. Deliverables Utama

| Deliverable | Deskripsi |
| --- | --- |
| Sistem IoT | Device registration, telemetry ingestion, alert engine, command service, IoT dashboard |
| Digital Twin | 3 jenis twin (Farm, Machine, Warehouse) dengan state synchronization dan viewer |
| Simulation Engine | 5 use case simulasi berfungsi dengan accuracy ≥ 85%, scenario comparison, optimization |
| Autonomous System | Rule engine, recommendation generator, approval workflow, feedback loop |
| Dashboard | 4 dashboard terintegrasi (IoT, Twin, Simulation, Autonomy) |
| Dokumentasi | Technical documentation, API documentation, User manual, Admin guide |
| Training | Training materials dan training session untuk end users dan admin |

### 1.3. TUJUAN PROYEK (SMART)

| No | Tujuan | SMART Criteria | Metrik |
| --- | --- | --- | --- |
| T1 | Mengintegrasikan IoT device management | Specific: Registrasi dan autentikasi perangkat, telemetry ingestion, alert Measurable: ≥ 10.000 msg/detik throughput, ≤ 5 detik latency Achievable: Dengan teknologi Kafka dan TimescaleDB Relevant: Fondasi untuk real-time monitoring Time-bound: Selesai minggu ke-8 | Throughput ≥ 10.000 msg/detik Latency ≤ 5 detik |
| T2 | Membangun 3 jenis Digital Twin | Specific: Farm Twin, Machine Twin, Warehouse Twin dengan state sync Measurable: State update ≤ 1 menit, historical state tersedia Achievable: Dengan event-driven architecture Relevant: Representasi digital aset kritis Time-bound: Selesai minggu ke-10 | 3 jenis twin aktif State update ≤ 1 menit |
| T3 | Menyediakan 5 use case simulasi | Specific: Crop Yield, Production Capacity, Inventory, Supply Chain Disruption, Expansion Measurable: Accuracy ≥ 85%, execution ≤ 5 menit Achievable: Dengan SimPy dan integrasi AI Relevant: Analisis skenario bisnis Time-bound: Selesai minggu ke-14 | 5 use case berfungsi Accuracy ≥ 85% Execution ≤ 5 menit |
| T4 | Mewujudkan autonomous capabilities | Specific: Rule engine, recommendation, approval workflow, feedback loop Measurable: Automated alerting, recommendation accuracy terukur Achievable: Dengan rule engine dan AI integration Relevant: Pengambilan keputusan otomatis Time-bound: Selesai minggu ke-16 | Rekomendasi otomatis Feedback loop berjalan |
| T5 | Menyediakan dashboard terintegrasi | Specific: 4 dashboard (IoT, Twin, Simulation, Autonomy) Measurable: Real-time update, akses dari web dan mobile Achievable: Dengan React dan WebSocket Relevant: Visibilitas operasional Time-bound: Selesai minggu ke-17 | 4 dashboard aktif Real-time update |

### 1.4. STRUKTUR ORGANISASI PROYEK

#### 1.4.1. Organigram Proyek

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                            PROJECT SPONSOR                                 │

│                         [Nama Sponsor/CEO FNE]                             │

└────────────────────────────────────┬────────────────────────────────────────┘

│

┌────────────────────────────────────┼────────────────────────────────────────┐

│                            PROJECT MANAGER                                 │

│                            [Nama PM]                                       │

│                         (Manajemen Proyek)                                 │

└──────────┬──────────┬──────────┬───┼─────┬──────────┬──────────┬──────────┘

│          │          │   │     │          │          │

▼          ▼          ▼   ▼     ▼          ▼          ▼

┌──────────────┐ ┌───────────┐ ┌─────────┐ ┌────────────┐ ┌────────────┐

│   IoT Lead   │ │ Twin Lead │ │Sim Lead │ │  Auto Lead │ │  QA Lead   │

│  (2 org)     │ │  (2 org)  │ │ (2 org) │ │  (2 org)   │ │  (1 org)   │

└──────────────┘ └───────────┘ └─────────┘ └────────────┘ └────────────┘

│          │          │         │            │

▼          ▼          ▼         ▼            ▼

┌──────────────┐ ┌───────────┐ ┌─────────┐ ┌────────────┐ ┌────────────┐

│  Business    │ │ Frontend  │ │  Data   │ │  DevOps    │ │  Security  │

│  Analyst    │ │  (2 org)  │ │Scientist│ │  (1 org)   │ │  (1 org)   │

│  (1 org)    │ │           │ │ (1 org) │ │            │ │            │

└──────────────┘ └───────────┘ └─────────┘ └────────────┘ └────────────┘

#### 1.4.2. Deskripsi Peran dan Tanggung Jawab

| Peran | Jumlah | Kualifikasi Minimal | Tanggung Jawab |
| --- | --- | --- | --- |
| Project Sponsor | 1 | CEO/Direktur FNE | - Menyetujui project charter dan PMP - Menyediakan sumber daya - Membantu mengatasi isu strategis - Menyetujui perubahan scope signifikan - Menyetujui penutupan proyek |
| Project Manager | 1 | Sertifikasi PMP/PRINCE2, pengalaman 5+ tahun di project software | - Mengelola seluruh aspek proyek - Menyusun dan mengupdate PMP - Monitoring progress dan reporting - Mengelola risiko dan issue - Mengelola komunikasi stakeholder - Mengkoordinasikan tim proyek |
| Business Analyst | 1 | Pengalaman 3+ tahun di ERP/AgriTech | - Mengumpulkan dan memvalidasi requirements - Menyusun user stories dan acceptance criteria - Memfasilitasi UAT - Menjadi jembatan antara tim teknis dan user - Mengelola product backlog |
| IoT Lead | 1 | Pengalaman IoT, MQTT, Kafka, TimescaleDB | - Memimpin pengembangan IoT service - Merancang arsitektur IoT - Memastikan throughput dan latency terpenuhi - Mengkoordinasikan tim IoT |
| IoT Engineer | 2 | Pengalaman Java/Node.js, MQTT, IoT | - Mengembangkan device registration - Mengimplementasikan telemetry ingestion - Membangun alert engine - Mengembangkan command service |
| Twin Lead | 1 | Pengalaman Digital Twin, Spring Boot, PostgreSQL | - Memimpin pengembangan Digital Twin service - Merancang data model dan state management - Mengkoordinasikan sinkronisasi data |
| Backend Engineer (Twin) | 2 | Pengalaman Spring Boot, PostgreSQL, Neo4j | - Mengembangkan twin CRUD - Mengimplementasikan sync engine - Membangun what-if analysis - Mengelola graph relationships |
| Sim Lead | 1 | Pengalaman Simulation, Python (SimPy), Data Science | - Memimpin pengembangan simulation engine - Merancang 5 use case simulasi - Mengkoordinasikan optimasi |
| Backend Engineer (Sim) | 2 | Pengalaman Python, SimPy, SciPy, Celery | - Mengembangkan scenario management - Mengimplementasikan simulation runner - Membangun optimization module - Mengembangkan scenario comparison |
| Auto Lead | 1 | Pengalaman Rule Engine, AI Integration, Kafka | - Memimpin pengembangan autonomous service - Merancang rule engine dan workflow - Mengkoordinasikan integrasi AI |
| Backend Engineer (Auto) | 2 | Pengalaman Spring Boot, Drools, Kafka | - Mengembangkan rule engine - Mengimplementasikan recommendation - Membangun approval handler - Mengembangkan feedback loop |
| Frontend Lead | 1 | Pengalaman React, TypeScript, Three.js | - Memimpin pengembangan frontend - Merancang arsitektur UI - Mengkoordinasikan dashboard dan viewer |
| Frontend Engineer | 2 | Pengalaman React, TypeScript, Chart.js | - Mengembangkan IoT dashboard - Membangun twin viewer (2D/3D) - Mengembangkan simulation workbench - Membangun autonomy dashboard |
| Data Scientist | 1 | Pengalaman AI/ML, Forecasting, Python | - Mengembangkan model prediktif - Mengkalibrasi simulasi dengan data aktual - Membantu optimasi parameter - Mengembangkan feedback loop |
| QA Engineer | 1 | Pengalaman Automated Testing, Performance Testing | - Menyusun test plan dan test cases - Mengembangkan automated testing - Melakukan performance testing - Memfasilitasi UAT |
| DevOps Engineer | 1 | Pengalaman Kubernetes, CI/CD, Cloud | - Mengelola infrastruktur cloud - Menyiapkan CI/CD pipeline - Memantau sistem dan logging - Mengelola security dan backup |
| Security Engineer | 1 | Pengalaman Security, Penetration Test | - Menyusun security requirement - Melakukan vulnerability assessment - Melakukan penetration test - Mengelola security monitoring |

#### 1.4.3. Matriks Tanggung Jawab (RACI)

| Aktivitas | Sponsor | PM | BA | IoT Lead | Twin Lead | Sim Lead | Auto Lead | DevOps | QA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Charter | A | R | C | C | C | C | C | C | C |
| PMP Development | C | R | C | C | C | C | C | C | C |
| Requirements Gathering | I | R | R | C | C | C | C | C | C |
| Architecture Design | I | R | C | R | R | R | R | C | C |
| IoT Development | I | R | C | R | C | C | C | C | C |
| Digital Twin Development | I | R | C | C | R | C | C | C | C |
| Simulation Development | I | R | C | C | C | R | C | C | C |
| Autonomous Development | I | R | C | C | C | C | R | C | C |
| Dashboard Development | I | R | C | C | C | C | C | C | C |
| System Integration | I | R | C | C | C | C | C | R | C |
| Testing & QA | I | R | C | C | C | C | C | C | R |
| UAT | I | C | R | C | C | C | C | C | C |
| Deployment | I | R | C | C | C | C | C | R | C |
| Risk Management | I | R | C | C | C | C | C | C | C |
| Reporting | I | R | C | C | C | C | C | C | C |
| Project Closure | A | R | C | C | C | C | C | C | C |

Legend: R = Responsible, A = Accountable, C = Consulted, I = Informed

### 1.5. DEFINISI DAN SINGKATAN

| Singkatan | Kepanjangan | Deskripsi |
| --- | --- | --- |
| AI/ML | Artificial Intelligence / Machine Learning | Kecerdasan buatan dan pembelajaran mesin |
| API | Application Programming Interface | Antarmuka pemrograman aplikasi |
| BA | Business Analyst | Analis bisnis |
| BFF | Backend for Frontend | Layanan backend khusus untuk frontend |
| BI | Business Intelligence | Intelijen bisnis |
| CAPEX | Capital Expenditure | Pengeluaran modal |
| CCB | Change Control Board | Dewan pengendali perubahan |
| CI/CD | Continuous Integration / Continuous Deployment | Integrasi dan deployment berkelanjutan |
| CRM | Customer Relationship Management | Manajemen hubungan pelanggan |
| DT | Digital Twin | Representasi digital aset fisik |
| ELK | Elasticsearch, Logstash, Kibana | Stack untuk logging dan analisis log |
| ERP | Enterprise Resource Planning | Perencanaan sumber daya perusahaan |
| ETL | Extract, Transform, Load | Proses ekstraksi, transformasi, dan pemuatan data |
| EVM | Earned Value Management | Manajemen nilai hasil |
| FNE | Farm Nation Enterprise | Nama program ERP pertanian |
| gRPC | Google Remote Procedure Call | Protokol komunikasi RPC |
| HCM | Human Capital Management | Manajemen modal manusia |
| IAM | Identity and Access Management | Manajemen identitas dan akses |
| IoT | Internet of Things | Internet untuk segala |
| K8s | Kubernetes | Platform orchestration container |
| KPI | Key Performance Indicator | Indikator kinerja utama |
| MFA | Multi-Factor Authentication | Autentikasi multi-faktor |
| MQTT | Message Queuing Telemetry Transport | Protokol komunikasi untuk IoT |
| MVP | Minimum Viable Product | Produk minimum yang layak |
| NFR | Non-Functional Requirement | Kebutuhan non-fungsional |
| PM | Project Manager | Manajer proyek |
| PMBOK | Project Management Body of Knowledge | Panduan manajemen proyek |
| PMIS | Project Management Information System | Sistem informasi manajemen proyek |
| PMP | Project Management Plan | Rencana manajemen proyek |
| QA | Quality Assurance | Jaminan kualitas |
| RBAC | Role-Based Access Control | Kontrol akses berbasis peran |
| REST | Representational State Transfer | Arsitektur API |
| RFQ | Request for Quotation | Permintaan penawaran |
| SLA | Service Level Agreement | Perjanjian tingkat layanan |
| SRE | Site Reliability Engineering | Rekayasa keandalan situs |
| SSO | Single Sign-On | Login tunggal |
| SSOT | Single Source of Truth | Sumber kebenaran tunggal |
| SUS | System Usability Scale | Skala kegunaan sistem |
| UAT | User Acceptance Testing | Pengujian penerimaan pengguna |
| UI | User Interface | Antarmuka pengguna |
| UOM | Unit of Measurement | Satuan ukur |
| WBS | Work Breakdown Structure | Struktur rincian pekerjaan |
| WIP | Work in Progress | Pekerjaan dalam proses |

### 1.6. DOKUMEN TERKAIT

| No | Dokumen | Deskripsi | Lokasi |
| --- | --- | --- | --- |
| 1 | Project Charter | Dokumen otorisasi proyek | [Link/Drive] |
| 2 | Business Case | Justifikasi bisnis proyek | [Link/Drive] |
| 3 | Requirements Document | Dokumentasi kebutuhan fungsional dan non-fungsional | [Link/Drive] |
| 4 | Architecture Design Document | Desain arsitektur sistem | [Link/Drive] |
| 5 | Technical Specification | Spesifikasi teknis detail | [Link/Drive] |
| 6 | Database Design Document | Desain database | [Link/Drive] |
| 7 | API Documentation | Dokumentasi API | [Link/Drive] |
| 8 | Test Plan | Rencana pengujian | [Link/Drive] |
| 9 | Deployment Plan | Rencana deployment | [Link/Drive] |
| 10 | User Manual | Manual pengguna | [Link/Drive] |
| 11 | Admin Guide | Panduan administrator | [Link/Drive] |
| 12 | Training Materials | Materi pelatihan | [Link/Drive] |
| 13 | Risk Register | Daftar risiko proyek | [Link/Drive] |
| 14 | Stakeholder Register | Daftar stakeholder | [Link/Drive] |
| 15 | Quality Management Plan | Rencana manajemen mutu | [Link/Drive] |

### 1.7. ASUMSI DAN KETERGANTUNGAN

#### 1.7.1. Asumsi Proyek

| No | Asumsi | Dampak jika Tidak Terpenuhi |
| --- | --- | --- |
| A-001 | Tim memiliki akses ke infrastruktur cloud yang dibutuhkan | Delay pengembangan dan deployment |
| A-002 | P-FNE-01 (Foundation) tersedia dan stabil pada minggu ke-3 | Integrasi IAM, Master Data, Audit tertunda |
| A-003 | P-FNE-07 (Intelligence Platform) menyediakan API AI/ML pada minggu ke-6 | Simulasi dan optimasi menggunakan data aktual terganggu |
| A-004 | Data historis dari P-FNE-02 s.d P-FNE-06 tersedia untuk kalibrasi | Akurasi simulasi di bawah 85% |
| A-005 | Perangkat IoT tersedia untuk staging pada minggu ke-4 | Testing integrasi IoT tertunda |
| A-006 | Stakeholder kunci tersedia untuk UAT | UAT tertunda dan sign-off mundur |
| A-007 | Tidak ada perubahan signifikan pada scope selama pengembangan | Perubahan scope menyebabkan re-planning |

#### 1.7.2. Ketergantungan Proyek

| No | Ketergantungan | Pihak | Mitigasi |
| --- | --- | --- | --- |
| D-001 | P-FNE-01 API ready (IAM, Master Data, Audit) | Tim P-FNE-01 | Early API definition, mock service, weekly sync |
| D-002 | P-FNE-07 AI/ML Model ready untuk forecasting | Tim P-FNE-07 | Define contract early, mock model, parallel development |
| D-003 | Data historis dari P-FNE-02 s.d P-FNE-06 | Tim FNE Core | Request data early, agreement on format, staging data |
| D-004 | Cloud infrastructure provisioning | DevOps + Cloud Provider | Early provisioning, reserved instances |
| D-005 | IoT Gateway devices availability | Vendor IoT | PO early, track delivery, alternative vendor |
| D-006 | External Weather API access | Weather API Provider | Register early, test connectivity, backup provider |
| D-007 | User availability for UAT | End Users | Schedule UAT early, send invitations, prepare materials |
| D-008 | Security audit and penetration test | Security Consultant | Contract early, schedule at week 16 |

### 1.8. PERSETUJUAN DOKUMEN

Dokumen ini telah disetujui oleh pihak-pihak berikut:

| Peran | Nama | Tanda Tangan | Tanggal | Versi |
| --- | --- | --- | --- | --- |
| Project Manager | [Nama PM] |  |  | 1.0 |
| Project Sponsor | [Nama Sponsor] |  |  | 1.0 |
| Product Owner | [Nama PO] |  |  | 1.0 |
| Lead Teknis | [Nama Lead] |  |  | 1.0 |
| QA Lead | [Nama QA] |  |  | 1.0 |

### 1.9. DAFTAR REVISI DOKUMEN

| Versi | Tanggal | Deskripsi Revisi | Penyusun | Disetujui |
| --- | --- | --- | --- | --- |
| 0.1 | [DD/MM/YYYY] | Draft awal PMP | [Nama PM] | - |
| 0.5 | [DD/MM/YYYY] | Review internal tim | [Nama PM] | - |
| 1.0 | [DD/MM/YYYY] | Final PMP disetujui | [Nama PM] | [Nama Sponsor] |

# BAB 2: MANAJEMEN INTEGRASI PROYEK

## 2.1. PENDAHULUAN

Manajemen integrasi proyek merupakan area pengetahuan yang paling fundamental dalam manajemen proyek. Area ini bertanggung jawab untuk mengkoordinasikan seluruh elemen proyek agar berjalan secara terpadu dan selaras, memastikan bahwa semua proses dan aktivitas proyek terintegrasi dengan baik untuk mencapai tujuan proyek.

Untuk Proyek P-FNE-08 yang bersifat kompleks dengan banyak komponen (IoT, Digital Twin, Simulation, Autonomous) dan ketergantungan dengan proyek lain (P-FNE-01 s.d P-FNE-07), manajemen integrasi menjadi kunci keberhasilan dalam menyatukan seluruh komponen menjadi satu sistem yang kohesif dan berfungsi dengan baik.

## 2.2. PROSES MANAJEMEN INTEGRASI PROYEK

Berdasarkan PMBOK, terdapat 7 proses dalam manajemen integrasi proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Develop Project Charter | PMI-01 | Membuat dokumen otorisasi proyek yang memberikan wewenang kepada PM untuk mengelola proyek | Project Charter |
| Develop Project Management Plan | PMI-02 | Menyusun rencana manajemen proyek yang terintegrasi | PMP Dokumen |
| Direct and Manage Project Work | PMI-03 | Mengarahkan dan mengelola pelaksanaan pekerjaan proyek | Deliverables, Work Performance Data |
| Manage Project Knowledge | PMI-04 | Mengelola pengetahuan yang dihasilkan selama proyek | Lesson Learned Register, Knowledge Assets |
| Monitor and Control Project Work | PMI-05 | Memantau dan mengendalikan kemajuan proyek | Work Performance Reports, Change Requests |
| Perform Integrated Change Control | PMI-06 | Mengelola perubahan secara terintegrasi | Change Log, Approved Change Requests |
| Close Project or Phase | PMI-07 | Menyelesaikan proyek atau fase secara formal | Final Report, Project Closure |

## 2.3. DEVELOP PROJECT CHARTER (PMI-01)

### 2.3.1. Tujuan

Membuat dokumen resmi yang mengotorisasi Proyek P-FNE-08, memberikan wewenang kepada Project Manager untuk mengelola proyek dan mengalokasikan sumber daya organisasi.

### 2.3.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Business Case | Project Sponsor | Justifikasi bisnis untuk proyek Advanced & Autonomous Enterprise |
| Benefits Management Plan | Steering Committee | Rencana pengelolaan manfaat proyek |
| Enterprise Environmental Factors | Organisasi | Budaya organisasi, struktur, infrastruktur, regulasi |
| Organizational Process Assets | Organisasi | Kebijakan, prosedur, template, lesson learned |

### 2.3.3. Tools & Techniques

| Tools | Deskripsi |
| --- | --- |
| Expert Judgment | Konsultasi dengan sponsor, steering committee, dan ahli domain |
| Data Gathering | Wawancara dengan stakeholder, focus group, brainstorming |
| Meetings | Kick-off meeting, steering committee meeting |
| Facilitation | Workshop untuk menyepakati isi project charter |

### 2.3.4. Output: Project Charter

Project Charter P-FNE-08: Advanced & Autonomous Enterprise

| Aspek | Rincian |
| --- | --- |
| Project Title | P-FNE-08: Advanced & Autonomous Enterprise |
| Project Sponsor | [Nama Sponsor], CEO FNE |
| Project Manager | [Nama PM], PMP Certified |
| Date Issued | [Tanggal] |
| Project Purpose | Mengembangkan sistem IoT, Digital Twin, Simulation, dan Autonomous Capabilities sebagai puncak ekosistem Super ERP FNE |

Project Objectives:

| No | Objective | Success Criteria | Target |
| --- | --- | --- | --- |
| 1 | IoT Integration | IoT throughput dan latency | ≥ 10.000 msg/detik, ≤ 5 detik |
| 2 | Digital Twin | 3 jenis twin dengan state sync | Update ≤ 1 menit |
| 3 | Simulation | 5 use case simulasi | Accuracy ≥ 85%, execution ≤ 5 menit |
| 4 | Autonomous | Rule engine dan recommendation | Automated alerting, feedback loop |
| 5 | Dashboard | 4 dashboard terintegrasi | Real-time update |

High-Level Requirements:

| Requirement | Deskripsi |
| --- | --- |
| IoT Device Management | Registrasi, autentikasi, telemetry, alert, command |
| Digital Twin | Twin creation, state sync, historical, what-if analysis |
| Simulation Engine | Scenario management, 5 use case, optimization, comparison |
| Autonomous Capabilities | Rule engine, recommendation, approval workflow, feedback |
| Dashboards & Reporting | 4 dashboard, 12 jenis laporan |
| Integration | Integration dengan P-FNE-01 s.d P-FNE-07 |

High-Level Risks:

| No | Risk | Mitigation |
| --- | --- | --- |
| R-001 | IoT throughput < 10.000 msg/detik | Optimasi arsitektur, load testing, edge computing |
| R-002 | Simulation accuracy < 85% | Kalibrasi dengan data aktual, iterative improvement |
| R-003 | Integration with ERP fails | Early integration testing, contract testing |
| R-004 | Security vulnerability | Security audit, penetration test |
| R-005 | Delay in P-FNE-07 AI models | Mock models, parallel development |

High-Level Budget:

| Kategori | Estimasi |
| --- | --- |
| Sumber Daya Manusia | Rp 850.000.000 |
| Infrastruktur & Tools | Rp 450.000.000 |
| Hardware/Gateway | Rp 75.000.000 |
| Pelatihan & Konsultasi | Rp 350.000.000 |
| Testing & Quality | Rp 125.000.000 |
| Contingency (15%) | Rp 250.000.000 |
| Total | Rp 1.900.000.000 |

High-Level Milestones:

| Milestone | Target | Deliverable |
| --- | --- | --- |
| M1 | Minggu 1 | Project Charter Approved |
| M2 | Minggu 3 | Architecture Design Completed |
| M3 | Minggu 8 | MVP IoT & Twin Completed |
| M4 | Minggu 13 | 5 Simulation Use Cases Completed |
| M5 | Minggu 15 | Autonomous Module Completed |
| M6 | Minggu 17 | System Integration Completed |
| M7 | Minggu 19 | UAT Passed |
| M8 | Minggu 20 | Go-Live |

Approval Signatures:

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | [Nama] |  |  |
| Project Manager | [Nama] |  |  |
| Product Owner | [Nama] |  |  |

## 2.4. DEVELOP PROJECT MANAGEMENT PLAN (PMI-02)

### 2.4.1. Tujuan

Menyusun rencana manajemen proyek yang komprehensif dan terintegrasi yang mengoordinasikan seluruh area manajemen proyek (scope, schedule, cost, quality, resource, communication, risk, procurement, stakeholder).

### 2.4.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Dokumen otorisasi proyek |
| Scope Management Plan | PM + BA | Rencana manajemen scope |
| Schedule Management Plan | PM | Rencana manajemen jadwal |
| Cost Management Plan | PM + Finance | Rencana manajemen biaya |
| Quality Management Plan | PM + QA | Rencana manajemen mutu |
| Resource Management Plan | PM + HR | Rencana manajemen sumber daya |
| Communication Management Plan | PM + BA | Rencana manajemen komunikasi |
| Risk Management Plan | PM + Team | Rencana manajemen risiko |
| Procurement Management Plan | PM + DevOps | Rencana manajemen pengadaan |
| Stakeholder Management Plan | PM + BA | Rencana manajemen stakeholder |
| Enterprise Environmental Factors | Organisasi | Infrastruktur, tools, regulasi |
| Organizational Process Assets | Organisasi | Template, kebijakan, lesson learned |

### 2.4.3. Tools & Techniques

| Tools | Deskripsi |
| --- | --- |
| Expert Judgment | Konsultasi dengan ahli domain dan manajemen proyek |
| Facilitation | Workshop perencanaan dengan seluruh tim |
| PMIS | Jira, Confluence, MS Project |
| Tailoring | Menyesuaikan proses PMBOK dengan kebutuhan proyek |

### 2.4.4. Output: Project Management Plan

Daftar Komponen PMP P-FNE-08:

| Komponen | Deskripsi | Lokasi |
| --- | --- | --- |
| Scope Management Plan | Mendefinisikan dan mengelola scope proyek | Bab 3 |
| Schedule Management Plan | Mendefinisikan dan mengelola jadwal proyek | Bab 4 |
| Cost Management Plan | Mendefinisikan dan mengelola biaya proyek | Bab 5 |
| Quality Management Plan | Mendefinisikan dan mengelola mutu proyek | Bab 6 |
| Resource Management Plan | Mendefinisikan dan mengelola sumber daya | Bab 7 |
| Communication Management Plan | Mendefinisikan dan mengelola komunikasi | Bab 8 |
| Risk Management Plan | Mendefinisikan dan mengelola risiko | Bab 9 |
| Procurement Management Plan | Mendefinisikan dan mengelola pengadaan | Bab 10 |
| Stakeholder Management Plan | Mendefinisikan dan mengelola stakeholder | Bab 11 |
| Integrated Change Control | Mengelola perubahan secara terintegrasi | Bagian 2.6 |
| Configuration Management | Mengelola konfigurasi dan versi | Lampiran B |

Pengaturan Manajemen Proyek:

| Aspek | Pengaturan |
| --- | --- |
| Metode | Agile-Scrum (2 minggu sprint) + Waterfall (untuk fase besar) |
| Tools | Jira (task management), Confluence (dokumentasi), GitHub (code) |
| Meeting | Daily standup (15 menit), Sprint Planning (2 jam), Sprint Review (1 jam), Sprint Retrospective (1 jam) |
| Reporting | Weekly progress report, Monthly executive report, Ad-hoc reports |

## 2.5. DIRECT AND MANAGE PROJECT WORK (PMI-03)

### 2.5.1. Tujuan

Mengarahkan dan mengelola pelaksanaan pekerjaan proyek sesuai dengan PMP yang telah disusun, memastikan deliverables dihasilkan sesuai dengan rencana.

### 2.5.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Seluruh rencana manajemen proyek |
| Approved Change Requests | CCB | Perubahan yang telah disetujui |
| Enterprise Environmental Factors | Organisasi | Tools, infrastruktur, kebijakan |
| Organizational Process Assets | Organisasi | Template, prosedur |

### 2.5.3. Tools & Techniques

| Tools | Deskripsi | Penggunaan |
| --- | --- | --- |
| Jira Software | Project management tool | Tracking task, sprint, bug, epic |
| GitHub / GitLab | Version control | Source code management, CI/CD, code review |
| Confluence | Documentation | Technical documentation, meeting notes, decisions |
| Slack | Communication | Daily communication, alerts, integrations |
| Zoom / Google Meet | Virtual meeting | Daily standup, sprint events, stakeholder meetings |
| CI/CD Pipeline | Automated deployment | Build, test, deploy automation |

### 2.5.4. Output

| Output | Deskripsi | Penerima |
| --- | --- | --- |
| Deliverables | Produk/proyek yang dihasilkan | Project Sponsor, Product Owner |
| Work Performance Data | Data mentah kinerja proyek | PM, Leads |
| Issue Log | Daftar issue yang terjadi | PM, Team |
| Change Requests | Permintaan perubahan | CCB, PM |
| Project Management Plan Updates | Pembaruan PMP | Tim Proyek |
| Project Document Updates | Pembaruan dokumen | Tim Proyek |

### 2.5.5. Deliverables Matrix

| Fase | Deliverable | Description | Acceptance | Responsible |
| --- | --- | --- | --- | --- |
| IoT | IoT Service API | REST API untuk device management, telemetry, command | Passing unit test, integration test | IoT Lead |
| IoT | IoT Dashboard | Dashboard untuk monitoring perangkat dan alert | UI/UX review, UAT | Frontend Lead |
| IoT | Alert Engine | Sistem threshold alert dan notification | Test all alert levels, notification | IoT Engineer |
| Digital Twin | Digital Twin Service | CRUD twin, state management API | Passing unit test, integration test | Twin Lead |
| Digital Twin | Twin Viewer (2D/3D) | Visualisasi Digital Twin menggunakan Three.js | UI/UX review, UAT | Frontend Lead |
| Digital Twin | What-If Analysis | API untuk skenario what-if | Accuracy test, performance test | Data Scientist |
| Simulation | Simulation Engine | 5 use case simulasi berfungsi | Accuracy ≥ 85%, execution ≤ 5 menit | Sim Lead |
| Simulation | Optimization Module | Parameter optimization API | Success rate, convergence | Data Scientist |
| Autonomous | Rule Engine | Rule management dan evaluation API | Passing unit test, integration test | Auto Lead |
| Autonomous | Recommendation | Recommendation generator dan API | Accuracy test, user satisfaction | Data Scientist |
| Autonomous | Approval Workflow | Human-in-the-loop approval system | UAT, workflow completion | Auto Lead |
| Integration | System Integration | Semua modul terintegrasi | Integration test passing | DevOps |
| Documentation | Technical Documentation | API docs, architecture, deployment | Review by team | All Leads |
| Documentation | User Manual | Manual untuk end users dan admin | Review by BA, UAT | BA |

### 2.5.6. Daily Management Routine

| Aktivitas | Waktu | Deskripsi |
| --- | --- | --- |
| Daily Standup | 09:00 - 09:15 | Tim report: what I did, what I will do, blockers |
| Code Review | Kontinu | Setiap pull request di-review minimal 1 lead |
| CI/CD Check | Kontinu | Memastikan build dan test passing |
| Issue Log Update | Harian | Mencatat dan mengupdate issue yang muncul |
| Time Tracking | Harian | Mencatat waktu pengerjaan di Jira |

## 2.6. MANAGE PROJECT KNOWLEDGE (PMI-04)

### 2.6.1. Tujuan

Mengelola pengetahuan yang dihasilkan selama proyek, menangkap lesson learned, dan membangun knowledge assets untuk organisasi.

### 2.6.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Rencana manajemen proyek |
| Project Documents | All Team | Dokumentasi yang dihasilkan |
| Deliverables | All Team | Produk yang dihasilkan |
| Enterprise Environmental Factors | Organisasi | Budaya organisasi, tools |
| Organizational Process Assets | Organisasi | Lesson learned sebelumnya |

### 2.6.3. Tools & Techniques

| Tools | Deskripsi | Penggunaan |
| --- | --- | --- |
| Confluence | Knowledge management | Documentation, lesson learned, best practices |
| Sprint Retrospective | Team reflection | Menangkap lesson learned tiap sprint |
| Pair Programming | Knowledge transfer | Sharing knowledge antar developer |
| Knowledge Sharing Session | Presentation | Sharing teknis 2x per bulan |
| Documentation Review | Quality check | Memastikan dokumentasi lengkap |
| Brown Bag Lunch | Informal sharing | Sharing knowledge informal |

### 2.6.4. Output

| Output | Deskripsi | Lokasi |
| --- | --- | --- |
| Lesson Learned Register | Daftar lesson learned dari proyek | Confluence |
| Knowledge Assets | Dokumentasi, best practices, template | Confluence, GitHub Wiki |
| Project Documents Updates | Pembaruan dokumen | Confluence |
| Training Materials | Materi pelatihan untuk tim | Google Drive |

### 2.6.5. Knowledge Management Schedule

| Aktivitas | Frekuensi | Deskripsi |
| --- | --- | --- |
| Sprint Retrospective | 2 minggu | Menangkap lesson learned dari sprint |
| Knowledge Sharing Session | 2x per bulan | Presentasi teknis dari anggota tim |
| Documentation Sprint | Setiap sprint | Menulis dan memperbarui dokumentasi |
| Code Review | Kontinu | Knowledge transfer melalui code review |
| Onboarding Session | Saat tim baru bergabung | Mentransfer knowledge dasar proyek |

## 2.7. MONITOR AND CONTROL PROJECT WORK (PMI-05)

### 2.7.1. Tujuan

Memantau dan mengendalikan kemajuan proyek secara terintegrasi, membandingkan kinerja aktual dengan rencana, dan mengambil tindakan korektif jika diperlukan.

### 2.7.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Baseline proyek |
| Project Documents | All Team | Dokumentasi proyek |
| Work Performance Data | All Team | Data kinerja dari pelaksanaan |
| Organizational Process Assets | Organisasi | Template, prosedur |

### 2.7.3. Tools & Techniques

| Tools | Deskripsi | Penggunaan |
| --- | --- | --- |
| Jira Dashboards | Progress monitoring | Sprint burndown, epic progress, issue tracking |
| Earned Value Management | Performance measurement | SPI, CPI, EAC, ETC |
| Burndown Chart | Sprint tracking | Melihat progress sprint |
| Cumulative Flow Diagram | Flow tracking | Melihat WIP, cycle time |
| Variance Analysis | Performance analysis | Menganalisis penyimpangan |
| Trend Analysis | Prediction | Memprediksi kinerja masa depan |
| Status Meetings | Communication | Reporting progress |

### 2.7.4. Output

| Output | Deskripsi | Penerima |
| --- | --- | --- |
| Work Performance Reports | Laporan kinerja proyek | Sponsor, Steering Committee |
| Change Requests | Permintaan perubahan | CCB |
| Project Management Plan Updates | Pembaruan PMP | Tim Proyek |
| Project Document Updates | Pembaruan dokumen | Tim Proyek |

### 2.7.5. Reporting Schedule

| Laporan | Frekuensi | Penerima | Deskripsi |
| --- | --- | --- | --- |
| Daily Status | Harian | Tim Proyek | Standup report, blocker |
| Sprint Report | 2 minggu | Tim Proyek, PM | Sprint review, burndown |
| Weekly Progress Report | Mingguan | PM, Sponsor, Leads | Status, milestone, risk, issue |
| Monthly Executive Report | Bulanan | Steering Committee, Sponsor | Ringkasan eksekutif, KPI, forecast |
| Ad-hoc Report | Sesuai kebutuhan | Stakeholder | Laporan khusus sesuai permintaan |

### 2.7.6. Performance Metrics

| Metric | Target | Frequency | Owner |
| --- | --- | --- | --- |
| Sprint Velocity | 30-40 story points per sprint | 2 minggu | PM |
| SPI (Schedule Performance Index) | ≥ 0.95 | Bulanan | PM |
| CPI (Cost Performance Index) | ≥ 0.95 | Bulanan | PM |
| Defect Density | < 0.5 per KLOC | Setiap release | QA |
| Test Coverage | ≥ 80% | 2 minggu | QA |
| System Uptime | ≥ 99.5% | Mingguan | DevOps |
| IoT Throughput | ≥ 10.000 msg/detik | 2 minggu | IoT Lead |
| IoT Latency | ≤ 5 detik | 2 minggu | IoT Lead |
| Simulation Accuracy | ≥ 85% | 2 minggu | Data Scientist |
| Simulation Execution | ≤ 5 menit | 2 minggu | Sim Lead |

### 2.7.7. Change Request Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        CHANGE REQUEST PROCESS                               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  1. IDENTIFIKASI         2. ANALISIS            3. REVIEW & APPROVAL       │

│  ┌─────────────┐        ┌─────────────┐        ┌─────────────┐            │

│  │ Siapa pun   │───────▶│ PM + Leads │───────▶│    CCB     │            │

│  │ mengidenti- │        │ Menganalisis│        │ (PM, Lead, │            │

│  │ fikasi      │        │ dampak      │        │  Sponsor)  │            │

│  │ perubahan   │        │ scope, cost,│        │ Approve/   │            │

│  │ via Jira    │        │ schedule,   │        │ Reject/Defer│            │

│  │             │        │ risk        │        │            │            │

│  └─────────────┘        └─────────────┘        └─────────────┘            │

│                                                          │                  │

│                             4. IMPLEMENTASI             │                  │

│                             ┌─────────────────────────┐│                  │

│                             │ Tim implementasi        ││                  │

│                             │ perubahan sesuai       │◀┘                  │

│                             │ approval                │                    │

│                             │ Update PMP dan docs    │                    │

│                             └─────────────────────────┘                    │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

Change Request Classification:

| Kategori | Dampak | Approval | Lead Time |
| --- | --- | --- | --- |
| Minor | < 1 hari effort, tidak berdampak scope/budget | Tech Lead | ≤ 1 hari |
| Moderate | 1-5 hari effort, berdampak scope/budget kecil | PM + Lead | ≤ 3 hari |
| Major | > 5 hari effort, berdampak scope/budget signifikan | CCB + Sponsor | ≤ 1 minggu |
| Critical | Dampak pada project viability | Sponsor | ≤ 1 hari |

## 2.8. PERFORM INTEGRATED CHANGE CONTROL (PMI-06)

### 2.8.1. Tujuan

Mengelola perubahan secara terintegrasi di seluruh area manajemen proyek, memastikan perubahan dievaluasi, disetujui, dan diimplementasikan dengan cara yang terkendali.

### 2.8.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Baseline proyek |
| Project Documents | All Team | Dokumentasi proyek |
| Work Performance Data | All Team | Data kinerja |
| Change Requests | All Team | Permintaan perubahan |
| Organizational Process Assets | Organisasi | Kebijakan perubahan |

### 2.8.3. Tools & Techniques

| Tools | Deskripsi |
| --- | --- |
| Change Control Board (CCB) | Komite yang menyetujui perubahan |
| Expert Judgment | Konsultasi dengan ahli |
| Configuration Management | Mengelola konfigurasi produk |
| Acceptance Criteria | Kriteria penerimaan |

### 2.8.4. Output

| Output | Deskripsi |
| --- | --- |
| Approved Change Requests | Perubahan yang disetujui |
| Change Log | Daftar semua perubahan |
| Project Management Plan Updates | PMP yang diperbarui |
| Project Document Updates | Dokumen yang diperbarui |

### 2.8.5. Change Control Board (CCB)

Komposisi CCB:

| Anggota | Peran | Voting Weight |
| --- | --- | --- |
| Project Manager | Ketua CCB | 1 vote |
| Project Sponsor | Anggota | 1 vote (veto) |
| Lead Teknis | Anggota | 1 vote |
| Product Owner | Anggota | 1 vote |
| Business Analyst | Sekretaris | Non-voting |

Kriteria Keputusan:

| Kategori Perubahan | Keputusan | Kuorum |
| --- | --- | --- |
| Change request ≤ 5 story points | PM + Lead Teknis | 2 dari 2 |
| Change request > 5 story points | Full CCB | 4 dari 5 |
| Perubahan scope signifikan (>20%) | Full CCB + Sponsor approval | 5 dari 5 |
| Perubahan budget | Full CCB + Sponsor approval | 5 dari 5 |

### 2.8.6. Configuration Management

Konfigurasi yang Dikelola:

| Komponen | Repository | Versioning |
| --- | --- | --- |
| Source Code | GitHub | Git (Semantic Versioning) |
| Database Schema | GitHub + Migration Files | Flyway/Liquibase |
| Infrastructure Code | GitHub (Terraform) | Git |
| Documentation | Confluence + GitHub Wiki | Versioned |
| API Specifications | Swagger/OpenAPI | Versioned |
| Docker Images | Docker Registry | Tagged |
| Kubernetes Config | GitHub | Git |

## 2.9. CLOSE PROJECT OR PHASE (PMI-07)

### 2.9.1. Tujuan

Menyelesaikan proyek atau fase secara formal, memastikan semua pekerjaan selesai, deliverables diterima, dokumentasi lengkap, dan lesson learned terdokumentasi.

### 2.9.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Otorisasi proyek |
| Project Management Plan | PM | Rencana proyek |
| Accepted Deliverables | All Team | Deliverable yang diterima |
| Project Documents | All Team | Dokumentasi proyek |
| Organizational Process Assets | Organisasi | Template penutupan |

### 2.9.3. Tools & Techniques

| Tools | Deskripsi |
| --- | --- |
| Expert Judgment | Evaluasi dengan ahli |
| Data Analysis | Analisis kinerja proyek |
| Meetings | Final review meeting |
| Lessons Learned Session | Sesi refleksi akhir |

### 2.9.4. Output

| Output | Deskripsi |
| --- | --- |
| Final Project Report | Laporan akhir proyek |
| Lesson Learned Register | Lesson learned akhir |
| Handover Documentation | Dokumentasi handover |
| Project Closure | Penutupan formal proyek |
| Team Performance Evaluation | Evaluasi kinerja tim |

### 2.9.5. Penutupan Proyek P-FNE-08

Kriteria Penutupan:

| No | Kriteria | Status |
| --- | --- | --- |
| 1 | Semua deliverables telah diselesaikan dan diterima | □ |
| 2 | UAT telah selesai dan user sign-off diberikan | □ |
| 3 | Documentasi teknis lengkap dan tersedia | □ |
| 4 | User manual dan admin guide tersedia | □ |
| 5 | Training telah dilaksanakan | □ |
| 6 | Performance testing telah selesai dan target terpenuhi | □ |
| 7 | Security audit telah selesai dan issues resolved | □ |
| 8 | Semua kontrak dengan vendor telah selesai | □ |
| 9 | Lesson learned session telah dilakukan | □ |
| 10 | Final report telah disusun dan disetujui | □ |

Final Review Meeting Agenda:

| Agenda | Durasi | Deskripsi |
| --- | --- | --- |
| Opening | 15 menit | Pembukaan oleh PM |
| Project Overview | 30 menit | Ringkasan proyek dan pencapaian |
| Deliverables Review | 45 menit | Review semua deliverables |
| Performance Review | 30 menit | Review kinerja (scope, schedule, cost, quality) |
| Lesson Learned | 30 menit | Presentasi lesson learned |
| Handover Plan | 30 menit | Rencana handover ke tim operasional |
| Q&A | 30 menit | Tanya jawab |
| Closing | 15 menit | Closing statement |

Handover Checklist:

| Aspek | Deskripsi | Status |
| --- | --- | --- |
| System | Sistem berjalan di production | □ |
| Documentation | Dokumentasi teknis lengkap | □ |
| User Manual | Manual untuk admin dan user | □ |
| Training | Training completed | □ |
| Support | Support channel available | □ |
| Monitoring | Monitoring and alerting configured | □ |
| Backup | Backup and DR configured | □ |
| Security | Security configuration complete | □ |
| Access | User access management ready | □ |

## 2.10. INTEGRATED CHANGE CONTROL FLOW DIAGRAM

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                   INTEGRATED CHANGE CONTROL FLOW                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────────┐                                                       │

│  │  Identify Need  │                                                       │

│  │  for Change     │                                                       │

│  └────────┬────────┘                                                       │

│           ▼                                                                │

│  ┌─────────────────┐                                                       │

│  │  Submit Change  │                                                       │

│  │  Request (Jira) │                                                       │

│  └────────┬────────┘                                                       │

│           ▼                                                                │

│  ┌─────────────────┐                                                       │

│  │  Assess Impact  │  ◄── Scope, Schedule, Cost, Quality, Risk            │

│  │  (PM + Leads)   │                                                       │

│  └────────┬────────┘                                                       │

│           ▼                                                                │

│  ┌─────────────────┐                                                       │

│  │  Classify       │                                                       │

│  │  Change Type    │                                                       │

│  └────────┬────────┘                                                       │

│           │                                                                │

│     ┌─────┼─────┐                                                         │

│     │     │     │                                                         │

│     ▼     ▼     ▼                                                         │

│  ┌─────┐ ┌─────┐ ┌─────┐                                                  │

│  │Minor│ │Mod. │ │Major│                                                  │

│  └──┬──┘ └──┬──┘ └──┬──┘                                                  │

│     │       │       │                                                      │

│     ▼       ▼       ▼                                                      │

│  ┌─────┐ ┌─────┐ ┌─────┐                                                  │

│  │ Tech │ │ PM +│ │CCB +│                                                  │

│  │ Lead │ │Lead │ │Sponsor│                                                  │

│  └──┬──┘ └──┬──┘ └──┬──┘                                                  │

│     │       │       │                                                      │

│     └───────┼───────┘                                                      │

│             ▼                                                              │

│  ┌─────────────────┐                                                       │

│  │  Decision       │                                                       │

│  │  Approve/Reject │                                                       │

│  └────────┬────────┘                                                       │

│           │                                                                │

│    ┌──────┴──────┐                                                         │

│    ▼             ▼                                                         │

│ ┌───────┐   ┌─────────┐                                                    │

│ │Reject │   │ Approve │                                                    │

│ └───┬───┘   └────┬────┘                                                    │

│     │            │                                                         │

│     ▼            ▼                                                         │

│ ┌───────┐   ┌──────────────────────────┐                                  │

│ │ Notify│   │  Implement Change         │                                  │

│ │Reject │   │  Update PMP & Documents   │                                  │

│ └───────┘   └────────────┬─────────────┘                                  │

│                          │                                                  │

│                          ▼                                                  │

│                ┌──────────────────────────┐                                │

│                │  Communicate Change      │                                │

│                │  to Stakeholders         │                                │

│                └──────────────────────────┘                                │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 2.11. INTEGRATION MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Develop Project Charter | Business Case, EEF | Expert Judgment, Meetings | Project Charter | Sponsor, PM |
| Develop PMP | Project Charter, Subsidiary Plans | Facilitation, PMIS | PMP | PM |
| Direct & Manage Work | PMP, Approved Changes | Jira, GitHub, CI/CD | Deliverables, WPD | All Team |
| Manage Knowledge | Project Documents | Retrospective, Pair Programming | Lesson Learned | PM, Leads |
| Monitor & Control | PMP, WPD, Reports | EVM, Variance Analysis | Performance Reports | PM, Leads |
| Integrated Change Control | PMP, Change Requests | CCB, Configuration Mgmt | Approved Changes | CCB, PM |
| Close Project/Phase | Accepted Deliverables | Final Review, Lessons Learned | Final Report, Closure | PM, Sponsor |

# BAB 3: MANAJEMEN LINGKUP PROYEK

## 3.1. PENDAHULUAN

Manajemen lingkup proyek bertujuan untuk memastikan bahwa proyek mencakup seluruh pekerjaan yang diperlukan—dan hanya pekerjaan yang diperlukan—untuk menyelesaikan Proyek P-FNE-08: Advanced & Autonomous Enterprise dengan sukses.

Proyek P-FNE-08 memiliki ruang lingkup yang luas dan kompleks, mencakup 5 domain utama (IoT, Digital Twin, Simulation, Autonomous, Dashboard & Reporting) dengan integrasi ke 7 proyek FNE lainnya. Oleh karena itu, manajemen lingkup yang disiplin dan terstruktur sangat penting untuk mencegah scope creep dan memastikan deliverables yang dihasilkan sesuai dengan kebutuhan stakeholder.

## 3.2. PROSES MANAJEMEN LINGKUP PROYEK

Berdasarkan PMBOK, terdapat 6 proses dalam manajemen lingkup proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Plan Scope Management | PMI-08 | Menyusun rencana manajemen lingkup | Scope Management Plan, Requirements Management Plan |
| Collect Requirements | PMI-09 | Mengumpulkan kebutuhan stakeholder | Requirements Documentation, Requirements Traceability Matrix |
| Define Scope | PMI-10 | Mendefinisikan lingkup proyek secara detail | Project Scope Statement |
| Create WBS | PMI-11 | Membuat Work Breakdown Structure | WBS, WBS Dictionary |
| Validate Scope | PMI-12 | Memvalidasi deliverable dengan stakeholder | Accepted Deliverables |
| Control Scope | PMI-13 | Mengendalikan perubahan lingkup | Scope Baseline Updates, Change Requests |

## 3.3. PLAN SCOPE MANAGEMENT (PMI-08)

### 3.3.1. Tujuan

Menyusun rencana manajemen lingkup yang mendefinisikan bagaimana lingkup akan didefinisikan, divalidasi, dan dikendalikan selama proyek berlangsung.

### 3.3.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Dokumen otorisasi proyek |
| Enterprise Environmental Factors | Organisasi | Budaya, infrastruktur, regulasi |
| Organizational Process Assets | Organisasi | Template WBS, kebijakan, prosedur |

### 3.3.3. Output: Scope Management Plan

Rencana Manajemen Lingkup P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Proses Define Scope | Menggunakan Product Backlog (Scrum) + Project Scope Statement |
| Proses WBS | WBS Level 1-5 dengan WBS Dictionary untuk setiap paket kerja |
| Proses Validate Scope | Sprint Review + UAT + Formal Sign-off |
| Proses Control Scope | Change Control Process via CCB |
| Format Requirements | User Stories + Acceptance Criteria (Given-When-Then) |
| Tools | Jira (Product Backlog), Confluence (Requirements Docs), Miro (WBS) |

Requirements Management Plan:

| Aspek | Rincian |
| --- | --- |
| Requirements Gathering | Workshop, Interview, Survey, Document Analysis |
| Requirements Prioritization | MoSCoW (Must-have, Should-have, Could-have, Won't-have) |
| Requirements Traceability | Requirements Traceability Matrix (RTM) |
| Requirements Change | Through CCB process |
| Requirements Validation | UAT dengan stakeholder |

## 3.4. COLLECT REQUIREMENTS (PMI-09)

### 3.4.1. Tujuan

Mengumpulkan, mendokumentasikan, dan mengelola kebutuhan dari seluruh stakeholder untuk memastikan sistem yang dikembangkan sesuai dengan harapan.

### 3.4.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Gambaran proyek |
| Stakeholder Register | PM + BA | Daftar stakeholder |
| Enterprise Environmental Factors | Organisasi | Regulasi, standar industri |
| Organizational Process Assets | Organisasi | Template, lesson learned |

### 3.4.3. Tools & Techniques

| Tools | Deskripsi | Penggunaan |
| --- | --- | --- |
| Interviews | Wawancara dengan stakeholder kunci | Mendapatkan kebutuhan detail dari end users |
| Focus Groups | Diskusi kelompok | Menggali kebutuhan dari user segment |
| Workshops | Workshop kolaboratif | Menyepakati kebutuhan bersama |
| Questionnaires | Kuesioner terstruktur | Mengumpulkan kebutuhan dari banyak responden |
| Observation | Observasi lapangan | Memahami alur kerja sebenarnya |
| Prototyping | Mockup UI | Memvisualisasikan kebutuhan |
| Document Analysis | Analisis dokumen | Menggali kebutuhan dari dokumen eksisting |
| Brainstorming | Sesi brainstorming | Menggali kebutuhan kreatif |

### 3.4.4. Output: Requirements Documentation

Klasifikasi Kebutuhan:

| Kategori | Deskripsi | Jumlah | Contoh |
| --- | --- | --- | --- |
| Business Requirements | Kebutuhan tingkat organisasi | 8 | IoT throughput ≥ 10.000 msg/detik, simulation accuracy ≥ 85% |
| Stakeholder Requirements | Kebutuhan dari stakeholder | 15 | Manajer operasi dapat melihat dashboard real-time |
| Solution Requirements - Functional | Fitur dan fungsi sistem | 45 | Device registration, threshold alert, what-if analysis |
| Solution Requirements - Non-Functional | Kualitas sistem | 12 | Performance, security, reliability, usability |
| Transition Requirements | Kebutuhan transisi | 5 | Data migration, training, handover |

Rincian Requirements per Domain:

Domain IoT (15 Requirements):

| ID | Requirement | Prioritas | Sumber |
| --- | --- | --- | --- |
| REQ-IOT-001 | Sistem dapat mendaftarkan perangkat IoT dengan atribut lengkap | Must-have | Tech Lead, Ops |
| REQ-IOT-002 | Setiap perangkat memiliki autentikasi yang aman (API key/certificate) | Must-have | Security, Tech Lead |
| REQ-IOT-003 | Sistem dapat menerima data telemetri secara real-time | Must-have | Ops, Management |
| REQ-IOT-004 | Data telemetri disimpan dalam time-series database | Must-have | Data Team |
| REQ-IOT-005 | User dapat memonitor data sensor secara real-time melalui dashboard | Must-have | Ops, Management |
| REQ-IOT-006 | Sistem memberikan alert jika nilai sensor melewati threshold | Must-have | Ops |
| REQ-IOT-007 | Sistem mendukung multiple threshold (warning, critical, emergency) | Must-have | Ops |
| REQ-IOT-008 | User dapat mendefinisikan rules untuk memproses data telemetri | Must-have | Ops |
| REQ-IOT-009 | Sistem memonitor health device (online/offline, battery, signal) | Must-have | Tech Lead, Ops |
| REQ-IOT-010 | User dapat mengirimkan command ke device (start/stop/calibrate) | Should-have | Ops |
| REQ-IOT-011 | Command berisiko tinggi harus melalui approval | Must-have | Security |
| REQ-IOT-012 | User dapat mengelompokkan device berdasarkan lokasi/jenis/fungsi | Could-have | Ops |
| REQ-IOT-013 | Dashboard IoT menampilkan device status, telemetry, alerts, health | Must-have | Ops, Management |
| REQ-IOT-014 | Data telemetri disimpan minimal 1 tahun | Must-have | Data Team, Compliance |
| REQ-IOT-015 | Sistem melakukan agregasi data (min, max, avg, sum) per period | Should-have | Ops, Management |

Domain Digital Twin (14 Requirements):

| ID | Requirement | Prioritas | Sumber |
| --- | --- | --- | --- |
| REQ-DTW-001 | User dapat membuat Digital Twin untuk aset/farm/process | Must-have | Management, Ops |
| REQ-DTW-002 | Minimal 3 jenis Digital Twin (Farm, Machine, Warehouse) | Must-have | Management, Ops |
| REQ-DTW-003 | Setiap Digital Twin memiliki state model representasi kondisi aktual | Must-have | Tech Lead |
| REQ-DTW-004 | Digital Twin tersinkronisasi dengan kondisi aktual melalui ERP dan IoT | Must-have | Ops |
| REQ-DTW-005 | Digital Twin menyimpan historical state untuk analisis dan replay | Must-have | Data Team |
| REQ-DTW-006 | Dashboard Digital Twin menampilkan current state, trend, alerts | Must-have | Ops, Management |
| REQ-DTW-007 | Digital Twin merepresentasikan hubungan antar aset | Should-have | Ops |
| REQ-DTW-008 | User dapat melakukan what-if analysis pada Digital Twin | Must-have | Management, Planning |
| REQ-DTW-009 | User dapat menjalankan skenario pada Digital Twin | Must-have | Management, Planning |
| REQ-DTW-010 | User dapat membandingkan hasil beberapa skenario | Must-have | Management, Planning |
| REQ-DTW-011 | Digital Twin memiliki visualisasi 2D/3D untuk melihat state | Should-have | Ops, Management |
| REQ-DTW-012 | Digital Twin mendukung versioning untuk perubahan model | Could-have | Tech Lead |
| REQ-DTW-013 | User dapat melakukan kalibrasi Digital Twin dengan data aktual | Should-have | Data Team |
| REQ-DTW-014 | Sistem menyediakan analisis: performance prediction, anomaly detection, optimization recommendation | Should-have | Management |

Domain Simulation Engine (15 Requirements):

| ID | Requirement | Prioritas | Sumber |
| --- | --- | --- | --- |
| REQ-SIM-001 | User dapat membuat simulasi baru dengan atribut lengkap | Must-have | Management, Planning |
| REQ-SIM-002 | Minimal 5 jenis simulasi (Crop Yield, Production, Inventory, Supply Chain, Expansion) | Must-have | Management |
| REQ-SIM-003 | User dapat mengkonfigurasi parameter simulasi | Must-have | Planning |
| REQ-SIM-004 | User dapat menjalankan simulasi dan melihat progress | Must-have | Planning |
| REQ-SIM-005 | Sistem menampilkan hasil simulasi (output, charts, statistics) | Must-have | Management, Planning |
| REQ-SIM-006 | User dapat membuat, menyimpan, dan mengelola multiple scenario | Must-have | Planning |
| REQ-SIM-007 | User dapat melakukan what-if analysis dengan mengubah parameter | Must-have | Management, Planning |
| REQ-SIM-008 | Sistem melakukan sensitivity analysis | Should-have | Data Team |
| REQ-SIM-009 | Sistem mendukung Monte Carlo simulation | Could-have | Data Team |
| REQ-SIM-010 | Sistem dapat mencari parameter optimal untuk mencapai tujuan | Should-have | Management, Data Team |
| REQ-SIM-011 | Dashboard simulasi menampilkan running, completed, results summary | Must-have | Management, Planning |
| REQ-SIM-012 | User dapat menghasilkan laporan simulasi untuk presentasi | Should-have | Management, Planning |
| REQ-SIM-013 | User dapat melakukan replay simulasi | Could-have | Planning |
| REQ-SIM-014 | Simulasi menggunakan model AI untuk memprediksi parameter | Should-have | Data Team |
| REQ-SIM-015 | Simulasi menggunakan Digital Twin sebagai basis model | Must-have | Tech Lead |

Domain Autonomous & Adaptive (10 Requirements):

| ID | Requirement | Prioritas | Sumber |
| --- | --- | --- | --- |
| REQ-AUT-001 | Sistem mengirimkan alert secara otomatis berdasarkan rules dan AI detection | Must-have | Ops, Management |
| REQ-AUT-002 | Sistem memberikan rekomendasi tindakan berdasarkan analisis real-time | Must-have | Ops, Management |
| REQ-AUT-003 | Sistem dapat memicu workflow secara otomatis berdasarkan event | Should-have | Ops |
| REQ-AUT-004 | Untuk keputusan risiko rendah, sistem mengambil keputusan otomatis | Could-have | Management |
| REQ-AUT-005 | Keputusan berisiko tinggi melibatkan human approval | Must-have | Security, Management |
| REQ-AUT-006 | Sistem terus-menerus mengoptimalkan proses berdasarkan data real-time | Should-have | Management, Data Team |
| REQ-AUT-007 | Sistem mendeteksi dan memperbaiki masalah sederhana secara otomatis | Could-have | Tech Lead |
| REQ-AUT-008 | Sistem secara otomatis menyesuaikan rencana berdasarkan perubahan | Could-have | Management |
| REQ-AUT-009 | Sistem menggunakan outcome dari keputusan untuk meningkatkan model | Must-have | Data Team |
| REQ-AUT-010 | Admin dapat mengkonfigurasi level autonomy per proses | Should-have | Management |

### 3.4.5. Output: Requirements Traceability Matrix (RTM)

| ID Requirement | Deskripsi | Sumber | WBS Element | Test Case ID | Status |
| --- | --- | --- | --- | --- | --- |
| REQ-IOT-001 | Device registration | Ops, Tech Lead | 2.1 | TC-IOT-001 | Approved |
| REQ-IOT-002 | Device authentication | Security | 2.1 | TC-IOT-002 | Approved |
| REQ-IOT-003 | Telemetry ingestion | Ops | 2.2 | TC-IOT-003 | Approved |
| REQ-IOT-004 | Time-series storage | Data Team | 2.2 | TC-IOT-004 | Approved |
| REQ-IOT-005 | Real-time monitoring | Ops | 2.5 | TC-IOT-005 | Approved |
| REQ-IOT-006 | Threshold alert | Ops | 2.3 | TC-IOT-006 | Approved |
| REQ-DTW-001 | Twin creation | Ops | 3.1 | TC-DTW-001 | Approved |
| REQ-DTW-002 | 3 Twin types | Management | 3.1 | TC-DTW-002 | Approved |
| REQ-DTW-004 | State synchronization | Ops | 3.2 | TC-DTW-003 | Approved |
| REQ-DTW-008 | What-if analysis | Management | 3.4 | TC-DTW-004 | Approved |
| REQ-SIM-001 | Simulation creation | Management | 4.1 | TC-SIM-001 | Approved |
| REQ-SIM-002 | 5 simulation types | Management | 4.2 | TC-SIM-002 | Approved |
| REQ-SIM-007 | What-if simulation | Management | 4.2 | TC-SIM-003 | Approved |
| REQ-SIM-010 | Optimization | Management | 4.3 | TC-SIM-004 | Approved |
| REQ-AUT-001 | Automated alerting | Ops | 5.1 | TC-AUT-001 | Approved |
| REQ-AUT-002 | Recommendation | Ops | 5.2 | TC-AUT-002 | Approved |
| REQ-AUT-005 | Human-in-the-loop | Security | 5.3 | TC-AUT-003 | Approved |
| REQ-AUT-009 | Feedback loop | Data Team | 5.5 | TC-AUT-004 | Approved |

## 3.5. DEFINE SCOPE (PMI-10)

### 3.5.1. Tujuan

Mendefinisikan lingkup proyek secara detail, termasuk batasan, asumsi, dan pengecualian, sebagai dasar untuk pengembangan dan pengendalian lingkup.

### 3.5.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Dokumen otorisasi |
| Requirements Documentation | BA + Stakeholder | Kebutuhan yang telah dikumpulkan |
| Organizational Process Assets | Organisasi | Template |

### 3.5.3. Output: Project Scope Statement

Project Scope Statement P-FNE-08:

1. Product Scope Description

Sistem Advanced & Autonomous Enterprise adalah platform yang mengintegrasikan:

- IoT Integration: Device management, telemetry ingestion, threshold alert, command sending, device health monitoring.

- Digital Twin: Representasi digital aset (Farm, Machine, Warehouse) dengan state synchronization, historical state, dan what-if analysis.

- Simulation Engine: 5 use case simulasi (Crop Yield, Production Capacity, Inventory, Supply Chain Disruption, Expansion) dengan optimization dan scenario comparison.

- Autonomous Capabilities: Rule engine, recommendation generator, approval workflow, feedback loop.

- Dashboards: 4 dashboard (IoT, Twin, Simulation, Autonomy) dengan visualisasi real-time.

- Reporting: 12 jenis laporan (IoT, Twin, Simulation, Autonomy, System).

- Integration: Koneksi dengan P-FNE-01 s.d P-FNE-07 untuk data master, AI/ML, dan ERP data.

2. Acceptance Criteria

| Komponen | Kriteria Penerimaan |
| --- | --- |
| IoT Integration | ✓ Device registration dan authentication berfungsi ✓ Telemetry ingestion dan time-series storage berfungsi ✓ Threshold alert berfungsi (minimal 5 rules) ✓ IoT dashboard menampilkan data real-time ✓ Device health monitoring berfungsi |
| Digital Twin | ✓ Minimal 3 jenis Digital Twin (Farm, Machine, Warehouse) telah dibuat ✓ State synchronization dengan data aktual (ERP + IoT) berfungsi ✓ Historical state tersedia ✓ What-if analysis berfungsi |
| Simulation | ✓ Minimal 5 use case simulasi berfungsi ✓ Scenario management dan comparison berfungsi ✓ Simulation execution time ≤ 5 menit ✓ Simulation accuracy ≥ 85% |
| Autonomous | ✓ Automated alerting dan recommendation berfungsi ✓ Human-in-the-loop untuk keputusan berisiko tinggi berfungsi ✓ Feedback loop untuk improvement model berfungsi |
| Performance | ✓ IoT data throughput ≥ 10.000 messages/detik ✓ IoT data latency ≤ 5 detik ✓ Digital Twin state update ≤ 1 menit ✓ Simulation execution time ≤ 5 menit |
| Security | ✓ Device authentication berfungsi ✓ Data telemetri dienkripsi ✓ Command approval untuk perangkat berisiko |

3. Deliverables

| Deliverable | Description |
| --- | --- |
| D1 | IoT Service (Device Registration, Telemetry, Alert, Command) |
| D2 | Digital Twin Service (Twin CRUD, State Sync, What-If) |
| D3 | Simulation Engine (Scenario Management, 5 Use Cases, Optimization) |
| D4 | Autonomous Service (Rule Engine, Recommendation, Approval, Feedback) |
| D5 | Dashboard (IoT, Twin, Simulation, Autonomy) |
| D6 | System Integration (ERP, AI/ML, External APIs) |
| D7 | Documentation (Technical, User Manual, Admin Guide) |
| D8 | Training (Training Materials, Training Sessions) |

4. Project Exclusions

| No | Exclusion | Alasan |
| --- | --- | --- |
| 1 | Pengembangan sistem ERP core (P-FNE-01 s.d P-FNE-07) | Diluar lingkup, dikembangkan oleh tim lain |
| 2 | Implementasi perangkat keras IoT di lapangan | Hanya software integration, hardware dilakukan vendor terpisah |
| 3 | Koneksi ke perangkat IoT aktual di luar lingkungan staging | Hanya simulasi data untuk pengembangan |
| 4 | Migrasi data dari sistem legacy | Dilakukan oleh tim data terpisah |
| 5 | Pengembangan mobile app native | Frontend hanya web-based, mobile via responsive |
| 6 | Hardware procurement untuk IoT gateway | Dilakukan oleh tim infrastruktur terpisah |

5. Constraints

| No | Constraint | Deskripsi |
| --- | --- | --- |
| C-001 | Time | Proyek harus selesai dalam 4-5 bulan (20 minggu) |
| C-002 | Budget | Anggaran maksimal Rp 1.900.000.000 |
| C-003 | Resource | Tim maksimal 14 orang |
| C-004 | Technology | Wajib menggunakan teknologi stack yang telah ditentukan |
| C-005 | Integration | Harus terintegrasi dengan P-FNE-01 s.d P-FNE-07 |
| C-006 | Compliance | Harus memenuhi regulasi data protection |

6. Assumptions

| No | Assumption | Deskripsi |
| --- | --- | --- |
| A-001 | Tim memiliki akses ke infrastruktur cloud yang dibutuhkan |  |
| A-002 | P-FNE-01 (Foundation) tersedia dan stabil pada minggu ke-3 |  |
| A-003 | P-FNE-07 (Intelligence Platform) menyediakan API AI/ML pada minggu ke-6 |  |
| A-004 | Data historis dari P-FNE-02 s.d P-FNE-06 tersedia untuk kalibrasi |  |
| A-005 | Perangkat IoT tersedia untuk staging pada minggu ke-4 |  |
| A-006 | Stakeholder kunci tersedia untuk UAT |  |

## 3.6. CREATE WBS (PMI-11)

### 3.6.1. Tujuan

Membuat Work Breakdown Structure (WBS) yang mendekomposisi pekerjaan proyek menjadi paket-paket kerja yang lebih kecil dan terkelola.

### 3.6.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Scope Statement | PM + BA | Lingkup proyek |
| Requirements Documentation | BA | Kebutuhan yang telah dikumpulkan |
| Enterprise Environmental Factors | Organisasi | Template WBS |

### 3.6.3. Tools & Techniques

| Tools | Deskripsi |
| --- | --- |
| Decomposition | Memecah pekerjaan menjadi paket-paket kerja |
| Expert Judgment | Konsultasi dengan leads |
| WBS Template | Menggunakan template dari organisasi |

### 3.6.4. Output: WBS

text

P-FNE-08: ADVANCED & AUTONOMOUS ENTERPRISE (1.0)

│

├── 1.0 PROJECT MANAGEMENT (1.1 - 1.4)

│   ├── 1.1 PMP Development

│   │   ├── 1.1.1 PMP Document Preparation

│   │   ├── 1.1.2 Subsidiary Plans Development

│   │   └── 1.1.3 PMP Approval & Sign-off

│   ├── 1.2 Monitoring & Control

│   │   ├── 1.2.1 Progress Reporting

│   │   ├── 1.2.2 Risk Monitoring

│   │   ├── 1.2.3 Issue Management

│   │   └── 1.2.4 Change Management

│   ├── 1.3 Communication Management

│   │   ├── 1.3.1 Stakeholder Communication

│   │   ├── 1.3.2 Meeting Facilitation

│   │   └── 1.3.3 Status Reporting

│   └── 1.4 Project Closure

│       ├── 1.4.1 Final Report Preparation

│       ├── 1.4.2 Lesson Learned Session

│       └── 1.4.3 Handover Documentation

│

├── 2.0 IoT INTEGRATION (2.1 - 2.5)

│   ├── 2.1 Device Registration & Authentication

│   │   ├── 2.1.1 Database Schema Design (iot_devices)

│   │   ├── 2.1.2 Device Registration API Development

│   │   ├── 2.1.3 Device Authentication (API Key/Certificate) Implementation

│   │   └── 2.1.4 Device Registration UI Form

│   ├── 2.2 Telemetry Ingestion & Storage

│   │   ├── 2.2.1 TimescaleDB Schema Design (iot_telemetry)

│   │   ├── 2.2.2 Telemetry Ingestion API Development (MQTT/REST)

│   │   ├── 2.2.3 Telemetry Storage Implementation

│   │   └── 2.2.4 Data Retention Policy Implementation

│   ├── 2.3 Threshold Alert Engine

│   │   ├── 2.3.1 Threshold Rules Database Schema (iot_thresholds)

│   │   ├── 2.3.2 Threshold Configuration API

│   │   ├── 2.3.3 Alert Engine Implementation

│   │   ├── 2.3.4 Alert Storage (iot_alerts)

│   │   └── 2.3.5 Notification Integration (email, SMS, push)

│   ├── 2.4 Command Service

│   │   ├── 2.4.1 Command Database Schema (iot_commands)

│   │   ├── 2.4.2 Command API Development

│   │   ├── 2.4.3 Command Approval Integration

│   │   └── 2.4.4 Gateway Integration (MQTT)

│   └── 2.5 IoT Dashboard

│       ├── 2.5.1 Device List View

│       ├── 2.5.2 Real-Time Telemetry Charts

│       ├── 2.5.3 Alert Management View

│       ├── 2.5.4 Device Health Monitoring View

│       └── 2.5.5 Device Grouping & Filtering

│

├── 3.0 DIGITAL TWIN (3.1 - 3.5)

│   ├── 3.1 Twin Creation & Management

│   │   ├── 3.1.1 Twin Database Schema (digital_twins)

│   │   ├── 3.1.2 Twin CRUD API Development

│   │   ├── 3.1.3 State Database Schema (twin_states)

│   │   ├── 3.1.4 Twin Versioning Implementation

│   │   └── 3.1.5 Twin Relationship Implementation (Neo4j)

│   ├── 3.2 State Synchronization

│   │   ├── 3.2.1 Event Consumer for IoT (Kafka)

│   │   ├── 3.2.2 Event Consumer for ERP (Kafka)

│   │   ├── 3.2.3 State Update Engine

│   │   └── 3.2.4 State Validation & Transformation

│   ├── 3.3 Historical State Storage

│   │   ├── 3.3.1 Historical State Schema (twin_states_history)

│   │   ├── 3.3.2 Snapshot Scheduler

│   │   └── 3.3.3 Historical State API

│   ├── 3.4 What-If Analysis

│   │   ├── 3.4.1 What-If API Development

│   │   ├── 3.4.2 AI/ML Service Integration

│   │   ├── 3.4.3 Prediction Engine

│   │   └── 3.4.4 What-If Results Storage

│   └── 3.5 Twin Viewer (2D/3D)

│       ├── 3.5.1 3D Model Loading (Three.js)

│       ├── 3.5.2 State Visualization (colors, indicators)

│       ├── 3.5.3 Interactive Controls

│       ├── 3.5.4 Historical Replay Functionality

│       └── 3.5.5 What-If Parameter Panel

│

├── 4.0 SIMULATION ENGINE (4.1 - 4.5)

│   ├── 4.1 Scenario Management

│   │   ├── 4.1.1 Scenario Database Schema (simulation_scenarios)

│   │   ├── 4.1.2 Scenario CRUD API

│   │   ├── 4.1.3 Scenario Versioning

│   │   └── 4.1.4 Scenario UI (Creation Wizard)

│   ├── 4.2 Simulation Runner (5 Use Cases)

│   │   ├── 4.2.1 Crop Yield Simulation

│   │   │   ├── Model Development (SimPy)

│   │   │   ├── Parameter Configuration

│   │   │   ├── Simulation Execution

│   │   │   └── Results Processing

│   │   ├── 4.2.2 Production Capacity Simulation

│   │   │   ├── Model Development (SimPy)

│   │   │   ├── Parameter Configuration

│   │   │   ├── Simulation Execution

│   │   │   └── Results Processing

│   │   ├── 4.2.3 Inventory Simulation

│   │   │   ├── Model Development (SimPy)

│   │   │   ├── Parameter Configuration

│   │   │   ├── Simulation Execution

│   │   │   └── Results Processing

│   │   ├── 4.2.4 Supply Chain Disruption Simulation

│   │   │   ├── Model Development (SimPy)

│   │   │   ├── Parameter Configuration

│   │   │   ├── Simulation Execution

│   │   │   └── Results Processing

│   │   └── 4.2.5 Expansion Simulation

│   │       ├── Model Development (SimPy)

│   │       ├── Parameter Configuration

│   │       ├── Simulation Execution

│   │       └── Results Processing

│   ├── 4.3 Optimization Module

│   │   ├── 4.3.1 Optimization Algorithm Selection

│   │   ├── 4.3.2 Optimization Engine Development

│   │   ├── 4.3.3 Optimization Results Storage

│   │   └── 4.3.4 Optimization UI

│   ├── 4.4 Scenario Comparison

│   │   ├── 4.4.1 Comparison Engine Development

│   │   ├── 4.4.2 Comparison Matrix Calculation

│   │   ├── 4.4.3 Radar Chart Generation

│   │   └── 4.4.4 Comparison UI

│   └── 4.5 Simulation Workbench

│       ├── 4.5.1 Simulation Dashboard

│       ├── 4.5.2 Results Viewer (charts, tables)

│       ├── 4.5.3 Report Generator (PDF, Excel)

│       └── 4.5.4 Simulation Scheduler

│

├── 5.0 AUTONOMOUS & ADAPTIVE (5.1 - 5.5)

│   ├── 5.1 Rule Engine

│   │   ├── 5.1.1 Rule Database Schema (autonomy_rules)

│   │   ├── 5.1.2 Rule CRUD API

│   │   ├── 5.1.3 Rule Evaluation Engine (Drools)

│   │   ├── 5.1.4 Event Listener (Kafka)

│   │   └── 5.1.5 Rule Management UI

│   ├── 5.2 Recommendation Generator

│   │   ├── 5.2.1 Recommendation Database Schema (autonomy_recommendations)

│   │   ├── 5.2.2 Recommendation Engine Development

│   │   ├── 5.2.3 AI/ML Integration for Prediction

│   │   ├── 5.2.4 Recommendation Prioritization

│   │   └── 5.2.5 Recommendation UI

│   ├── 5.3 Approval Handler (Human-in-the-Loop)

│   │   ├── 5.3.1 Approval Database Schema (autonomy_approvals)

│   │   ├── 5.3.2 Approval Workflow Implementation

│   │   ├── 5.3.3 Approval API

│   │   ├── 5.3.4 Notification Integration

│   │   └── 5.3.5 Approval UI

│   ├── 5.4 Action Executor

│   │   ├── 5.4.1 Action Execution Engine

│   │   ├── 5.4.2 Integration with IoT Command Service

│   │   ├── 5.4.3 Integration with Workflow Service

│   │   └── 5.4.4 Execution Logging

│   └── 5.5 Feedback Loop

│       ├── 5.5.1 Feedback Database Schema (autonomy_feedback)

│       ├── 5.5.2 Outcome Tracking

│       ├── 5.5.3 Accuracy Calculation

│       ├── 5.5.4 AI/ML Retraining Trigger

│       └── 5.5.5 Effectiveness Dashboard

│

├── 6.0 DASHBOARD & REPORTING (6.1 - 6.2)

│   ├── 6.1 Dashboards

│   │   ├── 6.1.1 IoT Dashboard

│   │   ├── 6.1.2 Digital Twin Dashboard

│   │   ├── 6.1.3 Simulation Dashboard

│   │   └── 6.1.4 Autonomy Dashboard

│   └── 6.2 Reporting

│       ├── 6.2.1 IoT Reports (Device Health, Alert Log)

│       ├── 6.2.2 Twin Reports (State Snapshot, What-If Analysis)

│       ├── 6.2.3 Simulation Reports (Execution Results, Comparison, Optimization)

│       ├── 6.2.4 Autonomy Reports (Recommendation Log, Audit Trail, Effectiveness)

│       └── 6.2.5 System Reports (Integration Status, Performance Metrics)

│

├── 7.0 INTEGRATION & DATA LAYER (7.1 - 7.4)

│   ├── 7.1 ERP Connector

│   │   ├── 7.1.1 Kafka Event Consumer

│   │   ├── 7.1.2 Event Mapping & Transformation

│   │   ├── 7.1.3 Twin Update Trigger

│   │   └── 7.1.4 Error Handling & Retry

│   ├── 7.2 AI/ML Service Integration

│   │   ├── 7.2.1 API Client Development

│   │   ├── 7.2.2 Model Invocation for Prediction

│   │   ├── 7.2.3 Model Invocation for Simulation

│   │   └── 7.2.4 Model Invocation for Recommendation

│   ├── 7.3 External API Integration

│   │   ├── 7.3.1 Weather API Integration

│   │   ├── 7.3.2 External Data Source Configuration

│   │   └── 7.3.3 Data Sync Scheduler

│   └── 7.4 Data Pipeline Setup

│       ├── 7.4.1 ETL/ELT Pipeline Setup

│       ├── 7.4.2 Data Aggregation Implementation

│       └── 7.4.3 Data Lake Integration

│

└── 8.0 TESTING & QUALITY ASSURANCE (8.1 - 8.5)

├── 8.1 Unit Testing

│   ├── 8.1.1 Backend Unit Tests

│   ├── 8.1.2 Frontend Unit Tests

│   └── 8.1.3 Test Coverage Measurement

├── 8.2 Integration Testing

│   ├── 8.2.1 Service Integration Tests

│   ├── 8.2.2 Database Integration Tests

│   └── 8.2.3 Event-Driven Integration Tests

├── 8.3 Performance Testing

│   ├── 8.3.1 IoT Throughput Test

│   ├── 8.3.2 IoT Latency Test

│   ├── 8.3.3 Simulation Performance Test

│   └── 8.3.4 System Load Test

├── 8.4 Security Testing

│   ├── 8.4.1 Vulnerability Scanning

│   ├── 8.4.2 Penetration Testing

│   ├── 8.4.3 Authentication & Authorization Testing

│   └── 8.4.4 Data Encryption Testing

└── 8.5 User Acceptance Testing (UAT)

├── 8.5.1 UAT Test Plan Preparation

├── 8.5.2 UAT Test Execution

├── 8.5.3 Bug Fixing & Retesting

└── 8.5.4 UAT Sign-off

### 3.6.5. WBS Dictionary (Contoh Detail)

| WBS Element | 2.2 Telemetry Ingestion & Storage |
| --- | --- |
| ID | 2.2 |
| Description | Mengembangkan sistem penerimaan dan penyimpanan data telemetri dari perangkat IoT secara real-time dengan menggunakan TimescaleDB sebagai time-series database. |
| Deliverables | - Telemetry Ingestion API (REST/MQTT) - TimescaleDB schema (iot_telemetry) - Data retention policy (1 tahun) - Data aggregation functions |
| Activities | 2.2.1 TimescaleDB Schema Design 2.2.2 Telemetry Ingestion API Development 2.2.3 Telemetry Storage Implementation 2.2.4 Data Retention Policy Implementation |
| Resources | 2 IoT Engineers |
| Duration | 2 minggu |
| Effort | 120 jam |
| Cost | Rp 45.000.000 |
| Acceptance Criteria | - API menerima ≥ 10.000 msg/detik - Latency ≤ 5 detik - Data retention 1 tahun - Passing all unit & integration tests |
| Dependencies | 2.1 Device Registration (database ready) |
| Assumptions | - TimescaleDB extension terinstal di PostgreSQL - Device terdaftar sebelum mengirim telemetry |

## 3.7. VALIDATE SCOPE (PMI-12)

### 3.7.1. Tujuan

Memvalidasi deliverable yang dihasilkan dengan stakeholder untuk memastikan sesuai dengan kebutuhan dan mendapatkan penerimaan formal.

### 3.7.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Rencana proyek |
| Requirements Documentation | BA | Kebutuhan yang telah dikumpulkan |
| Work Performance Data | All Team | Data kinerja |
| Accepted Deliverables | All Team | Deliverable yang siap divalidasi |

### 3.7.3. Tools & Techniques

| Tools | Deskripsi |
| --- | --- |
| Inspection | Review deliverable oleh stakeholder |
| Product Review | Review produk dengan stakeholder |
| User Acceptance Testing (UAT) | Pengujian oleh user |
| Sprint Review | Review deliverable setiap sprint |

### 3.7.4. Validate Scope Schedule

| Validasi | Frekuensi | Responsible | Peserta |
| --- | --- | --- | --- |
| Sprint Review | Setiap 2 minggu | PM, BA | Tim Proyek, Product Owner |
| UAT Phase 1 | Minggu 16-17 | BA, QA | End Users (Ops) |
| UAT Phase 2 | Minggu 18-19 | BA, QA | End Users (Ops, Management) |
| Final Sign-off | Minggu 20 | PM | Project Sponsor |

### 3.7.5. Acceptance Form Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│              DELIVERABLE ACCEPTANCE FORM                                   │

│                P-FNE-08: Advanced & Autonomous Enterprise                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Deliverable Name:                                                          │

│  WBS Element:                                                               │

│  Version:                                                                   │

│  Date:                                                                      │

│                                                                             │

│  Acceptance Criteria Check:                                                 │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │ # │ Criteria                    │ Status │ Notes               │       │

│  │---│-----------------------------│--------│---------------------│       │

│  │ 1 │ [Criteria]                  │ [✓/✗]  │                     │       │

│  │ 2 │ [Criteria]                  │ [✓/✗]  │                     │       │

│  │ 3 │ [Criteria]                  │ [✓/✗]  │                     │       │

│  └─────────────────────────────────────────────────────────────────┘       │

│                                                                             │

│  Quality Check:                                                             │

│  - Unit Testing: [Passed/Failed]                                            │

│  - Integration Testing: [Passed/Failed]                                    │

│  - Performance Testing: [Passed/Failed]                                    │

│  - Security Testing: [Passed/Failed]                                       │

│                                                                             │

│  Sign-off:                                                                  │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │ Role                │ Name      │ Signature │ Date              │       │

│  │---------------------│-----------│-----------│-------------------│       │

│  │ Project Manager     │           │           │                   │       │

│  │ Product Owner       │           │           │                   │       │

│  │ Lead Teknis         │           │           │                   │       │

│  │ Stakeholder User    │           │           │                   │       │

│  └─────────────────────────────────────────────────────────────────┘       │

│                                                                             │

│  Notes / Issues:                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 3.8. CONTROL SCOPE (PMI-13)

### 3.8.1. Tujuan

Mengendalikan perubahan lingkup proyek dan mencegah scope creep dengan memastikan setiap perubahan melalui proses yang terkendali.

### 3.8.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Baseline scope |
| Requirements Documentation | BA | Kebutuhan yang telah disepakati |
| Work Performance Data | All Team | Data kinerja |
| Change Requests | All Team | Permintaan perubahan |

### 3.8.3. Tools & Techniques

| Tools | Deskripsi |
| --- | --- |
| Variance Analysis | Membandingkan aktual dengan baseline |
| Configuration Management | Mengelola versi requirements |
| Change Control | Proses perubahan via CCB |

### 3.8.4. Scope Control Mechanism

| Aktivitas | Frekuensi | Owner |
| --- | --- | --- |
| Requirements Review | Setiap sprint | BA, PM |
| Scope Variance Analysis | Bulanan | PM |
| Change Request Review | Sesuai kebutuhan | CCB |
| Backlog Grooming | 2 minggu | BA, PM, Leads |

### 3.8.5. Scope Baseline

| Baseline Element | Approval Date | Version |
| --- | --- | --- |
| Project Scope Statement | [DD/MM/YYYY] | 1.0 |
| WBS | [DD/MM/YYYY] | 1.0 |
| Requirements Documentation | [DD/MM/YYYY] | 1.0 |
| RTM | [DD/MM/YYYY] | 1.0 |

## 3.9. SCOPE MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Plan Scope Management | Project Charter | Expert Judgment | Scope Management Plan | PM, BA |
| Collect Requirements | Stakeholder Register | Interviews, Workshops | Requirements Doc, RTM | BA |
| Define Scope | Requirements Doc | Expert Judgment | Project Scope Statement | PM, BA |
| Create WBS | Scope Statement | Decomposition | WBS, WBS Dictionary | PM, Leads |
| Validate Scope | Deliverables, Requirements | Inspection, UAT | Accepted Deliverables | BA, PM, User |
| Control Scope | PMP, Change Requests | Variance Analysis | Scope Baseline Updates | PM, CCB |

# BAB 4: MANAJEMEN PENJADWALAN PROYEK

## 4.1. PENDAHULUAN

Manajemen penjadwalan proyek bertujuan untuk memastikan bahwa Proyek P-FNE-08: Advanced & Autonomous Enterprise selesai tepat waktu dengan mengelola urutan, durasi, dan ketergantungan aktivitas proyek secara efektif.

Proyek P-FNE-08 memiliki durasi 4-5 bulan (20 minggu) dengan 13 milestone kritis dan lebih dari 80 paket kerja. Penjadwalan yang baik sangat penting mengingat:

- Ketergantungan dengan proyek lain (P-FNE-01 s.d P-FNE-07)

- Kompleksitas teknis yang membutuhkan waktu pengembangan signifikan

- Risiko keterlambatan pada komponen IoT dan simulasi

- Kebutuhan UAT yang melibatkan banyak stakeholder

## 4.2. PROSES MANAJEMEN PENJADWALAN PROYEK

Berdasarkan PMBOK, terdapat 6 proses dalam manajemen penjadwalan proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Plan Schedule Management | PMI-14 | Menyusun rencana manajemen penjadwalan | Schedule Management Plan |
| Define Activities | PMI-15 | Mendefinisikan aktivitas proyek | Activity List, Activity Attributes |
| Sequence Activities | PMI-16 | Mengurutkan aktivitas | Network Diagram |
| Estimate Activity Durations | PMI-17 | Mengestimasi durasi aktivitas | Duration Estimates |
| Develop Schedule | PMI-18 | Menyusun jadwal proyek | Project Schedule (Gantt Chart) |
| Control Schedule | PMI-19 | Mengendalikan jadwal | Schedule Updates, Change Requests |

## 4.3. PLAN SCHEDULE MANAGEMENT (PMI-14)

### 4.3.1. Tujuan

Menyusun rencana manajemen penjadwalan yang mendefinisikan bagaimana jadwal akan dikembangkan, dimonitor, dan dikendalikan selama proyek berlangsung.

### 4.3.2. Output: Schedule Management Plan

Rencana Manajemen Penjadwalan P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Schedule Development | Menggunakan metode Agile-Scrum (2 minggu sprint) + Waterfall untuk fase besar |
| Estimation Technique | Story Points (Agile) + Expert Judgment + Analogue Estimation |
| Schedule Tools | Jira (Sprint Management), Gantt Chart (MS Project / Smartsheet) |
| Progress Tracking | Burndown Chart, Sprint Velocity, EVM |
| Schedule Control | Variance Analysis (SPI), Buffer Management (15% buffer) |
| Reporting | Weekly Progress Report, Sprint Review, Monthly Status Report |
| Level of Accuracy | ±10% untuk estimasi durasi |
| Units of Measure | Story Points, Days, Weeks |
| Control Thresholds | SPI < 0.9 → Change Request |
| Rules of Performance | 0/100 rule untuk milestone, 50/50 rule untuk paket kerja |

## 4.4. DEFINE ACTIVITIES (PMI-15)

### 4.4.1. Tujuan

Mendefinisikan aktivitas spesifik yang perlu dilakukan untuk menghasilkan setiap deliverable proyek.

### 4.4.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| WBS | PM + Leads | Struktur rincian pekerjaan |
| WBS Dictionary | PM + Leads | Detail setiap WBS element |
| Project Scope Statement | PM + BA | Lingkup proyek |
| Enterprise Environmental Factors | Organisasi | Tools, metode |

### 4.4.3. Output: Activity List

Activity List P-FNE-08 (High-Level):

| WBS Element | Activity ID | Activity Name | Description | Responsible |
| --- | --- | --- | --- | --- |
| 1.1.1 | ACT-001 | PMP Document Preparation | Menyusun dokumen PMP lengkap | PM |
| 1.1.2 | ACT-002 | Subsidiary Plans Development | Menyusun seluruh rencana turunan | PM, Leads |
| 1.1.3 | ACT-003 | PMP Approval & Sign-off | Mendapatkan persetujuan sponsor | PM |
| 2.1.1 | ACT-004 | Database Schema Design (iot_devices) | Merancang tabel iot_devices | IoT Lead |
| 2.1.2 | ACT-005 | Device Registration API Development | Mengembangkan API registrasi | IoT Engineer |
| 2.1.3 | ACT-006 | Device Authentication Implementation | Mengimplementasikan API Key/Cert | IoT Engineer |
| 2.2.1 | ACT-007 | TimescaleDB Schema Design | Merancang tabel telemetry | IoT Lead |
| 2.2.2 | ACT-008 | Telemetry Ingestion API Development | Mengembangkan API telemetry | IoT Engineer |
| 2.2.3 | ACT-009 | Telemetry Storage Implementation | Implementasi penyimpanan | IoT Engineer |
| 2.3.1 | ACT-010 | Threshold Rules Database Schema | Merancang tabel threshold | IoT Engineer |
| 2.3.2 | ACT-011 | Threshold Configuration API | Mengembangkan API threshold | IoT Engineer |
| 2.3.3 | ACT-012 | Alert Engine Implementation | Implementasi engine alert | IoT Engineer |
| 2.3.4 | ACT-013 | Alert Storage (iot_alerts) | Implementasi storage alert | IoT Engineer |
| 2.3.5 | ACT-014 | Notification Integration | Integrasi email/SMS/push | IoT Engineer |
| 2.4.1 | ACT-015 | Command Database Schema | Merancang tabel command | IoT Engineer |
| 2.4.2 | ACT-016 | Command API Development | Mengembangkan API command | IoT Engineer |
| 2.4.3 | ACT-017 | Command Approval Integration | Integrasi approval | IoT Engineer |
| 2.4.4 | ACT-018 | Gateway Integration (MQTT) | Integrasi MQTT gateway | IoT Engineer |
| 2.5.1 | ACT-019 | Device List View | UI daftar perangkat | Frontend Engineer |
| 2.5.2 | ACT-020 | Real-Time Telemetry Charts | UI grafik telemetry real-time | Frontend Engineer |
| 2.5.3 | ACT-021 | Alert Management View | UI manajemen alert | Frontend Engineer |
| 2.5.4 | ACT-022 | Device Health Monitoring View | UI monitoring kesehatan | Frontend Engineer |
| 3.1.1 | ACT-023 | Twin Database Schema (digital_twins) | Merancang tabel twin | Twin Lead |
| 3.1.2 | ACT-024 | Twin CRUD API Development | Mengembangkan API CRUD twin | Twin Engineer |
| 3.1.3 | ACT-025 | State Database Schema (twin_states) | Merancang tabel state | Twin Engineer |
| 3.1.4 | ACT-026 | Twin Versioning Implementation | Implementasi versi twin | Twin Engineer |
| 3.1.5 | ACT-027 | Twin Relationship Implementation (Neo4j) | Implementasi relasi di Neo4j | Twin Engineer |
| 3.2.1 | ACT-028 | Event Consumer for IoT (Kafka) | Consumer event IoT | Twin Engineer |
| 3.2.2 | ACT-029 | Event Consumer for ERP (Kafka) | Consumer event ERP | Twin Engineer |
| 3.2.3 | ACT-030 | State Update Engine | Engine update state | Twin Engineer |
| 3.2.4 | ACT-031 | State Validation & Transformation | Validasi transformasi state | Twin Engineer |
| 3.3.1 | ACT-032 | Historical State Schema | Merancang skema state historis | Twin Engineer |
| 3.3.2 | ACT-033 | Snapshot Scheduler | Scheduler snapshot | Twin Engineer |
| 3.3.3 | ACT-034 | Historical State API | API state historis | Twin Engineer |
| 3.4.1 | ACT-035 | What-If API Development | Mengembangkan API what-if | Twin Engineer |
| 3.4.2 | ACT-036 | AI/ML Service Integration | Integrasi dengan AI/ML | Twin Engineer |
| 3.4.3 | ACT-037 | Prediction Engine | Engine prediksi | Data Scientist |
| 3.4.4 | ACT-038 | What-If Results Storage | Storage hasil what-if | Twin Engineer |
| 3.5.1 | ACT-039 | 3D Model Loading (Three.js) | Implementasi loading 3D | Frontend Engineer |
| 3.5.2 | ACT-040 | State Visualization | Visualisasi state | Frontend Engineer |
| 3.5.3 | ACT-041 | Interactive Controls | Kontrol interaktif | Frontend Engineer |
| 3.5.4 | ACT-042 | Historical Replay Functionality | Fungsionalitas replay | Frontend Engineer |
| 4.1.1 | ACT-043 | Scenario Database Schema (simulation_scenarios) | Merancang tabel scenario | Sim Lead |
| 4.1.2 | ACT-044 | Scenario CRUD API | Mengembangkan API CRUD scenario | Sim Engineer |
| 4.1.3 | ACT-045 | Scenario Versioning | Implementasi versi scenario | Sim Engineer |
| 4.1.4 | ACT-046 | Scenario UI (Creation Wizard) | UI wizard pembuatan scenario | Frontend Engineer |
| 4.2.1 | ACT-047 | Crop Yield Simulation Development | Mengembangkan simulasi crop yield | Sim Engineer |
| 4.2.2 | ACT-048 | Production Capacity Simulation Development | Mengembangkan simulasi produksi | Sim Engineer |
| 4.2.3 | ACT-049 | Inventory Simulation Development | Mengembangkan simulasi inventory | Sim Engineer |
| 4.2.4 | ACT-050 | Supply Chain Disruption Simulation Development | Mengembangkan simulasi supply chain | Sim Engineer |
| 4.2.5 | ACT-051 | Expansion Simulation Development | Mengembangkan simulasi ekspansi | Sim Engineer |
| 4.3.1 | ACT-052 | Optimization Algorithm Selection | Memilih algoritma optimasi | Data Scientist |
| 4.3.2 | ACT-053 | Optimization Engine Development | Mengembangkan engine optimasi | Sim Engineer |
| 4.3.3 | ACT-054 | Optimization Results Storage | Storage hasil optimasi | Sim Engineer |
| 4.3.4 | ACT-055 | Optimization UI | UI optimasi | Frontend Engineer |
| 4.4.1 | ACT-056 | Comparison Engine Development | Mengembangkan engine perbandingan | Sim Engineer |
| 4.4.2 | ACT-057 | Comparison Matrix Calculation | Kalkulasi matriks perbandingan | Sim Engineer |
| 4.4.3 | ACT-058 | Radar Chart Generation | Generasi radar chart | Frontend Engineer |
| 4.4.4 | ACT-059 | Comparison UI | UI perbandingan | Frontend Engineer |
| 4.5.1 | ACT-060 | Simulation Dashboard | Dashboard simulasi | Frontend Engineer |
| 4.5.2 | ACT-061 | Results Viewer | Viewer hasil simulasi | Frontend Engineer |
| 4.5.3 | ACT-062 | Report Generator (PDF, Excel) | Generator laporan | Frontend Engineer |
| 4.5.4 | ACT-063 | Simulation Scheduler | Scheduler simulasi | Sim Engineer |
| 5.1.1 | ACT-064 | Rule Database Schema (autonomy_rules) | Merancang tabel rule | Auto Lead |
| 5.1.2 | ACT-065 | Rule CRUD API | Mengembangkan API CRUD rule | Auto Engineer |
| 5.1.3 | ACT-066 | Rule Evaluation Engine (Drools) | Implementasi engine Drools | Auto Engineer |
| 5.1.4 | ACT-067 | Event Listener (Kafka) | Listener event Kafka | Auto Engineer |
| 5.1.5 | ACT-068 | Rule Management UI | UI manajemen rule | Frontend Engineer |
| 5.2.1 | ACT-069 | Recommendation Database Schema | Merancang tabel rekomendasi | Auto Engineer |
| 5.2.2 | ACT-070 | Recommendation Engine Development | Mengembangkan engine rekomendasi | Auto Engineer |
| 5.2.3 | ACT-071 | AI/ML Integration for Prediction | Integrasi AI/ML untuk prediksi | Data Scientist |
| 5.2.4 | ACT-072 | Recommendation Prioritization | Prioritas rekomendasi | Auto Engineer |
| 5.2.5 | ACT-073 | Recommendation UI | UI rekomendasi | Frontend Engineer |
| 5.3.1 | ACT-074 | Approval Database Schema | Merancang tabel approval | Auto Engineer |
| 5.3.2 | ACT-075 | Approval Workflow Implementation | Implementasi workflow approval | Auto Engineer |
| 5.3.3 | ACT-076 | Approval API | API approval | Auto Engineer |
| 5.3.4 | ACT-077 | Notification Integration | Integrasi notifikasi | Auto Engineer |
| 5.3.5 | ACT-078 | Approval UI | UI approval | Frontend Engineer |
| 5.4.1 | ACT-079 | Action Execution Engine | Engine eksekusi aksi | Auto Engineer |
| 5.4.2 | ACT-080 | Integration with IoT Command Service | Integrasi command service | Auto Engineer |
| 5.4.3 | ACT-081 | Integration with Workflow Service | Integrasi workflow service | Auto Engineer |
| 5.5.1 | ACT-082 | Feedback Database Schema | Merancang tabel feedback | Data Scientist |
| 5.5.2 | ACT-083 | Outcome Tracking | Tracking outcome | Data Scientist |
| 5.5.3 | ACT-084 | Accuracy Calculation | Kalkulasi akurasi | Data Scientist |
| 5.5.4 | ACT-085 | AI/ML Retraining Trigger | Trigger retraining AI/ML | Data Scientist |
| 6.1.1 | ACT-086 | IoT Dashboard Development | Mengembangkan dashboard IoT | Frontend Engineer |
| 6.1.2 | ACT-087 | Digital Twin Dashboard Development | Mengembangkan dashboard twin | Frontend Engineer |
| 6.1.3 | ACT-088 | Simulation Dashboard Development | Mengembangkan dashboard simulasi | Frontend Engineer |
| 6.1.4 | ACT-089 | Autonomy Dashboard Development | Mengembangkan dashboard autonomy | Frontend Engineer |
| 6.2.1 | ACT-090 | IoT Reports Development | Mengembangkan laporan IoT | Frontend Engineer |
| 6.2.2 | ACT-091 | Twin Reports Development | Mengembangkan laporan twin | Frontend Engineer |
| 6.2.3 | ACT-092 | Simulation Reports Development | Mengembangkan laporan simulasi | Frontend Engineer |
| 6.2.4 | ACT-093 | Autonomy Reports Development | Mengembangkan laporan autonomy | Frontend Engineer |
| 7.1.1 | ACT-094 | Kafka Event Consumer | Consumer event ERP | DevOps |
| 7.1.2 | ACT-095 | Event Mapping & Transformation | Mapping & transformasi event | DevOps |
| 7.1.3 | ACT-096 | Twin Update Trigger | Trigger update twin | DevOps |
| 7.2.1 | ACT-097 | AI/ML API Client Development | Mengembangkan client API | Data Scientist |
| 7.2.2 | ACT-098 | Model Invocation for Prediction | Invoke model untuk prediksi | Data Scientist |
| 7.2.3 | ACT-099 | Model Invocation for Simulation | Invoke model untuk simulasi | Data Scientist |
| 7.2.4 | ACT-100 | Model Invocation for Recommendation | Invoke model untuk rekomendasi | Data Scientist |
| 7.3.1 | ACT-101 | Weather API Integration | Integrasi weather API | DevOps |
| 7.3.2 | ACT-102 | External Data Source Configuration | Konfigurasi sumber data | DevOps |
| 7.4.1 | ACT-103 | ETL/ELT Pipeline Setup | Setup pipeline data | DevOps |
| 7.4.2 | ACT-104 | Data Aggregation Implementation | Implementasi agregasi | DevOps |
| 8.1.1 | ACT-105 | Backend Unit Tests | Unit test backend | All Engineer |
| 8.1.2 | ACT-106 | Frontend Unit Tests | Unit test frontend | Frontend Engineer |
| 8.2.1 | ACT-107 | Service Integration Tests | Integration test service | QA |
| 8.2.2 | ACT-108 | Database Integration Tests | Integration test database | QA |
| 8.3.1 | ACT-109 | IoT Throughput Test | Test throughput IoT | QA |
| 8.3.2 | ACT-110 | IoT Latency Test | Test latency IoT | QA |
| 8.3.3 | ACT-111 | Simulation Performance Test | Test performa simulasi | QA |
| 8.4.1 | ACT-112 | Vulnerability Scanning | Scan vulnerability | Security |
| 8.4.2 | ACT-113 | Penetration Testing | Penetration test | Security |
| 8.5.1 | ACT-114 | UAT Test Plan Preparation | Persiapan test plan UAT | BA, QA |
| 8.5.2 | ACT-115 | UAT Test Execution | Pelaksanaan UAT | BA, QA, User |
| 8.5.3 | ACT-116 | Bug Fixing & Retesting | Perbaikan bug & retest | All Engineer |
| 8.5.4 | ACT-117 | UAT Sign-off | Tanda tangan UAT | BA, PM, User |
| 1.4.1 | ACT-118 | Final Report Preparation | Persiapan laporan akhir | PM |
| 1.4.2 | ACT-119 | Lesson Learned Session | Sesi lesson learned | PM, All Team |
| 1.4.3 | ACT-120 | Handover Documentation | Dokumentasi handover | PM, Leads |

## 4.5. SEQUENCE ACTIVITIES (PMI-16)

### 4.5.1. Tujuan

Mengurutkan aktivitas proyek berdasarkan ketergantungan logis untuk menghasilkan network diagram yang menunjukkan urutan pekerjaan.

### 4.5.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Activity List | PM + Leads | Daftar aktivitas |
| Activity Attributes | PM + Leads | Atribut aktivitas (durasi, resource) |
| Milestone List | PM | Daftar milestone |
| Project Scope Statement | PM + BA | Lingkup proyek |

### 4.5.3. Tools & Techniques

| Tools | Deskripsi |
| --- | --- |
| Precedence Diagramming Method (PDM) | Menggambarkan ketergantungan aktivitas |
| Dependency Determination | Mandatory, Discretionary, External |
| Lead and Lags | Menentukan lead/lag antar aktivitas |
| Network Diagram | Visualisasi urutan aktivitas |

### 4.5.4. Ketergantungan Aktivitas

Jenis Ketergantungan:

| Jenis | Deskripsi | Contoh |
| --- | --- | --- |
| Finish-to-Start (FS) | Aktivitas B dimulai setelah A selesai | Database Schema (2.1.1) → API Development (2.1.2) |
| Start-to-Start (SS) | Aktivitas B dimulai saat A dimulai | Frontend UI dimulai saat Backend API dimulai |
| Finish-to-Finish (FF) | Aktivitas B selesai saat A selesai | Unit Testing selesai saat Development selesai |
| Start-to-Finish (SF) | Aktivitas B selesai saat A dimulai | Jarang digunakan |

### 4.5.5. Network Diagram (High-Level)

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                           NETWORK DIAGRAM P-FNE-08 (HIGH-LEVEL)                    │

└─────────────────────────────────────────────────────────────────────────────────────┘

M1: Project Charter Approved (W1)

│

▼

┌─────────────────────────────────────────────────────────────────────────────────┐

│  PHASE 1: INISIASI & DESAIN (Minggu 1-4)                                        │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                 │

│  ACT-001: PMP Preparation  ────────────────▶  ACT-002: Subs Plans              │

│         │                                          │                           │

│         ▼                                          ▼                           │

│  ACT-003: PMP Approval         ACT-004: Database Design (IoT)                   │

│         │                              │                                        │

│         ▼                              ▼                                        │

│  ACT-005: Architecture Design    ACT-006: Database Design (Twin)                │

│         │                              │                                        │

│         ▼                              ▼                                        │

│  ACT-007: UI/UX Design           ACT-008: Database Design (Sim)                 │

│         │                              │                                        │

│         └──────────────┬───────────────┘                                        │

│                        ▼                                                        │

│               M2: Architecture Design Completed (W3)                            │

└─────────────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────────────┐

│  PHASE 2: DEVELOPMENT - SPRINT 1-4 (Minggu 5-12)                               │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                 │

│  ACT-004..009: IoT Development  │  ACT-023..034: Twin Development              │

│         │                        │         │                                    │

│         ▼                        │         ▼                                    │

│  ACT-010..014: Alert Engine      │  ACT-035..038: What-If Analysis             │

│         │                        │         │                                    │

│         ▼                        │         ▼                                    │

│  ACT-015..018: Command Service   │  ACT-039..042: Twin Viewer                  │

│         │                        │         │                                    │

│         ▼                        │         ▼                                    │

│  ACT-019..022: IoT Dashboard     │  M3: MVP IoT & Twin (W8)                    │

│         │                        │                                             │

│         └──────────────┬─────────┘                                             │

│                        ▼                                                        │

│  ACT-043..046: Scenario Management  │  ACT-047..051: 5 Sim Use Cases           │

│         │                            │         │                                │

│         ▼                            │         ▼                                │

│  ACT-052..055: Optimization Module   │  ACT-056..059: Comparison               │

│         │                            │         │                                │

│         └────────────────┬───────────┘                                        │

│                          ▼                                                      │

│  ACT-060..063: Simulation Workbench                                             │

│                          │                                                      │

│                          ▼                                                      │

│               M4: 5 Simulation Use Cases Done (W13)                            │

└─────────────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────────────┐

│  PHASE 3: DEVELOPMENT - SPRINT 5-7 (Minggu 13-17)                              │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                 │

│  ACT-064..068: Rule Engine  │  ACT-069..073: Recommendation                    │

│         │                   │         │                                        │

│         ▼                   │         ▼                                        │

│  ACT-074..078: Approval Handler │  ACT-079..081: Action Executor               │

│         │                   │         │                                        │

│         └───────────┬───────┘         │                                        │

│                     ▼                  │                                        │

│  ACT-082..085: Feedback Loop          │                                        │

│                     │                  │                                        │

│                     ▼                  │                                        │

│  ACT-086..089: Dashboards (4)         │                                        │

│                     │                  │                                        │

│                     ▼                  │                                        │

│  ACT-090..093: Reports (12)           │                                        │

│                     │                  │                                        │

│                     ▼                  │                                        │

│          M5: Autonomous Module (W15)   M6: System Integration (W17)            │

└─────────────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────────────┐

│  PHASE 4: TESTING & DEPLOYMENT (Minggu 16-20)                                  │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                 │

│  ACT-105..106: Unit Testing  │  ACT-107..108: Integration Testing              │

│         │                    │         │                                       │

│         ▼                    │         ▼                                       │

│  ACT-109..111: Performance Testing │  ACT-112..113: Security Testing           │

│         │                    │         │                                       │

│         └───────────┬────────┘         │                                       │

│                     ▼                  │                                       │

│  ACT-114..115: UAT Execution          │                                       │

│                     │                  │                                       │

│                     ▼                  │                                       │

│  ACT-116: Bug Fixing & Retesting      │                                       │

│                     │                  │                                       │

│                     ▼                  │                                       │

│          M7: UAT Passed (W19)          │                                       │

│                     │                  │                                       │

│                     ▼                  │                                       │

│          ACT-117: UAT Sign-off          │                                       │

│                     │                  │                                       │

│                     ▼                  │                                       │

│  ACT-118: Final Report │  ACT-119: Lesson Learned │  ACT-120: Handover        │

│                     │                  │                                       │

│                     ▼                  │                                       │

│          M8: Go-Live (W20)              │                                       │

└─────────────────────────────────────────────────────────────────────────────────┘

## 4.6. ESTIMATE ACTIVITY DURATIONS (PMI-17)

### 4.6.1. Tujuan

Mengestimasi durasi setiap aktivitas proyek berdasarkan sumber daya yang tersedia dan kompleksitas pekerjaan.

### 4.6.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Activity List | PM + Leads | Daftar aktivitas |
| Activity Attributes | PM + Leads | Atribut aktivitas |
| Resource Requirements | PM + Leads | Kebutuhan sumber daya |
| Resource Breakdown Structure | PM + Leads | Struktur sumber daya |

### 4.6.3. Tools & Techniques

| Tools | Deskripsi | Penggunaan |
| --- | --- | --- |
| Expert Judgment | Konsultasi dengan ahli | Semua aktivitas |
| Analogous Estimating | Berdasarkan proyek sebelumnya | Aktivitas serupa |
| Parametric Estimating | Berdasarkan parameter | Development per story point |
| Three-Point Estimating | Optimistic, Most Likely, Pessimistic | Aktivitas kritis |
| Reserve Analysis | Buffer untuk risiko | 15% buffer |

### 4.6.4. Duration Estimates

Contoh Estimasi Aktivitas Kritis:

| Activity ID | Activity Name | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected (O+4M+P)/6 | Resource | Effort (hours) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ACT-004 | Database Schema Design (iot_devices) | 8 | 16 | 24 | 16 | IoT Lead | 16 |
| ACT-005 | Device Registration API Development | 32 | 48 | 72 | 51 | IoT Eng 1 | 48 |
| ACT-006 | Device Authentication Implementation | 24 | 32 | 56 | 35 | IoT Eng 1 | 32 |
| ACT-008 | Telemetry Ingestion API Development | 40 | 64 | 88 | 64 | IoT Eng 2 | 64 |
| ACT-012 | Alert Engine Implementation | 48 | 72 | 104 | 74 | IoT Eng 2 | 72 |
| ACT-023 | Twin Database Schema (digital_twins) | 16 | 24 | 40 | 25 | Twin Lead | 24 |
| ACT-024 | Twin CRUD API Development | 32 | 48 | 72 | 51 | Twin Eng 1 | 48 |
| ACT-030 | State Update Engine | 40 | 64 | 88 | 64 | Twin Eng 2 | 64 |
| ACT-035 | What-If API Development | 32 | 48 | 72 | 51 | Twin Eng 2 | 48 |
| ACT-047 | Crop Yield Simulation Development | 40 | 64 | 96 | 65 | Sim Eng 1 | 64 |
| ACT-048 | Production Capacity Simulation Development | 32 | 56 | 80 | 57 | Sim Eng 2 | 56 |
| ACT-049 | Inventory Simulation Development | 32 | 48 | 72 | 51 | Sim Eng 2 | 48 |
| ACT-050 | Supply Chain Disruption Simulation | 40 | 56 | 88 | 58 | Sim Eng 1 | 56 |
| ACT-051 | Expansion Simulation Development | 32 | 48 | 72 | 51 | Sim Eng 2 | 48 |
| ACT-066 | Rule Evaluation Engine (Drools) | 40 | 64 | 96 | 65 | Auto Eng 1 | 64 |
| ACT-070 | Recommendation Engine Development | 32 | 56 | 80 | 57 | Auto Eng 2 | 56 |
| ACT-075 | Approval Workflow Implementation | 32 | 48 | 72 | 51 | Auto Eng 1 | 48 |
| ACT-086 | IoT Dashboard Development | 40 | 64 | 96 | 65 | Frontend 1 | 64 |
| ACT-087 | Digital Twin Dashboard Development | 32 | 56 | 80 | 57 | Frontend 2 | 56 |

### 4.6.5. Velocity Planning (Agile)

| Sprint | Sprint Goal | Story Points | Velocity |
| --- | --- | --- | --- |
| Sprint 1 (W1-2) | Project Setup, Architecture Design | 20 | 20 |
| Sprint 2 (W3-4) | Database Design, UI/UX Design | 25 | 22 |
| Sprint 3 (W5-6) | IoT MVP (Device Registration, Telemetry) | 30 | 25 |
| Sprint 4 (W7-8) | IoT Complete (Alert, Command, Dashboard) | 35 | 28 |
| Sprint 5 (W9-10) | Twin MVP (Creation, State Sync) | 30 | 26 |
| Sprint 6 (W11-12) | Twin Complete (What-If, Viewer) | 35 | 28 |
| Sprint 7 (W13-14) | Simulation (Scenarios, Use Cases) | 40 | 30 |
| Sprint 8 (W15-16) | Autonomous (Rule Engine, Recommendation, Approval) | 35 | 28 |
| Sprint 9 (W17-18) | Integration, Dashboards, Reporting | 30 | 26 |
| Sprint 10 (W19-20) | Testing, UAT, Deployment | 20 | 20 |

## 4.7. DEVELOP SCHEDULE (PMI-18)

### 4.7.1. Tujuan

Mengembangkan jadwal proyek yang terintegrasi dengan milestone, aktivitas, durasi, dan ketergantungan yang telah ditentukan.

### 4.7.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Activity List | PM + Leads | Daftar aktivitas |
| Activity Attributes | PM + Leads | Atribut aktivitas |
| Duration Estimates | PM + Leads | Estimasi durasi |
| Resource Calendars | PM + HR | Kalender sumber daya |
| Project Scope Statement | PM + BA | Lingkup proyek |

### 4.7.3. Output: Project Schedule

Gantt Chart P-FNE-08 (High-Level):

| Fase | Sprint | Minggu 1-2 | Minggu 3-4 | Minggu 5-6 | Minggu 7-8 | Minggu 9-10 | Minggu 11-12 | Minggu 13-14 | Minggu 15-16 | Minggu 17-18 | Minggu 19-20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PHASE 1: INISIASI & DESAIN |  |  |  |  |  |  |  |  |  |  |  |
| PMP & Planning | S0 | ██ |  |  |  |  |  |  |  |  |  |
| Architecture Design | S1 | ██ | ██ |  |  |  |  |  |  |  |  |
| Database Design | S1 |  | ██ |  |  |  |  |  |  |  |  |
| UI/UX Design | S1 |  | ██ |  |  |  |  |  |  |  |  |
| Milestone M1-M2 |  | ● | ● |  |  |  |  |  |  |  |  |
| PHASE 2: DEVELOPMENT - SPRINT 1-4 |  |  |  |  |  |  |  |  |  |  |  |
| IoT Development | S2-S3 |  |  | ██ | ██ | ██ |  |  |  |  |  |
| IoT Dashboard | S3 |  |  |  | ██ |  |  |  |  |  |  |
| Digital Twin Development | S4-S5 |  |  |  |  | ██ | ██ | ██ |  |  |  |
| Twin Viewer | S5 |  |  |  |  |  | ██ |  |  |  |  |
| Milestone M3: MVP IoT & Twin |  |  |  |  | ● |  |  |  |  |  |  |
| Simulation - 5 Use Cases | S6-S7 |  |  |  |  |  |  | ██ | ██ |  |  |
| Optimization & Comparison | S7 |  |  |  |  |  |  |  | ██ |  |  |
| Simulation Workbench | S7 |  |  |  |  |  |  |  | ██ |  |  |
| Milestone M4: Simulation Done |  |  |  |  |  |  |  | ● |  |  |  |
| PHASE 3: DEVELOPMENT - SPRINT 5-7 |  |  |  |  |  |  |  |  |  |  |  |
| Autonomous - Rule Engine | S8 |  |  |  |  |  |  |  | ██ |  |  |
| Autonomous - Recommendation | S8 |  |  |  |  |  |  |  | ██ |  |  |
| Autonomous - Approval & Executor | S9 |  |  |  |  |  |  |  |  | ██ |  |
| Autonomous - Feedback Loop | S9 |  |  |  |  |  |  |  |  | ██ |  |
| Dashboards & Reporting | S9 |  |  |  |  |  |  |  |  | ██ |  |
| Milestone M5-M6: Auto & Integration |  |  |  |  |  |  |  |  | ● | ● |  |
| PHASE 4: TESTING & DEPLOYMENT |  |  |  |  |  |  |  |  |  |  |  |
| Unit & Integration Testing | S10 |  |  |  |  |  |  |  |  | ██ |  |
| Performance Testing | S10 |  |  |  |  |  |  |  |  |  | ██ |
| Security Testing | S10 |  |  |  |  |  |  |  |  |  | ██ |
| UAT Execution | S10 |  |  |  |  |  |  |  |  |  | ██ |
| Bug Fixing & Retesting | S10 |  |  |  |  |  |  |  |  |  | ██ |
| Deployment & Handover | S10 |  |  |  |  |  |  |  |  |  | ██ |
| Milestone M7-M8: UAT & Go-Live |  |  |  |  |  |  |  |  |  | ● | ● |

### 4.7.4. Milestone Schedule

| Milestone ID | Milestone Name | Tanggal Target | Waktu (Minggu) | Kriteria Sukses |
| --- | --- | --- | --- | --- |
| M1 | Project Charter Approved | [DD/MM/YYYY] | W1 | Dokumen ditandatangani sponsor |
| M2 | Architecture Design Completed | [DD/MM/YYYY] | W3 | Desain arsitektur tervalidasi |
| M3 | MVP IoT & Twin Completed | [DD/MM/YYYY] | W8 | Device registration + Twin creation berfungsi |
| M4 | 5 Simulation Use Cases Completed | [DD/MM/YYYY] | W13 | 5 simulasi berfungsi dengan accuracy ≥85% |
| M5 | Autonomous Module Completed | [DD/MM/YYYY] | W15 | Rule engine + approval flow berfungsi |
| M6 | System Integration Completed | [DD/MM/YYYY] | W17 | Semua modul terintegrasi |
| M7 | UAT Passed | [DD/MM/YYYY] | W19 | User sign-off |
| M8 | Go-Live | [DD/MM/YYYY] | W20 | Sistem berjalan di production |

### 4.7.5. Buffer Management

| Jenis Buffer | Alokasi | Deskripsi |
| --- | --- | --- |
| Project Buffer | 2 minggu (15%) | Buffer untuk seluruh proyek di akhir schedule |
| Sprint Buffer | 1 hari per sprint | Buffer untuk setiap sprint untuk mengatasi issue |
| Milestone Buffer | 2-3 hari per milestone | Buffer untuk milestone kritis |

## 4.8. CONTROL SCHEDULE (PMI-19)

### 4.8.1. Tujuan

Mengendalikan jadwal proyek dengan memonitor kemajuan aktual, menganalisis varian, dan mengambil tindakan korektif jika diperlukan.

### 4.8.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Baseline jadwal |
| Work Performance Data | All Team | Data kemajuan aktual |
| Sprint Reports | All Team | Laporan sprint |
| Change Requests | All Team | Permintaan perubahan |

### 4.8.3. Tools & Techniques

| Tools | Deskripsi | Penggunaan |
| --- | --- | --- |
| Earned Value Management (EVM) | Mengukur kinerja jadwal dan biaya | Bulanan |
| Burndown Chart | Memantau progress sprint | Harian |
| Variance Analysis | Menganalisis penyimpangan | Mingguan |
| Trend Analysis | Memprediksi kinerja masa depan | 2 minggu |
| Schedule Compression | Crashing atau fast-tracking | Jika terjadi delay |
| Reserve Analysis | Mengelola buffer | Bulanan |
| Performance Reviews | Review kinerja tim | 2 minggu |

### 4.8.4. Performance Metrics

| Metric | Formula | Target | Frequency |
| --- | --- | --- | --- |
| SPI (Schedule Performance Index) | SPI = EV / PV | ≥ 0.95 | Bulanan |
| SV (Schedule Variance) | SV = EV - PV | ≥ 0 | Bulanan |
| EAC (Estimate at Completion) | EAC = AC + (BAC - EV) | Dalam budget | Bulanan |
| ETC (Estimate to Complete) | ETC = EAC - AC | Akurat | Bulanan |
| Sprint Velocity | Story points per sprint | 20-30 SP/sprint | 2 minggu |
| Burndown | Remaining vs time | On track | Harian |

### 4.8.5. Schedule Control Thresholds

| Level | SPI Range | Tindakan |
| --- | --- | --- |
| Green | ≥ 0.95 | Normal monitoring |
| Yellow | 0.85 - 0.94 | Analisis akar masalah, rencana mitigasi |
| Red | < 0.85 | Change request, schedule recovery plan, sponsor notification |

### 4.8.6. Schedule Recovery Plan Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    SCHEDULE RECOVERY PLAN                                  │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Date: [DD/MM/YYYY]                                                         │

│  Prepared By: [PM Name]                                                     │

│                                                                             │

│  CURRENT STATUS:                                                            │

│  ───────────────────────────────────────────────────────────────────────── │

│  - Baseline Completion Date: [DD/MM/YYYY]                                 │

│  - Forecast Completion Date: [DD/MM/YYYY]                                 │

│  - SPI: [Value]                                                            │

│  - Delay: [X] days/weeks                                                   │

│                                                                             │

│  ROOT CAUSE:                                                                │

│  ───────────────────────────────────────────────────────────────────────── │

│  - [Cause 1]                                                               │

│  - [Cause 2]                                                               │

│                                                                             │

│  RECOVERY STRATEGY:                                                         │

│  ───────────────────────────────────────────────────────────────────────── │

│  - [Strategy 1 - Crashing/Adding Resources]                                │

│  - [Strategy 2 - Fast-tracking]                                            │

│  - [Strategy 3 - Scope Reduction (if approved)]                            │

│                                                                             │

│  ACTION PLAN:                                                               │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ # │ Action                │ Owner   │ Target Date │ Status             │

│  │---│-----------------------│---------│-------------│--------------------│

│  │ 1 │                       │         │             │                    │

│  │ 2 │                       │         │             │                    │

│  │ 3 │                       │         │             │                    │

│                                                                             │

│  REVISED SCHEDULE:                                                          │

│  ───────────────────────────────────────────────────────────────────────── │

│  - New Completion Date: [DD/MM/YYYY]                                      │

│  - Buffer Used: [X] days                                                   │

│  - Remaining Buffer: [X] days                                              │

│                                                                             │

│  APPROVAL:                                                                  │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Role                │ Name      │ Signature │ Date                     │

│  │---------------------│-----------│-----------│--------------------------│

│  │ Project Manager     │           │           │                          │

│  │ Project Sponsor     │           │           │                          │

│  └──────────────────────────────────────────────────────────────────────── │

└─────────────────────────────────────────────────────────────────────────────┘

### 4.8.7. Reporting Schedule

| Laporan | Frekuensi | Format | Penerima |
| --- | --- | --- | --- |
| Daily Standup | Harian | Verbal/Charts | Tim Proyek |
| Sprint Burndown | 2 minggu | Chart | Tim Proyek, PM |
| Weekly Progress Report | Mingguan | Slides/PDF | PM, Sponsor |
| Monthly Executive Report | Bulanan | Slides/PDF | Steering Committee |
| Milestone Report | Saat milestone | PDF | Sponsor, Steering Committee |
| EVM Report | Bulanan | Spreadsheet | PM, Sponsor |

### 4.8.8. Schedule Performance Baseline

| Baseline Element | Approval Date | Version |
| --- | --- | --- |
| Project Schedule (Gantt Chart) | [DD/MM/YYYY] | 1.0 |
| Milestone Schedule | [DD/MM/YYYY] | 1.0 |
| Resource Calendar | [DD/MM/YYYY] | 1.0 |
| Sprint Plan | [DD/MM/YYYY] | 1.0 |

## 4.9. SCHEDULE MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Plan Schedule Management | WBS, Scope Statement | Expert Judgment | Schedule Management Plan | PM |
| Define Activities | WBS, WBS Dictionary | Decomposition | Activity List | PM, Leads |
| Sequence Activities | Activity List | PDM | Network Diagram | PM, Leads |
| Estimate Durations | Activity List, Resources | Three-Point, Expert | Duration Estimates | PM, Leads |
| Develop Schedule | Activity List, Estimates | Gantt, Resource Leveling | Project Schedule | PM |
| Control Schedule | Schedule, Performance Data | EVM, Variance Analysis | Schedule Updates | PM |

## 4.10. KRITISITAS JADWAL

### 4.10.1. Critical Path

Identifikasi Critical Path:

| Path | Aktivitas | Durasi Total |
| --- | --- | --- |
| Critical Path | ACT-004 → ACT-005 → ACT-008 → ACT-012 → ACT-019 → ACT-023 → ACT-024 → ACT-030 → ACT-035 → ACT-047 → ACT-066 → ACT-070 → ACT-075 → ACT-086 → ACT-107 → ACT-109 → ACT-114 → ACT-116 → ACT-117 | 120 hari |

### 4.10.2. Critical Path Analysis

| Activity | ES | EF | LS | LF | Float |
| --- | --- | --- | --- | --- | --- |
| ACT-004 (IoT DB) | 0 | 3 | 0 | 3 | 0 |
| ACT-005 (Reg API) | 3 | 6 | 3 | 6 | 0 |
| ACT-008 (Telemetry API) | 6 | 10 | 6 | 10 | 0 |
| ACT-012 (Alert Engine) | 10 | 14 | 10 | 14 | 0 |
| ACT-019 (IoT Dashboard) | 14 | 17 | 14 | 17 | 0 |
| ACT-023 (Twin DB) | 17 | 20 | 17 | 20 | 0 |
| ACT-024 (Twin CRUD) | 20 | 24 | 20 | 24 | 0 |
| ACT-030 (State Sync) | 24 | 28 | 24 | 28 | 0 |
| ACT-035 (What-If) | 28 | 32 | 28 | 32 | 0 |
| ACT-047 (Crop Sim) | 32 | 37 | 32 | 37 | 0 |
| ACT-066 (Rule Engine) | 37 | 41 | 37 | 41 | 0 |
| ACT-070 (Recommendation) | 41 | 44 | 41 | 44 | 0 |
| ACT-075 (Approval) | 44 | 48 | 44 | 48 | 0 |
| ACT-086 (IoT Dashboard) | 48 | 52 | 48 | 52 | 0 |
| ACT-107 (Integration Test) | 52 | 55 | 52 | 55 | 0 |
| ACT-109 (Performance Test) | 55 | 57 | 55 | 57 | 0 |
| ACT-114 (UAT Execution) | 57 | 59 | 57 | 59 | 0 |
| ACT-116 (Bug Fixing) | 59 | 61 | 59 | 61 | 0 |
| ACT-117 (UAT Sign-off) | 61 | 62 | 61 | 62 | 0 |

Critical Path Duration: 62 hari kerja ≈ 90 hari kalender ≈ 18 minggu

Slack/Total Float: Aktivitas non-kritis memiliki float 5-15 hari

## 4.11. RINGKASAN PENJADWALAN

| Aspek | Rincian |
| --- | --- |
| Total Durasi Proyek | 20 minggu (140 hari) |
| Critical Path Duration | 18 minggu (124 hari) |
| Project Buffer | 2 minggu (16 hari) |
| Total Sprint | 10 sprint (2 minggu per sprint) |
| Milestone Total | 8 milestone |
| Aktivitas Total | 120 aktivitas |
| Resource Load | 8-14 orang peak |
| Schedule Risk | Medium (15% buffer) |

# BAB 5: MANAJEMEN BIAYA PROYEK

## 5.1. PENDAHULUAN

Manajemen biaya proyek bertujuan untuk memastikan bahwa Proyek P-FNE-08: Advanced & Autonomous Enterprise selesai sesuai anggaran yang telah ditetapkan dengan mengelola estimasi, penganggaran, dan pengendalian biaya secara efektif.

Proyek P-FNE-08 memiliki anggaran total Rp 1.900.000.000 dengan komponen biaya utama meliputi:

- Sumber Daya Manusia (45% dari total) – menggunakan tarif personil sesuai standar Inkindo 2026

- Infrastruktur & Tools (24% dari total)

- Pelatihan & Konsultasi (18% dari total)

- Testing & Quality (7% dari total)

- Contingency (6% dari total)

## 5.2. PROSES MANAJEMEN BIAYA PROYEK

Berdasarkan PMBOK, terdapat 4 proses dalam manajemen biaya proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Plan Cost Management | PMI-20 | Menyusun rencana manajemen biaya | Cost Management Plan |
| Estimate Costs | PMI-21 | Mengestimasi biaya aktivitas | Cost Estimates |
| Determine Budget | PMI-22 | Menentukan anggaran proyek | Project Budget |
| Control Costs | PMI-23 | Mengendalikan biaya | Cost Forecasts, Budget Updates |

## 5.3. PLAN COST MANAGEMENT (PMI-20)

### 5.3.1. Tujuan

Menyusun rencana manajemen biaya yang mendefinisikan bagaimana biaya akan diestimasi, dianggarkan, dimonitor, dan dikendalikan selama proyek berlangsung.

### 5.3.2. Output: Cost Management Plan

Rencana Manajemen Biaya P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Estimation Technique | Activity Based Costing (ABC) + Bottom-Up Estimating |
| Cost Baseline | Anggaran berdasarkan WBS dengan breakdown per paket kerja |
| Unit of Measure | Rupiah (IDR) |
| Level of Accuracy | ±10% untuk total anggaran |
| Control Thresholds | CPI < 0.90 → Change Request; CPI < 0.85 → Sponsor Notification |
| Performance Measurement | Earned Value Management (EVM) per bulan |
| Reporting | Monthly Cost Report, EVM Report |
| Reserve | Contingency Reserve: 5% (Rp 100.000.000), Management Reserve: 5% (Rp 100.000.000) |
| Cost Control | Weekly cost monitoring, monthly variance analysis |
| Payment Terms | 40% upfront, 30% milestone-based, 30% completion |

## 5.4. ESTIMATE COSTS (PMI-21)

### 5.4.1. Tujuan

Mengestimasi biaya setiap aktivitas proyek menggunakan metode Activity Based Costing (ABC) dengan memperhatikan tarif personil sesuai standar Inkindo 2026.

### 5.4.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Activity List | PM + Leads | Daftar aktivitas proyek |
| Resource Requirements | PM + Leads | Kebutuhan sumber daya per aktivitas |
| Resource Rates | HR + Finance | Tarif personil per jam (Inkindo 2026) |
| Enterprise Environmental Factors | Organisasi | Tarif pasar, inflasi 2026 |

### 5.4.3. Tarif Personil Berdasarkan Inkindo 2026

Berikut adalah tarif personil standar Inkindo (Ikatan Nasional Konsultan Indonesia) Tahun 2026 untuk berbagai level jabatan yang digunakan dalam estimasi biaya proyek:

| Level | Peran | Tarif per Jam (IDR) | Tarif per Hari (IDR) | Tarif per Bulan (IDR) |
| --- | --- | --- | --- | --- |
| Level 1 | Project Manager, Project Sponsor | Rp 850.000 | Rp 6.800.000 | Rp 136.000.000 |
| Level 2 | Lead Teknis (IoT/Twin/Sim/Auto Lead), Data Scientist | Rp 650.000 | Rp 5.200.000 | Rp 104.000.000 |
| Level 3 | Backend Engineer, Frontend Engineer, DevOps Engineer, Security Engineer | Rp 550.000 | Rp 4.400.000 | Rp 88.000.000 |
| Level 4 | Business Analyst, QA Engineer | Rp 450.000 | Rp 3.600.000 | Rp 72.000.000 |
| Level 5 | Junior Engineer, Support Staff | Rp 350.000 | Rp 2.800.000 | Rp 56.000.000 |

Catatan: Tarif di atas adalah tarif rata-rata untuk proyek skala enterprise sesuai dengan standar Inkindo 2026 dan telah memperhitungkan biaya overhead, administrasi, dan keuntungan konsultan.

### 5.4.4. Activity Based Costing (ABC) - Estimasi Biaya Personil

Metodologi Activity Based Costing:

- Identifikasi Aktivitas: Setiap aktivitas di WBS diidentifikasi

- Resource Driver: Identifikasi sumber daya yang digunakan per aktivitas

- Cost Driver: Alokasikan biaya berdasarkan resource driver

- Cost Pool: Kumpulkan biaya per kategori aktivitas

- Cost Assignment: Tentukan biaya total per aktivitas

#### 5.4.4.1. Estimasi Biaya Personil - Fase Inisiasi & Desain (Minggu 1-4)

| WBS Element | Aktivitas | Role | Durasi (Jam) | Tarif/Jam (IDR) | Total Biaya (IDR) |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 | PMP Document Preparation | PM | 40 | 850.000 | 34.000.000 |
| 1.1.1 | PMP Document Preparation | BA | 20 | 450.000 | 9.000.000 |
| 1.1.2 | Subsidiary Plans Development | PM | 30 | 850.000 | 25.500.000 |
| 1.1.2 | Subsidiary Plans Development | All Leads | 60 | 650.000 | 39.000.000 |
| 1.1.3 | PMP Approval & Sign-off | PM | 8 | 850.000 | 6.800.000 |
| 1.1.3 | PMP Approval & Sign-off | Sponsor | 4 | 850.000 | 3.400.000 |
| 1.2.1 | Architecture Design | IoT Lead | 40 | 650.000 | 26.000.000 |
| 1.2.1 | Architecture Design | Twin Lead | 40 | 650.000 | 26.000.000 |
| 1.2.1 | Architecture Design | Sim Lead | 40 | 650.000 | 26.000.000 |
| 1.2.1 | Architecture Design | Auto Lead | 40 | 650.000 | 26.000.000 |
| 1.2.1 | Architecture Design | DevOps | 30 | 550.000 | 16.500.000 |
| 1.3.1 | Database Schema Design (IoT) | IoT Lead | 24 | 650.000 | 15.600.000 |
| 1.3.2 | Database Schema Design (Twin) | Twin Lead | 24 | 650.000 | 15.600.000 |
| 1.3.3 | Database Schema Design (Sim) | Sim Lead | 24 | 650.000 | 15.600.000 |
| 1.3.4 | Database Schema Design (Auto) | Auto Lead | 16 | 650.000 | 10.400.000 |
| 1.4.1 | UI/UX Design - IoT Dashboard | Frontend Lead | 32 | 650.000 | 20.800.000 |
| 1.4.1 | UI/UX Design - Twin Viewer | Frontend Lead | 32 | 650.000 | 20.800.000 |
| 1.4.1 | UI/UX Design - Simulation | Frontend Lead | 24 | 650.000 | 15.600.000 |
| 1.4.1 | UI/UX Design - Autonomy | Frontend Lead | 16 | 650.000 | 10.400.000 |
| 1.4.2 | UI/UX Design - Frontend Development | Frontend Eng 1 | 40 | 550.000 | 22.000.000 |
| 1.4.2 | UI/UX Design - Frontend Development | Frontend Eng 2 | 40 | 550.000 | 22.000.000 |

| Subtotal Fase Inisiasi & Desain | | | | | Rp 407.400.000 |

#### 5.4.4.2. Estimasi Biaya Personil - Fase Development IoT (Minggu 5-8)

| WBS Element | Aktivitas | Role | Durasi (Jam) | Tarif/Jam (IDR) | Total Biaya (IDR) |
| --- | --- | --- | --- | --- | --- |
| 2.1.2 | Device Registration API | IoT Eng 1 | 48 | 550.000 | 26.400.000 |
| 2.1.3 | Device Authentication | IoT Eng 1 | 32 | 550.000 | 17.600.000 |
| 2.1.4 | Device Registration UI | Frontend Eng 1 | 24 | 550.000 | 13.200.000 |
| 2.2.2 | Telemetry Ingestion API | IoT Eng 2 | 64 | 550.000 | 35.200.000 |
| 2.2.3 | Telemetry Storage | IoT Eng 2 | 32 | 550.000 | 17.600.000 |
| 2.2.4 | Data Retention Policy | IoT Lead | 16 | 650.000 | 10.400.000 |
| 2.3.2 | Threshold Configuration API | IoT Eng 1 | 32 | 550.000 | 17.600.000 |
| 2.3.3 | Alert Engine | IoT Eng 2 | 72 | 550.000 | 39.600.000 |
| 2.3.4 | Alert Storage | IoT Eng 2 | 24 | 550.000 | 13.200.000 |
| 2.3.5 | Notification Integration | IoT Eng 1 | 32 | 550.000 | 17.600.000 |
| 2.4.2 | Command API | IoT Eng 1 | 32 | 550.000 | 17.600.000 |
| 2.4.3 | Command Approval Integration | IoT Eng 2 | 24 | 550.000 | 13.200.000 |
| 2.4.4 | Gateway Integration (MQTT) | IoT Lead | 24 | 650.000 | 15.600.000 |
| 2.5.1 | Device List View | Frontend Eng 2 | 32 | 550.000 | 17.600.000 |
| 2.5.2 | Real-Time Telemetry Charts | Frontend Eng 1 | 40 | 550.000 | 22.000.000 |
| 2.5.3 | Alert Management View | Frontend Eng 2 | 32 | 550.000 | 17.600.000 |
| 2.5.4 | Device Health Monitoring View | Frontend Eng 1 | 24 | 550.000 | 13.200.000 |

| Subtotal Fase Development IoT | | | | | Rp 327.400.000 |

#### 5.4.4.3. Estimasi Biaya Personil - Fase Development Digital Twin (Minggu 9-12)

| WBS Element | Aktivitas | Role | Durasi (Jam) | Tarif/Jam (IDR) | Total Biaya (IDR) |
| --- | --- | --- | --- | --- | --- |
| 3.1.2 | Twin CRUD API | Twin Eng 1 | 48 | 550.000 | 26.400.000 |
| 3.1.3 | State Database Schema | Twin Eng 2 | 24 | 550.000 | 13.200.000 |
| 3.1.4 | Twin Versioning | Twin Eng 1 | 24 | 550.000 | 13.200.000 |
| 3.1.5 | Twin Relationship (Neo4j) | Twin Lead | 32 | 650.000 | 20.800.000 |
| 3.2.1 | Event Consumer for IoT | Twin Eng 2 | 32 | 550.000 | 17.600.000 |
| 3.2.2 | Event Consumer for ERP | Twin Eng 2 | 32 | 550.000 | 17.600.000 |
| 3.2.3 | State Update Engine | Twin Eng 1 | 64 | 550.000 | 35.200.000 |
| 3.2.4 | State Validation & Transformation | Twin Lead | 24 | 650.000 | 15.600.000 |
| 3.3.2 | Snapshot Scheduler | Twin Eng 1 | 24 | 550.000 | 13.200.000 |
| 3.3.3 | Historical State API | Twin Eng 2 | 24 | 550.000 | 13.200.000 |
| 3.4.1 | What-If API | Twin Eng 2 | 48 | 550.000 | 26.400.000 |
| 3.4.2 | AI/ML Service Integration | Twin Eng 1 | 32 | 550.000 | 17.600.000 |
| 3.4.3 | Prediction Engine | Data Scientist | 40 | 650.000 | 26.000.000 |
| 3.4.4 | What-If Results Storage | Twin Eng 2 | 24 | 550.000 | 13.200.000 |
| 3.5.1 | 3D Model Loading (Three.js) | Frontend Eng 1 | 40 | 550.000 | 22.000.000 |
| 3.5.2 | State Visualization | Frontend Eng 2 | 32 | 550.000 | 17.600.000 |
| 3.5.3 | Interactive Controls | Frontend Eng 1 | 32 | 550.000 | 17.600.000 |
| 3.5.4 | Historical Replay | Frontend Eng 2 | 24 | 550.000 | 13.200.000 |

| Subtotal Fase Development Digital Twin | | | | | Rp 360.400.000 |

#### 5.4.4.4. Estimasi Biaya Personil - Fase Development Simulation (Minggu 13-14)

| WBS Element | Aktivitas | Role | Durasi (Jam) | Tarif/Jam (IDR) | Total Biaya (IDR) |
| --- | --- | --- | --- | --- | --- |
| 4.1.2 | Scenario CRUD API | Sim Eng 1 | 40 | 550.000 | 22.000.000 |
| 4.1.3 | Scenario Versioning | Sim Eng 2 | 24 | 550.000 | 13.200.000 |
| 4.1.4 | Scenario UI Wizard | Frontend Eng 1 | 32 | 550.000 | 17.600.000 |
| 4.2.1 | Crop Yield Simulation | Sim Eng 1 | 64 | 550.000 | 35.200.000 |
| 4.2.2 | Production Capacity Simulation | Sim Eng 2 | 56 | 550.000 | 30.800.000 |
| 4.2.3 | Inventory Simulation | Sim Eng 2 | 48 | 550.000 | 26.400.000 |
| 4.2.4 | Supply Chain Disruption Sim | Sim Eng 1 | 56 | 550.000 | 30.800.000 |
| 4.2.5 | Expansion Simulation | Sim Eng 2 | 48 | 550.000 | 26.400.000 |
| 4.3.1 | Optimization Algorithm Selection | Data Scientist | 32 | 650.000 | 20.800.000 |
| 4.3.2 | Optimization Engine | Sim Eng 1 | 40 | 550.000 | 22.000.000 |
| 4.3.3 | Optimization Results Storage | Sim Eng 2 | 24 | 550.000 | 13.200.000 |
| 4.3.4 | Optimization UI | Frontend Eng 2 | 32 | 550.000 | 17.600.000 |
| 4.4.1 | Comparison Engine | Sim Eng 1 | 32 | 550.000 | 17.600.000 |
| 4.4.2 | Comparison Matrix Calculation | Sim Eng 2 | 24 | 550.000 | 13.200.000 |
| 4.4.3 | Radar Chart Generation | Frontend Eng 1 | 24 | 550.000 | 13.200.000 |
| 4.4.4 | Comparison UI | Frontend Eng 2 | 32 | 550.000 | 17.600.000 |
| 4.5.2 | Results Viewer | Frontend Eng 1 | 32 | 550.000 | 17.600.000 |
| 4.5.3 | Report Generator | Frontend Eng 2 | 32 | 550.000 | 17.600.000 |
| 4.5.4 | Simulation Scheduler | Sim Eng 1 | 24 | 550.000 | 13.200.000 |

| Subtotal Fase Development Simulation | | | | | Rp 397.000.000 |

#### 5.4.4.5. Estimasi Biaya Personil - Fase Development Autonomous (Minggu 15-17)

| WBS Element | Aktivitas | Role | Durasi (Jam) | Tarif/Jam (IDR) | Total Biaya (IDR) |
| --- | --- | --- | --- | --- | --- |
| 5.1.2 | Rule CRUD API | Auto Eng 1 | 32 | 550.000 | 17.600.000 |
| 5.1.3 | Rule Evaluation Engine (Drools) | Auto Eng 1 | 64 | 550.000 | 35.200.000 |
| 5.1.4 | Event Listener (Kafka) | Auto Eng 2 | 32 | 550.000 | 17.600.000 |
| 5.1.5 | Rule Management UI | Frontend Eng 1 | 32 | 550.000 | 17.600.000 |
| 5.2.2 | Recommendation Engine | Auto Eng 2 | 56 | 550.000 | 30.800.000 |
| 5.2.3 | AI/ML Integration for Prediction | Data Scientist | 32 | 650.000 | 20.800.000 |
| 5.2.4 | Recommendation Prioritization | Auto Eng 1 | 24 | 550.000 | 13.200.000 |
| 5.2.5 | Recommendation UI | Frontend Eng 2 | 32 | 550.000 | 17.600.000 |
| 5.3.2 | Approval Workflow | Auto Eng 1 | 48 | 550.000 | 26.400.000 |
| 5.3.3 | Approval API | Auto Eng 2 | 32 | 550.000 | 17.600.000 |
| 5.3.4 | Notification Integration | Auto Eng 2 | 24 | 550.000 | 13.200.000 |
| 5.3.5 | Approval UI | Frontend Eng 1 | 32 | 550.000 | 17.600.000 |
| 5.4.1 | Action Execution Engine | Auto Eng 1 | 32 | 550.000 | 17.600.000 |
| 5.4.2 | IoT Command Integration | Auto Eng 2 | 24 | 550.000 | 13.200.000 |
| 5.4.3 | Workflow Service Integration | Auto Eng 1 | 24 | 550.000 | 13.200.000 |
| 5.5.3 | Accuracy Calculation | Data Scientist | 24 | 650.000 | 15.600.000 |
| 5.5.4 | AI/ML Retraining Trigger | Data Scientist | 24 | 650.000 | 15.600.000 |

| Subtotal Fase Development Autonomous | | | | | Rp 306.000.000 |

#### 5.4.4.6. Estimasi Biaya Personil - Fase Testing, Integration & Deployment (Minggu 18-20)

| WBS Element | Aktivitas | Role | Durasi (Jam) | Tarif/Jam (IDR) | Total Biaya (IDR) |
| --- | --- | --- | --- | --- | --- |
| 7.1.1 | Kafka Event Consumer | DevOps | 32 | 550.000 | 17.600.000 |
| 7.1.2 | Event Mapping & Transformation | DevOps | 32 | 550.000 | 17.600.000 |
| 7.1.3 | Twin Update Trigger | DevOps | 24 | 550.000 | 13.200.000 |
| 7.2.1 | AI/ML API Client | Data Scientist | 32 | 650.000 | 20.800.000 |
| 7.3.1 | Weather API Integration | DevOps | 24 | 550.000 | 13.200.000 |
| 7.4.1 | ETL/ELT Pipeline Setup | DevOps | 40 | 550.000 | 22.000.000 |
| 7.4.2 | Data Aggregation | DevOps | 32 | 550.000 | 17.600.000 |
| 8.1.1 | Backend Unit Tests | All Engineers | 120 | 550.000 | 66.000.000 |
| 8.1.2 | Frontend Unit Tests | Frontend Eng | 48 | 550.000 | 26.400.000 |
| 8.2.1 | Service Integration Tests | QA | 40 | 450.000 | 18.000.000 |
| 8.2.2 | Database Integration Tests | QA | 24 | 450.000 | 10.800.000 |
| 8.3.1 | IoT Throughput Test | QA | 32 | 450.000 | 14.400.000 |
| 8.3.2 | IoT Latency Test | QA | 16 | 450.000 | 7.200.000 |
| 8.3.3 | Simulation Performance Test | QA | 24 | 450.000 | 10.800.000 |
| 8.4.1 | Vulnerability Scanning | Security | 24 | 550.000 | 13.200.000 |
| 8.4.2 | Penetration Testing | Security | 40 | 550.000 | 22.000.000 |
| 8.5.1 | UAT Test Plan | BA, QA | 40 | 450.000 | 18.000.000 |
| 8.5.2 | UAT Test Execution | BA, QA, User | 80 | 450.000 | 36.000.000 |
| 8.5.3 | Bug Fixing & Retesting | All Engineers | 80 | 550.000 | 44.000.000 |
| 8.5.4 | UAT Sign-off | PM, BA, User | 16 | 450.000 | 7.200.000 |
| 1.4.1 | Final Report Preparation | PM | 24 | 850.000 | 20.400.000 |
| 1.4.2 | Lesson Learned Session | All Team | 24 | 550.000 | 13.200.000 |
| 1.4.3 | Handover Documentation | All Leads | 32 | 650.000 | 20.800.000 |

| Subtotal Fase Testing, Integration & Deployment | | | | | Rp 469.800.000 |

### 5.4.5. Rekapitulasi Biaya Personil (Activity Based Costing)

| Fase | Minggu | Aktivitas | Total Biaya Personil (IDR) |
| --- | --- | --- | --- |
| Fase 1 | Minggu 1-4 | Inisiasi & Desain | Rp 407.400.000 |
| Fase 2 | Minggu 5-8 | Development IoT | Rp 327.400.000 |
| Fase 3 | Minggu 9-12 | Development Digital Twin | Rp 360.400.000 |
| Fase 4 | Minggu 13-14 | Development Simulation | Rp 397.000.000 |
| Fase 5 | Minggu 15-17 | Development Autonomous | Rp 306.000.000 |
| Fase 6 | Minggu 18-20 | Testing, Integration & Deployment | Rp 469.800.000 |
| Total Biaya Personil (ABL) |  |  | Rp 2.268.000.000 |

### 5.4.6. Estimasi Biaya Non-Personil

| Kategori | Komponen | Estimasi Biaya (IDR) | Keterangan |
| --- | --- | --- | --- |
| Infrastruktur Cloud | AWS/GCP - Compute, Storage, Database, Kafka | Rp 300.000.000 | 5 bulan |
| Software Licenses | TimescaleDB License | Rp 50.000.000 | Enterprise license |
| Software Licenses | Neo4j License | Rp 30.000.000 | Enterprise license |
| Software Licenses | Confluent Kafka | Rp 20.000.000 | Enterprise license |
| Software Licenses | Grafana, ELK Stack | Rp 20.000.000 | Enterprise license |
| Hardware | IoT Gateway Devices (staging) | Rp 75.000.000 | 5 unit gateway |
| Training | IoT Training for Team | Rp 50.000.000 | 2 hari workshop |
| Training | Digital Twin Training | Rp 50.000.000 | 2 hari workshop |
| Training | Simulation & AI Training | Rp 50.000.000 | 2 hari workshop |
| Konsultan | IoT Consultant | Rp 100.000.000 | 2 bulan part-time |
| Konsultan | Simulation/AI Consultant | Rp 100.000.000 | 2 bulan part-time |
| Security | Penetration Testing Service | Rp 75.000.000 | External firm |
| Testing | Performance Testing Tools | Rp 50.000.000 | JMeter, LoadRunner |
| Operasional | Meeting, Travel, Documentation | Rp 50.000.000 | 5 bulan |
| Subtotal Non-Personil |  | Rp 1.020.000.000 |  |

## 5.5. DETERMINE BUDGET (PMI-22)

### 5.5.1. Tujuan

Menentukan anggaran proyek secara keseluruhan dengan mengagregasikan estimasi biaya aktivitas dan menambahkan reserve yang sesuai.

### 5.5.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Cost Estimates | PM + Leads | Estimasi biaya per aktivitas |
| Basis of Estimates | PM + Leads | Dasar estimasi biaya |
| Project Schedule | PM | Jadwal proyek |
| Resource Calendars | PM + HR | Kalender sumber daya |
| Risk Register | PM + Leads | Daftar risiko proyek |

### 5.5.3. Project Budget P-FNE-08

| Kategori | Komponen Biaya | Estimasi (IDR) | % Total |
| --- | --- | --- | --- |
| A. Biaya Personil | Project Manager | Rp 136.000.000 | 6.6% |
|  | Lead Teknis (4 org) | Rp 416.000.000 | 20.2% |
|  | Backend Engineers (6 org) | Rp 528.000.000 | 25.6% |
|  | Frontend Engineers (2 org) | Rp 176.000.000 | 8.5% |
|  | Data Scientist | Rp 104.000.000 | 5.0% |
|  | Business Analyst | Rp 72.000.000 | 3.5% |
|  | QA Engineer | Rp 72.000.000 | 3.5% |
|  | DevOps Engineer | Rp 88.000.000 | 4.3% |
|  | Security Engineer | Rp 88.000.000 | 4.3% |
|  | Subtotal Personil | Rp 1.680.000.000 | 81.6% |
| B. Biaya Non-Personil |  |  |  |
|  | Infrastruktur Cloud | Rp 300.000.000 | 14.6% |
|  | Software Licenses | Rp 120.000.000 | 5.8% |
|  | Hardware (IoT Gateway) | Rp 75.000.000 | 3.6% |
|  | Training | Rp 150.000.000 | 7.3% |
|  | Konsultan | Rp 200.000.000 | 9.7% |
|  | Security Testing | Rp 75.000.000 | 3.6% |
|  | Performance Testing Tools | Rp 50.000.000 | 2.4% |
|  | Operasional | Rp 50.000.000 | 2.4% |
|  | Subtotal Non-Personil | Rp 1.020.000.000 | 49.5% |
|  | Total Biaya Dasar (Baseline) | Rp 2.700.000.000 | 131.1% |
| C. Reserve |  |  |  |
|  | Contingency Reserve (5%) | Rp 100.000.000 | 4.9% |
|  | Management Reserve (5%) | Rp 100.000.000 | 4.9% |
|  | Total Reserve | Rp 200.000.000 | 9.7% |
|  | TOTAL ANGGARAN PROYEK | Rp 2.900.000.000 | 140.8% |

Catatan: Total biaya personil lebih tinggi dari perhitungan sebelumnya karena menggunakan tarif Inkindo 2026 yang lebih tinggi, ditambah dengan biaya overhead dan administrasi konsultan.

### 5.5.4. Budget Breakdown per Fase

| Fase | Minggu | Personil | Non-Personil | Total | % Total |
| --- | --- | --- | --- | --- | --- |
| Fase 1: Inisiasi & Desain | 1-4 | Rp 407.400.000 | Rp 50.000.000 | Rp 457.400.000 | 15.8% |
| Fase 2: Development IoT | 5-8 | Rp 327.400.000 | Rp 150.000.000 | Rp 477.400.000 | 16.5% |
| Fase 3: Development Twin | 9-12 | Rp 360.400.000 | Rp 100.000.000 | Rp 460.400.000 | 15.9% |
| Fase 4: Development Sim | 13-14 | Rp 397.000.000 | Rp 120.000.000 | Rp 517.000.000 | 17.8% |
| Fase 5: Development Auto | 15-17 | Rp 306.000.000 | Rp 150.000.000 | Rp 456.000.000 | 15.7% |
| Fase 6: Testing & Deployment | 18-20 | Rp 469.800.000 | Rp 50.000.000 | Rp 519.800.000 | 17.9% |
| Total Biaya Dasar |  | Rp 2.268.000.000 | Rp 620.000.000 | Rp 2.888.000.000 | 99.6% |
| Reserve |  | - | - | Rp 200.000.000 | 6.9% |
| TOTAL ANGGARAN |  | Rp 2.268.000.000 | Rp 620.000.000 | Rp 2.900.000.000 | 100% |

Catatan: Non-personil dialokasikan berdasarkan kebutuhan per fase, dengan cloud dan software licenses tersebar sepanjang proyek.

### 5.5.5. Cash Flow Projection

| Bulan | Minggu | Biaya Terpakai (IDR) | Kumulatif (IDR) | % Selesai |
| --- | --- | --- | --- | --- |
| Bulan 1 | W1-W4 | Rp 457.400.000 | Rp 457.400.000 | 15.8% |
| Bulan 2 | W5-W8 | Rp 477.400.000 | Rp 934.800.000 | 32.2% |
| Bulan 3 | W9-W12 | Rp 460.400.000 | Rp 1.395.200.000 | 48.1% |
| Bulan 4 | W13-W16 | Rp 517.000.000 | Rp 1.912.200.000 | 65.9% |
| Bulan 5 | W17-W20 | Rp 519.800.000 | Rp 2.432.000.000 | 83.9% |
| Subtotal |  | Rp 2.432.000.000 |  |  |
| Reserve |  | Rp 200.000.000 | Rp 2.632.000.000 | 90.8% |

### 5.5.6. Cost Baseline

Cost Baseline P-FNE-08:

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    COST BASELINE - P-FNE-08                                 │├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Total Budget: Rp 2,900,000,000                                            │

│                                                                             │

│  ┌───────────────────────────────────────────────────────────────────────┐ │

│  │                                                                       │ │

│  │ Rp 3.5M  ■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■   │ │

│  │ Rp 3.0M  ■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■   │ │

│  │ Rp 2.5M  ■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■   │ │

│  │ Rp 2.0M  ■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■   │ │

│  │ Rp 1.5M  ■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■   │ │

│  │ Rp 1.0M  ■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■   │ │

│  │ Rp 0.5M  ■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■■   │ │

│  │ Rp 0.0M  ────┬────┬────┬────┬────┬────┬────┬────┬────┬────┬────┬──── │ │

│  │          W1  W2  W3  W4  W5  W6  W7  W8  W9  W10 W11 W12 W13 W14    │ │

│  │          ────┬────┬────┬────┬────┬────┬────┬────┬────┬────┬────┬──── │ │

│  │          W15 W16 W17 W18 W19 W20                                     │ │

│  │                                                                       │ │

│  │  Legend: ■■■ = Cumulative Cost                                         │ │

│  │  ──── = Planned Value                                                 │ │

│  └───────────────────────────────────────────────────────────────────────┘ │

│                                                                             │

│  Milestone Cost:                                                            │

│  M1 (W1): Rp 100,000,000  │  M2 (W3): Rp 250,000,000                     │

│  M3 (W8): Rp 650,000,000  │  M4 (W13): Rp 1,600,000,000                  │

│  M5 (W15): Rp 1,900,000,000  │  M6 (W17): Rp 2,200,000,000              │

│  M7 (W19): Rp 2,600,000,000  │  M8 (W20): Rp 2,700,000,000 (Baseline)   │

│                                                                             │

│  Reserve: Rp 200,000,000 (Management + Contingency)                        │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 5.6. CONTROL COSTS (PMI-23)

### 5.6.1. Tujuan

Mengendalikan biaya proyek dengan memonitor pengeluaran aktual, menganalisis varian terhadap baseline, dan mengambil tindakan korektif jika diperlukan.

### 5.6.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Cost baseline |
| Work Performance Data | All Team | Data biaya aktual |
| Change Requests | All Team | Permintaan perubahan |
| Organizational Process Assets | Organisasi | Template cost control |

### 5.6.3. Tools & Techniques

| Tools | Deskripsi | Penggunaan |
| --- | --- | --- |
| Earned Value Management (EVM) | Mengukur kinerja biaya | Bulanan |
| Cost Variance Analysis | Menganalisis penyimpangan | Bulanan |
| Trend Analysis | Memprediksi kinerja masa depan | Bulanan |
| Forecasting | Estimate at Completion (EAC) | Bulanan |
| Reserve Analysis | Mengelola reserve | Bulanan |
| Performance Reviews | Review kinerja biaya | 2 minggu |

### 5.6.4. Earned Value Management (EVM)

EVM Metrics:

| Metric | Formula | Target | Frequency |
| --- | --- | --- | --- |
| Planned Value (PV) | Budgeted cost of work scheduled | Baseline | Bulanan |
| Earned Value (EV) | Budgeted cost of work performed | ≥ 0.95 | Bulanan |
| Actual Cost (AC) | Actual cost of work performed | ≤ EV | Bulanan |
| Cost Performance Index (CPI) | CPI = EV / AC | ≥ 0.95 | Bulanan |
| Cost Variance (CV) | CV = EV - AC | ≥ 0 | Bulanan |
| Estimate at Completion (EAC) | EAC = AC + (BAC - EV) | ≤ Budget | Bulanan |
| Estimate to Complete (ETC) | ETC = EAC - AC | Akurat | Bulanan |
| Variance at Completion (VAC) | VAC = BAC - EAC | ≥ 0 | Bulanan |

### 5.6.5. Cost Control Thresholds

| Level | CPI Range | Tindakan |
| --- | --- | --- |
| Green | ≥ 0.95 | Normal monitoring |
| Yellow | 0.85 - 0.94 | Analisis akar masalah, rencana mitigasi |
| Red | < 0.85 | Change request, cost recovery plan, sponsor notification |

### 5.6.6. Monthly Cost Report Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    MONTHLY COST REPORT                                     │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Report Period: [DD/MM/YYYY] - [DD/MM/YYYY]                               │

│  Prepared By: [PM Name]                                                     │

│  Date: [DD/MM/YYYY]                                                         │

│                                                                             │

│  1. SUMMARY                                                                 │

│  ───────────────────────────────────────────────────────────────────────── │

│  Total Budget (BAC):  Rp 2,900,000,000                                    │

│  Planned Value (PV):   Rp [xx,xxx,xxx]                                    │

│  Earned Value (EV):    Rp [xx,xxx,xxx]                                    │

│  Actual Cost (AC):     Rp [xx,xxx,xxx]                                    │

│  Cost Variance (CV):   Rp [xx,xxx,xxx]                                    │

│  CPI:                  [xx.xx]                                            │

│  EAC:                  Rp [xx,xxx,xxx]                                    │

│  VAC:                  Rp [xx,xxx,xxx]                                    │

│                                                                             │

│  2. BUDGET PER PHASE                                                        │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Phase       │ Budget   │ Actual   │ Variance │ % Complete             │

│  │-------------│----------│----------│----------│------------------------│

│  │ Fase 1      │ 457.4M   │ [xx.xM]  │ [xx.xM]  │ [xx]%                  │

│  │ Fase 2      │ 477.4M   │ [xx.xM]  │ [xx.xM]  │ [xx]%                  │

│  │ Fase 3      │ 460.4M   │ [xx.xM]  │ [xx.xM]  │ [xx]%                  │

│  │ Fase 4      │ 517.0M   │ [xx.xM]  │ [xx.xM]  │ [xx]%                  │

│  │ Fase 5      │ 456.0M   │ [xx.xM]  │ [xx.xM]  │ [xx]%                  │

│  │ Fase 6      │ 519.8M   │ [xx.xM]  │ [xx.xM]  │ [xx]%                  │

│                                                                             │

│  3. RESERVE USAGE                                                           │

│  ───────────────────────────────────────────────────────────────────────── │

│  Contingency Reserve:  Rp 100,000,000  │  Used: Rp [xx,xxx,xxx]          │

│  Management Reserve:   Rp 100,000,000  │  Used: Rp [xx,xxx,xxx]          │

│  Total Reserve Remaining: Rp [xx,xxx,xxx]                                 │

│                                                                             │

│  4. VARIANCE ANALYSIS                                                       │

│  ───────────────────────────────────────────────────────────────────────── │

│  Variance: [Positive/Negative]                                             │

│  Root Cause: [Cause description]                                           │

│  Corrective Action: [Action plan]                                         │

│                                                                             │

│  5. FORECAST                                                                │

│  ───────────────────────────────────────────────────────────────────────── │

│  EAC: Rp [xx,xxx,xxx]                                                     │

│  ETC: Rp [xx,xxx,xxx]                                                     │

│  Project Status: [On Track / At Risk / Over Budget]                       │

│                                                                             │

│  6. RECOMMENDATIONS                                                         │

│  ───────────────────────────────────────────────────────────────────────── │

│  [Recommendation 1]                                                        │

│  [Recommendation 2]                                                        │

│                                                                             │

│  APPROVAL:                                                                  │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Role                │ Name      │ Signature │ Date                     │

│  │---------------------│-----------│-----------│--------------------------│

│  │ Project Manager     │           │           │                          │

│  │ Project Sponsor     │           │           │                          │

│  └──────────────────────────────────────────────────────────────────────── │

└─────────────────────────────────────────────────────────────────────────────┘

### 5.6.7. Cost Control Process Flow

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        COST CONTROL PROCESS FLOW                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  1. MONITOR                                                                 │

│  ┌─────────────────────────┐                                               │

│  │ Weekly Cost Tracking    │                                               │

│  │ Monthly Cost Reporting  │                                               │

│  │ EVM Calculation         │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  2. ANALYZE                                                                │

│  ┌─────────────────────────┐                                               │

│  │ Cost Variance Analysis  │                                               │

│  │ Root Cause Analysis     │                                               │

│  │ Trend Analysis          │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  3. EVALUATE                                                               │

│  ┌─────────────────────────┐                                               │

│  │ Evaluate Impact         │                                               │

│  │ Check Thresholds        │                                               │

│  │ Determine Action        │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  4. ACT                                                                    │

│  ┌─────────────────────────┐                                               │

│  │ CPI ≥ 0.95: Continue    │                                               │

│  │ CPI 0.85-0.94: Mitigate │                                               │

│  │ CPI < 0.85: Recovery    │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  5. REPORT                                                                 │

│  ┌─────────────────────────┐                                               │

│  │ Update Cost Baseline    │                                               │

│  │ Update EAC/EAC Forecast │                                               │

│  │ Report to Sponsor       │                                               │

│  └─────────────────────────┘                                               │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 5.7. COST MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Plan Cost Management | Project Charter, EEF | Expert Judgment | Cost Management Plan | PM |
| Estimate Costs | Activity List, Resources | Activity Based Costing (ABC), Inkindo Tariff | Cost Estimates | PM, Leads |
| Determine Budget | Cost Estimates, Schedule | Aggregation, Reserve Analysis | Project Budget, Cost Baseline | PM |
| Control Costs | PMP, Performance Data | EVM, Variance Analysis | Cost Updates, Forecasts | PM, Finance |

## 5.8. RINGKASAN ANGGARAN PROYEK

| Aspek | Rincian |
| --- | --- |
| Total Anggaran (BAC) | Rp 2.900.000.000 |
| Cost Baseline | Rp 2.700.000.000 |
| Contingency Reserve | Rp 100.000.000 (5%) |
| Management Reserve | Rp 100.000.000 (5%) |
| Biaya Personil | Rp 1.680.000.000 (57.9%) |
| Biaya Non-Personil | Rp 1.020.000.000 (35.2%) |
| Reserve | Rp 200.000.000 (6.9%) |
| Level of Accuracy | ±10% |
| Control Threshold | CPI ≥ 0.95 |
| Reporting Frequency | Bulanan dengan EVM |

# BAB 6: MANAJEMEN MUTU PROYEK

## 6.1. PENDAHULUAN

Manajemen mutu proyek bertujuan untuk memastikan bahwa hasil proyek (deliverables) dan proses pelaksanaan proyek memenuhi standar kualitas yang ditetapkan dan sesuai dengan kebutuhan stakeholder. Untuk Proyek P-FNE-08: Advanced & Autonomous Enterprise, manajemen mutu menjadi sangat kritis karena sistem yang dikembangkan memiliki tuntutan kinerja tinggi (IoT throughput, latency, akurasi simulasi) dan harus terintegrasi dengan aman ke dalam ekosistem FNE.

## 6.2. PROSES MANAJEMEN MUTU PROYEK

Berdasarkan PMBOK, terdapat 3 proses dalam manajemen mutu proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Plan Quality Management | PMI-24 | Menyusun rencana manajemen mutu | Quality Management Plan |
| Manage Quality | PMI-25 | Melakukan quality assurance dan audit | Quality Reports, Test Reports |
| Control Quality | PMI-26 | Mengendalikan kualitas deliverable | Quality Control Measurements, Verified Deliverables |

## 6.3. PLAN QUALITY MANAGEMENT (PMI-24)

### 6.3.1. Tujuan

Menyusun rencana manajemen mutu yang mendefinisikan standar kualitas, metrik, proses pengujian, dan aktivitas quality assurance untuk proyek.

### 6.3.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Persyaratan mutu tingkat tinggi |
| Requirements Documentation | BA | Kebutuhan fungsional dan non-fungsional |
| Stakeholder Register | PM + BA | Kebutuhan stakeholder |
| Enterprise Environmental Factors | Organisasi | Standar industri, regulasi |
| Organizational Process Assets | Organisasi | Kebijakan mutu, template |

### 6.3.3. Standar Mutu yang Digunakan

| Standar | Deskripsi | Penerapan |
| --- | --- | --- |
| ISO 9001:2015 | Sistem manajemen mutu | Proses pengembangan dan QA |
| ISO/IEC 25010 | Software Quality Model | Kualitas produk (functionality, reliability, performance, security) |
| ISO/IEC 27001 | Keamanan informasi | Security requirement dan testing |
| OWASP | Web Application Security | Keamanan aplikasi web |
| ISTQB | Software Testing | Proses pengujian |
| IEEE 829 | Software Test Documentation | Dokumentasi pengujian |

### 6.3.4. Output: Quality Management Plan

Rencana Manajemen Mutu P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Quality Policy | "Deliver a reliable, high-performance, and secure Advanced & Autonomous Enterprise system that meets or exceeds stakeholder expectations through continuous quality improvement." |
| Quality Standards | ISO 9001:2015, ISO/IEC 25010, ISO/IEC 27001, OWASP, ISTQB |
| Quality Metrics | Performance, Reliability, Security, Usability, Maintainability |
| Quality Tools | Test Automation, Static Code Analysis, Performance Testing, Security Scanning |
| Quality Assurance | Code Review, Automated Testing, Continuous Integration, Audit |
| Quality Control | Unit Testing, Integration Testing, Performance Testing, Security Testing, UAT |
| Defect Management | Jira (Bug Tracking), Severity/Priority Classification |
| Documentation | Test Plan, Test Cases, Test Reports, Quality Reports |

## 6.4. QUALITY METRICS & TARGETS

### 6.4.1. Quality Metrics Matrix

| Kategori | Metric | Target | Measurement Method | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- |
| Performance | IoT Throughput | ≥ 10.000 msg/detik | Load Testing (JMeter) | Setiap milestone | QA Engineer |
| Performance | IoT Latency | ≤ 5 detik | End-to-End Testing | Setiap milestone | QA Engineer |
| Performance | Twin State Update | ≤ 1 menit | Performance Monitoring | Setiap milestone | QA Engineer |
| Performance | Simulation Time | ≤ 5 menit | Execution Tracking | Setiap milestone | QA Engineer |
| Accuracy | Simulation Accuracy | ≥ 85% | Validation vs Historical Data | Setiap milestone | Data Scientist |
| Reliability | System Uptime | ≥ 99.5% | Monitoring (Prometheus) | Mingguan | DevOps |
| Reliability | Error Rate | < 1% | Application Logs | Mingguan | DevOps |
| Code Quality | Unit Test Coverage | ≥ 80% | SonarQube/Jest Coverage | Setiap Sprint | All Engineers |
| Code Quality | Code Duplication | < 5% | SonarQube | Setiap Sprint | Tech Lead |
| Code Quality | Complexity | ≤ 10 per method | SonarQube | Setiap Sprint | Tech Lead |
| Security | Critical Vulnerabilities | 0 | Security Scan (OWASP ZAP) | Setiap Sprint | Security Engineer |
| Security | High Vulnerabilities | < 5 | Security Scan (OWASP ZAP) | Setiap Sprint | Security Engineer |
| Usability | User Satisfaction (SUS) | ≥ 70 | UAT Survey | UAT Phase | BA |
| Usability | Task Completion Rate | ≥ 95% | UAT Observation | UAT Phase | BA |
| Documentation | API Documentation Completeness | 100% | Swagger/OpenAPI Review | Setiap milestone | Tech Lead |

### 6.4.2. Quality Metrics - Functional vs Non-Functional

Functional Quality Metrics:

| Metric | Target | Method |
| --- | --- | --- |
| Functional Completeness | 100% of requirements implemented | Traceability Matrix Review |
| Requirements Traceability | 100% | RTM (Requirements Traceability Matrix) |
| User Story Acceptance | 100% of acceptance criteria met | UAT, Sprint Review |
| Business Logic Correctness | 0 critical bugs in business logic | Integration Testing |
| Integration Completeness | 100% of integrations working | Integration Testing |

Non-Functional Quality Metrics:

| Metric | Target | Method |
| --- | --- | --- |
| IoT Throughput | ≥ 10.000 msg/detik | Load Testing |
| IoT Latency | ≤ 5 detik | End-to-End Testing |
| Twin State Update | ≤ 1 menit | Performance Monitoring |
| Simulation Execution | ≤ 5 menit (1 tahun simulasi) | Performance Testing |
| Simulation Accuracy | ≥ 85% | Validation Testing |
| System Uptime | ≥ 99.5% | Monitoring |
| Critical Vulnerabilities | 0 | Security Scanning |
| Unit Test Coverage | ≥ 80% | Code Coverage Tools |
| System Usability Scale (SUS) | ≥ 70 | UAT Survey |

## 6.5. QUALITY ASSURANCE (MANAGE QUALITY - PMI-25)

### 6.5.1. Tujuan

Melakukan quality assurance untuk memastikan proses proyek berjalan sesuai dengan rencana dan standar mutu yang telah ditetapkan.

### 6.5.2. Quality Assurance Activities

| Aktivitas | Deskripsi | Frekuensi | Responsible |
| --- | --- | --- | --- |
| Code Review | Peer review setiap pull request | Setiap PR | Tech Lead / Peer |
| Static Code Analysis | Analisis kode statis (SonarQube) | Setiap build | DevOps |
| Automated Testing | Unit test, integration test | Setiap build | QA Engineer |
| Performance Testing | Load test, stress test | Setiap milestone | QA Engineer |
| Security Scanning | Vulnerability scan, penetration test | Setiap sprint | Security Engineer |
| Internal Audit | Audit proses pengembangan | Setiap bulan | PM + QA Lead |
| Peer Review | Review desain dan dokumentasi | Setiap milestone | Tech Lead |
| Continuous Integration | Build & test otomatis | Setiap commit | DevOps |
| Continuous Delivery | Deployment otomatis ke staging | Setiap sprint | DevOps |

### 6.5.3. Quality Audit Checklist

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        QUALITY AUDIT CHECKLIST                             │

│                   P-FNE-08: Advanced & Autonomous Enterprise               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Audit Date: [DD/MM/YYYY]                                                   │

│  Auditor: [Name]                                                            │

│  Audit Area: [Area Name]                                                    │

│  Sprint: [X]                                                                │

│                                                                             │

│  1. PROCESS COMPLIANCE                                                      │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │ # │ Check Item                           │ Status │ Notes       │       │

│  │---│--------------------------------------│--------│-------------│       │

│  │ 1 │ Agile/Scrum process followed         │ [✓/✗]  │             │       │

│  │ 2 │ Daily standup conducted              │ [✓/✗]  │             │       │

│  │ 3 │ Sprint planning completed            │ [✓/✗]  │             │       │

│  │ 4 │ Sprint retrospective conducted       │ [✓/✗]  │             │       │

│  │ 5 │ Jira updated with task status        │ [✓/✗]  │             │       │

│  │ 6 │ Code review performed                │ [✓/✗]  │             │       │

│  │ 7 │ CI/CD pipeline operational           │ [✓/✗]  │             │       │

│  └─────────────────────────────────────────────────────────────────┘       │

│                                                                             │

│  2. CODE QUALITY                                                            │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │ # │ Check Item                           │ Status │ Notes       │       │

│  │---│--------------------------------------│--------│-------------│       │

│  │ 8 │ Unit test coverage ≥ 80%             │ [✓/✗]  │             │       │

│  │ 9 │ Code duplication < 5%                │ [✓/✗]  │             │       │

│  │10 │ Complexity ≤ 10 per method           │ [✓/✗]  │             │       │

│  │11 │ No critical security vulnerabilities │ [✓/✗]  │             │       │

│  │12 │ Code standard compliance             │ [✓/✗]  │             │       │

│  │13 │ Documentation completeness           │ [✓/✗]  │             │       │

│  └─────────────────────────────────────────────────────────────────┘       │

│                                                                             │

│  3. TESTING QUALITY                                                         │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │ # │ Check Item                           │ Status │ Notes       │       │

│  │---│--------------------------------------│--------│-------------│       │

│  │14 │ Test plan exists and updated         │ [✓/✗]  │             │       │

│  │15 │ Test cases documented                │ [✓/✗]  │             │       │

│  │16 │ All test cases executed              │ [✓/✗]  │             │       │

│  │17 │ Defects logged and tracked           │ [✓/✗]  │             │       │

│  │18 │ Critical defects resolved            │ [✓/✗]  │             │       │

│  │19 │ Performance tests executed           │ [✓/✗]  │             │       │

│  │20 │ Security tests executed              │ [✓/✗]  │             │       │

│  └─────────────────────────────────────────────────────────────────┘       │

│                                                                             │

│  4. DOCUMENTATION QUALITY                                                   │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │ # │ Check Item                           │ Status │ Notes       │       │

│  │---│--------------------------------------│--------│-------------│       │

│  │21 │ Technical documentation updated      │ [✓/✗]  │             │       │

│  │22 │ API documentation complete           │ [✓/✗]  │             │       │

│  │23 │ User manual exists                   │ [✓/✗]  │             │       │

│  │24 │ Admin guide exists                   │ [✓/✗]  │             │       │

│  │25 │ Deployment guide exists              │ [✓/✗]  │             │       │

│  └─────────────────────────────────────────────────────────────────┘       │

│                                                                             │

│  Findings Summary:                                                          │

│  - Major Issues: [X]                                                        │

│  - Minor Issues: [X]                                                        │

│  - Recommendations: [List]                                                 │

│                                                                             │

│  Auditor Signature: _______________  Date: _______________                │

│  PM Signature: _______________      Date: _______________                │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.5.4. Continuous Improvement Cycle

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                  CONTINUOUS IMPROVEMENT CYCLE (PDCA)                        │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │                     PLAN                                        │       │

│  │  - Define quality objectives                                   │       │

│  │  - Identify improvement opportunities                          │       │

│  │  - Plan corrective actions                                     │       │

│  └────────────────────────┬───────────────────────────────────────┘       │

│                           │                                                │

│                           ▼                                                │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │                     DO                                          │       │

│  │  - Implement corrective actions                                │       │

│  │  - Execute quality activities                                  │       │

│  │  - Monitor progress                                             │       │

│  └────────────────────────┬───────────────────────────────────────┘       │

│                           │                                                │

│                           ▼                                                │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │                    CHECK                                         │       │

│  │  - Measure results                                             │       │

│  │  - Compare with targets                                        │       │

│  │  - Analyze variance                                            │       │

│  └────────────────────────┬───────────────────────────────────────┘       │

│                           │                                                │

│                           ▼                                                │

│  ┌─────────────────────────────────────────────────────────────────┐       │

│  │                     ACT                                          │       │

│  │  - Standardize successful improvements                         │       │

│  │  - Update quality standards                                    │       │

│  │  - Plan next improvement cycle                                  │       │

│  └─────────────────────────────────────────────────────────────────┘       │

│                                                                             │

│  Sprint Retrospective: Setiap 2 minggu                                     │

│  Quality Review Meeting: Setiap bulan                                      │

│  Process Improvement Plan: Setiap milestone                                │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 6.6. QUALITY CONTROL (CONTROL QUALITY - PMI-26)

### 6.6.1. Tujuan

Mengendalikan kualitas deliverable dengan melakukan pengujian, inspeksi, dan verifikasi untuk memastikan deliverables memenuhi standar kualitas yang ditetapkan.

### 6.6.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Management Plan | PM | Quality baseline |
| Quality Metrics | PM + QA | Target kualitas |
| Work Performance Data | All Team | Data pengujian |
| Approved Change Requests | CCB | Perubahan yang disetujui |

### 6.6.3. Testing Strategy

Testing Pyramid:

text

┌─────────────────────────────┐

│         UAT                 │

│   (User Acceptance Test)    │

│     - End-to-End Testing    │

│     - Usability Testing     │

└─────────────┬───────────────┘

│

┌─────────────┴───────────────┐

│       Integration Testing   │

│  - Service Integration      │

│  - Database Integration     │

│  - Event-Driven Testing     │

└─────────────┬───────────────┘

│

┌─────────────┴───────────────┐

│         Unit Testing        │

│  - Backend Unit Tests       │

│  - Frontend Unit Tests      │

│  - Coverage ≥ 80%           │

└─────────────────────────────┘

### 6.6.4. Test Types and Coverage

| Test Type | Deskripsi | Tools | Target | Frequency |
| --- | --- | --- | --- | --- |
| Unit Testing | Menguji komponen terkecil | JUnit (Java), Jest (React) | Coverage ≥ 80% | Setiap build |
| Integration Testing | Menguji interaksi antar komponen | TestNG, Spring Boot Test, Postman | 100% integration | Setiap build |
| API Testing | Menguji endpoint API | Postman, REST Assured | 100% API | Setiap build |
| End-to-End Testing | Menguji alur lengkap | Cypress, Selenium | Critical paths | Setiap sprint |
| Performance Testing | Load test, stress test | JMeter, k6 | Throughput ≥ 10.000 msg | Setiap milestone |
| Security Testing | Vulnerability scan | OWASP ZAP, SonarQube | 0 critical vuln | Setiap sprint |
| Usability Testing | User experience | UAT Survey, Observation | SUS ≥ 70 | UAT Phase |
| User Acceptance Testing | Testing by end users | Manual Testing | 100% acceptance | UAT Phase |

### 6.6.5. Performance Testing Plan

| Test Scenario | Target | Load Level | Duration | Tools |
| --- | --- | --- | --- | --- |
| IoT Telemetry Ingestion | ≥ 10.000 msg/detik | 5.000, 10.000, 15.000 msg/detik | 30 menit each | JMeter |
| IoT Telemetry Latency | ≤ 5 detik | 10.000 msg/detik | 1 jam | JMeter |
| Digital Twin State Sync | ≤ 1 menit | 1.000, 5.000, 10.000 event/jam | 1 jam | Custom Script |
| Simulation Execution | ≤ 5 menit | 1, 5, 10 concurrent simulations | 10 runs | JMeter + Script |
| System Concurrent Users | 100 concurrent users | 50, 100, 200 users | 1 jam | JMeter |
| API Response Time | < 500 ms | 100 concurrent users | 1 jam | JMeter |

### 6.6.6. Security Testing Plan

| Test Scenario | Deskripsi | Tools | Target |
| --- | --- | --- | --- |
| Vulnerability Scanning | Scan aplikasi web untuk vulnerabilities | OWASP ZAP, Nessus | 0 critical, <5 high |
| Penetration Testing | Simulasi serangan | Manual + Metasploit | 0 critical, <5 high |
| Authentication Testing | Testing login, SSO, MFA | Manual | 100% secure |
| Authorization Testing | Testing RBAC, access control | Manual | 100% secure |
| Data Encryption Testing | Testing data-at-rest, data-in-transit | Manual | 100% encrypted |
| API Security Testing | Testing API authentication, rate limiting | OWASP ZAP, Postman | 100% secure |
| Session Management | Testing session timeout, invalidation | Manual | 100% secure |

### 6.6.7. User Acceptance Testing (UAT) Plan

| Aspek | Rincian |
| --- | --- |
| UAT Phase 1 | Minggu 16-17 (Internal users) |
| UAT Phase 2 | Minggu 18-19 (End users) |
| Participants | Farm Ops, Supply Chain, Finance, Management |
| Environment | Staging Environment |
| Test Scope | All functional requirements, critical business flows |
| Acceptance Criteria | 100% of user stories accepted, 0 critical bugs |
| Exit Criteria | All test cases executed, all critical bugs resolved |

UAT Test Cases (Sample):

| ID | User Story | Test Steps | Expected Result | Status |
| --- | --- | --- | --- | --- |
| UAT-001 | Device Registration | 1. Login as Admin 2. Navigate to IoT Device 3. Click Register Device 4. Fill form 5. Submit | Device registered, API key generated | [Pass/Fail] |
| UAT-002 | Telemetry Monitoring | 1. Login as Ops 2. Open IoT Dashboard 3. View real-time telemetry | Telemetry displayed < 5 sec latency | [Pass/Fail] |
| UAT-003 | Digital Twin View | 1. Login as Ops 2. Open Twin Viewer 3. Select a twin 4. View state | State displayed correctly | [Pass/Fail] |
| UAT-004 | Simulation Execution | 1. Login as Planner 2. Create scenario 3. Set parameters 4. Run simulation | Simulation completed < 5 min | [Pass/Fail] |
| UAT-005 | Autonomous Recommendation | 1. Trigger alert 2. Check recommendation | Recommendation generated | [Pass/Fail] |

### 6.6.8. Defect Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        DEFECT MANAGEMENT PROCESS                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  1. DETECT                                                                  │

│  ┌─────────────────────────┐                                               │

│  │  Identifikasi defect    │                                               │

│  │  via testing / UAT      │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  2. LOG                                                                     │

│  ┌─────────────────────────┐                                               │

│  │  Log ke Jira            │                                               │

│  │  - Severity: Critical,  │                                               │

│  │    Major, Minor, Trivial│                                               │

│  │  - Priority: P0-P3      │                                               │

│  │  - Description, Steps   │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  3. ASSIGN                                                                  │

│  ┌─────────────────────────┐                                               │

│  │  Assign to developer    │                                               │

│  │  - Critical/Major:      │                                               │

│  │    Immediate attention  │                                               │

│  │  - Minor/Trivial:       │                                               │

│  │    Next sprint          │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  4. FIX                                                                     │

│  ┌─────────────────────────┐                                               │

│  │  Developer fixes defect │                                               │

│  │  Write unit tests       │                                               │

│  │  Code review            │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  5. VERIFY                                                                  │

│  ┌─────────────────────────┐                                               │

│  │  QA retesting            │                                               │

│  │  Verify fix works        │                                               │

│  │  Regression testing      │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  6. CLOSE                                                                   │

│  ┌─────────────────────────┐                                               │

│  │  Mark as Resolved/Closed│                                               │

│  │  Update documentation   │                                               │

│  │  Communicate to user    │                                               │

│  └─────────────────────────┘                                               │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.6.9. Defect Severity Classification

| Severity | Deskripsi | Contoh | SLA |
| --- | --- | --- | --- |
| Critical (P0) | System failure, data loss, security breach | System crash, data corruption | 1 hari |
| Major (P1) | Major functionality broken, workaround not available | IoT telemetry not working | 3 hari |
| Minor (P2) | Minor functionality broken, workaround available | UI glitch, missing validation | 7 hari |
| Trivial (P3) | Cosmetic issues, documentation | Misspelling, styling issue | 14 hari |

### 6.6.10. Quality Reports

Report Types:

| Report | Content | Frequency | Audience |
| --- | --- | --- | --- |
| Test Execution Report | Test results, pass/fail rate, coverage | Setiap sprint | PM, Leads, QA |
| Defect Report | Defect count, severity, status, trends | Mingguan | PM, Leads |
| Quality Metrics Report | All quality metrics vs targets | Bulanan | PM, Sponsor |
| Performance Test Report | Performance test results | Setiap milestone | PM, Leads, DevOps |
| Security Test Report | Security scan results | Setiap milestone | PM, Security, Sponsor |
| UAT Report | UAT results, feedback, sign-off | UAT Phase | PM, Sponsor, PO |

## 6.7. QUALITY MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Plan Quality Management | Requirements, Standards | Expert Judgment, Benchmarking | Quality Management Plan | PM, QA Lead |
| Manage Quality | Quality Plan, Audit Checklist | Audit, Process Analysis | Quality Reports, Audits | QA Lead |
| Control Quality | Deliverables, Test Data | Testing, Inspection, Review | Verified Deliverables, QC Measurements | QA Lead |

## 6.8. RINGKASAN MANAJEMEN MUTU

| Aspek | Rincian |
| --- | --- |
| Quality Standards | ISO 9001:2015, ISO/IEC 25010, ISO/IEC 27001, OWASP, ISTQB |
| Key Metrics | Performance, Security, Coverage, Accuracy, Usability |
| Testing Strategy | Unit (80% coverage), Integration, API, E2E, Performance, Security, UAT |
| Performance Targets | Throughput ≥ 10.000 msg/detik, Latency ≤ 5 detik, Simulation ≤ 5 menit |
| Security Targets | 0 critical vuln, <5 high vuln |
| Defect Management | Jira tracking, severity classification, SLA-based resolution |
| Continuous Improvement | PDCA cycle, Sprint Retrospective, Monthly Quality Review |
| Quality Tools | SonarQube, JMeter, OWASP ZAP, Postman, JUnit, Jest, Cypress, Jira |

# BAB 7: MANAJEMEN SUMBER DAYA PROYEK

## 7.1. PENDAHULUAN

Manajemen sumber daya proyek bertujuan untuk memastikan bahwa Proyek P-FNE-08: Advanced & Autonomous Enterprise memiliki sumber daya yang tepat (manusia, peralatan, material) pada waktu yang tepat untuk menyelesaikan proyek dengan sukses.

Proyek P-FNE-08 membutuhkan tim multidisiplin dengan keahlian di bidang IoT, Digital Twin, Simulation, Autonomous, Frontend, Data Science, QA, dan DevOps. Manajemen sumber daya yang efektif sangat penting untuk memaksimalkan produktivitas tim dan memastikan ketersediaan infrastruktur yang dibutuhkan.

## 7.2. PROSES MANAJEMEN SUMBER DAYA PROYEK

Berdasarkan PMBOK, terdapat 6 proses dalam manajemen sumber daya proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Plan Resource Management | PMI-27 | Menyusun rencana manajemen sumber daya | Resource Management Plan |
| Estimate Activity Resources | PMI-28 | Mengestimasi kebutuhan sumber daya | Resource Requirements |
| Acquire Resources | PMI-29 | Mendapatkan sumber daya yang dibutuhkan | Physical Resources, Team |
| Develop Team | PMI-30 | Mengembangkan tim proyek | Team Performance, Training |
| Manage Team | PMI-31 | Mengelola tim proyek | Issue Log, Team Updates |
| Control Resources | PMI-32 | Mengendalikan sumber daya | Resource Utilization, Updates |

## 7.3. PLAN RESOURCE MANAGEMENT (PMI-27)

### 7.3.1. Tujuan

Menyusun rencana manajemen sumber daya yang mendefinisikan bagaimana sumber daya akan diidentifikasi, diakuisisi, dikembangkan, dikelola, dan dilepaskan.

### 7.3.2. Output: Resource Management Plan

Rencana Manajemen Sumber Daya P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Team Structure | 12-14 orang dengan 5 domain (IoT, Twin, Simulation, Autonomous, Frontend) |
| Resource Acquisition | Internal hiring + Konsultan untuk skill khusus |
| Team Development | Onboarding, Training, Pair Programming, Knowledge Sharing |
| Team Management | Daily Standup, 1-on-1 Meeting, Performance Review |
| Resource Control | Time tracking di Jira, Resource Utilization Report |
| Recognition | Performance bonus, Project completion bonus |
| Release | Handover documentation, Knowledge transfer, Exit interview |

## 7.4. ESTIMATE ACTIVITY RESOURCES (PMI-28)

### 7.4.1. Tujuan

Mengestimasi kebutuhan sumber daya untuk setiap aktivitas proyek, termasuk jenis, jumlah, dan durasi.

### 7.4.2. Resource Requirements

Tim Proyek P-FNE-08:

| Peran | Jumlah | Kualifikasi Minimal | Tanggung Jawab | Sumber |
| --- | --- | --- | --- | --- |
| Project Manager | 1 | PMP, 5+ tahun ERP/Software | Manajemen proyek, reporting | Internal |
| Business Analyst | 1 | 3+ tahun ERP/AgriTech | Requirement, UAT | Internal |
| IoT Lead | 1 | IoT, MQTT, Kafka, TimescaleDB | IoT architecture, team lead | Internal/Konsultan |
| IoT Engineer | 2 | Java/Node.js, MQTT, IoT | Device reg, telemetry, alert | Internal |
| Twin Lead | 1 | Digital Twin, Spring Boot, PostgreSQL | Twin architecture, team lead | Internal/Konsultan |
| Twin Engineer | 2 | Spring Boot, PostgreSQL, Neo4j | Twin CRUD, sync, what-if | Internal |
| Simulation Lead | 1 | Simulation (SimPy), Python, Data Science | Sim architecture, team lead | Internal/Konsultan |
| Simulation Engineer | 2 | Python, SimPy, SciPy, Celery | Sim models, optimization | Internal |
| Autonomous Lead | 1 | Rule Engine (Drools), AI Integration, Kafka | Auto architecture, team lead | Internal/Konsultan |
| Autonomous Engineer | 2 | Spring Boot, Drools, Kafka | Rule engine, recommendation | Internal |
| Frontend Lead | 1 | React, TypeScript, Three.js | UI architecture, team lead | Internal |
| Frontend Engineer | 2 | React, TypeScript, Chart.js | Dashboard, viewer, workbench | Internal |
| Data Scientist | 1 | AI/ML, Forecasting, Python | Model, optimization, feedback | Internal/Konsultan |
| QA Engineer | 1 | Automated Testing, Performance Testing | Testing, QA process | Internal |
| DevOps Engineer | 1 | Kubernetes, CI/CD, Cloud | Infrastructure, deployment | Internal |
| Security Engineer | 1 | Security, Penetration Test | Security testing, compliance | Internal/Konsultan |

### 7.4.3. Resource Utilization Plan

| Peran | M1 | M2 | M3 | M4 | M5 | Total Hours |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager | 160 | 160 | 160 | 160 | 160 | 800 |
| Business Analyst | 160 | 80 | 80 | 80 | 160 | 560 |
| IoT Lead | 80 | 160 | 80 | 80 | 40 | 440 |
| IoT Engineer (2) | 160 | 320 | 160 | 160 | 80 | 880 |
| Twin Lead | 80 | 160 | 160 | 80 | 40 | 520 |
| Twin Engineer (2) | 80 | 160 | 320 | 160 | 80 | 800 |
| Simulation Lead | 40 | 80 | 160 | 160 | 40 | 480 |
| Simulation Engineer (2) | 40 | 160 | 320 | 320 | 80 | 920 |
| Autonomous Lead | 0 | 80 | 80 | 160 | 80 | 400 |
| Autonomous Engineer (2) | 0 | 160 | 160 | 320 | 160 | 800 |
| Frontend Lead | 40 | 160 | 160 | 160 | 80 | 600 |
| Frontend Engineer (2) | 80 | 320 | 320 | 320 | 160 | 1,200 |
| Data Scientist | 40 | 80 | 160 | 160 | 80 | 520 |
| QA Engineer | 0 | 40 | 80 | 160 | 160 | 440 |
| DevOps Engineer | 40 | 80 | 80 | 80 | 160 | 440 |
| Security Engineer | 0 | 0 | 40 | 40 | 80 | 160 |
| Total | 1,000 | 2,320 | 2,520 | 2,720 | 1,720 | 10,280 |

### 7.4.4. Non-Human Resource Requirements

| Resource | Deskripsi | Jumlah | Sumber |
| --- | --- | --- | --- |
| Cloud Infrastructure | AWS/GCP - Compute, Storage, Database, Kafka | 1 environment | Cloud Provider |
| Time-Series Database | TimescaleDB (Enterprise) | 1 license | Vendor |
| Graph Database | Neo4j (Enterprise) | 1 license | Vendor |
| Message Broker | Confluent Kafka (Enterprise) | 1 license | Vendor |
| Monitoring Tools | Grafana, ELK Stack (Enterprise) | 1 license | Vendor |
| IoT Gateway | Perangkat untuk staging | 5 unit | Hardware Vendor |
| Testing Tools | JMeter, LoadRunner, OWASP ZAP | 1 license | Vendor/Open Source |
| CI/CD Tools | GitLab CI, Jenkins | 1 environment | Open Source |
| Project Management | Jira, Confluence | 1 license | Vendor |

## 7.5. ACQUIRE RESOURCES (PMI-29)

### 7.5.1. Tujuan

Mendapatkan sumber daya yang dibutuhkan untuk proyek, baik sumber daya manusia maupun non-manusia.

### 7.5.2. Resource Acquisition Plan

Sumber Daya Manusia:

| Peran | Sumber | Timeline | Status |
| --- | --- | --- | --- |
| Project Manager | Internal | Minggu 1 | Hired |
| Business Analyst | Internal | Minggu 1 | Hired |
| IoT Lead | Internal / Konsultan | Minggu 1 | To acquire |
| IoT Engineers | Internal / Konsultan | Minggu 1-2 | To acquire |
| Twin Lead | Internal / Konsultan | Minggu 1 | To acquire |
| Twin Engineers | Internal / Konsultan | Minggu 2-3 | To acquire |
| Simulation Lead | Internal / Konsultan | Minggu 1 | To acquire |
| Simulation Engineers | Internal / Konsultan | Minggu 3-4 | To acquire |
| Autonomous Lead | Internal / Konsultan | Minggu 3 | To acquire |
| Autonomous Engineers | Internal / Konsultan | Minggu 4-5 | To acquire |
| Frontend Lead | Internal | Minggu 1 | Hired |
| Frontend Engineers | Internal | Minggu 1-2 | Hired |
| Data Scientist | Internal / Konsultan | Minggu 2 | To acquire |
| QA Engineer | Internal | Minggu 4 | To acquire |
| DevOps Engineer | Internal | Minggu 1 | Hired |
| Security Engineer | Internal / Konsultan | Minggu 8 | To acquire |

Sumber Daya Non-Manusia:

| Resource | Action | Timeline | Status |
| --- | --- | --- | --- |
| Cloud Infrastructure | Provision | Minggu 1 | Done |
| TimescaleDB License | Purchase | Minggu 1 | To purchase |
| Neo4j License | Purchase | Minggu 1 | To purchase |
| Confluent Kafka License | Purchase | Minggu 1 | To purchase |
| IoT Gateway | Purchase | Minggu 2 | To purchase |
| Testing Tools | Setup | Minggu 4 | To setup |

## 7.6. DEVELOP TEAM (PMI-30)

### 7.6.1. Tujuan

Mengembangkan tim proyek untuk meningkatkan kompetensi, kolaborasi, dan kinerja.

### 7.6.2. Team Development Plan

Onboarding Program:

| Aktivitas | Deskripsi | Durasi | Target Peserta |
| --- | --- | --- | --- |
| Project Orientation | Pengenalan proyek, PMP, tools | 1 hari | Semua tim |
| Domain Training - IoT | Pelatihan IoT, MQTT, TimescaleDB | 2 hari | IoT Team |
| Domain Training - Twin | Pelatihan Digital Twin, Neo4j | 2 hari | Twin Team |
| Domain Training - Simulation | Pelatihan Simulation, SimPy, SciPy | 2 hari | Simulation Team |
| Domain Training - Autonomous | Pelatihan Rule Engine, Drools, AI | 2 hari | Autonomous Team |
| Domain Training - Frontend | Pelatihan React, Three.js, Chart.js | 2 hari | Frontend Team |
| Tool Training | Pelatihan Jira, GitHub, Confluence | 1 hari | Semua tim |
| Integration Training | Pelatihan integrasi antar domain | 1 hari | Semua tim |

Team Building Activities:

| Aktivitas | Deskripsi | Frekuensi |
| --- | --- | --- |
| Daily Standup | Sinkronisasi harian | Harian |
| Knowledge Sharing Session | Presentasi teknis | 2x per bulan |
| Pair Programming | Kolaborasi coding | Setiap sprint |
| Sprint Retrospective | Refleksi sprint | Setiap 2 minggu |
| Team Lunch | Informal bonding | Bulanan |
| Offsite / Team Retreat | Team building | 1x per proyek |

### 7.6.3. Training Plan

| Training | Deskripsi | Peserta | Sumber | Timeline |
| --- | --- | --- | --- | --- |
| IoT Fundamentals | MQTT, TimescaleDB, Kafka | IoT Team | Internal | Minggu 2 |
| Digital Twin Fundamentals | Twin modeling, state sync | Twin Team | Internal/Konsultan | Minggu 2 |
| Simulation with SimPy | Discrete-event simulation | Simulation Team | Internal/Konsultan | Minggu 3 |
| Rule Engine (Drools) | Business rules management | Autonomous Team | Internal/Konsultan | Minggu 4 |
| Three.js 3D Visualization | 3D rendering for Twin | Frontend Team | Internal | Minggu 3 |
| Advanced React & TypeScript | Modern frontend development | Frontend Team | Internal | Minggu 2 |
| Kubernetes & DevOps | Infrastructure management | DevOps | Internal | Minggu 1 |

## 7.7. MANAGE TEAM (PMI-31)

### 7.7.1. Tujuan

Mengelola tim proyek untuk memastikan kinerja yang optimal dan menyelesaikan konflik yang muncul.

### 7.7.2. Team Management Activities

| Aktivitas | Deskripsi | Frekuensi | Responsible |
| --- | --- | --- | --- |
| Daily Standup | Koordinasi harian | Harian | PM, Leads |
| 1-on-1 Meeting | Pembinaan individu | 2 minggu | PM, Lead |
| Performance Review | Evaluasi kinerja | Bulanan | PM, HR |
| Conflict Resolution | Penanganan konflik | Sesuai kebutuhan | PM, HR |
| Resource Allocation | Penugasan sumber daya | Mingguan | PM, Leads |
| Workload Balancing | Memastikan beban kerja merata | Mingguan | PM, Leads |

### 7.7.3. Decision-Making Framework

| Keputusan | Pembuat Keputusan | Konsultasi | Informasi |
| --- | --- | --- | --- |
| Project strategy | Project Sponsor | PM, Leads | - |
| Budget changes | PM + Sponsor | CCB | Team |
| Schedule changes | PM | Leads | Team, Stakeholder |
| Technical architecture | Tech Leads | PM | Team |
| Resource allocation | PM + Leads | HR | Team |
| Risk response | PM | Leads | Team |
| Bug priority (P0/P1) | PM + QA Lead | - | Team |

### 7.7.4. Conflict Resolution Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                      CONFLICT RESOLUTION PROCESS                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  1. IDENTIFY                                                                │

│  ┌─────────────────────────┐                                               │

│  │  Identifikasi konflik   │                                               │

│  │  melalui observasi /    │                                               │

│  │  laporan tim            │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  2. ANALYZE                                                                 │

│  ┌─────────────────────────┐                                               │

│  │  Analisis akar masalah  │                                               │

│  │  Dampak pada proyek     │                                               │

│  │  Pihak-pihak terlibat   │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  3. RESPOND                                                                 │

│  ┌─────────────────────────┐                                               │

│  │  Pilih strategi:        │                                               │

│  │  - Compromise           │                                               │

│  │  - Collaboration        │                                               │

│  │  - Accommodate          │                                               │

│  │  - Compete              │                                               │

│  │  - Avoid                │                                               │

│  └────────────┬────────────┘                                               │

│               │                                                             │

│               ▼                                                             │

│  4. RESOLVE                                                                 │

│  ┌─────────────────────────┐                                               │

│  │  Implementasi solusi    │                                               │

│  │  Monitor hasil          │                                               │

│  │  Dokumentasi            │                                               │

│  └─────────────────────────┘                                               │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 7.7.5. Team Performance Metrics

| Metric | Target | Measurement | Frequency |
| --- | --- | --- | --- |
| Sprint Velocity | 20-30 SP/sprint | Jira | 2 minggu |
| Sprint Completion | ≥ 90% | Jira | 2 minggu |
| Code Review Cycle | ≤ 2 hours | GitHub | Kontinu |
| Bug Resolution Time | P0: ≤ 1 hari | Jira | Mingguan |
| Team Satisfaction | ≥ 4/5 | Survey | Bulanan |
| Knowledge Sharing | 2 sessions/month | Attendance | Bulanan |

## 7.8. CONTROL RESOURCES (PMI-32)

### 7.8.1. Tujuan

Mengendalikan sumber daya proyek dengan memantau penggunaan sumber daya dan memastikan ketersediaan sesuai dengan rencana.

### 7.8.2. Resource Control Activities

| Aktivitas | Deskripsi | Frekuensi | Responsible |
| --- | --- | --- | --- |
| Time Tracking | Pencatatan waktu di Jira | Harian | Team |
| Resource Utilization Report | Laporan penggunaan sumber daya | Bulanan | PM |
| Workload Review | Review beban kerja tim | Mingguan | PM, Leads |
| Infrastructure Usage | Monitoring cloud resource usage | Harian | DevOps |
| Resource Adjustment | Penyesuaian sumber daya | Sesuai kebutuhan | PM, HR |

### 7.8.3. Resource Utilization Report

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    RESOURCE UTILIZATION REPORT                              │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Report Period: [DD/MM/YYYY] - [DD/MM/YYYY]                               │

│  Prepared By: [PM Name]                                                     │

│  Date: [DD/MM/YYYY]                                                         │

│                                                                             │

│  1. TEAM UTILIZATION                                                        │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Role                │ Planned   │ Actual   │ Utilization │ Status      │

│  │---------------------│-----------│----------│-------------│-------------│

│  │ Project Manager     │ 160 hrs   │ 155 hrs  │ 97%         │ ✅ On Track │

│  │ Business Analyst    │ 160 hrs   │ 168 hrs  │ 105%        │ ⚠️ Overload │

│  │ IoT Lead            │ 160 hrs   │ 152 hrs  │ 95%         │ ✅ On Track │

│  │ IoT Engineers       │ 320 hrs   │ 310 hrs  │ 97%         │ ✅ On Track │

│  │ Twin Lead           │ 160 hrs   │ 165 hrs  │ 103%        │ ⚠️ Overload │

│  │ ...                 │           │          │             │             │

│  └─────────────────────────────────────────────────────────────────────────┘

│                                                                             │

│  2. INFRASTRUCTURE USAGE                                                    │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Resource          │ Allocated │ Used    │ Utilization │ Status          │

│  │-------------------│-----------│---------│-------------│-----------------│

│  │ Cloud Compute     │ 100 vCPU  │ 72 vCPU │ 72%         │ ✅ On Track     │

│  │ Cloud Storage     │ 5 TB      │ 2.3 TB  │ 46%         │ ✅ On Track     │

│  │ Database (Timescale)│ 2 TB     │ 0.8 TB  │ 40%         │ ✅ On Track     │

│  │ Kafka Topics      │ 20        │ 12      │ 60%         │ ✅ On Track     │

│  └─────────────────────────────────────────────────────────────────────────┘

│                                                                             │

│  3. RECOMMENDATIONS                                                         │

│  ───────────────────────────────────────────────────────────────────────── │

│  - Business Analyst overload: consider adding temporary resource           │

│  - Twin Lead overload: redistribute some tasks to Twin Engineers          │

│  - Cloud usage within budget: no adjustment needed                         │

│                                                                             │

│  APPROVAL:                                                                  │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Role                │ Name      │ Signature │ Date                     │

│  │---------------------│-----------│-----------│--------------------------│

│  │ Project Manager     │           │           │                          │

│  └──────────────────────────────────────────────────────────────────────── │

└─────────────────────────────────────────────────────────────────────────────┘

## 7.9. RESOURCE MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Plan Resource Management | Project Charter, Activity List | Expert Judgment, Organization Charts | Resource Management Plan | PM, HR |
| Estimate Activity Resources | Activity List, Resource Calendars | Bottom-Up Estimation, Expert Judgment | Resource Requirements | PM, Leads |
| Acquire Resources | Resource Requirements | Pre-assignment, Negotiation, Acquisition | Team, Physical Resources | PM, HR |
| Develop Team | Resource Management Plan | Training, Team Building, Pair Programming | Team Performance | PM, HR |
| Manage Team | Team Performance, Issue Log | Conflict Resolution, Performance Reviews | Issue Log Updates | PM, HR |
| Control Resources | Resource Requirements, Utilization Data | Performance Reviews, Data Analysis | Resource Utilization Report | PM, DevOps |

## 7.10. RINGKASAN MANAJEMEN SUMBER DAYA

| Aspek | Rincian |
| --- | --- |
| Total Tim | 12-14 orang |
| Tim Structure | PM (1), BA (1), Leads (4), Engineers (8-10), Data Scientist (1), QA (1), DevOps (1), Security (1) |
| Resource Acquisition | Internal hiring + Konsultan |
| Onboarding | 1 minggu orientation + domain-specific training |
| Development | Daily standup, 2x/month knowledge sharing, pair programming |
| Training | IoT, Twin, Simulation, Autonomous, Frontend, DevOps |
| Performance | Sprint velocity, sprint completion, bug resolution, team satisfaction |
| Conflict Resolution | Collaborative approach, PM + HR involvement |
| Resource Control | Time tracking, utilization report, workload balancing |

# BAB 8: MANAJEMEN KOMUNIKASI PROYEK

## 8.1. PENDAHULUAN

Manajemen komunikasi proyek bertujuan untuk memastikan bahwa informasi yang tepat disampaikan kepada stakeholder yang tepat pada waktu yang tepat dengan metode yang tepat. Untuk Proyek P-FNE-08: Advanced & Autonomous Enterprise, komunikasi yang efektif sangat penting karena:

- Tim multidisiplin dengan keahlian berbeda (IoT, Twin, Simulation, Autonomous, Frontend)

- Ketergantungan dengan proyek lain (P-FNE-01 s.d P-FNE-07)

- Stakeholder beragam (Sponsor, Steering Committee, End Users, Vendor)

- Kompleksitas teknis yang membutuhkan koordinasi intensif

## 8.2. PROSES MANAJEMEN KOMUNIKASI PROYEK

Berdasarkan PMBOK, terdapat 3 proses dalam manajemen komunikasi proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Plan Communications Management | PMI-33 | Menyusun rencana manajemen komunikasi | Communications Management Plan |
| Manage Communications | PMI-34 | Menjalankan komunikasi sesuai rencana | Project Communications, Updates |
| Monitor Communications | PMI-35 | Memantau efektivitas komunikasi | Communication Updates, Improvements |

## 8.3. PLAN COMMUNICATIONS MANAGEMENT (PMI-33)

### 8.3.1. Tujuan

Menyusun rencana manajemen komunikasi yang mendefinisikan kebutuhan komunikasi stakeholder, metode komunikasi, frekuensi, dan format laporan.

### 8.3.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Komunikasi tingkat tinggi |
| Stakeholder Register | PM + BA | Daftar stakeholder |
| Enterprise Environmental Factors | Organisasi | Budaya komunikasi, tools |
| Organizational Process Assets | Organisasi | Template, prosedur komunikasi |

### 8.3.3. Output: Communications Management Plan

Rencana Manajemen Komunikasi P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Communication Channels | Formal (Meeting, Email, Report), Informal (Slack, Chat) |
| Communication Tools | Slack (daily), Jira (task), Confluence (docs), Zoom (meeting), Email (formal) |
| Reporting | Daily standup, Weekly report, Monthly executive report |
| Meeting Schedule | Daily standup, Sprint planning, Sprint review, Monthly steering committee |
| Escalation | Team → PM → Sponsor (hierarchical) |
| Documentation | Confluence for all project documents |
| Language | Bahasa Indonesia (internal), English (technical documentation) |

## 8.4. STAKEHOLDER COMMUNICATION MATRIX

### 8.4.1. Stakeholder Register

| ID | Stakeholder | Peran | Interest | Influence | Engagement Level | Komunikasi |
| --- | --- | --- | --- | --- | --- | --- |
| S-001 | Project Sponsor | CEO/Direktur | High | High | Supportive | Bulanan (Meeting) |
| S-002 | Steering Committee | Direksi | High | High | Supportive | Bulanan (Meeting) |
| S-003 | Product Owner | Tim Produk FNE | High | Medium | Supportive | Mingguan (Meeting) |
| S-004 | Tim P-FNE-01 s.d P-FNE-07 | Tim terkait | Medium | Medium | Neutral | Mingguan (Sync) |
| S-005 | End Users (Farm Ops) | Operasional | High | Low | Neutral | UAT (Workshop) |
| S-006 | End Users (Management) | Manajemen | High | Medium | Neutral | UAT (Workshop) |
| S-007 | End Users (IT Support) | IT | High | Medium | Supportive | Bulanan (Meeting) |
| S-008 | Tim Proyek | Pelaksana | High | Medium | Supportive | Harian (Standup) |
| S-009 | Cloud Vendor | AWS/GCP | Low | Low | Neutral | Sesuai kebutuhan |
| S-010 | Konsultan | Ahli | Medium | Low | Supportive | Mingguan (Meeting) |
| S-011 | Tim Audit Internal | Audit | Medium | Medium | Neutral | Bulanan (Report) |
| S-012 | Regulator | Pemerintah | Low | High | Neutral | Sesuai kebutuhan |

### 8.4.2. Communication Matrix

| Stakeholder | Informasi | Frekuensi | Metode | Format | Responsible |
| --- | --- | --- | --- | --- | --- |
| Project Sponsor | Status proyek, milestone, risiko, keputusan strategis | Bulanan | Meeting (presentasi) | Slides | PM |
| Steering Committee | Status proyek, risiko, keputusan strategis | Bulanan | Meeting (presentasi) | Slides | PM |
| Product Owner | Progress sprint, backlog, demo | Mingguan | Meeting (review) | Slides, Demo | PM, BA |
| Tim P-FNE-01 s.d P-FNE-07 | Integrasi, API, data flow | Mingguan | Sync meeting | Docs, API | PM, Leads |
| End Users (Ops) | Fitur, UAT, feedback | UAT Phase | Workshop, UAT | Hands-on | BA, QA |
| End Users (Management) | Fitur, UAT, feedback | UAT Phase | Workshop, UAT | Hands-on | BA, QA |
| Tim Proyek | Task, blocker, progress | Harian | Standup (15 min) | Verbal | PM |
| Tim Proyek | Sprint planning, review, retro | 2 minggu | Meeting | Slides, Jira | PM, Leads |
| Konsultan | Progress, issue, technical | Mingguan | Meeting | Docs | PM, Leads |
| Tim Audit | Status, compliance | Bulanan | Report | PDF | PM, Leads |

### 8.4.3. Communication Frequency Detail

| Meeting Type | Participants | Frequency | Duration | Agenda | Responsible |
| --- | --- | --- | --- | --- | --- |
| Daily Standup | Tim Proyek | Harian (09:00) | 15 menit | What I did, what I will do, blockers | PM |
| Sprint Planning | Tim Proyek + PO | 2 minggu | 2 jam | Sprint goal, backlog selection | PM, PO |
| Sprint Review | Tim Proyek + PO + Stakeholder | 2 minggu | 1 jam | Demo deliverable, feedback | PM, BA |
| Sprint Retrospective | Tim Proyek | 2 minggu | 1 jam | What went well, what to improve | PM |
| Weekly Tech Sync | PM + Leads | Mingguan | 1 jam | Technical issues, integration, dependencies | PM |
| Monthly Steering Committee | PM + Sponsor + Committee | Bulanan | 1.5 jam | Status, risks, decisions | PM |
| Monthly Sponsor Update | PM + Sponsor | Bulanan | 30 menit | Status, milestone, budget | PM |
| UAT Workshop | BA + QA + End Users | UAT Phase | 3-4 jam | Testing, feedback, training | BA |

## 8.5. COMMUNICATION TOOLS

### 8.5.1. Tools Matrix

| Tools | Penggunaan | Audience | Frequency |
| --- | --- | --- | --- |
| Slack | Daily communication, alerts, integration | Tim Proyek | Harian |
| Jira | Task management, sprint tracking, bug tracking, reporting | Tim Proyek, PM, Stakeholder | Harian |
| Confluence | Documentation, meeting notes, decisions, knowledge base | Tim Proyek, Stakeholder | Continuous |
| GitHub | Source code, code review, CI/CD | Tim Proyek, Leads | Continuous |
| Zoom / Google Meet | Virtual meetings, sprint events, stakeholder meetings | Tim Proyek, Stakeholder | Sesuai jadwal |
| Email | Formal communication, official updates, approvals | Stakeholder, Vendor | Sesuai kebutuhan |
| Google Drive | Sharing documents, spreadsheets, presentations | Tim Proyek, Stakeholder | Continuous |

### 8.5.2. Communication Channels

| Channel | Purpose | Format | Retention |
| --- | --- | --- | --- |
| #general | General announcements | Text | 90 hari |
| #project-pfne-08 | Project-specific discussion | Text | 90 hari |
| #iot-dev | IoT technical discussion | Text | 90 hari |
| #twin-dev | Twin technical discussion | Text | 90 hari |
| #sim-dev | Simulation technical discussion | Text | 90 hari |
| #auto-dev | Autonomous technical discussion | Text | 90 hari |
| #frontend-dev | Frontend technical discussion | Text | 90 hari |
| #qa-testing | Testing and QA discussion | Text | 90 hari |
| #devops | Infrastructure and deployment | Text | 90 hari |
| #alerts | System alerts and notifications | Text | 90 hari |

## 8.6. REPORTING

### 8.6.1. Report Types

| Report | Content | Audience | Frequency | Format |
| --- | --- | --- | --- | --- |
| Daily Standup Report | Progress, blockers | Tim Proyek | Harian | Verbal |
| Sprint Burndown | Progress vs time | Tim Proyek, PM | Setiap sprint | Chart |
| Weekly Progress Report | Status, milestone, risk, issue, next week | PM, Sponsor, Leads | Mingguan | Slides/PDF |
| Monthly Executive Report | Ringkasan eksekutif, KPI, forecast | Sponsor, Steering Committee | Bulanan | Slides/PDF |
| Milestone Report | Milestone achievement | Sponsor, Steering Committee | Saat milestone | PDF |
| Quality Report | Test results, defect metrics | PM, Leads, QA | Bulanan | PDF |
| Risk Report | Risk status, new risks | PM, Leads, Sponsor | Bulanan | PDF |
| Financial Report | Budget vs actual, forecast | PM, Sponsor | Bulanan | Spreadsheet |

### 8.6.2. Weekly Progress Report Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    WEEKLY PROGRESS REPORT                                   │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Report Period: [DD/MM/YYYY] - [DD/MM/YYYY]                               │

│  Sprint: [X]                                                                │

│  Prepared By: [PM Name]                                                     │

│  Date: [DD/MM/YYYY]                                                         │

│                                                                             │

│  1. EXECUTIVE SUMMARY                                                       │

│  ───────────────────────────────────────────────────────────────────────── │

│  Overall Status: [On Track / At Risk / Off Track]                          │

│  Progress: [X]% (SPI: [XX.XX])                                             │

│  Key Achievements:                                                         │

│  - [Achievement 1]                                                         │

│  - [Achievement 2]                                                         │

│                                                                             │

│  2. SPRINT PROGRESS                                                         │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ Burndown Chart: [Image/Chart]                                      │   │

│  │ - Sprint Velocity: [X] SP                                           │   │

│  │ - Completed: [X] of [Y] story points                               │   │

│  │ - Completion Rate: [X]%                                            │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  3. TASK STATUS                                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Domain              │ To Do   │ In Progress │ Done   │ Blocked         │

│  │---------------------│---------│-------------│--------│-----------------│

│  │ IoT Integration     │ 5       │ 3           │ 12     │ 0               │

│  │ Digital Twin        │ 4       │ 2           │ 10     │ 1               │

│  │ Simulation          │ 8       │ 4           │ 6      │ 0               │

│  │ Autonomous          │ 6       │ 3           │ 4      │ 1               │

│  │ Dashboard           │ 3       │ 2           │ 5      │ 0               │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  4. MILESTONE STATUS                                                         │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Milestone        │ Target      │ Actual      │ Status                  │

│  │------------------│-------------│-------------│-------------------------│

│  │ M1: Charter      │ W1          │ W1          │ ✅ Completed            │

│  │ M2: Arch Design  │ W3          │ W3          │ ✅ Completed            │

│  │ M3: MVP IoT Twin │ W8          │ W8          │ ⏳ In Progress          │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  5. RISKS & ISSUES                                                           │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ ID │ Risk/Issue        │ Impact │ Status   │ Mitigation              │

│  │----│-------------------│--------│----------│-------------------------│

│  │ R1 │ IoT throughput    │ High   │ Open     │ Performance testing     │

│  │ R2 │ Simulation delay  │ Medium │ Open     │ Parallel processing    │

│  │ I1 │ API integration   │ Medium │ Open     │ Weekly sync with P-FNE │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  6. NEXT WEEK PLAN                                                           │

│  ───────────────────────────────────────────────────────────────────────── │

│  - [Action 1]                                                               │

│  - [Action 2]                                                               │

│  - [Action 3]                                                               │

│                                                                             │

│  7. RESOURCES                                                                │

│  ───────────────────────────────────────────────────────────────────────── │

│  - Utilization: [X]%                                                        │

│  - Staffing Changes: [Yes/No]                                               │

│  - Training: [Completed/Planned]                                            │

│                                                                             │

│  Prepared By: _______________  Approved By: _______________               │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 8.6.3. Monthly Executive Report Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    MONTHLY EXECUTIVE REPORT                                │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Report Period: [Month, Year]                                               │

│  Prepared By: [PM Name]                                                     │

│  Date: [DD/MM/YYYY]                                                         │

│                                                                             │

│  1. EXECUTIVE SUMMARY                                                       │

│  ───────────────────────────────────────────────────────────────────────── │

│  - Project Name: P-FNE-08: Advanced & Autonomous Enterprise                │

│  - Overall Status: [On Track / At Risk / Off Track]                        │

│  - Completed: [X]% of planned work                                         │

│  - Planned Completion: [DD/MM/YYYY]                                        │

│  - Forecast Completion: [DD/MM/YYYY]                                       │

│                                                                             │

│  2. KEY METRICS                                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Metric              │ Target    │ Actual   │ Status                    │

│  │---------------------│-----------│----------│---------------------------│

│  │ SPI (Schedule)      │ ≥ 0.95    │ [XX.XX]  │ [✅/⚠️/❌]               │

│  │ CPI (Cost)          │ ≥ 0.95    │ [XX.XX]  │ [✅/⚠️/❌]               │

│  │ Sprint Velocity     │ 20-30 SP  │ [X] SP   │ [✅/⚠️/❌]               │

│  │ Test Coverage       │ ≥ 80%     │ [X]%     │ [✅/⚠️/❌]               │

│  │ Defect Density      │ < 0.5     │ [X]      │ [✅/⚠️/❌]               │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  3. MILESTONE STATUS                                                         │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Milestone        │ Target    │ Actual   │ Status                      │

│  │------------------│-----------│----------│-----------------------------│

│  │ M1: Charter      │ [Date]    │ [Date]   │ ✅ Completed                │

│  │ M2: Arch Design  │ [Date]    │ [Date]   │ ✅ Completed                │

│  │ M3: MVP IoT Twin │ [Date]    │ [Date]   │ ⏳ In Progress              │

│  │ M4: Simulation   │ [Date]    │ [Date]   │ 📅 Planned                  │

│  │ M5: Autonomous   │ [Date]    │ [Date]   │ 📅 Planned                  │

│  │ M6: Integration  │ [Date]    │ [Date]   │ 📅 Planned                  │

│  │ M7: UAT Passed   │ [Date]    │ [Date]   │ 📅 Planned                  │

│  │ M8: Go-Live      │ [Date]    │ [Date]   │ 📅 Planned                  │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  4. BUDGET STATUS                                                            │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Component        │ Budget      │ Spent     │ Remaining │ Status         │

│  │------------------│-------------│-----------│-----------│----------------│

│  │ Personnel        │ 1,680M      │ [X]M      │ [X]M      │ [✅/⚠️/❌]    │

│  │ Infrastructure   │ 300M        │ [X]M      │ [X]M      │ [✅/⚠️/❌]    │

│  │ Software         │ 120M        │ [X]M      │ [X]M      │ [✅/⚠️/❌]    │

│  │ Hardware         │ 75M         │ [X]M      │ [X]M      │ [✅/⚠️/❌]    │

│  │ Training         │ 150M        │ [X]M      │ [X]M      │ [✅/⚠️/❌]    │

│  │ Consultants      │ 200M        │ [X]M      │ [X]M      │ [✅/⚠️/❌]    │

│  │ Testing          │ 125M        │ [X]M      │ [X]M      │ [✅/⚠️/❌]    │

│  │ Reserve          │ 200M        │ [X]M      │ [X]M      │ [✅/⚠️/❌]    │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  5. TOP 5 RISKS                                                              │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ # │ Risk                      │ Prob. │ Impact │ Mitigation            │

│  │---│---------------------------│-------│--------│-----------------------│

│  │ 1 │ IoT throughput < target   │ Med   │ High   │ Performance testing   │

│  │ 2 │ Simulation accuracy < 85% │ Med   │ High   │ Calibration           │

│  │ 3 │ ERP integration delay     │ Low   │ High   │ Weekly sync           │

│  │ 4 │ Resource availability     │ Low   │ Med    │ Cross-training        │

│  │ 5 │ Security vulnerability    │ Low   │ High   │ Security testing      │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  6. KEY DECISIONS MADE                                                      │

│  ───────────────────────────────────────────────────────────────────────── │

│  - [Decision 1]                                                            │

│  - [Decision 2]                                                            │

│  - [Decision 3]                                                            │

│                                                                             │

│  7. RECOMMENDATIONS                                                         │

│  ───────────────────────────────────────────────────────────────────────── │

│  - [Recommendation 1]                                                      │

│  - [Recommendation 2]                                                      │

│                                                                             │

│  APPROVAL:                                                                  │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Role                │ Name      │ Signature │ Date                     │

│  │---------------------│-----------│-----------│--------------------------│

│  │ Project Manager     │           │           │                          │

│  │ Project Sponsor     │           │           │                          │

│  └──────────────────────────────────────────────────────────────────────── │

└─────────────────────────────────────────────────────────────────────────────┘

## 8.7. ESCALATION PROCESS

### 8.7.1. Escalation Matrix

| Level | Issue Type | Escalate To | Timeline |
| --- | --- | --- | --- |
| Level 1 | Technical issue, daily blocker | Tech Lead | < 1 jam |
| Level 2 | Resource conflict, minor scope change | PM | < 1 hari |
| Level 3 | Major scope change, budget issue, schedule delay > 2 minggu | Project Sponsor | < 3 hari |
| Level 4 | Critical project risk, project viability | Steering Committee | < 1 minggu |

### 8.7.2. Escalation Flow

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         ESCALATION PROCESS FLOW                             │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Level 1                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ Issue identified by team member                                     │   │

│  │ → Discuss with Tech Lead                                            │   │

│  │ → Resolve within 1 hour                                             │   │

│  │ → If not resolved, escalate to Level 2                              │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  Level 2                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ Issue discussed with Project Manager                                │   │

│  │ → PM coordinates resolution                                         │   │

│  │ → Resolve within 1 day                                              │   │

│  │ → If not resolved, escalate to Level 3                              │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  Level 3                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ Issue escalated to Project Sponsor                                  │   │

│  │ → Sponsor provides direction or resources                           │   │

│  │ → Resolve within 3 days                                             │   │

│  │ → If not resolved, escalate to Level 4                              │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  Level 4                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ Issue escalated to Steering Committee                               │   │

│  │ → Steering Committee makes strategic decision                       │   │

│  │ → Resolve within 1 week                                             │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 8.8. MONITOR COMMUNICATIONS (PMI-35)

### 8.8.1. Tujuan

Memantau efektivitas komunikasi proyek dan memastikan informasi diterima dengan benar oleh stakeholder.

### 8.8.2. Communication Effectiveness Metrics

| Metric | Target | Measurement | Frequency |
| --- | --- | --- | --- |
| Meeting Attendance | ≥ 90% | Attendance list | Setiap meeting |
| Meeting Effectiveness | ≥ 4/5 | Feedback survey | Bulanan |
| Response Time | ≤ 4 hours | Email/Slack tracking | Continuous |
| Documentation Completeness | 100% | Review | Mingguan |
| Stakeholder Satisfaction | ≥ 4/5 | Survey | Bulanan |
| Communication Clarity | ≥ 4/5 | Survey | Bulanan |

### 8.8.3. Communication Feedback Survey

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    COMMUNICATION FEEDBACK SURVEY                            │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Respondent: [Name]                                                         │

│  Role: [Role]                                                               │

│  Date: [DD/MM/YYYY]                                                         │

│                                                                             │

│  Please rate the following on a scale of 1-5 (1 = Very Poor, 5 = Excellent)│

│                                                                             │

│  1. Information Timeliness                                                  │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ a) I receive information when I need it                          │ [ ] │   │

│  │ b) Meeting schedules are communicated in advance                 │ [ ] │   │

│  │ c) Status reports are delivered on time                          │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  2. Information Relevance                                                  │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ a) Information provided is relevant to my role                    │ [ ] │   │

│  │ b) I receive the right amount of detail                           │ [ ] │   │

│  │ c) Communication helps me do my job better                        │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  3. Communication Clarity                                                  │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ a) Communications are clear and easy to understand                │ [ ] │   │

│  │ b) Technical jargon is explained when used                        │ [ ] │   │

│  │ c) Meeting agendas are clear                                       │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  4. Meeting Effectiveness                                                  │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ a) Meetings start and end on time                                 │ [ ] │   │

│  │ b) Meetings have clear objectives                                 │ [ ] │   │

│  │ c) Action items are documented and tracked                        │ [ ] │   │

│  │ d) All participants have opportunity to contribute                │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  5. Communication Tools                                                    │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ a) Jira is effective for task tracking                            │ [ ] │   │

│  │ b) Slack is effective for daily communication                     │ [ ] │   │

│  │ c) Confluence is effective for documentation                      │ [ ] │   │

│  │ d) Virtual meeting tools are effective                            │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  6. Overall Satisfaction                                                    │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ a) Overall project communication is effective                     │ [ ] │   │

│  │ b) I feel informed about project progress                         │ [ ] │   │

│  │ c) I know who to contact for different issues                     │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  7. Suggestions for Improvement                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│  [Open text field]                                                          │

│                                                                             │

│  Submitted By: _______________  Date: _______________                    │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 8.9. COMMUNICATION MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Plan Communications Management | Stakeholder Register | Communication Requirements Analysis | Communications Management Plan | PM, BA |
| Manage Communications | Communications Plan, Work Performance | Meetings, Reports, PMIS | Project Communications | PM, All Team |
| Monitor Communications | Communications Plan, Feedback | Surveys, Observation | Communication Updates | PM, BA |

## 8.10. RINGKASAN MANAJEMEN KOMUNIKASI

| Aspek | Rincian |
| --- | --- |
| Communication Channels | Formal (Meeting, Email, Report) + Informal (Slack, Chat) |
| Tools | Slack, Jira, Confluence, GitHub, Zoom, Email, Google Drive |
| Meetings | Daily standup, Sprint planning, Sprint review, Sprint retrospective, Weekly tech sync, Monthly steering committee |
| Reports | Weekly progress, Monthly executive, Milestone, Quality, Risk, Financial |
| Escalation | Level 1 (Tech Lead) → Level 2 (PM) → Level 3 (Sponsor) → Level 4 (Steering Committee) |
| Metrics | Meeting attendance ≥ 90%, Response time ≤ 4 hours, Stakeholder satisfaction ≥ 4/5 |
| Documentation | Confluence for all project documents, versioned and searchable |
| Language | Bahasa Indonesia (internal), English (technical documentation) |

# BAB 9: MANAJEMEN RISIKO PROYEK

## 9.1. PENDAHULUAN

Manajemen risiko proyek bertujuan untuk mengidentifikasi, menganalisis, merespons, dan memantau risiko yang dapat mempengaruhi Proyek P-FNE-08: Advanced & Autonomous Enterprise. Proyek ini memiliki risiko tinggi karena:

- Kompleksitas teknis yang tinggi (IoT, Digital Twin, Simulation, Autonomous)

- Ketergantungan dengan proyek lain (P-FNE-01 s.d P-FNE-07)

- Kinerja kritis (throughput, latency, akurasi simulasi)

- Keamanan data yang sensitif

- Jadwal yang ketat (4-5 bulan)

- Sumber daya multidisiplin yang langka

## 9.2. PROSES MANAJEMEN RISIKO PROYEK

Berdasarkan PMBOK, terdapat 7 proses dalam manajemen risiko proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Plan Risk Management | PMI-36 | Menyusun rencana manajemen risiko | Risk Management Plan |
| Identify Risks | PMI-37 | Mengidentifikasi risiko proyek | Risk Register |
| Perform Qualitative Risk Analysis | PMI-38 | Analisis risiko kualitatif | Risk Prioritization |
| Perform Quantitative Risk Analysis | PMI-39 | Analisis risiko kuantitatif | Quantitative Risk Analysis |
| Plan Risk Responses | PMI-40 | Menentukan respons risiko | Risk Response Plan |
| Implement Risk Responses | PMI-41 | Mengimplementasikan respons | Risk Response Implementation |
| Monitor Risks | PMI-42 | Memantau risiko | Risk Register Updates |

## 9.3. PLAN RISK MANAGEMENT (PMI-36)

### 9.3.1. Tujuan

Menyusun rencana manajemen risiko yang mendefinisikan bagaimana risiko akan diidentifikasi, dianalisis, direspons, dan dimonitor.

### 9.3.2. Output: Risk Management Plan

Rencana Manajemen Risiko P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Risk Identification | Brainstorming, Checklist, Delphi technique, Expert interview |
| Risk Analysis | Qualitative (Probability-Impact Matrix) + Quantitative (Monte Carlo) |
| Risk Response | Avoid, Transfer, Mitigate, Accept |
| Risk Monitoring | Risk review monthly, Trigger-based monitoring |
| Risk Reporting | Risk report in monthly executive report, risk register weekly |
| Risk Tolerance | Sponsor: Low; PM: Medium; Team: Depends on domain |
| Risk Categories | Technical, Organizational, External, Resource, Schedule, Cost, Quality |

## 9.4. IDENTIFY RISKS (PMI-37)

### 9.4.1. Tujuan

Mengidentifikasi semua risiko potensial yang dapat mempengaruhi proyek.

### 9.4.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Risiko tingkat tinggi |
| Project Management Plan | PM | Baseline proyek |
| Requirements Documentation | BA | Kebutuhan proyek |
| Stakeholder Register | PM + BA | Stakeholder risiko |
| Enterprise Environmental Factors | Organisasi | Faktor eksternal |

### 9.4.3. Output: Risk Register

### 9.4.3.1. Teknis Risiko

| ID | Kategori | Risiko | Deskripsi | Trigger |
| --- | --- | --- | --- | --- |
| R-001 | Teknis - Performance | IoT Throughput Failure | Sistem IoT tidak dapat mencapai throughput ≥ 10.000 msg/detik | Performance test gagal di minggu 8 |
| R-002 | Teknis - Performance | IoT Latency High | Latensi IoT > 5 detik dari sensor ke dashboard | Latency test > 5 detik |
| R-003 | Teknis - Accuracy | Simulation Accuracy Low | Akurasi simulasi < 85% dibandingkan data aktual | Validation test gagal |
| R-004 | Teknis - Performance | Simulation Execution Slow | Simulasi 1 tahun > 5 menit | Execution time > 5 menit |
| R-005 | Teknis - Integration | ERP Integration Failure | Integrasi dengan P-FNE-01 s.d P-FNE-07 gagal | Integration test gagal |
| R-006 | Teknis - Security | Security Vulnerability | Terdapat celah keamanan pada sistem IoT/Autonomous | Security scan menemukan critical vulnerability |
| R-007 | Teknis - Data | Data Quality Poor | Data dari ERP/IoT tidak lengkap atau tidak akurat | Data validation gagal |
| R-008 | Teknis - Architecture | Architecture Scalability Issue | Arsitektur tidak mendukung scaling untuk > 10.000 perangkat | Load test gagal |
| R-009 | Teknis - Digital Twin | State Synchronization Delay | Sinkronisasi state Digital Twin > 1 menit | Sync latency > 1 menit |
| R-010 | Teknis - AI/ML | AI Model Inaccuracy | Model AI/ML tidak akurat untuk prediksi | Model validation gagal |

### 9.4.3.2. Sumber Daya & Organisasi Risiko

| ID | Kategori | Risiko | Deskripsi | Trigger |
| --- | --- | --- | --- | --- |
| R-011 | Resource - Availability | Key Person Departure | Anggota kunci tim proyek keluar | Resignation notification |
| R-012 | Resource - Skill | Skill Gap | Tim kurang keahlian di IoT/Simulation/Autonomous | Skill assessment gagal |
| R-013 | Resource - Capacity | Resource Overload | Tim kelebihan beban kerja | Utilization > 120% |
| R-014 | Resource - Acquisition | Hiring Delay | Kesulitan mendapatkan sumber daya yang dibutuhkan | Hiring process > 4 minggu |

### 9.4.3.3. Eksternal Risiko

| ID | Kategori | Risiko | Deskripsi | Trigger |
| --- | --- | --- | --- | --- |
| R-015 | Eksternal - Dependency | P-FNE-07 Delay | Proyek P-FNE-07 (AI/ML) terlambat menyediakan API | API not ready on time |
| R-016 | Eksternal - Dependency | P-FNE-01 Delay | Proyek P-FNE-01 (Foundation) terlambat | IAM/Data not ready |
| R-017 | Eksternal - Vendor | Cloud Provider Issue | Gangguan pada cloud provider (AWS/GCP) | Cloud outage |
| R-018 | Eksternal - Vendor | Software License Delay | Lisensi software (TimescaleDB, Neo4j) tidak tersedia | License not delivered |
| R-019 | Eksternal - Regulatory | Regulatory Change | Perubahan regulasi yang mempengaruhi sistem | New regulation announced |
| R-020 | Eksternal - Market | Technology Obsolescence | Teknologi yang digunakan menjadi usang | New tech release |

### 9.4.3.4. Penjadwalan & Biaya Risiko

| ID | Kategori | Risiko | Deskripsi | Trigger |
| --- | --- | --- | --- | --- |
| R-021 | Schedule - Delay | Development Delay | Pengembangan lebih lambat dari rencana | Sprint tidak selesai |
| R-022 | Schedule - Delay | Testing Delay | Pengujian (performance, security) lebih lambat | Testing phase extended |
| R-023 | Schedule - Delay | Integration Delay | Integrasi dengan sistem lain memakan waktu lama | Integration test extended |
| R-024 | Cost - Overrun | Budget Overrun | Biaya proyek melebihi anggaran | Cost > budget by 10% |
| R-025 | Cost - Overrun | Cloud Cost Spike | Biaya cloud meningkat tidak terduga | Cloud cost > forecast by 20% |
| R-026 | Cost - Overrun | Consultant Cost Overrun | Biaya konsultan melebihi estimasi | Consultant bill > contract |

### 9.4.3.5. Mutu & Keamanan Risiko

| ID | Kategori | Risiko | Deskripsi | Trigger |
| --- | --- | --- | --- | --- |
| R-027 | Quality - Defect | High Defect Rate | Jumlah defect melebihi target | Defect density > 0.5/KLOC |
| R-028 | Quality - Test Coverage | Low Test Coverage | Coverage < 80% | SonarQube report |
| R-029 | Quality - User Acceptance | UAT Failure | User tidak menerima sistem | UAT sign-off failed |
| R-030 | Security - Data Breach | Data Breach | Kebocoran data telemetri atau sistem | Security incident |
| R-031 | Security - IoT Device | IoT Device Compromise | Perangkat IoT disusupi | Unauthorized access detected |

## 9.5. PERFORM QUALITATIVE RISK ANALYSIS (PMI-38)

### 9.5.1. Tujuan

Menganalisis risiko secara kualitatif untuk menentukan prioritas risiko berdasarkan probabilitas dan dampak.

### 9.5.2. Probability and Impact Definitions

Probability Scale:

| Level | Probabilitas | Deskripsi |
| --- | --- | --- |
| Very High | > 70% | Hampir pasti terjadi |
| High | 50% - 70% | Kemungkinan besar terjadi |
| Medium | 30% - 50% | Mungkin terjadi |
| Low | 10% - 30% | Kemungkinan kecil terjadi |
| Very Low | < 10% | Sangat kecil kemungkinan terjadi |

Impact Scale:

| Level | Dampak | Schedule | Cost | Quality/Performance |
| --- | --- | --- | --- | --- |
| Very High | 0.8 - 1.0 | Delay > 4 minggu | > 20% over budget | Kritis, target gagal total |
| High | 0.6 - 0.8 | Delay 2-4 minggu | 10-20% over budget | Mayor, target tidak tercapai |
| Medium | 0.4 - 0.6 | Delay 1-2 minggu | 5-10% over budget | Sedang, target sebagian tercapai |
| Low | 0.2 - 0.4 | Delay < 1 minggu | < 5% over budget | Minor, target tercapai dengan effort tambahan |
| Very Low | 0.0 - 0.2 | Tidak ada delay | < 2% over budget | Tidak berdampak signifikan |

### 9.5.3. Probability-Impact Matrix

Risk Matrix:

text

Impact

│

VH │         R-007  R-001  R-002  R-004  R-005  R-006  R-007  R-030

│

H  │         R-010  R-003  R-009  R-011  R-015  R-016  R-017

│

M  │         R-008  R-012  R-013  R-014  R-018  R-019  R-020  R-022

│

L  │         R-021  R-023  R-024  R-025  R-026  R-027  R-028  R-029

│

VL │         R-031

│

└─────────────────────────────────────────────────────────────── Probability

VL      L       M       H      VH

Legend:

Red Zone (Priority 1): Immediate action required

Yellow Zone (Priority 2): Action plan needed

Green Zone (Priority 3): Monitor only

### 9.5.4. Risk Prioritization

| Priority | Risiko | Prob. | Impact | Risk Score | Status |
| --- | --- | --- | --- | --- | --- |
| 1 - Critical | R-001 IoT Throughput Failure | High (0.6) | High (0.8) | 0.48 | 🔴 Critical |
| 1 - Critical | R-005 ERP Integration Failure | Medium (0.4) | Very High (0.9) | 0.36 | 🔴 Critical |
| 1 - Critical | R-006 Security Vulnerability | Medium (0.4) | Very High (0.9) | 0.36 | 🔴 Critical |
| 1 - Critical | R-030 Data Breach | Low (0.2) | Very High (0.9) | 0.18 | 🔴 Critical |
| 2 - High | R-003 Simulation Accuracy Low | High (0.6) | High (0.7) | 0.42 | 🟡 High |
| 2 - High | R-004 Simulation Execution Slow | High (0.6) | High (0.7) | 0.42 | 🟡 High |
| 2 - High | R-002 IoT Latency High | High (0.6) | Medium (0.6) | 0.36 | 🟡 High |
| 2 - High | R-009 State Sync Delay | High (0.6) | Medium (0.6) | 0.36 | 🟡 High |
| 2 - High | R-011 Key Person Departure | Medium (0.5) | High (0.7) | 0.35 | 🟡 High |
| 2 - High | R-015 P-FNE-07 Delay | Medium (0.5) | High (0.7) | 0.35 | 🟡 High |
| 2 - High | R-016 P-FNE-01 Delay | Medium (0.5) | High (0.7) | 0.35 | 🟡 High |
| 3 - Medium | R-007 Data Quality Poor | Medium (0.4) | High (0.7) | 0.28 | 🟢 Medium |
| 3 - Medium | R-008 Architecture Scalability | Medium (0.4) | High (0.7) | 0.28 | 🟢 Medium |
| 3 - Medium | R-010 AI Model Inaccuracy | Medium (0.4) | High (0.7) | 0.28 | 🟢 Medium |
| 3 - Medium | R-012 Skill Gap | Medium (0.4) | Medium (0.6) | 0.24 | 🟢 Medium |
| 3 - Medium | R-013 Resource Overload | Medium (0.4) | Medium (0.6) | 0.24 | 🟢 Medium |
| 3 - Medium | R-017 Cloud Provider Issue | Medium (0.4) | Medium (0.6) | 0.24 | 🟢 Medium |
| 3 - Medium | R-021 Development Delay | Medium (0.4) | Medium (0.6) | 0.24 | 🟢 Medium |
| 3 - Medium | R-022 Testing Delay | Medium (0.4) | Medium (0.6) | 0.24 | 🟢 Medium |
| 4 - Low | R-014 Hiring Delay | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-018 Software License Delay | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-019 Regulatory Change | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-020 Tech Obsolescence | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-023 Integration Delay | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-024 Budget Overrun | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-025 Cloud Cost Spike | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-026 Consultant Cost Overrun | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-027 High Defect Rate | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-028 Low Test Coverage | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-029 UAT Failure | Low (0.3) | Medium (0.6) | 0.18 | 🟢 Low |
| 4 - Low | R-031 IoT Device Compromise | Very Low (0.1) | Very High (0.9) | 0.09 | 🟢 Low |

## 9.6. PERFORM QUANTITATIVE RISK ANALYSIS (PMI-39)

### 9.6.1. Tujuan

Menganalisis risiko secara kuantitatif untuk menentukan dampak numerik terhadap proyek.

### 9.6.2. Quantitative Risk Analysis Result

Top 5 Critical Risks - Quantitative Impact:

| Risk ID | Risiko | Prob. | Cost Impact | Schedule Impact (hari) | Expected Monetary Value (EMV) |
| --- | --- | --- | --- | --- | --- |
| R-001 | IoT Throughput Failure | 60% | Rp 200,000,000 | 10 | Rp 120,000,000 |
| R-005 | ERP Integration Failure | 40% | Rp 300,000,000 | 15 | Rp 120,000,000 |
| R-006 | Security Vulnerability | 40% | Rp 250,000,000 | 10 | Rp 100,000,000 |
| R-003 | Simulation Accuracy Low | 60% | Rp 150,000,000 | 10 | Rp 90,000,000 |
| R-004 | Simulation Execution Slow | 60% | Rp 100,000,000 | 7 | Rp 60,000,000 |
| Total EMV Top 5 |  |  |  |  | Rp 490,000,000 |

Monte Carlo Simulation Results:

| Metric | Target | P80 | P50 | P20 | Probability of Success |
| --- | --- | --- | --- | --- | --- |
| Project Completion Date | 20 minggu | 22.5 minggu | 21.0 minggu | 19.5 minggu | 55% |
| Project Cost | Rp 2,900,000,000 | Rp 3,150,000,000 | Rp 3,050,000,000 | Rp 2,850,000,000 | 50% |
| IoT Throughput | ≥ 10.000 msg/detik | 8.500 | 9.200 | 10.500 | 60% |
| Simulation Accuracy | ≥ 85% | 82% | 86% | 90% | 65% |

Interpretasi:

- Probabilitas proyek selesai tepat waktu: 55% (perlu buffer tambahan)

- Probabilitas proyek selesai sesuai budget: 50% (perlu cost control ketat)

- Probabilitas IoT throughput mencapai target: 60% (perlu optimasi arsitektur)

- Probabilitas simulation accuracy mencapai target: 65% (perlu kalibrasi intensif)

## 9.7. PLAN RISK RESPONSES (PMI-40)

### 9.7.1. Tujuan

Menentukan respons untuk setiap risiko kritis untuk mengurangi dampak negatif atau memanfaatkan peluang.

### 9.7.2. Risk Response Plan

#### 9.7.2.1. Critical Risks (Priority 1)

| Risk ID | Risiko | Strategi | Respons | Owner | Cost | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | IoT Throughput < 10.000 msg/detik | Reduce | - Optimasi Kafka: increase partitions, consumer groups - Implementasi edge computing untuk agregasi - Load testing minggu ke-6 & ke-8 - Horizontal scaling readiness | IoT Lead | Rp 50,000,000 | Minggu 6-8 |
| R-005 | ERP Integration Failure | Reduce | - Contract testing dengan P-FNE-01 s.d P-FNE-07 - Mock services untuk parallel development - Weekly sync dengan tim FNE - Integration testing bertahap | Integration Lead | Rp 30,000,000 | Minggu 10-17 |
| R-006 | Security Vulnerability | Avoid | - Security requirements from day 1 - Code review dengan security checklist - Regular vulnerability scanning (OWASP ZAP) - Penetration testing di minggu 16-17 | Security Engineer | Rp 75,000,000 | Minggu 1-17 |
| R-030 | Data Breach | Avoid | - Data encryption at rest and in transit - Access control (RBAC) - Audit logging - Security awareness training | Security Engineer | Rp 50,000,000 | Minggu 1-4 |

#### 9.7.2.2. High Risks (Priority 2)

| Risk ID | Risiko | Strategi | Respons | Owner | Cost | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| R-003 | Simulation Accuracy < 85% | Reduce | - Kalibrasi dengan data historis (P-FNE-02 s.d P-FNE-06) - Iterative improvement dengan feedback loop - Parallel testing dengan multiple models | Data Scientist | Rp 40,000,000 | Minggu 12-14 |
| R-004 | Simulation Execution > 5 menit | Reduce | - Optimasi kode SimPy (NumPy vectorization) - Parallel execution (Celery workers) - Horizon simulasi adjustable | Sim Lead | Rp 30,000,000 | Minggu 12-13 |
| R-002 | IoT Latency > 5 detik | Reduce | - Optimasi MQTT: QoS 0 atau 1 - Edge computing untuk preprocessing - Cache layer (Redis) untuk data frequently accessed | IoT Lead | Rp 25,000,000 | Minggu 6-8 |
| R-009 | State Sync Delay > 1 menit | Reduce | - Optimasi Kafka consumer group - Batch processing untuk state update - Redis cache untuk hot data | Twin Lead | Rp 20,000,000 | Minggu 9-10 |
| R-011 | Key Person Departure | Mitigate | - Cross-training antar tim - Knowledge documentation (Confluence) - Pair programming - Succession plan | PM + HR | Rp 15,000,000 | Minggu 1-20 |
| R-015 | P-FNE-07 Delay | Mitigate | - Mock models untuk parallel development - Weekly sync dengan P-FNE-07 team - Fallback: simple rule-based model | PM + Sim Lead | Rp 20,000,000 | Minggu 6-12 |
| R-016 | P-FNE-01 Delay | Mitigate | - Mock IAM/Master Data services - Early integration testing - Weekly sync dengan P-FNE-01 team | PM + Twin Lead | Rp 15,000,000 | Minggu 3-10 |

#### 9.7.2.3. Medium Risks (Priority 3)

| Risk ID | Risiko | Strategi | Respons | Owner | Cost | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| R-007 | Data Quality Poor | Reduce | - Data validation at ingestion - Quality flag in data model - Data quality monitoring | IoT Lead + Twin Lead | Rp 10,000,000 | Minggu 4-10 |
| R-008 | Architecture Scalability Issue | Reduce | - Design for horizontal scaling from start - Load testing for scalability verification - Kubernetes HPA configuration | DevOps | Rp 15,000,000 | Minggu 1-8 |
| R-010 | AI Model Inaccuracy | Reduce | - Multiple model testing - Ensemble approach - Continuous retraining | Data Scientist | Rp 20,000,000 | Minggu 8-14 |
| R-012 | Skill Gap | Reduce | - Training plan (IoT, Twin, Simulation, Autonomous) - Konsultan untuk skill khusus - Internal knowledge sharing | PM + HR | Rp 50,000,000 | Minggu 1-4 |
| R-013 | Resource Overload | Reduce | - Sprint planning: realistic capacity - Workload monitoring - Temporary resource addition if needed | PM | Rp 10,000,000 | Minggu 1-20 |
| R-017 | Cloud Provider Issue | Transfer | - Multi-AZ deployment - Disaster recovery plan - Multi-cloud strategy (optional) | DevOps | Rp 20,000,000 | Minggu 1-2 |
| R-021 | Development Delay | Reduce | - Sprint buffer (1 hari per sprint) - Daily standup untuk blocker identification - Schedule compression if needed | PM + Leads | Rp 10,000,000 | Minggu 1-20 |

#### 9.7.2.4. Low Risks (Priority 4)

| Risk ID | Risiko | Strategi | Respons | Owner | Cost | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| R-014 | Hiring Delay | Mitigate | - Start hiring process early - Use consultants as interim - Internal reallocation | HR + PM | Rp 20,000,000 | Minggu 1-4 |
| R-018 | Software License Delay | Mitigate | - Early procurement - Use trial/open-source alternatives | DevOps | Rp 5,000,000 | Minggu 1 |
| R-019 | Regulatory Change | Monitor | - Monitor regulatory changes - Compliance checklist | PM + BA | Rp 5,000,000 | Minggu 1-20 |
| R-020 | Tech Obsolescence | Monitor | - Regular tech stack review - Follow industry trends | PM + Leads | Rp 5,000,000 | Minggu 1-20 |
| R-022 | Testing Delay | Accept | - Test automation from early stage - Parallel testing - Additional QA if needed | QA Lead | Rp 10,000,000 | Minggu 4-19 |
| R-024 | Budget Overrun | Accept | - Monthly budget review - Cost control measures - Use reserve if needed | PM | Rp 0 | Minggu 1-20 |
| R-025 | Cloud Cost Spike | Reduce | - Auto-scaling with cost limits - Reserved instances - Cloud cost monitoring | DevOps | Rp 10,000,000 | Minggu 1-20 |
| R-027 | High Defect Rate | Reduce | - Code review - Automated testing - Quality gates in CI/CD | QA Lead | Rp 10,000,000 | Minggu 1-20 |
| R-028 | Low Test Coverage | Reduce | - Enforce coverage in CI/CD - Test-driven development | QA Lead | Rp 5,000,000 | Minggu 1-20 |
| R-029 | UAT Failure | Reduce | - Early UAT preparation - End user involvement from early stage - User training | BA | Rp 15,000,000 | Minggu 14-19 |
| R-031 | IoT Device Compromise | Mitigate | - Device authentication - Certificate-based communication - Device monitoring | IoT Lead + Security | Rp 20,000,000 | Minggu 2-8 |

## 9.8. IMPLEMENT RISK RESPONSES (PMI-41)

### 9.8.1. Tujuan

Mengimplementasikan respons risiko yang telah direncanakan.

### 9.8.2. Risk Response Implementation Schedule

| Risk ID | Respons | Implementation Date | Status | Owner |
| --- | --- | --- | --- | --- |
| R-001 | Optimasi Kafka + edge computing | Minggu 6-8 | ✅ Planned | IoT Lead |
| R-003 | Kalibrasi dengan data historis | Minggu 12-14 | ✅ Planned | Data Scientist |
| R-005 | Contract testing + weekly sync | Minggu 1-17 | ✅ Planned | Integration Lead |
| R-006 | Security requirements + scanning | Minggu 1-17 | ✅ Planned | Security Engineer |
| R-011 | Cross-training + documentation | Minggu 1-20 | ✅ Planned | PM + HR |
| R-012 | Training plan | Minggu 1-4 | ✅ Planned | PM + HR |
| R-013 | Workload monitoring | Minggu 1-20 | ✅ Planned | PM |
| R-015 | Mock models + weekly sync | Minggu 6-12 | ✅ Planned | PM + Sim Lead |
| R-016 | Mock services + weekly sync | Minggu 3-10 | ✅ Planned | PM + Twin Lead |
| R-017 | Multi-AZ + DR plan | Minggu 1-2 | ✅ Planned | DevOps |

### 9.8.3. Risk Response Implementation Checklist

| Risk ID | Check Item | Status | Verification | Date |
| --- | --- | --- | --- | --- |
| R-001 | Kafka optimization completed | □ | Throughput test ≥ 10.000 msg/detik |  |
| R-001 | Edge computing implemented | □ | Latency < 5 detik |  |
| R-003 | Calibration with historical data | □ | Accuracy ≥ 85% |  |
| R-003 | Feedback loop implemented | □ | Continuous improvement |  |
| R-005 | Contract tests created | □ | Integration test passing |  |
| R-005 | Weekly sync established | □ | Meeting minutes |  |
| R-006 | Security requirements documented | □ | Security spec approved |  |
| R-006 | Vulnerability scanning active | □ | No critical vulnerabilities |  |
| R-011 | Cross-training completed | □ | Knowledge transfer verified |  |
| R-011 | Documentation updated | □ | Confluence complete |  |
| R-012 | Training completed | □ | Attendance & assessment |  |

## 9.9. MONITOR RISKS (PMI-42)

### 9.9.1. Tujuan

Memantau risiko secara terus-menerus, mengidentifikasi risiko baru, dan memperbarui risk register.

### 9.9.2. Risk Monitoring Activities

| Aktivitas | Frekuensi | Responsible | Deskripsi |
| --- | --- | --- | --- |
| Risk Review | Bulanan | PM + Leads | Review status risiko, update probabilitas & dampak |
| Trigger Monitoring | Mingguan | PM + Leads | Memeriksa trigger untuk setiap risiko |
| New Risk Identification | Bulanan | PM + Leads + Team | Identifikasi risiko baru dari perubahan proyek |
| Risk Report | Bulanan | PM | Laporan risiko dalam executive report |
| Risk Retrospective | Setiap sprint | Team | Review risiko yang terjadi dalam sprint |

### 9.9.3. Risk Monitoring Dashboard

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                       RISK MONITORING DASHBOARD                            │

│                   P-FNE-08: Advanced & Autonomous Enterprise               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Risk Overview                                                              │

│  ───────────────────────────────────────────────────────────────────────── │

│  Total Risks Identified:   31                                              │

│  Critical Risks (P1):      4                                               │

│  High Risks (P2):          7                                               │

│  Medium Risks (P3):        10                                              │

│  Low Risks (P4):           10                                              │

│                                                                             │

│  Risk Status Chart:                                                         │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ Open:     ████████████████████████████████████████████  20 (65%)   │   │

│  │ Mitigating: ██████████████████  6 (19%)                            │   │

│  │ Closed:   ████████  4 (13%)                                        │   │

│  │ Triggered: ██  1 (3%)                                              │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  Top 5 Active Risks:                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ # │ ID │ Risk                 │ Prob. │ Impact │ Status            │   │

│  │---│----│----------------------│-------│--------│-------------------│   │

│  │ 1 │R001│ IoT Throughput       │ 60%   │ High   │ Mitigating        │   │

│  │ 2 │R005│ ERP Integration      │ 40%   │ V.High │ Monitoring        │   │

│  │ 3 │R006│ Security Vulnerability│ 40%   │ V.High │ Mitigating        │   │

│  │ 4 │R003│ Simulation Accuracy  │ 60%   │ High   │ Mitigating        │   │

│  │ 5 │R004│ Simulation Execution │ 60%   │ High   │ Mitigating        │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  Risks Triggered This Month:                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ ID │ Risk                 │ Trigger Date │ Status  │ Action         │   │

│  │----│----------------------│--------------│---------│----------------│   │

│  │ R12│ Skill Gap             │ 15/09/2026   │ Closed  │ Training done  │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  New Risks Identified:                                                      │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ ID │ Risk                 │ Prob. │ Impact │ Type  │ Owner          │   │

│  │----│----------------------│-------│--------│-------│----------------│   │

│  │ R32│ New API dependency   │ Med   │ Med    │ Tech  │ DevOps         │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  Risk Report Date: [DD/MM/YYYY]                                             │

│  Prepared By: [PM Name]                                                     │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 9.9.4. Risk Monitoring Checklist

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                       RISK MONITORING CHECKLIST                             │

│                    P-FNE-08: Advanced & Autonomous Enterprise              │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Date: [DD/MM/YYYY]                                                         │

│  Prepared By: [PM Name]                                                     │

│                                                                             │

│  1. RISK REVIEW                                                             │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ # │ Check Item                                 │ Status │ Notes     │   │

│  │---│--------------------------------------------│--------│-----------│   │

│  │ 1 │ All risks reviewed                         │ [✓/✗]  │           │   │

│  │ 2 │ Probabilities updated                      │ [✓/✗]  │           │   │

│  │ 3 │ Impacts updated                            │ [✓/✗]  │           │   │

│  │ 4 │ Risk priorities reviewed                   │ [✓/✗]  │           │   │

│  │ 5 │ New risks identified                       │ [✓/✗]  │           │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  2. RISK RESPONSE CHECK                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ # │ Check Item                                 │ Status │ Notes     │   │

│  │---│--------------------------------------------│--------│-----------│   │

│  │ 6 │ Mitigation actions on track                 │ [✓/✗]  │           │   │

│  │ 7 │ Triggers being monitored                    │ [✓/✗]  │           │   │

│  │ 8 │ Risk owners identified                      │ [✓/✗]  │           │   │

│  │ 9 │ Risk response budget used                   │ [✓/✗]  │           │   │

│  │10 │ Closed risks documented                     │ [✓/✗]  │           │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  3. EMERGENCY PREPAREDNESS                                                  │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ # │ Check Item                                 │ Status │ Notes     │   │

│  │---│--------------------------------------------│--------│-----------│   │

│  │11 │ Escalation process updated                  │ [✓/✗]  │           │   │

│  │12 │ Contingency plan ready                      │ [✓/✗]  │           │   │

│  │13 │ Emergency contacts updated                  │ [✓/✗]  │           │   │

│  │14 │ Backup/DR plan tested                       │ [✓/✗]  │           │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  Recommendations:                                                           │

│  [List recommendations]                                                     │

│                                                                             │

│  Signed: _______________  Date: _______________                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 9.10. RISK MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Plan Risk Management | Project Charter, EEF | Expert Judgment | Risk Management Plan | PM |
| Identify Risks | PMP, Requirements | Brainstorming, Checklists | Risk Register | PM, Team |
| Qualitative Risk Analysis | Risk Register | Probability-Impact Matrix | Risk Prioritization | PM, Leads |
| Quantitative Risk Analysis | Risk Register | Monte Carlo Simulation | Quantitative Analysis | PM, Data Scientist |
| Plan Risk Responses | Risk Register | Expert Judgment | Risk Response Plan | PM, Leads |
| Implement Risk Responses | Risk Response Plan | Risk Owners | Risk Response Implementation | PM, Leads |
| Monitor Risks | Risk Register, Work Performance | Risk Reviews | Risk Register Updates | PM, Leads |

## 9.11. RINGKASAN MANAJEMEN RISIKO

| Aspek | Rincian |
| --- | --- |
| Total Risks Identified | 31 risiko |
| Critical Risks | 4 risiko (R-001, R-005, R-006, R-030) |
| High Risks | 7 risiko |
| Medium Risks | 10 risiko |
| Low Risks | 10 risiko |
| Risk Reserve | Contingency: Rp 100.000.000, Management: Rp 100.000.000 |
| Risk Tolerance | Sponsor: Low; PM: Medium |
| Risk Review Frequency | Bulanan (formal), Mingguan (informal) |
| Top 5 EMV | Rp 490.000.000 |
| Probability of Success | Schedule: 55%, Cost: 50%, Performance: 60-65% |
| Risk Tools | Risk Register, Probability-Impact Matrix, Monte Carlo Simulation |

# BAB 10: MANAJEMEN PENGADAAN PROYEK

## 10.1. PENDAHULUAN

Manajemen pengadaan proyek bertujuan untuk mengelola akuisisi barang dan jasa dari pihak eksternal yang dibutuhkan untuk menyelesaikan Proyek P-FNE-08: Advanced & Autonomous Enterprise. Pengadaan yang efektif sangat penting untuk memastikan ketersediaan sumber daya tepat waktu, dengan kualitas yang sesuai, dan pada harga yang kompetitif.

Proyek P-FNE-08 membutuhkan berbagai pengadaan, termasuk:

- Infrastruktur Cloud (AWS/GCP)

- Lisensi Software (TimescaleDB, Neo4j, Kafka)

- Perangkat Keras IoT (Gateway untuk staging)

- Jasa Konsultan (IoT, Simulation, Autonomous, Security)

- Jasa Pelatihan

- Jasa Pengujian Keamanan (Penetration Testing)

## 10.2. PROSES MANAJEMEN PENGADAAN PROYEK

Berdasarkan PMBOK, terdapat 4 proses dalam manajemen pengadaan proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Plan Procurement Management | PMI-43 | Menyusun rencana manajemen pengadaan | Procurement Management Plan |
| Conduct Procurements | PMI-44 | Melakukan pengadaan | Seller Selection, Contract |
| Control Procurements | PMI-45 | Mengendalikan pengadaan | Procurement Updates |
| Close Procurements | PMI-46 | Menyelesaikan kontrak | Closed Procurements |

## 10.3. PLAN PROCUREMENT MANAGEMENT (PMI-43)

### 10.3.1. Tujuan

Menyusun rencana manajemen pengadaan yang mendefinisikan bagaimana pengadaan akan dilakukan, dikendalikan, dan ditutup.

### 10.3.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Pengadaan tingkat tinggi |
| Resource Requirements | PM + Leads | Kebutuhan sumber daya |
| Risk Register | PM + Leads | Risiko terkait pengadaan |
| Enterprise Environmental Factors | Organisasi | Vendor, kontrak, regulasi |
| Organizational Process Assets | Organisasi | Kebijakan pengadaan, template |

### 10.3.3. Output: Procurement Management Plan

Rencana Manajemen Pengadaan P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Procurement Strategy | Competitive bidding untuk pengadaan besar; Single source untuk pengadaan kecil/khusus |
| Contract Types | Fixed-price untuk software/hardware; Time & Material untuk konsultan |
| Vendor Selection Criteria | Technical capability (30%), Cost (25%), Track record (20%), Support/SLA (15%), Timeline (10%) |
| Procurement Process | RFI → RFP → Vendor Evaluation → Contract Award |
| Vendor Management | Vendor Performance Review bulanan, Issue escalation |
| Approval Authority | PM (≤ Rp 50 Juta), Sponsor (≤ Rp 200 Juta), Board (> Rp 200 Juta) |
| Contract Management | Contract repository, milestone-based payment, SLA enforcement |

## 10.4. PROCUREMENT ITEMS

### 10.4.1. Procurement Register

| ID | Item | Kategori | Jenis | Estimasi (IDR) | Vendor | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| P-001 | Cloud Infrastructure (AWS/GCP) | Infrastruktur | Service | Rp 300.000.000 | AWS/GCP | Minggu 1-20 |
| P-002 | TimescaleDB Enterprise License | Software | License | Rp 50.000.000 | Timescale | Minggu 1 |
| P-003 | Neo4j Enterprise License | Software | License | Rp 30.000.000 | Neo4j | Minggu 1 |
| P-004 | Confluent Kafka License | Software | License | Rp 20.000.000 | Confluent | Minggu 1 |
| P-005 | Grafana Enterprise License | Software | License | Rp 20.000.000 | Grafana Labs | Minggu 2 |
| P-006 | IoT Gateway Devices | Hardware | Physical | Rp 75.000.000 | Vendor IoT | Minggu 2 |
| P-007 | IoT Consultant | Service | Consultant | Rp 100.000.000 | Konsultan IoT | Minggu 2-8 |
| P-008 | Simulation/AI Consultant | Service | Consultant | Rp 100.000.000 | Konsultan Sim | Minggu 4-12 |
| P-009 | Penetration Testing Service | Service | Testing | Rp 75.000.000 | Security Firm | Minggu 16 |
| P-010 | Training - IoT/Twin/Sim/Auto | Service | Training | Rp 150.000.000 | Training Provider | Minggu 1-4 |
| P-011 | Performance Testing Tools | Software | License | Rp 50.000.000 | Vendor Testing | Minggu 4 |

Total Procurement Budget: Rp 970.000.000 (excludes personnel)

## 10.5. PROCUREMENT DETAILS

### 10.5.1. P-001: Cloud Infrastructure (AWS/GCP)

| Aspek | Rincian |
| --- | --- |
| Item | Cloud Infrastructure - Compute, Storage, Database, Kafka |
| Justifikasi | Dibutuhkan untuk hosting aplikasi P-FNE-08 dengan skalabilitas tinggi |
| Spesifikasi Teknis | - Compute: Kubernetes cluster (min 3 nodes) - Storage: 5 TB object storage - Database: PostgreSQL + TimescaleDB extension - Message Broker: Managed Kafka (Confluent Cloud) - Monitoring: Prometheus + Grafana |
| Kriteria Seleksi | 1. Technical capability (30%) 2. Cost (25%) 3. Support & SLA (20%) 4. Security & Compliance (15%) 5. Track record (10%) |
| Contract Type | Pay-as-you-go / Reserved Instance |
| Timeline | Minggu 1-20 |
| Vendor | AWS atau GCP |

### 10.5.2. P-002: TimescaleDB Enterprise License

| Aspek | Rincian |
| --- | --- |
| Item | TimescaleDB Enterprise License |
| Justifikasi | Time-series database untuk menyimpan data telemetri IoT dengan retention 1 tahun |
| Spesifikasi Teknis | - Enterprise edition dengan compression - Multi-node clustering - Continuous aggregates - Data retention policy |
| Kriteria Seleksi | 1. Technical fit (40%) 2. Cost (30%) 3. Support (20%) 4. Track record (10%) |
| Contract Type | Fixed-price (annual subscription) |
| Timeline | Minggu 1 |
| Vendor | Timescale Inc. |

### 10.5.3. P-003: Neo4j Enterprise License

| Aspek | Rincian |
| --- | --- |
| Item | Neo4j Enterprise License |
| Justifikasi | Graph database untuk menyimpan relasi antar Digital Twin dan Knowledge Graph |
| Spesifikasi Teknis | - Enterprise edition - Multi-node clustering - Graph analytics capabilities |
| Kriteria Seleksi | 1. Technical fit (40%) 2. Cost (30%) 3. Support (20%) 4. Track record (10%) |
| Contract Type | Fixed-price (annual subscription) |
| Timeline | Minggu 1 |
| Vendor | Neo4j Inc. |

### 10.5.4. P-004: Confluent Kafka License

| Aspek | Rincian |
| --- | --- |
| Item | Confluent Kafka Enterprise License |
| Justifikasi | Event-driven architecture untuk komunikasi asynchronous antar layanan dan IoT |
| Spesifikasi Teknis | - Confluent Cloud or Self-managed - 20 topics with 3 partitions - High throughput (≥ 10.000 msg/detik) - Schema registry |
| Kriteria Seleksi | 1. Technical fit (40%) 2. Cost (30%) 3. Support (20%) 4. Track record (10%) |
| Contract Type | Fixed-price (annual subscription) |
| Timeline | Minggu 1 |
| Vendor | Confluent Inc. |

### 10.5.5. P-005: Grafana Enterprise License

| Aspek | Rincian |
| --- | --- |
| Item | Grafana Enterprise License |
| Justifikasi | Dashboard dan monitoring untuk IoT, Twin, Simulation, Autonomy |
| Spesifikasi Teknis | - Enterprise edition - Multi-tenancy - Advanced alerting - Dashboard as code |
| Kriteria Seleksi | 1. Technical fit (40%) 2. Cost (30%) 3. Support (20%) 4. Track record (10%) |
| Contract Type | Fixed-price (annual subscription) |
| Timeline | Minggu 2 |
| Vendor | Grafana Labs |

### 10.5.6. P-006: IoT Gateway Devices

| Aspek | Rincian |
| --- | --- |
| Item | IoT Gateway Devices for Staging Environment |
| Justifikasi | Dibutuhkan untuk menguji integrasi IoT di lingkungan staging sebelum production |
| Spesifikasi Teknis | - MQTT support - 4G/LTE connectivity - Edge computing capability - Power: 12-24V DC - 5 unit untuk berbagai skenario |
| Kriteria Seleksi | 1. Technical specification (35%) 2. Cost (30%) 3. Delivery timeline (20%) 4. Vendor reputation (15%) |
| Contract Type | Fixed-price (one-time purchase) |
| Timeline | Minggu 2 |
| Vendor | Vendor IoT Terpilih |

### 10.5.7. P-007: IoT Consultant

| Aspek | Rincian |
| --- | --- |
| Item | IoT Consultant |
| Justifikasi | Keahlian IoT (MQTT, TimescaleDB, Kafka) untuk membantu tim internal |
| Scope of Work | - Arsitektur IoT - Optimasi throughput dan latency - Edge computing design - Telemetry data modeling - Training tim internal |
| Kriteria Seleksi | 1. Technical expertise (35%) 2. Project experience (25%) 3. Cost (20%) 4. Availability (10%) 5. References (10%) |
| Contract Type | Time & Material (2 bulan) |
| Timeline | Minggu 2-8 |
| Vendor | Konsultan IoT Terpilih |

### 10.5.8. P-008: Simulation/AI Consultant

| Aspek | Rincian |
| --- | --- |
| Item | Simulation & AI Consultant |
| Justifikasi | Keahlian Simulation (SimPy) dan AI/ML untuk optimasi dan kalibrasi |
| Scope of Work | - Simulation architecture (5 use cases) - Optimization algorithms - AI model integration - Simulation calibration - Training tim internal |
| Kriteria Seleksi | 1. Technical expertise (35%) 2. Project experience (25%) 3. Cost (20%) 4. Availability (10%) 5. References (10%) |
| Contract Type | Time & Material (2 bulan) |
| Timeline | Minggu 4-12 |
| Vendor | Konsultan Sim/AI Terpilih |

### 10.5.9. P-009: Penetration Testing Service

| Aspek | Rincian |
| --- | --- |
| Item | Penetration Testing Service |
| Justifikasi | Untuk memastikan keamanan sistem IoT, Twin, Simulation, Autonomous |
| Scope of Work | - Vulnerability assessment - Penetration testing (web, API, IoT) - Security report with findings - Remediation recommendations |
| Kriteria Seleksi | 1. Security expertise (35%) 2. Industry certifications (25%) 3. Cost (20%) 4. Reporting quality (10%) 5. References (10%) |
| Contract Type | Fixed-price (project-based) |
| Timeline | Minggu 16 |
| Vendor | Security Firm Terpilih |

### 10.5.10. P-010: Training Services

| Aspek | Rincian |
| --- | --- |
| Item | Training Services - IoT, Twin, Simulation, Autonomous |
| Justifikasi | Meningkatkan skill tim internal untuk pengembangan dan pemeliharaan |
| Scope of Work | - IoT Training (2 hari) - Digital Twin Training (2 hari) - Simulation & AI Training (2 hari) - Autonomous & Rule Engine Training (2 hari) Total 8 hari training |
| Kriteria Seleksi | 1. Trainer expertise (30%) 2. Training materials quality (25%) 3. Cost (25%) 4. Flexibility (10%) 5. References (10%) |
| Contract Type | Fixed-price |
| Timeline | Minggu 1-4 |
| Vendor | Training Provider Terpilih |

### 10.5.11. P-011: Performance Testing Tools

| Aspek | Rincian |
| --- | --- |
| Item | Performance Testing Tools |
| Justifikasi | Untuk melakukan load testing dan performance testing sistem |
| Spesifikasi Teknis | - JMeter Enterprise / LoadRunner - Load testing up to 15.000 concurrent users - Reporting and analytics |
| Kriteria Seleksi | 1. Technical capability (35%) 2. Cost (30%) 3. Ease of use (20%) 4. Support (15%) |
| Contract Type | Fixed-price (annual subscription) |
| Timeline | Minggu 4 |
| Vendor | Vendor Testing Terpilih |

## 10.6. CONDUCT PROCUREMENTS (PMI-44)

### 10.6.1. Tujuan

Melakukan proses pengadaan, termasuk mengeluarkan RFP/RFQ, evaluasi vendor, dan negosiasi kontrak.

### 10.6.2. Procurement Process Flow

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        PROCUREMENT PROCESS FLOW                             │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  1. IDENTIFY NEED                                                           │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Identifikasi kebutuhan pengadaan                                 │   │

│  │  Siapkan SOW (Statement of Work)                                  │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  2. RFI / RFP / RFQ                                                         │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Keluarkan RFI (Request for Information) atau RFP (Request for     │   │

│  │  Proposal) atau RFQ (Request for Quotation)                        │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  3. VENDOR EVALUATION                                                       │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Evaluasi proposal berdasarkan criteria                             │   │

│  │  Scoring matrix                                                    │   │

│  │  Shortlist vendor                                                  │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  4. NEGOTIATION                                                            │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Negosiasi harga, termin, SLA                                      │   │

│  │  Legal review                                                      │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  5. CONTRACT AWARD                                                         │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Tanda tangan kontrak                                              │   │

│  │  Award notification                                                │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  6. CONTRACT MANAGEMENT                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Monitoring kinerja vendor                                         │   │

│  │  Payment processing                                                │   │

│  │  Issue resolution                                                  │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 10.6.3. Vendor Evaluation Scoring Matrix

| Vendor | Technical (30%) | Cost (25%) | Track Record (20%) | Support/SLA (15%) | Timeline (10%) | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Vendor A | 28/30 | 22/25 | 18/20 | 14/15 | 9/10 | 91/100 |
| Vendor B | 25/30 | 23/25 | 17/20 | 13/15 | 8/10 | 86/100 |
| Vendor C | 22/30 | 24/25 | 15/20 | 12/15 | 7/10 | 80/100 |

Decision: Vendor A selected (highest technical capability with good cost).

### 10.6.4. Contract Templates

Contract Types:

| Contract Type | Usage | Items |
| --- | --- | --- |
| Fixed-Price | Software licenses, Hardware | P-002, P-003, P-004, P-005, P-006, P-009, P-011 |
| Time & Material | Consultant services | P-007, P-008 |
| Pay-as-you-go | Cloud infrastructure | P-001 |
| Fixed-Price with Milestones | Training services | P-010 |

## 10.7. CONTROL PROCUREMENTS (PMI-45)

### 10.7.1. Tujuan

Mengendalikan pengadaan dengan memantau kinerja vendor dan memastikan kepatuhan terhadap kontrak.

### 10.7.2. Procurement Control Activities

| Aktivitas | Frekuensi | Responsible | Deskripsi |
| --- | --- | --- | --- |
| Vendor Performance Review | Bulanan | PM + Owner | Review kinerja vendor terhadap SLA |
| Contract Compliance Check | Bulanan | PM + Legal | Memastikan kepatuhan terhadap kontrak |
| Invoice Verification | Sesuai termin | PM + Finance | Verifikasi tagihan dengan pekerjaan |
| Issue Resolution | Sesuai kebutuhan | PM + Vendor | Menyelesaikan issue dengan vendor |
| Change Request | Sesuai kebutuhan | PM + CCB | Perubahan kontrak jika diperlukan |

### 10.7.3. Vendor Performance Metrics

| Metric | Target | Measurement | Frequency |
| --- | --- | --- | --- |
| On-time Delivery | ≥ 95% | Delivery date vs agreed | Bulanan |
| Quality of Deliverables | ≥ 90% | Inspection/Testing | Bulanan |
| Issue Response Time | ≤ 4 hours | SLA compliance | Bulanan |
| Issue Resolution Time | ≤ 24 hours | SLA compliance | Bulanan |
| Communication Quality | ≥ 4/5 | Vendor survey | Bulanan |
| Cost Adherence | Within budget | Invoice vs contract | Bulanan |

### 10.7.4. Vendor Performance Review Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                     VENDOR PERFORMANCE REVIEW                               │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Vendor Name: [Vendor Name]                                                 │

│  Contract ID: [Contract ID]                                                 │

│  Review Period: [DD/MM/YYYY] - [DD/MM/YYYY]                               │

│  Prepared By: [PM Name]                                                     │

│  Date: [DD/MM/YYYY]                                                         │

│                                                                             │

│  1. PERFORMANCE METRICS                                                     │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Metric                    │ Target    │ Actual   │ Status              │

│  │---------------------------│-----------│----------│---------------------│

│  │ On-time Delivery          │ ≥ 95%     │ [X]%     │ [✅/⚠️/❌]         │

│  │ Quality of Deliverables   │ ≥ 90%     │ [X]%     │ [✅/⚠️/❌]         │

│  │ Issue Response Time       │ ≤ 4 hrs   │ [X] hrs  │ [✅/⚠️/❌]         │

│  │ Issue Resolution Time     │ ≤ 24 hrs  │ [X] hrs  │ [✅/⚠️/❌]         │

│  │ Communication Quality     │ ≥ 4/5     │ [X]      │ [✅/⚠️/❌]         │

│  │ Cost Adherence            │ Within    │ [X]%     │ [✅/⚠️/❌]         │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  2. DELIVERABLES STATUS                                                      │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Deliverable           │ Due Date  │ Status   │ Notes                  │

│  │-----------------------│-----------│----------│------------------------│

│  │ [Deliverable 1]       │ [Date]    │ [Done/In Progress/Issue] │       │

│  │ [Deliverable 2]       │ [Date]    │ [Done/In Progress/Issue] │       │

│  │ [Deliverable 3]       │ [Date]    │ [Done/In Progress/Issue] │       │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  3. ISSUES & CONCERNS                                                        │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ ID │ Issue                │ Severity │ Status   │ Action               │

│  │----│----------------------│----------│----------│----------------------│

│  │ 1  │ [Issue 1]            │ [High/Med/Low] │ [Open/Closed] │ [Action]   │

│  │ 2  │ [Issue 2]            │ [High/Med/Low] │ [Open/Closed] │ [Action]   │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  4. FEEDBACK                                                                 │

│  ───────────────────────────────────────────────────────────────────────── │

│  Strengths:                                                                 │

│  - [Strength 1]                                                             │

│  - [Strength 2]                                                             │

│                                                                             │

│  Areas for Improvement:                                                     │

│  - [Improvement 1]                                                          │

│  - [Improvement 2]                                                          │

│                                                                             │

│  5. ACTION PLAN                                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ # │ Action               │ Owner   │ Target Date │ Status              │

│  │---│----------------------│---------│-------------│---------------------│

│  │ 1 │ [Action 1]           │ [Name]  │ [Date]      │ [Pending/In Progress]│

│  │ 2 │ [Action 2]           │ [Name]  │ [Date]      │ [Pending/In Progress]│

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  Vendor Representative: _______________  Date: _______________            │

│  Project Manager: _______________       Date: _______________            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 10.8. CLOSE PROCUREMENTS (PMI-46)

### 10.8.1. Tujuan

Menyelesaikan kontrak pengadaan secara formal setelah semua pekerjaan selesai dan deliverables diterima.

### 10.8.2. Procurement Closure Checklist

| Contract ID | Item | Final Deliverable Accepted | Final Payment Made | Contract Closed |
| --- | --- | --- | --- | --- |
| P-001 | Cloud Infrastructure | ☐ | ☐ | ☐ |
| P-002 | TimescaleDB License | ☐ | ☐ | ☐ |
| P-003 | Neo4j License | ☐ | ☐ | ☐ |
| P-004 | Confluent Kafka License | ☐ | ☐ | ☐ |
| P-005 | Grafana License | ☐ | ☐ | ☐ |
| P-006 | IoT Gateway Devices | ☐ | ☐ | ☐ |
| P-007 | IoT Consultant | ☐ | ☐ | ☐ |
| P-008 | Simulation/AI Consultant | ☐ | ☐ | ☐ |
| P-009 | Penetration Testing | ☐ | ☐ | ☐ |
| P-010 | Training Services | ☐ | ☐ | ☐ |
| P-011 | Performance Testing Tools | ☐ | ☐ | ☐ |

### 10.8.3. Procurement Closure Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                       PROCUREMENT CLOSURE PROCESS                           │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  1. VERIFY                                                                  │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Verifikasi semua deliverable telah diterima dan sesuai dengan     │   │

│  │  kontrak                                                           │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  2. ACCEPT                                                                  │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Tanda tangan acceptance form oleh PM dan sponsor                  │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  3. PAYMENT                                                                 │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Proses final payment sesuai kontrak                               │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  4. DOCUMENT                                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Dokumentasi semua vendor performance, deliverables,               │   │

│  │  dan lesson learned terkait pengadaan                              │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                              │                                              │

│                              ▼                                              │

│  5. CLOSE                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │  Tanda tangan contract closure oleh vendor dan PM                  │   │

│  │  Archive contract documents                                         │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 10.9. PROCUREMENT MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Plan Procurement Management | Requirements, Resource Plan | Expert Judgment, Make-or-Buy Analysis | Procurement Management Plan | PM, Procurement |
| Conduct Procurements | Procurement Plan, SOW | RFI/RFP/RFQ, Bid Evaluation, Negotiation | Seller Selection, Contract | PM, Procurement |
| Control Procurements | Contract, Performance Data | Vendor Review, Performance Metrics | Procurement Updates, Change Requests | PM, Procurement |
| Close Procurements | Contract, Accepted Deliverables | Contract Closure, Lessons Learned | Closed Procurements | PM, Procurement |

## 10.10. RINGKASAN MANAJEMEN PENGADAAN

| Aspek | Rincian |
| --- | --- |
| Total Procurement Items | 11 items |
| Total Procurement Budget | Rp 970.000.000 |
| Contract Types | Fixed-price, Time & Material, Pay-as-you-go |
| Key Vendors | AWS/GCP, Timescale, Neo4j, Confluent, Grafana, IoT Hardware Vendor, IoT Consultant, Simulation Consultant, Security Firm, Training Provider, Testing Tools Vendor |
| Vendor Selection Criteria | Technical (30%), Cost (25%), Track Record (20%), Support/SLA (15%), Timeline (10%) |
| Vendor Review Frequency | Bulanan |
| Approval Authority | PM (≤ Rp 50 Juta), Sponsor (≤ Rp 200 Juta), Board (> Rp 200 Juta) |
| Procurement Process | RFI → RFP → Vendor Evaluation → Contract Award → Contract Management → Contract Closure |

# BAB 11: MANAJEMEN PEMANGKU KEPENTINGAN PROYEK

## 11.1. PENDAHULUAN

Manajemen pemangku kepentingan proyek bertujuan untuk mengidentifikasi semua pihak yang berkepentingan dengan Proyek P-FNE-08: Advanced & Autonomous Enterprise, memahami kebutuhan dan harapan mereka, serta melibatkan mereka secara efektif sepanjang siklus hidup proyek.

Proyek P-FNE-08 memiliki stakeholder yang beragam, mulai dari sponsor dan steering committee, tim proyek internal, tim proyek FNE lainnya, end users (operasional pertanian, manajemen, IT), hingga vendor dan regulator. Manajemen stakeholder yang efektif sangat penting untuk:

- Mendapatkan dukungan untuk proyek

- Mengurangi resistensi terhadap perubahan

- Memastikan kebutuhan terpenuhi

- Menghindari konflik yang tidak perlu

## 11.2. PROSES MANAJEMEN PEMANGKU KEPENTINGAN PROYEK

Berdasarkan PMBOK, terdapat 4 proses dalam manajemen pemangku kepentingan proyek yang akan diterapkan pada Proyek P-FNE-08:

| Proses | Kode | Deskripsi | Output Utama |
| --- | --- | --- | --- |
| Identify Stakeholders | PMI-47 | Mengidentifikasi stakeholder proyek | Stakeholder Register |
| Plan Stakeholder Engagement | PMI-48 | Merencanakan keterlibatan stakeholder | Stakeholder Engagement Plan |
| Manage Stakeholder Engagement | PMI-49 | Mengelola keterlibatan stakeholder | Stakeholder Updates, Issue Log |
| Monitor Stakeholder Engagement | PMI-50 | Memantau keterlibatan stakeholder | Stakeholder Engagement Status |

## 11.3. IDENTIFY STAKEHOLDERS (PMI-47)

### 11.3.1. Tujuan

Mengidentifikasi semua individu, kelompok, atau organisasi yang dapat mempengaruhi atau dipengaruhi oleh Proyek P-FNE-08.

### 11.3.2. Input

| Input | Sumber | Deskripsi |
| --- | --- | --- |
| Project Charter | Project Sponsor | Stakeholder tingkat tinggi |
| Procurement Documents | PM + Procurement | Vendor dan kontraktor |
| Enterprise Environmental Factors | Organisasi | Budaya organisasi, struktur |
| Organizational Process Assets | Organisasi | Stakeholder register sebelumnya |

### 11.3.3. Output: Stakeholder Register

Stakeholder Register P-FNE-08:

| ID | Stakeholder | Peran/Organisasi | Kategori | Interest | Influence | Power | Engagement Level | Komunikasi |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S-001 | Project Sponsor | CEO/Direktur FNE | Internal | High | High | High | Supportive | Bulanan (Meeting) |
| S-002 | Steering Committee | Direksi FNE | Internal | High | High | High | Supportive | Bulanan (Meeting) |
| S-003 | Product Owner | Tim Produk FNE | Internal | High | Medium | Medium | Supportive | Mingguan (Meeting) |
| S-004 | Tim P-FNE-01 | Foundation Team | Internal | High | Medium | Medium | Supportive | Mingguan (Sync) |
| S-005 | Tim P-FNE-02 | Agricultural Operations Team | Internal | High | Medium | Medium | Supportive | Mingguan (Sync) |
| S-006 | Tim P-FNE-03 | Supply Chain Team | Internal | Medium | Medium | Medium | Neutral | 2 Mingguan |
| S-007 | Tim P-FNE-04 | Production Team | Internal | Medium | Medium | Medium | Neutral | 2 Mingguan |
| S-008 | Tim P-FNE-05 | Commerce Team | Internal | Medium | Medium | Medium | Neutral | 2 Mingguan |
| S-009 | Tim P-FNE-06 | Finance & HCM Team | Internal | Medium | Medium | Medium | Neutral | 2 Mingguan |
| S-010 | Tim P-FNE-07 | Intelligence Team | Internal | High | Medium | Medium | Supportive | Mingguan (Sync) |
| S-011 | End Users - Farm Ops | Operasional Lapangan | Internal | High | Low | Low | Neutral | UAT, Training |
| S-012 | End Users - Supply Chain | Manajemen Rantai Pasok | Internal | High | Medium | Medium | Neutral | UAT, Training |
| S-013 | End Users - Management | Manajemen Puncak | Internal | High | High | High | Neutral | UAT, Demo |
| S-014 | End Users - IT Support | IT Department | Internal | High | Medium | Medium | Supportive | Bulanan |
| S-015 | Tim Proyek P-FNE-08 | Pelaksana Proyek | Internal | High | Medium | Medium | Supportive | Harian |
| S-016 | Cloud Vendor | AWS/GCP | Eksternal | Low | Low | Low | Neutral | Sesuai kebutuhan |
| S-017 | Software Vendor | Timescale/Neo4j/Confluent | Eksternal | Low | Low | Low | Neutral | Sesuai kebutuhan |
| S-018 | Hardware Vendor | IoT Gateway Vendor | Eksternal | Low | Low | Low | Neutral | Sesuai kebutuhan |
| S-019 | IoT Consultant | Konsultan IoT | Eksternal | Medium | Low | Low | Supportive | Mingguan |
| S-020 | Simulation Consultant | Konsultan Sim/AI | Eksternal | Medium | Low | Low | Supportive | Mingguan |
| S-021 | Security Firm | Penetration Testing | Eksternal | Low | Low | Low | Neutral | Sesuai kebutuhan |
| S-022 | Training Provider | Training Services | Eksternal | Low | Low | Low | Neutral | Sesuai kebutuhan |
| S-023 | Internal Audit | Audit Internal | Internal | Medium | Medium | Medium | Neutral | Bulanan |
| S-024 | Regulator | Pemerintah | Eksternal | Low | High | High | Neutral | Sesuai kebutuhan |

## 11.4. STAKEHOLDER ANALYSIS

### 11.4.1. Power/Interest Grid

text

Power/Influence

│

H │ S-001 ●  S-002 ●         S-024 ●

i │

g │          S-004 ●  S-005 ●

h │          S-010 ●          S-013 ●

│

M │ S-003 ●  S-006 ●  S-007 ●  S-008 ●  S-009 ●

e │          S-011 ●  S-012 ●  S-014 ●  S-015 ●

d │          S-023 ●

i │

u │

m │ S-016 ●  S-017 ●  S-018 ●  S-019 ●  S-020 ●

│ S-021 ●  S-022 ●

L │

o │

w │

└─────────────────────────────────────────────────────────────── Interest

Low                     Medium                     High

Legend:

● High Power, High Interest: Manage Closely (S-001, S-002)

● High Power, Low Interest: Keep Satisfied (S-024)

● Low Power, High Interest: Keep Informed (S-004, S-005, S-010, S-013, S-015)

● Low Power, Low Interest: Monitor (S-016, S-017, S-018, S-021, S-022)

### 11.4.2. Stakeholder Analysis Matrix

| Stakeholder | Power | Interest | Influence | Urgency | Legitimacy | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| S-001: Sponsor | High | High | High | High | High | 1 - Highest |
| S-002: Steering Committee | High | High | High | Medium | High | 1 - Highest |
| S-003: Product Owner | Medium | High | Medium | High | High | 2 - High |
| S-004: P-FNE-01 Team | Medium | High | Medium | High | High | 2 - High |
| S-005: P-FNE-02 Team | Medium | High | Medium | High | High | 2 - High |
| S-010: P-FNE-07 Team | Medium | High | Medium | High | High | 2 - High |
| S-013: Management | High | High | High | Medium | High | 2 - High |
| S-015: Tim Proyek | Medium | High | Medium | High | High | 2 - High |
| S-006: P-FNE-03 Team | Medium | Medium | Medium | Medium | Medium | 3 - Medium |
| S-007: P-FNE-04 Team | Medium | Medium | Medium | Medium | Medium | 3 - Medium |
| S-008: P-FNE-05 Team | Medium | Medium | Medium | Medium | Medium | 3 - Medium |
| S-009: P-FNE-06 Team | Medium | Medium | Medium | Medium | Medium | 3 - Medium |
| S-011: Farm Ops | Low | High | Low | High | High | 3 - Medium |
| S-012: Supply Chain | Medium | High | Medium | High | High | 3 - Medium |
| S-014: IT Support | Medium | High | Medium | Medium | High | 3 - Medium |
| S-023: Internal Audit | Medium | Medium | Medium | Medium | High | 3 - Medium |
| S-019: IoT Consultant | Low | Medium | Low | Medium | Medium | 4 - Low |
| S-020: Sim Consultant | Low | Medium | Low | Medium | Medium | 4 - Low |
| S-024: Regulator | High | Low | High | Low | High | 4 - Low |
| S-016: Cloud Vendor | Low | Low | Low | Low | Low | 5 - Lowest |
| S-017: Software Vendor | Low | Low | Low | Low | Low | 5 - Lowest |
| S-018: Hardware Vendor | Low | Low | Low | Low | Low | 5 - Lowest |
| S-021: Security Firm | Low | Low | Low | Low | Low | 5 - Lowest |
| S-022: Training Provider | Low | Low | Low | Low | Low | 5 - Lowest |

## 11.5. PLAN STAKEHOLDER ENGAGEMENT (PMI-48)

### 11.5.1. Tujuan

Merencanakan strategi keterlibatan stakeholder untuk memastikan stakeholder yang tepat terlibat pada tingkat yang tepat.

### 11.5.2. Output: Stakeholder Engagement Plan

Rencana Keterlibatan Stakeholder P-FNE-08:

| Aspek | Rincian |
| --- | --- |
| Engagement Strategy | Tailored per stakeholder berdasarkan power/interest grid |
| Communication | Melalui Communications Management Plan |
| Involvement | Steering Committee (strategic), PM & Leads (tactical), Team (operational) |
| Feedback Mechanism | Survey, meeting feedback, UAT feedback |
| Issue Resolution | Escalation process, issue log |
| Stakeholder Satisfaction | Survey bulanan, quarterly review |

### 11.5.3. Stakeholder Engagement Plan Detail

| Stakeholder | Desired Engagement | Current Engagement | Gap | Strategy | Action | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| S-001: Sponsor | Supportive | Supportive | None | Keep informed, highlight success | Monthly executive report, milestone celebration | PM |
| S-002: Steering Committee | Supportive | Supportive | None | Present roadmap, risks, decisions | Monthly presentation, strategic decisions | PM |
| S-003: Product Owner | Supportive | Supportive | None | Alignment on product vision | Weekly backlog grooming, sprint review | PM, BA |
| S-004: P-FNE-01 | Supportive → Collaborative | Neutral | Gap | Emphasize integration benefits | Weekly sync, integration demo | PM, Twin Lead |
| S-005: P-FNE-02 | Supportive → Collaborative | Neutral | Gap | Emphasize data flow benefits | Weekly sync, data integration demo | PM, IoT Lead |
| S-006: P-FNE-03 | Supportive | Neutral | Gap | Highlight supply chain simulation | Monthly sync, simulation demo | PM, Sim Lead |
| S-007: P-FNE-04 | Supportive | Neutral | Gap | Highlight production simulation | Monthly sync, simulation demo | PM, Sim Lead |
| S-008: P-FNE-05 | Supportive | Neutral | Gap | Highlight commerce integration | Monthly sync, commerce demo | PM, Sim Lead |
| S-009: P-FNE-06 | Supportive | Neutral | Gap | Highlight financial simulation | Monthly sync, simulation demo | PM, Sim Lead |
| S-010: P-FNE-07 | Supportive → Collaborative | Neutral | Gap | Emphasize AI/ML integration | Weekly sync, model integration demo | PM, Data Scientist |
| S-011: Farm Ops | Supportive | Neutral | Gap | Early involvement, feedback | UAT workshop, user training, feedback sessions | BA, QA |
| S-012: Supply Chain | Supportive | Neutral | Gap | Early involvement, feedback | UAT workshop, user training, feedback sessions | BA, QA |
| S-013: Management | Supportive | Neutral | Gap | Demonstrate business value | UAT workshop, demo, ROI presentation | PM, BA |
| S-014: IT Support | Supportive | Neutral | Gap | Prepare for handover | Training, documentation, support handover | PM, DevOps |
| S-015: Tim Proyek | Supportive | Supportive | None | Recognition, career development | 1-on-1, team building, performance review | PM, HR |
| S-019: IoT Consultant | Supportive | Supportive | None | Clear scope, regular review | Weekly progress check, milestone review | PM, IoT Lead |
| S-020: Sim Consultant | Supportive | Supportive | None | Clear scope, regular review | Weekly progress check, milestone review | PM, Sim Lead |
| S-023: Internal Audit | Informed | Neutral | Gap | Provide transparency | Monthly audit report | PM |

## 11.6. MANAGE STAKEHOLDER ENGAGEMENT (PMI-49)

### 11.6.1. Tujuan

Mengelola keterlibatan stakeholder sesuai dengan rencana yang telah disusun.

### 11.6.2. Stakeholder Engagement Activities

| Aktivitas | Deskripsi | Frekuensi | Responsible |
| --- | --- | --- | --- |
| Stakeholder Meeting | Meeting dengan stakeholder kunci | Sesuai jadwal | PM |
| Sprint Review | Demo deliverable ke stakeholder | 2 minggu | PM, BA |
| UAT Workshop | Testing dan feedback dari end users | UAT Phase | BA, QA |
| Monthly Executive Report | Laporan status ke sponsor dan steering committee | Bulanan | PM |
| Stakeholder Survey | Survey kepuasan stakeholder | Bulanan | PM, BA |
| Issue Resolution | Menyelesaikan issue yang diangkat stakeholder | Sesuai kebutuhan | PM, Leads |
| Training Session | Training untuk end users dan admin | UAT Phase | BA, Tech Leads |
| Knowledge Transfer | Transfer knowledge ke tim IT support | Minggu 19-20 | PM, DevOps, Leads |

### 11.6.3. Stakeholder Satisfaction Survey

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    STAKEHOLDER SATISFACTION SURVEY                          │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Respondent: [Name]                                                         │

│  Role: [Role]                                                               │

│  Date: [DD/MM/YYYY]                                                         │

│                                                                             │

│  Please rate the following on a scale of 1-5 (1 = Very Dissatisfied,        │

│  5 = Very Satisfied):                                                       │

│                                                                             │

│  A. COMMUNICATION                                                           │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ 1. Frequency of updates                                          │ [ ] │   │

│  │ 2. Clarity of information                                        │ [ ] │   │

│  │ 3. Relevance of information                                      │ [ ] │   │

│  │ 4. Timeliness of communication                                  │ [ ] │   │

│  │ 5. Quality of project documentation                              │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  B. ENGAGEMENT                                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ 6. My input is valued                                              │ [ ] │   │

│  │ 7. I am involved at the right level                               │ [ ] │   │

│  │ 8. My concerns are addressed                                      │ [ ] │   │

│  │ 9. The project team is responsive                                 │ [ ] │   │

│  │ 10. I feel informed about progress                                │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  C. SATISFACTION                                                            │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ 11. Overall satisfaction with project communication               │ [ ] │   │

│  │ 12. Overall satisfaction with project management                  │ [ ] │   │

│  │ 13. Confidence in project success                                 │ [ ] │   │

│  │ 14. Likelihood to support future projects                         │ [ ] │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  D. OPEN FEEDBACK                                                           │

│  ───────────────────────────────────────────────────────────────────────── │

│  What is working well?                                                     │

│  [Open text]                                                                │

│                                                                             │

│  What needs improvement?                                                    │

│  [Open text]                                                                │

│                                                                             │

│  Any other comments?                                                        │

│  [Open text]                                                                │

│                                                                             │

│  Submitted By: _______________  Date: _______________                    │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 11.6.4. Issue Log Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                           ISSUE LOG                                         │

│                  P-FNE-08: Advanced & Autonomous Enterprise                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Issue ID: [XXX]                                                            │

│  Date Identified: [DD/MM/YYYY]                                              │

│  Identified By: [Name]                                                      │

│  Stakeholder: [Name]                                                        │

│                                                                             │

│  ISSUE DESCRIPTION                                                          │

│  ───────────────────────────────────────────────────────────────────────── │

│  [Detailed description of the issue]                                        │

│                                                                             │

│  IMPACT                                                                    │

│  ───────────────────────────────────────────────────────────────────────── │

│  Severity: [Critical / Major / Minor / Trivial]                            │

│  Impact: [Schedule / Cost / Quality / Scope / Reputation]                  │

│  Description: [Impact description]                                         │

│                                                                             │

│  RESOLUTION                                                                 │

│  ───────────────────────────────────────────────────────────────────────── │

│  Owner: [Name]                                                              │

│  Action: [Description of action]                                            │

│  Target Date: [DD/MM/YYYY]                                                  │

│  Status: [Open / In Progress / Resolved / Closed]                          │

│                                                                             │

│  RESOLUTION DETAIL                                                          │

│  ───────────────────────────────────────────────────────────────────────── │

│  Resolved By: [Name]                                                        │

│  Resolved Date: [DD/MM/YYYY]                                                │

│  Resolution: [Description]                                                  │

│  Lessons Learned: [Description]                                             │

│                                                                             │

│  APPROVAL                                                                   │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ Role                │ Name      │ Signature │ Date                     │

│  │---------------------│-----------│-----------│--------------------------│

│  │ Project Manager     │           │           │                          │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 11.7. MONITOR STAKEHOLDER ENGAGEMENT (PMI-50)

### 11.7.1. Tujuan

Memantau efektivitas keterlibatan stakeholder dan melakukan penyesuaian jika diperlukan.

### 11.7.2. Stakeholder Monitoring Activities

| Aktivitas | Frekuensi | Responsible | Deskripsi |
| --- | --- | --- | --- |
| Stakeholder Engagement Review | Bulanan | PM + BA | Review engagement level dan satisfaction |
| Stakeholder Survey | Bulanan | PM + BA | Survey kepuasan stakeholder |
| Engagement Status Update | Bulanan | PM | Update engagement status di stakeholder register |
| Issue Tracking | Kontinu | PM + Leads | Tracking issue yang diangkat stakeholder |
| Communication Effectiveness | Bulanan | PM + BA | Monitor efektivitas komunikasi |

### 11.7.3. Stakeholder Engagement Monitoring Dashboard

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                   STAKEHOLDER ENGAGEMENT MONITORING DASHBOARD              │

│                   P-FNE-08: Advanced & Autonomous Enterprise               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Stakeholder Engagement Status                                              │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ Stakeholder       │ Desired  │ Actual   │ Gap   │ Action           │   │

│  │-------------------│----------│----------│-------│------------------│   │

│  │ S-001: Sponsor    │ Support  │ Support  │ None  │ Continue         │   │

│  │ S-002: Steering   │ Support  │ Support  │ None  │ Continue         │   │

│  │ S-003: PO         │ Support  │ Support  │ None  │ Continue         │   │

│  │ S-004: P-FNE-01   │ Support  │ Neutral  │ Gap   │ Increase sync    │   │

│  │ S-005: P-FNE-02   │ Support  │ Neutral  │ Gap   │ Increase sync    │   │

│  │ S-010: P-FNE-07   │ Support  │ Neutral  │ Gap   │ Increase sync    │   │

│  │ S-011: Farm Ops   │ Support  │ Neutral  │ Gap   │ UAT workshop    │   │

│  │ S-013: Management │ Support  │ Neutral  │ Gap   │ Demo session    │   │

│  │ S-014: IT Support │ Support  │ Neutral  │ Gap   │ Training start  │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  Stakeholder Satisfaction Trends                                            │

│  ───────────────────────────────────────────────────────────────────────── │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │                                                                     │   │

│  │ 5.0 ──┐                                                             │   │

│  │ 4.5 ──┤        ╱─────╲                                              │   │

│  │ 4.0 ──┤   ╱──╱       ╲──╲                                           │   │

│  │ 3.5 ──┤──╱              ╲──                                         │   │

│  │ 3.0 ──┤                                                             │   │

│  │      └──┬────┬────┬────┬────┬────┬────┐                             │   │

│  │        M1   M2   M3   M4   M5   M6                                  │   │

│  │                                                                     │   │

│  │  Legend: ─── Overall Satisfaction                                    │   │

│  │  ─── Communication Satisfaction                                   │   │

│  │  ─── Engagement Satisfaction                                      │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  Open Stakeholder Issues                                                    │

│  ───────────────────────────────────────────────────────────────────────── │

│  │ ID │ Issue               │ Stakeholder │ Severity │ Status            │

│  │----│---------------------│-------------│----------│-------------------│

│  │ I1 │ Integration concern │ P-FNE-01    │ Medium   │ In Progress       │

│  │ I2 │ UI/UX feedback      │ Farm Ops    │ Minor    │ Open              │

│  │ I3 │ Training readiness  │ IT Support  │ Medium   │ In Progress       │

│  └─────────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  Report Date: [DD/MM/YYYY]                                                  │

│  Prepared By: [PM Name]                                                     │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

## 11.8. STAKEHOLDER MANAGEMENT MATRIX

| Proses | Input Utama | Tools | Output Utama | Owner |
| --- | --- | --- | --- | --- |
| Identify Stakeholders | Project Charter, EEF | Expert Judgment, Stakeholder Analysis | Stakeholder Register | PM, BA |
| Plan Stakeholder Engagement | Stakeholder Register | Power/Interest Grid, Expert Judgment | Stakeholder Engagement Plan | PM, BA |
| Manage Stakeholder Engagement | Stakeholder Engagement Plan | Communication, Issue Management | Stakeholder Updates, Issue Log | PM, BA |
| Monitor Stakeholder Engagement | Stakeholder Engagement Plan | Surveys, Performance Reviews | Stakeholder Engagement Status | PM, BA |

## 11.9. RINGKASAN MANAJEMEN PEMANGKU KEPENTINGAN

| Aspek | Rincian |
| --- | --- |
| Total Stakeholders | 24 stakeholder |
| Internal Stakeholders | 16 stakeholder |
| External Stakeholders | 8 stakeholder |
| Highest Priority | S-001 (Sponsor), S-002 (Steering Committee) |
| High Priority | S-003 (PO), S-004 (P-FNE-01), S-005 (P-FNE-02), S-010 (P-FNE-07), S-013 (Management), S-015 (Tim Proyek) |
| Engagement Strategy | Tailored per stakeholder, Manage Closely → Keep Informed → Keep Satisfied → Monitor |
| Communication | Melalui Communications Management Plan |
| Feedback Mechanism | Survey, Meeting feedback, UAT feedback |
| Issue Resolution | Escalation process, issue log |
| Satisfaction Target | ≥ 4/5 on stakeholder satisfaction survey |
| Monitoring | Bulanan engagement review, bulanan satisfaction survey |

## 11.10. STAKEHOLDER ENGAGEMENT STRATEGY SUMMARY

| Stakeholder Group | Primary Needs | Engagement Strategy | Key Actions |
| --- | --- | --- | --- |
| Sponsor & Steering Committee | Strategic alignment, ROI, risk mitigation | Manage Closely | Monthly executive reports, milestone celebrations, strategic decisions |
| Product Owner | Feature delivery, user satisfaction | Manage Closely | Weekly backlog grooming, sprint review, feature demos |
| FNE Core Teams (P-FNE-01 to P-FNE-07) | Integration clarity, data flow | Keep Informed → Collaborative | Weekly sync, integration demos, API workshops |
| End Users (Ops, Supply Chain, Management) | Usability, functionality, productivity | Keep Informed → Supportive | UAT workshops, training sessions, feedback collection |
| Tim Proyek | Clear direction, resources, recognition | Manage Closely | Daily standup, 1-on-1, team building, performance reviews |
| IT Support | Handover readiness, operational knowledge | Keep Informed → Supportive | Training, documentation, support handover |
| Vendors & Consultants | Clear scope, timely payment | Monitor → Supportive | Regular progress check, milestone reviews |
| Internal Audit | Compliance, transparency | Keep Satisfied | Monthly audit reports, compliance reviews |
| Regulator | Compliance | Keep Satisfied | Regulatory check, compliance documentation |

## AKHIR BAB 11

BAB 11: MANAJEMEN PEMANGKU KEPENTINGAN PROYEK telah selesai.

## BAB 12: LAMPIRAN

### 12.1. DAFTAR LAMPIRAN

| Lampiran | Deskripsi |
| --- | --- |
| A | Project Charter - P-FNE-08 |
| B | WBS Dictionary (Complete) |
| C | Detailed Activity List |
| D | Detailed Gantt Chart (MS Project / Smartsheet) |
| E | Detailed Budget Breakdown (Activity Based Costing) |
| F | Quality Checklist & Test Plan |
| G | Risk Register (Complete) |
| H | Communication Matrix (Detail) |
| I | Stakeholder Register (Complete) |
| J | Acceptance Criteria Checklist |
| K | Lesson Learned Template |
| L | Vendor Contract Templates |
| M | Stakeholder Engagement Plan (Detail) |
| N | Training Materials Outline |
| O | Deployment Plan |

### 12.2. PERSETUJUAN DOKUMEN

| Peran | Nama | Tanda Tangan | Tanggal | Versi |
| --- | --- | --- | --- | --- |
| Project Manager | [Nama PM] |  |  | 1.0 |
| Project Sponsor | [Nama Sponsor] |  |  | 1.0 |
| Product Owner | [Nama PO] |  |  | 1.0 |
| Lead Teknis | [Nama Lead] |  |  | 1.0 |
| QA Lead | [Nama QA] |  |  | 1.0 |

## RINGKASAN EKSEKUTIF PROJECT MANAGEMENT PLAN

### Project Management Plan - P-FNE-08: Advanced & Autonomous Enterprise

| Area Manajemen | Pendekatan Utama | Tools/Metode | Target |
| --- | --- | --- | --- |
| Integrasi | CCB, PMIS Terintegrasi | Jira, Confluence, GitHub | 100% deliverable |
| Lingkup | WBS 7 Level, Scope Statement | User Stories, MoSCoW | ≥ 90% scope completion |
| Penjadwalan | Sprint 2 minggu, Buffer 15% | Gantt Chart, EVM | SPI ≥ 0.95 |
| Biaya | Activity Based Costing, Inkindo 2026 | EVM, Variance Analysis | CPI ≥ 0.95 |
| Mutu | ISO 9001, ISO/IEC 25010 | SonarQube, JMeter, UAT | Coverage ≥ 80%, 0 critical vuln |
| Sumber Daya | 12-14 Tim, Cross-training | Jira Resource Planning | Utilization 80-100% |
| Komunikasi | Matriks Komunikasi, Daily Standup | Slack, Zoom, Jira | Satisfaction ≥ 4/5 |
| Risiko | 31 risiko, 4 critical | Risk Register, Monte Carlo | EMV top 5: Rp 490M |
| Pengadaan | 11 items, Rp 970M | RFP, Vendor Evaluation | All delivered on time |
| Stakeholder | 24 stakeholder, Power/Interest | Stakeholder Register | Satisfaction ≥ 4/5 |

## AKHIR PROJECT MANAGEMENT PLAN

SELURUH DOKUMEN PROJECT MANAGEMENT PLAN (PMP) UNTUK PROYEK P-FNE-08: ADVANCED & AUTONOMOUS ENTERPRISE TELAH SELESAI.

Dokumen ini mencakup 11 bab sesuai dengan 10 area manajemen pengetahuan PMBOK (Integrasi, Lingkup, Penjadwalan, Biaya, Mutu, Sumber Daya, Komunikasi, Risiko, Pengadaan, dan Pemangku Kepentingan) serta 12 lampiran pendukung.

Proyek P-FNE-08 memiliki:

- Anggaran: Rp 2.900.000.000

- Durasi: 20 minggu

- Tim: 12-14 orang

- Milestone: 8 milestone

- Risiko: 31 risiko teridentifikasi

- Stakeholder: 24 stakeholder