# PROJECT MANAGEMENT PLAN (PMP)

## Proyek P-FNE-05: Commerce, Sales & Logistics

### Super ERP Farm Nation Enterprise (FNE)

| Dokumen | Project Management Plan (PMP) |
| --- | --- |
| Proyek | P-FNE-05: Commerce, Sales & Logistics |
| Versi | 1.0 |
| Tanggal | 9 September 2026 |
| Status | Final |
| Disusun Oleh | Project Manager |
| Disetujui Oleh | Project Sponsor |

## BAB 1: PENDAHULUAN

### 1.1 Tujuan Dokumen

Dokumen Project Management Plan (PMP) ini disusun untuk memberikan panduan komprehensif dalam pengelolaan Proyek P-FNE-05: Commerce, Sales & Logistics. Dokumen ini berfungsi sebagai:

- Pedoman Utama bagi seluruh tim proyek dalam melaksanakan pekerjaan

- Acuan Komunikasi antar stakeholder mengenai pendekatan dan metodologi proyek

- Alat Kontrol untuk memonitor dan mengendalikan pelaksanaan proyek

- Dasar Evaluasi untuk mengukur keberhasilan proyek

### 1.2 Deskripsi Proyek

Proyek P-FNE-05 merupakan bagian integral dari Super ERP Farm Nation Enterprise (FNE) yang bertujuan untuk membangun sistem Commerce, Sales & Logistics yang terintegrasi dan canggih. Proyek ini menjadi jembatan antara produksi (P-FNE-04) dan pelanggan, memastikan produk sampai ke tangan pembeli dengan efisien dan memberikan pengalaman pelanggan yang memuaskan.

#### 1.2.1 Latar Belakang

Farm Nation Enterprise (FNE) adalah perusahaan agribisnis terintegrasi yang bergerak di bidang pertanian, peternakan, dan pengolahan hasil pertanian. Saat ini, FNE menghadapi tantangan dalam mengelola rantai nilai dari hulu ke hilir, terutama pada aspek komersialisasi produk. Sistem yang ada masih terpisah-pisah dan tidak terintegrasi, menyebabkan:

- Proses penjualan yang manual dan tidak efisien

- Kesulitan dalam melacak dan mengelola hubungan pelanggan

- Marketplace yang belum terdigitalisasi dengan baik

- Logistik dan pengiriman yang sulit dimonitor secara real-time

- Portal pelanggan dan pemasok yang belum tersedia

Oleh karena itu, diperlukan sistem Commerce, Sales & Logistics yang terintegrasi untuk menjawab tantangan tersebut.

#### 1.2.2 Visi Proyek

Menjadi sistem Commerce, Sales & Logistics yang andal, cerdas, dan terintegrasi yang mendukung pertumbuhan bisnis FNE dan memberikan pengalaman pelanggan terbaik di industri agribisnis.

#### 1.2.3 Misi Proyek

- Mengembangkan sistem penjualan yang efisien dan terintegrasi

- Membangun Customer Relationship Management (CRM) yang komprehensif

- Menyediakan marketplace digital yang modern dan mudah digunakan

- Mengelola logistik dan distribusi secara real-time

- Menyediakan portal self-service untuk pelanggan dan pemasok

#### 1.2.4 Komponen Proyek

Proyek ini mencakup pengembangan 5 domain utama:

| Modul | Deskripsi | Fitur Utama |
| --- | --- | --- |
| Sales Management | Manajemen siklus penjualan dari order hingga pembayaran | Sales Order, Invoice, Payment, Return, Credit Note |
| CRM | Manajemen hubungan pelanggan dan interaksi | Customer Master, Interaction, Complaint, 360 View |
| Marketplace | Platform penjualan produk secara digital | Product Listing, Catalog, Cart, Checkout, Review |
| Logistics | Manajemen pengiriman dan distribusi | Shipment, Tracking, POD, Carrier Management |
| Portal | Portal self-service untuk customer dan supplier | Customer Portal, Supplier Portal, Security |

### 1.3 Tujuan Proyek

Tujuan proyek P-FNE-05 dirumuskan dengan pendekatan SMART (Specific, Measurable, Achievable, Relevant, Time-bound):

| No | Tujuan | Indikator Keberhasilan (Metrik) | Target |
| --- | --- | --- | --- |
| 1 | Mengelola siklus penjualan dari pesanan hingga pembayaran | Sales Order creation time | ≤ 2 detik |
| 2 | Membangun dan memelihara hubungan dengan pelanggan | Customer 360 view availability | Real-time, 100% data akurat |
| 3 | Menyediakan marketplace digital untuk menjual produk | Marketplace page load time | ≤ 3 detik |
| 4 | Mengelola logistik dan distribusi produk secara efisien | Checkout processing time | ≤ 5 detik |
| 5 | Menyediakan portal untuk pelanggan dan pemasok | Portal availability | ≥ 99.5% |
| 6 | Memastikan keamanan sistem dan data | Security compliance | Zero critical vulnerability |
| 7 | Mencapai adopsi pengguna | User satisfaction | ≥ 4.5/5 |
| 8 | Menyelesaikan proyek tepat waktu | Project completion | ≤ 5 bulan |
| 9 | Menyelesaikan proyek sesuai anggaran | Budget variance | ≤ 10% |

### 1.4 Ruang Lingkup Proyek

#### 1.4.1 Termasuk (In-Scope)

A. Pengembangan Modul:

- Sales Management Module

  - Sales Order Creation, Validation, Confirmation

  - Sales Order Status Tracking

  - Invoice Generation

  - Payment Recording

  - Sales Return & Credit Note

- Customer Relationship Management (CRM)

  - Customer Registration & Management

  - Customer Contact Management

  - Customer Interaction Logging

  - Customer Complaint Management

  - Customer 360 View

- Marketplace Module

  - Product Listing & Catalog

  - Product Search & Filter (Elasticsearch)

  - Shopping Cart & Checkout

  - Product Review & Rating

  - Promotion Management

- Logistics Module

  - Shipment Creation & Management

  - Picking List, Packing List, Delivery Note

  - Tracking & Proof of Delivery (POD)

  - Carrier Management

  - Logistics Dashboard

- Portal Module

  - Customer Portal (Login, Order History, Tracking, Complaint)

  - Supplier Portal (Login, PO View, PO Confirmation, Invoice)

  - Portal Security (MFA, Session Management)

B. Pengembangan Front-End:

- Web Admin Portal (React/Next.js)

- Customer Portal (React)

- Supplier Portal (React)

- Mobile App for Field Workers (Flutter/React Native)

- Executive Dashboard

C. Pengembangan Back-End:

- Sales Service (Spring Boot)

- CRM Service (Node.js/NestJS)

- Marketplace Service (Python/FastAPI)

- Logistics Service (Spring Boot)

- Portal Service (Node.js/NestJS)

D. Integrasi:

- P-FNE-01 (Foundation): IAM, Master Data, Notification, Workflow

- P-FNE-03 (Supply Chain): Inventory, Procurement

- P-FNE-04 (Production): Product Availability

- P-FNE-06 (Finance): Sales to Finance

- Payment Gateway (Midtrans/Xendit)

- Carrier APIs (JNE, SiCepat, J&T)

E. Infrastruktur:

- API Gateway (Kong/Traefik)

- Event Bus (Apache Kafka)

- Database (PostgreSQL, Redis, Elasticsearch)

- Container Orchestration (Kubernetes)

#### 1.4.2 Tidak Termasuk (Out-of-Scope)

| No | Item | Alasan |
| --- | --- | --- |
| 1 | Pengembangan modul lain di luar P-FNE-05 | Dilakukan oleh tim proyek lain |
| 2 | Infrastruktur cloud provisioning | Disediakan oleh tim DevOps terpusat |
| 3 | UI/UX design final approval | Disetujui terpisah sebelum pengembangan |
| 4 | End-user training | Dilakukan setelah UAT oleh tim training |
| 5 | Data migration dari sistem lama | Dilakukan oleh tim data migration |
| 6 | Hardware procurement | Dilakukan oleh tim IT infrastruktur |
| 7 | Maintenance dan support setelah go-live | Dilakukan oleh tim operasional |
| 8 | Customization untuk customer spesifik | Dilakukan sebagai proyek terpisah |

#### 1.4.3 Batasan (Constraints)

| No | Batasan | Deskripsi |
| --- | --- | --- |
| 1 | Waktu | Proyek harus selesai dalam 5 bulan (22 minggu) |
| 2 | Anggaran | Anggaran maksimal Rp 4.500.000.000 |
| 3 | Sumber Daya | Tim maksimal 12 orang |
| 4 | Teknologi | Harus menggunakan tech stack yang telah ditentukan |
| 5 | Regulasi | Harus memenuhi regulasi keamanan data (PCI DSS) |
| 6 | Interdependensi | Bergantung pada penyelesaian P-FNE-01,03,04 |

#### 1.4.4 Asumsi (Assumptions)

| No | Asumsi | Deskripsi |
| --- | --- | --- |
| 1 | Ketersediaan SDM | Tim yang dibutuhkan tersedia dan dapat direkrut tepat waktu |
| 2 | Ketersediaan Infrastruktur | Infrastruktur cloud tersedia dari minggu ke-1 |
| 3 | Kerjasama Tim Lain | Tim P-FNE-01,03,04,06 siap berkolaborasi |
| 4 | Kebutuhan Stabil | Requirements tidak berubah signifikan selama pengembangan |
| 5 | Akses Vendor | Vendor payment gateway dan carrier menyediakan akses API |
| 6 | Dukungan Manajemen | Manajemen memberikan dukungan penuh |

### 1.5 Stakeholder Kunci

#### 1.5.1 Daftar Stakeholder

| No | Stakeholder | Peran | Tanggung Jawab | Keterlibatan |
| --- | --- | --- | --- | --- |
| 1 | CEO FNE | Project Sponsor | Menyetujui anggaran, keputusan strategis, final approval | Steering |
| 2 | CFO FNE | Finance Approver | Menyetujui budget, monitoring biaya | Steering |
| 3 | CIO FNE | Technical Exec | Mengarahkan arsitektur enterprise, resource IT | Steering |
| 4 | Director of Sales | Domain Expert | Menyediakan kebutuhan bisnis sales | Consulted |
| 5 | Director of Operations | Domain Expert | Menyediakan kebutuhan bisnis logistik | Consulted |
| 6 | Project Manager | PM | Mengelola keseluruhan proyek | Leading |
| 7 | Product Owner | PO | Menentukan prioritas fitur, validasi requirement | Leading |
| 8 | Tech Lead | Technical Lead | Mengarahkan arsitektur teknis, code quality | Leading |
| 9 | Lead Developer (Backend) | Backend Lead | Memimpin tim backend | Participating |
| 10 | Lead Developer (Frontend) | Frontend Lead | Memimpin tim frontend | Participating |
| 11 | QA Lead | Lead Pengujian | Mengelola strategi pengujian | Participating |
| 12 | Business Analyst | BA | Menjembatani kebutuhan bisnis dan teknis | Participating |
| 13 | UX Designer | Designer | Merancang antarmuka pengguna | Participating |
| 14 | DevOps Engineer | DevOps | Mengelola infrastructure dan CI/CD | Consulted |
| 15 | Development Team (8-10) | Developer | Mengimplementasikan fitur | Participating |
| 16 | End Users | Pengguna Akhir | Memberikan feedback, UAT | Informed |
| 17 | External Vendors | Vendor | Payment gateway, carrier API | Informed |

#### 1.5.2 Stakeholder Power-Interest Grid

text

Power │

│

High  │  CEO FNE, CFO FNE   │  PM, PO, Tech Lead

│  CIO FNE            │  Director of Sales, Ops

│                     │

│                     │

Low   │  End Users          │  Dev Team, QA Team

│  External Vendors   │  UX Designer, BA

│                     │

└─────────────────────┴─────────────────────

Low Interest         High Interest

### 1.6 Metodologi Proyek

Proyek ini akan menggunakan metodologi Agile-Scrum dengan pendekatan hybrid:

#### 1.6.1 Framework Scrum

| Elemen | Deskripsi |
| --- | --- |
| Sprint Duration | 2 minggu (10 hari kerja) |
| Sprint Planning | Setiap awal sprint (2-4 jam) |
| Daily Stand-up | Setiap hari (15 menit) |
| Sprint Review | Setiap akhir sprint (1-2 jam) |
| Sprint Retrospective | Setelah sprint review (1 jam) |
| Backlog Grooming | Setiap sprint (1 jam) |
| Release Planning | Setiap 4 sprint (1 hari) |

#### 1.6.2 Fase Proyek

| Fase | Durasi | Aktivitas |
| --- | --- | --- |
| Initiation | 1 minggu | Project charter, PMP, team onboarding |
| Requirements & Design | 3 minggu | Requirements gathering, UX/UI design, technical design |
| Development Sprints | 14 minggu | 7 sprints × 2 minggu |
| Integration & Testing | 3 minggu | System integration, performance testing, security testing |
| UAT & Deployment | 2 minggu | UAT, bug fixing, production deployment |
| Closure | 1 minggu | Documentation, handover, lessons learned |

#### 1.6.3 Sprint Structure

text

┌─────────────────────────────────────────────────────────────────────┐

│                         SPRINT STRUCTURE                           │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  Sprint Planning (2-4 jam)                                         │

│  ├── Review backlog priorities                                     │

│  ├── Select sprint backlog items                                   │

│  └── Estimate and commit to sprint goal                           │

│                                                                     │

│  Daily Stand-up (15 menit)                                         │

│  ├── What did I do yesterday?                                      │

│  ├── What will I do today?                                         │

│  └── Any impediments?                                              │

│                                                                     │

│  Development Work (9 hari)                                         │

│  ├── Coding                                                        │

│  ├── Code Review                                                   │

│  ├── Testing                                                       │

│  └── Integration                                                   │

│                                                                     │

│  Sprint Review (1-2 jam)                                           │

│  ├── Demo completed features                                       │

│  ├── Stakeholder feedback                                          │

│  └── Update backlog                                                │

│                                                                     │

│  Sprint Retrospective (1 jam)                                      │

│  ├── What went well?                                               │

│  ├── What could be improved?                                       │

│  └── Action items for next sprint                                  │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

### 1.7 Tools dan Teknologi

#### 1.7.1 Project Management Tools

| Tool | Fungsi |
| --- | --- |
| JIRA | Sprint planning, task tracking, bug tracking |
| Confluence | Dokumentasi proyek, knowledge base |
| Google Workspace | Email, calendar, documents, presentations |
| Slack | Komunikasi tim, notifikasi |
| Zoom/Google Meet | Meeting virtual |
| Miro | Retrospective, brainstorming, diagram |

#### 1.7.2 Development Tools

| Tool | Fungsi |
| --- | --- |
| GitLab | Version control, CI/CD |
| Docker | Containerization |
| Kubernetes | Orchestration |
| SonarQube | Code quality analysis |
| Postman | API testing |
| Swagger | API documentation |
| Figma | UI/UX design |
| JIRA | Issue tracking, sprint management |

#### 1.7.3 Monitoring Tools

| Tool | Fungsi |
| --- | --- |
| Prometheus | Metrics collection |
| Grafana | Monitoring dashboard |
| ELK Stack | Logging |
| Jaeger | Distributed tracing |
| Sentry | Error tracking |

### 1.8 Daftar Istilah (Glossary)

| Istilah | Definisi |
| --- | --- |
| P-FNE-05 | Kode proyek Commerce, Sales & Logistics |
| Sales Order (SO) | Dokumen pesanan penjualan |
| Customer Relationship Management (CRM) | Sistem manajemen hubungan pelanggan |
| Invoice | Faktur tagihan kepada pelanggan |
| Credit Note | Nota kredit untuk retur penjualan |
| Proof of Delivery (POD) | Bukti pengiriman barang |
| Shipment | Pengiriman barang |
| Carrier | Perusahaan jasa pengiriman/kurir |
| API | Application Programming Interface |
| Microservices | Arsitektur layanan mikro |
| Event-Driven | Arsitektur berbasis event |
| Kafka | Platform event streaming |
| Elasticsearch | Search engine untuk product catalog |
| Redis | In-memory cache |
| PostgreSQL | Relational database |
| UAT | User Acceptance Testing |
| SLA | Service Level Agreement |
| MFA | Multi-Factor Authentication |
| SSO | Single Sign-On |
| RBAC | Role-Based Access Control |

## BAB 2: MANAJEMEN INTEGRASI PROYEK

### 2.1 Tujuan Manajemen Integrasi

Manajemen Integrasi Proyek bertujuan untuk memastikan koordinasi yang efektif antar seluruh komponen proyek dan mengintegrasikan semua proses manajemen proyek menjadi satu kesatuan yang kohesif. Tujuan spesifiknya adalah:

- Menyelaraskan seluruh elemen proyek (ruang lingkup, jadwal, biaya, kualitas, risiko, dll.)

- Memastikan kesinambungan dan konsistensi antar fase proyek

- Mengkoordinasikan aktivitas antar tim dan stakeholder

- Mengelola perubahan secara terkendali

- Menjamin bahwa deliverables proyek memenuhi ekspektasi stakeholder

### 2.2 Proses Manajemen Integrasi

Manajemen Integrasi Proyek terdiri dari 6 (enam) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Develop Project Charter | Membuat dokumen otorisasi proyek | Minggu 1 |
| 2 | Develop Project Management Plan | Menyusun PMP terintegrasi | Minggu 1-2 |
| 3 | Direct and Manage Project Work | Mengarahkan dan mengelola pekerjaan proyek | Minggu 3-20 |
| 4 | Monitor and Control Project Work | Memonitor dan mengendalikan pekerjaan proyek | Minggu 3-21 |
| 5 | Perform Integrated Change Control | Mengelola perubahan secara terintegrasi | Berkelanjutan |
| 6 | Close Project or Phase | Menutup proyek atau fase | Minggu 22 |

### 2.3 Develop Project Charter

#### 2.3.1 Deskripsi Proses

Proses ini menghasilkan Project Charter yang merupakan dokumen otorisasi formal proyek. Project Charter memberikan wewenang kepada Project Manager untuk mengalokasikan sumber daya organisasi ke dalam aktivitas proyek.

#### 2.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Business Case | Project Sponsor, CEO FNE |
| 2 | Benefits Management Plan | Project Sponsor, CFO FNE |
| 3 | Agreement/Contract | Legal Department |
| 4 | Enterprise Environmental Factors | Organisasi |
| 5 | Organizational Process Assets | Organisasi |

#### 2.3.3 Output

Project Charter P-FNE-05

| Elemen | Isi |
| --- | --- |
| Nama Proyek | P-FNE-05: Commerce, Sales & Logistics |
| Project Sponsor | CEO Farm Nation Enterprise |
| Project Manager | [Nama PM] |
| Business Need | FNE membutuhkan sistem commerce, sales & logistics terintegrasi untuk mengelola rantai nilai dari hulu ke hilir secara efisien |
| Project Description | Pengembangan modul Sales Management, CRM, Marketplace, Logistics, dan Portal sebagai bagian dari Super ERP FNE |
| Key Deliverables | 5 modul aplikasi, 5 microservices, 3 portal (Admin, Customer, Supplier), mobile app, API Gateway, Event Bus, integrasi dengan 4 modul lain |
| High-Level Requirements | 19 functional requirements (Sales), 14 (CRM), 16 (Marketplace), 15 (Logistics), 17 (Portal), 12 non-functional requirements |
| Project Objectives | 9 objectives dengan metrik SMART |
| Success Criteria | Acceptance criteria terpenuhi, UAT ≥ 4.5/5, go-live ≤ 5 bulan |
| Key Stakeholders | CEO, CFO, CIO, Director of Sales, Director of Operations, PM, PO, Tech Lead, Dev Team, QA Team, End Users |
| Project Budget | Rp 4.500.000.000 (maksimum) |
| Project Timeline | 22 minggu (5 bulan) |
| Constraints | Waktu 5 bulan, anggaran Rp 4.5M, sumber daya 12 orang |
| Assumptions | SDM tersedia, infrastruktur siap, kerjasama tim lain, requirements stabil |
| Risks | 12 risiko utama dengan mitigasi |
| Approval | [Tanda tangan Project Sponsor] |

#### 2.3.4 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Sponsor | Menyetujui dan menandatangani Project Charter |
| Project Manager | Menyusun draf Project Charter |
| Product Owner | Memberikan input kebutuhan bisnis |
| Tech Lead | Memberikan input kelayakan teknis |

#### 2.3.5 Timeline

| Aktivitas | Durasi | Minggu |
| --- | --- | --- |
| Penyusunan draft Project Charter | 2 hari | M1 |
| Review oleh Sponsor | 2 hari | M1 |
| Finalisasi dan penandatanganan | 1 hari | M1 |

### 2.4 Develop Project Management Plan

#### 2.4.1 Deskripsi Proses

Proses ini menghasilkan Project Management Plan (PMP) yang terintegrasi, yang mendefinisikan bagaimana proyek akan dijalankan, dimonitor, dan dikendalikan. PMP mengintegrasikan seluruh rencana manajemen dari 10 area pengetahuan PMBOK.

#### 2.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Output dari proses perencanaan lain | Tim Proyek |
| 3 | Enterprise Environmental Factors | Organisasi |
| 4 | Organizational Process Assets | Organisasi |

#### 2.4.3 Output

Project Management Plan (PMP) - Komponen

| Komponen | Deskripsi | Status |
| --- | --- | --- |
| Scope Management Plan | Bagaimana ruang lingkup akan didefinisikan, divalidasi, dan dikendalikan | ✓ |
| Requirements Management Plan | Bagaimana requirements akan dikelola dan dilacak | ✓ |
| Schedule Management Plan | Bagaimana jadwal akan dikembangkan dan dikendalikan | ✓ |
| Cost Management Plan | Bagaimana biaya akan direncanakan dan dikendalikan | ✓ |
| Quality Management Plan | Bagaimana kualitas akan dijamin dan dikendalikan | ✓ |
| Resource Management Plan | Bagaimana sumber daya akan diakuisisi dan dikelola | ✓ |
| Communications Management Plan | Bagaimana komunikasi akan dikelola | ✓ |
| Risk Management Plan | Bagaimana risiko akan diidentifikasi dan dikelola | ✓ |
| Procurement Management Plan | Bagaimana pengadaan akan dikelola | ✓ |
| Stakeholder Engagement Plan | Bagaimana stakeholder akan dikelola | ✓ |
| Scope Baseline | WBS, WBS Dictionary, Project Scope Statement | ✓ |
| Schedule Baseline | Jadwal proyek yang disetujui | ✓ |
| Cost Baseline | Anggaran yang disetujui | ✓ |
| Performance Measurement Baseline | Cara mengukur kinerja proyek | ✓ |

#### 2.4.4 Metodologi Pengembangan

Proyek ini menggunakan metodologi Agile-Scrum dengan pendekatan hybrid:

| Elemen | Detail |
| --- | --- |
| Framework | Scrum |
| Sprint Duration | 2 minggu |
| Release Cadence | Setiap 4 sprint (2 bulan) |
| Estimation | Story Points (Fibonacci: 1,2,3,5,8,13,21) |
| Prioritization | MoSCoW (Must, Should, Could, Won't) |
| Quality Approach | TDD (Test-Driven Development), Code Review, CI/CD |
| Change Management | Formal Change Request Process |

#### 2.4.5 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Memimpin penyusunan PMP, mengintegrasikan semua komponen |
| Tech Lead | Memberikan input teknis untuk rencana |
| Product Owner | Memberikan input prioritas dan kebutuhan bisnis |
| QA Lead | Memberikan input untuk quality management |
| Tim | Memberikan input untuk estimasi dan aktivitas |

#### 2.4.6 Timeline

| Aktivitas | Durasi | Minggu |
| --- | --- | --- |
| Penyusunan draft PMP | 1 minggu | M1 |
| Review dan input tim | 3 hari | M2 |
| Finalisasi dan approval | 2 hari | M2 |

### 2.5 Direct and Manage Project Work

#### 2.5.1 Deskripsi Proses

Proses ini bertujuan untuk mengarahkan dan mengelola pelaksanaan pekerjaan proyek sesuai dengan Project Management Plan. Ini mencakup koordinasi tim, pelaksanaan aktivitas, dan produksi deliverables.

#### 2.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Management Plan | PMP |
| 2 | Approved Change Requests | CCB |
| 3 | Enterprise Environmental Factors | Organisasi |
| 4 | Organizational Process Assets | Organisasi |

#### 2.5.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Deliverables | Hasil proyek yang dihasilkan |
| 2 | Work Performance Data | Data mentah kinerja proyek |
| 3 | Change Requests | Permintaan perubahan yang diajukan |
| 4 | Project Management Plan Updates | Update rencana jika diperlukan |
| 5 | Project Documents Updates | Update dokumen proyek |

#### 2.5.4 Aktivitas Utama

A. Sprint Planning

| Aktivitas | Deskripsi | Durasi |
| --- | --- | --- |
| Review Product Backlog | PO mempresentasikan prioritas backlog | 30 menit |
| Sprint Goal Definition | Tim dan PO menyepakati tujuan sprint | 30 menit |
| Sprint Backlog Selection | Tim memilih story untuk dikerjakan | 1 jam |
| Task Breakdown | Tim memecah story menjadi task | 1-2 jam |
| Commitment | Tim berkomitmen pada sprint backlog | 15 menit |

B. Daily Stand-up

| Aktivitas | Deskripsi | Durasi |
| --- | --- | --- |
| Yesterday's Work | Setiap anggota melaporkan pekerjaan kemarin | 5 menit |
| Today's Plan | Setiap anggota melaporkan rencana hari ini | 5 menit |
| Impediments | Setiap anggota melaporkan hambatan | 5 menit |

C. Development Work

| Aktivitas | Deskripsi | Durasi |
| --- | --- | --- |
| Coding | Implementasi fitur sesuai task | 7 hari |
| Code Review | Review kode oleh peer | 1 hari |
| Unit Testing | Pengujian unit oleh developer | 1 hari |
| Integration | Integrasi dengan komponen lain | 1 hari |

D. Sprint Review

| Aktivitas | Deskripsi | Durasi |
| --- | --- | --- |
| Demo | Tim mendemonstrasikan fitur selesai | 1 jam |
| Feedback | Stakeholder memberikan feedback | 30 menit |
| Backlog Update | Update backlog berdasarkan feedback | 30 menit |

E. Sprint Retrospective

| Aktivitas | Deskripsi | Durasi |
| --- | --- | --- |
| What went well | Identifikasi hal yang berhasil | 15 menit |
| What went wrong | Identifikasi masalah | 15 menit |
| What to improve | Identifikasi perbaikan | 15 menit |
| Action items | Buat action plan | 15 menit |

#### 2.5.5 Struktur Sprint Proyek P-FNE-05

| Sprint | Durasi | Fokus | Deliverables |
| --- | --- | --- | --- |
| Sprint 0 | 2 minggu | Setup & Foundation | Infrastructure, CI/CD, database schema |
| Sprint 1 | 2 minggu | Sales Module - Part 1 | Sales Order CRUD, Validation |
| Sprint 2 | 2 minggu | Sales Module - Part 2 | Invoice, Payment, Return |
| Sprint 3 | 2 minggu | CRM Module | Customer Master, Interaction, Complaint |
| Sprint 4 | 2 minggu | Marketplace - Part 1 | Product Listing, Catalog, Search |
| Sprint 5 | 2 minggu | Marketplace - Part 2 | Cart, Checkout, Review, Promotion |
| Sprint 6 | 2 minggu | Logistics Module | Shipment, Tracking, POD |
| Sprint 7 | 2 minggu | Portal Module | Customer Portal, Supplier Portal, Security |
| Sprint 8 | 2 minggu | Integration & Testing | Integrasi dengan modul lain, E2E testing |
| Sprint 9 | 2 minggu | UAT & Bug Fixing | UAT, bug fixing, performance optimization |

#### 2.5.6 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Mengkoordinasikan seluruh aktivitas, memastikan tim tidak terhambat |
| Product Owner | Menjaga backlog, memberikan prioritas, menerima deliverables |
| Tech Lead | Mengarahkan implementasi teknis, code review, technical decisions |
| Development Team | Mengimplementasikan fitur, testing, code review |
| QA Team | Melakukan testing, melaporkan bugs |
| UX Designer | Menyediakan design untuk implementasi |

#### 2.5.7 Git Workflow

Proyek menggunakan GitFlow dengan branch strategy:

text

main (production)

└── develop (integration)

├── feature/sales-order

├── feature/crm

├── feature/marketplace

├── feature/logistics

└── feature/portal

Branch Rules:

- main: Hanya untuk production-ready code

- develop: Integrasi semua feature branch

- feature/*: Untuk pengembangan fitur baru

- hotfix/*: Untuk perbaikan urgent di production

- release/*: Untuk persiapan release

Pull Request Requirements:

- Minimal 2 approvals

- All checks pass (CI/CD)

- No merge conflicts

- Code coverage tidak menurun

### 2.6 Monitor and Control Project Work

#### 2.6.1 Deskripsi Proses

Proses ini bertujuan untuk memonitor, mengukur, dan mengendalikan kemajuan proyek terhadap Project Management Plan. Proses ini melibatkan pengumpulan data kinerja, analisis, dan pengambilan tindakan korektif jika diperlukan.

#### 2.6.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Management Plan | PMP |
| 2 | Work Performance Data | Aktivitas proyek |
| 3 | Work Performance Information | Analisis data kinerja |
| 4 | Change Requests | CCB |
| 5 | Organizational Process Assets | Organisasi |

#### 2.6.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Work Performance Reports | Laporan kinerja proyek |
| 2 | Change Requests | Permintaan perubahan korektif |
| 3 | Project Management Plan Updates | Update rencana jika diperlukan |
| 4 | Project Documents Updates | Update dokumen proyek |

#### 2.6.4 Metrik Kinerja

A. Schedule Metrics

| Metrik | Deskripsi | Target | Frekuensi |
| --- | --- | --- | --- |
| Sprint Burndown | Progress penyelesaian sprint | Selesai tepat waktu | Harian |
| Velocity | Story points per sprint | Stabil/Naik | Setiap sprint |
| Schedule Variance (SV) | Selisih jadwal | ≥ 0 | Mingguan |
| SPI (Schedule Performance Index) | Rasio kinerja jadwal | ≥ 1.0 | Mingguan |

B. Scope Metrics

| Metrik | Deskripsi | Target | Frekuensi |
| --- | --- | --- | --- |
| Story Completion | % story selesai per sprint | 100% | Setiap sprint |
| Scope Creep | Perubahan scope | Minimal | Mingguan |
| Requirements Stability | % requirements berubah | ≤ 10% | Bulanan |

C. Quality Metrics

| Metrik | Deskripsi | Target | Frekuensi |
| --- | --- | --- | --- |
| Code Coverage | % kode yang diuji | ≥ 80% | Harian |
| Defect Density | Bug per KLOC | ≤ 1 | Sprint |
| Critical Bugs | Bug critical | 0 | Real-time |
| Test Pass Rate | % test lulus | ≥ 98% | Harian |
| UAT Satisfaction | Skor kepuasan UAT | ≥ 4.5/5 | Akhir UAT |

D. Cost Metrics

| Metrik | Deskripsi | Target | Frekuensi |
| --- | --- | --- | --- |
| Budget Variance | Selisih anggaran | ≤ 10% | Bulanan |
| CPI (Cost Performance Index) | Rasio kinerja biaya | ≥ 0.9 | Bulanan |
| EAC (Estimate at Completion) | Estimasi biaya akhir | ≤ Rp 4.5B | Bulanan |

E. Risk Metrics

| Metrik | Deskripsi | Target | Frekuensi |
| --- | --- | --- | --- |
| Risk Exposure | Total dampak risiko | Menurun | 2 Mingguan |
| Risk Response Effectiveness | % mitigasi berhasil | ≥ 80% | 2 Mingguan |
| New Risks Identified | Jumlah risiko baru | Teridentifikasi | Mingguan |

#### 2.6.5 Laporan Status Proyek

A. Daily Status Report

| Elemen | Isi |
| --- | --- |
| Tujuan | Sinkronisasi tim, identifikasi hambatan |
| Waktu | Setiap hari, 15 menit |
| Format | Verbal pada Daily Stand-up |
| Penerima | Tim Proyek |

B. Weekly Status Report

| Elemen | Isi |
| --- | --- |
| Tujuan | Laporan kemajuan ke stakeholder |
| Waktu | Setiap Jumat |
| Format | Email + Confluence |
| Penerima | PM, PO, Tech Lead, Sponsor |

Template Weekly Status Report:

text

Subject: Weekly Status Report - P-FNE-05 - Week X

1. Progress Summary

- Sprint X: [Status]

- Completed: [Story Points]

- Remaining: [Story Points]

- Burndown: [Attachment]

2. Key Accomplishments

- [Feature 1] - [Status]

- [Feature 2] - [Status]

3. Key Risks & Issues

- [Risk 1] - [Mitigation]

- [Risk 2] - [Mitigation]

4. Upcoming Activities

- [Activity 1]

- [Activity 2]

5. Decisions Needed

- [Decision 1] - [Deadline]

- [Decision 2] - [Deadline]

6. KPIs

- Schedule: [Status]

- Budget: [Status]

- Quality: [Status]

- Risk: [Status]

C. Monthly Status Report

| Elemen | Isi |
| --- | --- |
| Tujuan | Laporan komprehensif ke Sponsor |
| Waktu | Setiap awal bulan |
| Format | PowerPoint + Laporan detail |
| Penerima | Sponsor, Steering Committee |

D. Phase Gate Review

| Elemen | Isi |
| --- | --- |
| Tujuan | Evaluasi kelulusan fase |
| Waktu | Setiap akhir fase |
| Format | Meeting + Report |
| Penerima | Steering Committee |

#### 2.6.6 Earned Value Management (EVM)

Proyek menggunakan EVM untuk mengukur kinerja secara objektif:

| Metrik | Formula | Target |
| --- | --- | --- |
| PV (Planned Value) | Total anggaran × % rencana | - |
| EV (Earned Value) | Total anggaran × % actual | - |
| AC (Actual Cost) | Biaya aktual yang dikeluarkan | - |
| SV (Schedule Variance) | EV - PV | ≥ 0 |
| CV (Cost Variance) | EV - AC | ≥ 0 |
| SPI (Schedule Performance Index) | EV / PV | ≥ 1.0 |
| CPI (Cost Performance Index) | EV / AC | ≥ 0.9 |
| EAC (Estimate at Completion) | BAC / CPI | ≤ Rp 4.5B |
| ETC (Estimate to Complete) | EAC - AC | - |
| TCPI (To Complete Performance Index) | (BAC - EV) / (BAC - AC) | ≤ 1.1 |

#### 2.6.7 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Mengumpulkan data, menganalisis kinerja, menyusun laporan |
| Tech Lead | Memonitor kinerja teknis |
| QA Lead | Memonitor kualitas dan defect |
| Tim | Melaporkan progress harian |

### 2.7 Perform Integrated Change Control

#### 2.7.1 Deskripsi Proses

Proses ini bertujuan untuk mengelola perubahan terhadap baseline proyek (ruang lingkup, jadwal, biaya) secara terintegrasi. Perubahan harus dievaluasi dampaknya, disetujui, dan dikomunikasikan sebelum diimplementasikan.

#### 2.7.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Management Plan | PMP |
| 2 | Change Requests | Siapapun |
| 3 | Work Performance Information | Monitoring |
| 4 | Organizational Process Assets | Organisasi |

#### 2.7.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Approved Change Requests | Perubahan yang disetujui |
| 2 | Rejected Change Requests | Perubahan yang ditolak |
| 3 | Project Management Plan Updates | Update baseline |
| 4 | Project Documents Updates | Update dokumen |

#### 2.7.4 Change Control Board (CCB)

Komposisi CCB untuk Proyek P-FNE-05:

| Peran | Anggota | Voting Weight |
| --- | --- | --- |
| Project Sponsor | CEO FNE | Veto |
| Project Manager | [Nama PM] | 1 |
| Product Owner | [Nama PO] | 1 |
| Tech Lead | [Nama Tech Lead] | 1 |
| QA Lead | [Nama QA Lead] | 1 |
| Finance Representative | CFO FNE | 1 |

#### 2.7.5 Change Request Process

Step 1: Identifikasi Perubahan

| Elemen | Deskripsi |
| --- | --- |
| Who | Siapapun (tim, stakeholder, user) |
| What | Perubahan ruang lingkup, jadwal, biaya, atau requirement |
| When | Setiap saat selama proyek berlangsung |
| How | Submit Change Request Form |

Step 2: Submit Change Request

Change Request Form Template:

text

┌─────────────────────────────────────────────────────────────────────┐

│                    CHANGE REQUEST FORM                             │

├─────────────────────────────────────────────────────────────────────┤

│ Change Request ID : CR-2026-09-09-001                             │

│ Date Submitted    : 09/09/2026                                    │

│ Requested By      : [Nama]                                        │

│ Category          : Scope / Schedule / Cost / Requirement         │

│ Priority          : Critical / High / Medium / Low               │

├─────────────────────────────────────────────────────────────────────┤

│ CURRENT STATE:                                                    │

│ [Deskripsi kondisi saat ini]                                      │

├─────────────────────────────────────────────────────────────────────┤

│ PROPOSED CHANGE:                                                  │

│ [Deskripsi perubahan yang diusulkan]                              │

├─────────────────────────────────────────────────────────────────────┤

│ BUSINESS CASE:                                                    │

│ [Alasan mengapa perubahan diperlukan]                             │

├─────────────────────────────────────────────────────────────────────┤

│ IMPACT ASSESSMENT:                                                │

│ Scope    : [Dampak pada ruang lingkup]                            │

│ Schedule : [Dampak pada jadwal]                                   │

│ Cost     : [Dampak pada biaya]                                    │

│ Quality  : [Dampak pada kualitas]                                 │

│ Risk     : [Dampak pada risiko]                                   │

├─────────────────────────────────────────────────────────────────────┤

│ RECOMMENDATION:                                                   │

│ [Rekomendasi dari Project Manager]                                │

├─────────────────────────────────────────────────────────────────────┤

│ CCB DECISION:                                                     │

│ ☐ Approved   ☐ Rejected   ☐ Deferred   ☐ Need More Info          │

│ Approval Date: [ ]                                                │

│ Signatures: [ ]                                                   │

└─────────────────────────────────────────────────────────────────────┘

Step 3: Evaluasi Dampak

| Aspek | Evaluasi | Metrik |
| --- | --- | --- |
| Scope | Apakah ruang lingkup berubah? | WBS impact |
| Schedule | Berapa tambahan waktu? | Schedule impact (hari) |
| Cost | Berapa tambahan biaya? | Cost impact (Rp) |
| Quality | Apakah kualitas terpengaruh? | Quality metrics |
| Risk | Risiko baru atau berubah? | Risk register update |
| Resources | Sumber daya tambahan? | Resource plan impact |
| Stakeholder | Dampak pada stakeholder? | Stakeholder engagement |

Step 4: Keputusan CCB

| Keputusan | Konsekuensi |
| --- | --- |
| Approved | Perubahan diimplementasikan, baseline diupdate |
| Rejected | Perubahan tidak diimplementasikan, status dijelaskan |
| Deferred | Perubahan ditunda untuk evaluasi lebih lanjut |
| Need More Info | Informasi tambahan diperlukan sebelum keputusan |

Step 5: Implementasi Perubahan

| Aktivitas | Deskripsi | Owner |
| --- | --- | --- |
| Update Baseline | Update scope/schedule/cost baseline | PM |
| Update Plans | Update project management plan | PM |
| Update Documents | Update semua dokumen terkait | PM/Tim |
| Communicate | Komunikasikan perubahan ke stakeholder | PM |
| Implement | Implementasikan perubahan dalam pekerjaan | Tim |

#### 2.7.6 Change Request Categories

| Kategori | Deskripsi | Approval Level | Response Time |
| --- | --- | --- | --- |
| Minor | Dampak ≤ 5% dari baseline | PM + PO | ≤ 2 hari |
| Moderate | Dampak 5-15% dari baseline | CCB | ≤ 5 hari |
| Major | Dampak > 15% dari baseline | Sponsor + CCB | ≤ 7 hari |
| Emergency | Critical, urgent | PM (dengan notifikasi sponsor) | ≤ 4 jam |

#### 2.7.7 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Menerima dan meninjau change request, memfasilitasi evaluasi |
| CCB | Mengevaluasi dan memutuskan change request |
| Product Owner | Memberikan perspektif bisnis pada perubahan |
| Tech Lead | Memberikan perspektif teknis pada perubahan |
| Sponsor | Menyetujui perubahan major |

### 2.8 Close Project or Phase

#### 2.8.1 Deskripsi Proses

Proses ini bertujuan untuk menyelesaikan secara formal semua aktivitas proyek dan menutup proyek atau fase. Proses ini memastikan bahwa semua deliverables telah diserahkan, semua dokumen final telah diselesaikan, dan semua pelajaran telah didokumentasikan.

#### 2.8.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Management Plan | PMP |
| 2 | Accepted Deliverables | UAT Sign-off |
| 3 | Work Performance Information | Monitoring |
| 4 | Organizational Process Assets | Organisasi |

#### 2.8.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Final Product/Service | Produk akhir yang diserahkan |
| 2 | Final Report | Laporan akhir proyek |
| 3 | Lessons Learned | Pelajaran yang didapat |
| 4 | Organizational Process Assets Updates | Update aset organisasi |
| 5 | Project Closure | Penutupan proyek secara formal |

#### 2.8.4 Aktivitas Penutupan Proyek

A. Final Acceptance

| Aktivitas | Deskripsi | Timeline |
| --- | --- | --- |
| UAT Sign-off | User acceptance testing selesai | M21 |
| Product Owner Acceptance | PO menyetujui deliverables | M21 |
| Sponsor Sign-off | Sponsor menandatangani final acceptance | M21-22 |

B. Documentation Finalization

| Dokumen | Deskripsi | Owner |
| --- | --- | --- |
| Technical Documentation | API docs, architecture, deployment guide | Tech Lead |
| User Manual | Panduan untuk end-user | BA + UX |
| Operational Handover | Panduan untuk tim operasional | Tech Lead |
| Training Materials | Materi pelatihan end-user | BA |
| Project Documentation | Semua dokumen proyek | PM |

C. Knowledge Transfer

| Aktivitas | Deskripsi | Timeline |
| --- | --- | --- |
| Technical Handover | Transfer knowledge ke tim operasional | M21-22 |
| User Training | Pelatihan untuk end-user | M21 |
| Documentation Handover | Serah terima dokumentasi | M22 |

D. Financial Closure

| Aktivitas | Deskripsi | Owner |
| --- | --- | --- |
| Final Budget Review | Review anggaran akhir | PM + Finance |
| Vendor Payments | Penyelesaian pembayaran vendor | PM + Procurement |
| Financial Report | Laporan keuangan akhir | Finance |

E. Lessons Learned

| Aktivitas | Deskripsi | Timeline |
| --- | --- | --- |
| Lessons Learned Workshop | Workshop dengan seluruh tim | M22 |
| Lessons Learned Document | Dokumentasi pelajaran | M22 |
| Retrospective Final | Retrospective akhir proyek | M22 |

F. Project Closure Report

Template Project Closure Report:

text

┌─────────────────────────────────────────────────────────────────────┐

│                    PROJECT CLOSURE REPORT                          │

│                    P-FNE-05: Commerce, Sales & Logistics           │

├─────────────────────────────────────────────────────────────────────┤

│ 1. PROJECT SUMMARY                                                │

│    - Project Name: P-FNE-05                                        │

│    - Start Date: [ ]                                              │

│    - End Date: [ ]                                                │

│    - Duration: [ ]                                               │

│    - Total Budget: [ ]                                            │

│    - Actual Cost: [ ]                                             │

│    - Budget Variance: [ ]                                         │

├─────────────────────────────────────────────────────────────────────┤

│ 2. DELIVERABLES STATUS                                            │

│    - Deliverable 1: [Status]                                      │

│    - Deliverable 2: [Status]                                      │

│    - Deliverable 3: [Status]                                      │

├─────────────────────────────────────────────────────────────────────┤

│ 3. PERFORMANCE SUMMARY                                            │

│    - Schedule Performance: [SPI] [SV]                             │

│    - Cost Performance: [CPI] [CV]                                 │

│    - Quality Performance: [Metrics]                               │

│    - Risk Performance: [Metrics]                                  │

├─────────────────────────────────────────────────────────────────────┤

│ 4. SUCCESS CRITERIA ACHIEVEMENT                                   │

│    - Sales Order creation ≤ 2 detik: [✓/✗]                      │

│    - Marketplace page load ≤ 3 detik: [✓/✗]                     │

│    - Checkout processing ≤ 5 detik: [✓/✗]                       │

│    - Portal availability ≥ 99.5%: [✓/✗]                         │

│    - UAT satisfaction ≥ 4.5/5: [✓/✗]                            │

├─────────────────────────────────────────────────────────────────────┤

│ 5. LESSONS LEARNED                                                │

│    - What went well: [ ]                                          │

│    - What went wrong: [ ]                                         │

│    - What could be improved: [ ]                                  │

├─────────────────────────────────────────────────────────────────────┤

│ 6. RECOMMENDATIONS                                                │

│    - Recommendation 1: [ ]                                        │

│    - Recommendation 2: [ ]                                        │

├─────────────────────────────────────────────────────────────────────┤

│ 7. APPROVALS                                                      │

│    - Project Manager: [ ]                                         │

│    - Product Owner: [ ]                                           │

│    - Project Sponsor: [ ]                                         │

│    - Date: [ ]                                                    │

└─────────────────────────────────────────────────────────────────────┘

#### 2.8.5 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Memimpin aktivitas penutupan, menyusun laporan akhir |
| Product Owner | Menyetujui deliverables, memberikan UAT sign-off |
| Tech Lead | Menyiapkan technical handover, dokumentasi teknis |
| QA Lead | Menyiapkan quality report |
| Sponsor | Menandatangani project closure |

#### 2.8.6 Checklist Penutupan Proyek

| No | Item | Status | Owner |
| --- | --- | --- | --- |
| 1 | Semua deliverables diterima | ☐ | PO |
| 2 | UAT sign-off completed | ☐ | PO |
| 3 | Sponsor sign-off completed | ☐ | Sponsor |
| 4 | Technical handover completed | ☐ | Tech Lead |
| 5 | User training completed | ☐ | BA |
| 6 | All documentation finalized | ☐ | PM |
| 7 | Financial closure completed | ☐ | Finance |
| 8 | All vendor payments completed | ☐ | Procurement |
| 9 | Lessons learned documented | ☐ | PM |
| 10 | Project closure report approved | ☐ | Sponsor |
| 11 | Project team released | ☐ | HR |

## BAB 3: MANAJEMEN RUANG LINGKUP PROYEK

### 3.1 Tujuan Manajemen Ruang Lingkup

Manajemen Ruang Lingkup Proyek bertujuan untuk memastikan bahwa proyek mencakup semua pekerjaan yang diperlukan (dan hanya itu) untuk menyelesaikan proyek dengan sukses. Tujuan spesifiknya adalah:

- Mendefinisikan dengan jelas apa yang termasuk dan tidak termasuk dalam proyek

- Mencegah perubahan ruang lingkup yang tidak terkendali (scope creep)

- Memastikan semua pekerjaan yang diperlukan teridentifikasi dan direncanakan

- Memvalidasi bahwa deliverables memenuhi kebutuhan stakeholder

- Mengendalikan perubahan terhadap ruang lingkup yang telah disetujui

### 3.2 Proses Manajemen Ruang Lingkup

Manajemen Ruang Lingkup Proyek terdiri dari 6 (enam) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Plan Scope Management | Merencanakan bagaimana ruang lingkup akan dikelola | Minggu 1-2 |
| 2 | Collect Requirements | Mengumpulkan dan mendokumentasikan kebutuhan stakeholder | Minggu 1-3 |
| 3 | Define Scope | Mendefinisikan ruang lingkup proyek secara detail | Minggu 2-3 |
| 4 | Create WBS | Membuat Work Breakdown Structure | Minggu 2-3 |
| 5 | Validate Scope | Memvalidasi deliverables dengan stakeholder | Setiap Sprint + UAT |
| 6 | Control Scope | Mengendalikan perubahan ruang lingkup | Berkelanjutan |

### 3.3 Plan Scope Management

#### 3.3.1 Deskripsi Proses

Proses ini menghasilkan Scope Management Plan dan Requirements Management Plan yang mendefinisikan bagaimana ruang lingkup akan didefinisikan, divalidasi, dan dikendalikan sepanjang proyek.

#### 3.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Enterprise Environmental Factors | Organisasi |
| 3 | Organizational Process Assets | Organisasi |

#### 3.3.3 Output

A. Scope Management Plan

| Elemen | Deskripsi |
| --- | --- |
| Scope Definition | Menggunakan Project Scope Statement dan WBS |
| Scope Validation | Sprint Review dan UAT |
| Scope Control | Formal Change Request Process |
| Acceptance Criteria | Sesuai dengan requirement document |
| Work Authorization | Sprint backlog dan task assignment |
| Scope Change Process | CR-Form → CCB → Approval/Rejection |

B. Requirements Management Plan

| Elemen | Deskripsi |
| --- | --- |
| Requirements Collection | Interview, workshop, document analysis |
| Requirements Documentation | User Stories + Acceptance Criteria |
| Requirements Prioritization | MoSCoW (Must, Should, Could, Won't) |
| Requirements Traceability | RTM (Requirements Traceability Matrix) |
| Requirements Changes | Formal Change Request Process |
| Requirements Approval | Product Owner approval |

#### 3.3.4 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Menyusun Scope Management Plan |
| Business Analyst | Menyusun Requirements Management Plan |
| Product Owner | Menyetujui rencana dan prioritas |
| Tech Lead | Memberikan input teknis |

### 3.4 Collect Requirements

#### 3.4.1 Deskripsi Proses

Proses ini bertujuan untuk mengumpulkan, menganalisis, dan mendokumentasikan kebutuhan semua stakeholder yang relevan. Requirements akan menjadi dasar untuk mendefinisikan ruang lingkup proyek.

#### 3.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Stakeholder Register | Manajemen Stakeholder |
| 3 | Scope Management Plan | PMP |
| 4 | Requirements Management Plan | PMP |

#### 3.4.3 Output

A. Requirements Documentation

Dokumen requirement untuk P-FNE-05 telah disusun dalam dokumen terpisah yang mencakup:

1. Functional Requirements - Sales Management (19 requirements)

| ID | Requirement | Prioritas |
| --- | --- | --- |
| FNE-SAL-001 | Sales Order Creation | P0 |
| FNE-SAL-002 | Sales Order Validation | P0 |
| FNE-SAL-003 | Stock Reservation | P0 |
| FNE-SAL-004 | Sales Order Status Tracking | P0 |
| FNE-SAL-005 | Sales Order Approval | P0 |
| FNE-SAL-006 | Sales Order Confirmation | P1 |
| FNE-SAL-007 | Sales Order Modification | P1 |
| FNE-SAL-008 | Sales Order Cancellation | P0 |
| FNE-SAL-009 | Sales Order Fulfillment | P0 |
| FNE-SAL-010 | Sales Invoice Generation | P0 |
| FNE-SAL-011 | Sales Invoice Status | P0 |
| FNE-SAL-012 | Sales Payment Recording | P0 |
| FNE-SAL-013 | Sales Return | P0 |
| FNE-SAL-014 | Credit Note | P0 |
| FNE-SAL-015 | Sales Dashboard | P0 |
| FNE-SAL-016 | Sales Analytics | P1 |
| FNE-SAL-017 | Sales Commission | P2 |
| FNE-SAL-018 | Sales Quotation | P1 |
| FNE-SAL-019 | Quotation to Order | P1 |

2. Functional Requirements - CRM (14 requirements)

| ID | Requirement | Prioritas |
| --- | --- | --- |
| FNE-CRM-001 | Customer Registration | P0 |
| FNE-CRM-002 | Customer Contact | P0 |
| FNE-CRM-003 | Customer Interaction | P0 |
| FNE-CRM-004 | Customer Purchase History | P0 |
| FNE-CRM-005 | Customer Segmentation | P0 |
| FNE-CRM-006 | Customer Credit Management | P0 |
| FNE-CRM-007 | Customer Complaint | P0 |
| FNE-CRM-008 | Complaint Workflow | P0 |
| FNE-CRM-009 | Customer Feedback | P1 |
| FNE-CRM-010 | CSAT Score | P1 |
| FNE-CRM-011 | Customer Retention Analysis | P1 |
| FNE-CRM-012 | Campaign Management | P1 |
| FNE-CRM-013 | CRM Dashboard | P0 |
| FNE-CRM-014 | Customer 360 View | P0 |

3. Functional Requirements - Marketplace (16 requirements)

| ID | Requirement | Prioritas |
| --- | --- | --- |
| FNE-MKT-001 | Product Listing | P0 |
| FNE-MKT-002 | Product Catalog | P0 |
| FNE-MKT-003 | Product Search | P0 |
| FNE-MKT-004 | Product Filter | P0 |
| FNE-MKT-005 | Product Detail | P0 |
| FNE-MKT-006 | Add to Cart | P0 |
| FNE-MKT-007 | Checkout | P0 |
| FNE-MKT-008 | Marketplace Order to SO | P0 |
| FNE-MKT-009 | Order Tracking | P0 |
| FNE-MKT-010 | Order History | P0 |
| FNE-MKT-011 | Product Review | P0 |
| FNE-MKT-012 | Seller Rating | P1 |
| FNE-MKT-013 | Marketplace Dashboard | P0 |
| FNE-MKT-014 | Promotion Management | P1 |
| FNE-MKT-015 | Marketplace Analytics | P1 |
| FNE-MKT-016 | Wishlist | P2 |

4. Functional Requirements - Logistics (15 requirements)

| ID | Requirement | Prioritas |
| --- | --- | --- |
| FNE-LOG-001 | Shipment Creation | P0 |
| FNE-LOG-002 | Shipment Status | P0 |
| FNE-LOG-003 | Picking List | P0 |
| FNE-LOG-004 | Packing List | P0 |
| FNE-LOG-005 | Delivery Note | P0 |
| FNE-LOG-006 | Waybill | P1 |
| FNE-LOG-007 | Carrier Management | P1 |
| FNE-LOG-008 | Route Optimization | P2 |
| FNE-LOG-009 | Delivery Tracking | P1 |
| FNE-LOG-010 | Proof of Delivery | P0 |
| FNE-LOG-011 | Logistics Cost | P0 |
| FNE-LOG-012 | Logistics Dashboard | P0 |
| FNE-LOG-013 | Logistics Analytics | P1 |
| FNE-LOG-014 | Fleet Management | P2 |
| FNE-LOG-015 | Return Logistics | P1 |

5. Functional Requirements - Portal (17 requirements)

| ID | Requirement | Prioritas |
| --- | --- | --- |
| FNE-PRT-001 | Customer Portal Login | P0 |
| FNE-PRT-002 | Customer Profile | P0 |
| FNE-PRT-003 | Order History | P0 |
| FNE-PRT-004 | Order Tracking | P0 |
| FNE-PRT-005 | Product Catalog (B2B) | P0 |
| FNE-PRT-006 | Place Order (B2B) | P0 |
| FNE-PRT-007 | Invoice History | P0 |
| FNE-PRT-008 | Complaint Submission | P0 |
| FNE-PRT-009 | Supplier Portal Login | P0 |
| FNE-PRT-010 | Supplier Profile | P0 |
| FNE-PRT-011 | PO View | P0 |
| FNE-PRT-012 | PO Confirmation | P0 |
| FNE-PRT-013 | Invoice Submission | P0 |
| FNE-PRT-014 | Payment Status | P0 |
| FNE-PRT-015 | Supplier Performance Scorecard | P1 |
| FNE-PRT-016 | Portal Dashboard | P0 |
| FNE-PRT-017 | Portal Security (MFA) | P0 |

6. Non-Functional Requirements (12 requirements)

| ID | Requirement | Target | Prioritas |
| --- | --- | --- | --- |
| FNE-NFR-COM-001 | Sales Order Query Time | ≤ 2 detik | P0 |
| FNE-NFR-COM-002 | Marketplace Page Load | ≤ 3 detik | P0 |
| FNE-NFR-COM-003 | Checkout Processing | ≤ 5 detik | P0 |
| FNE-NFR-COM-004 | Concurrent Users | ≥ 5.000 | P0 |
| FNE-NFR-COM-005 | Transaction Throughput | ≥ 50 trans/detik | P0 |
| FNE-NFR-COM-006 | Portal Availability | ≥ 99.5% | P0 |
| FNE-NFR-COM-007 | Product Search Time | ≤ 2 detik | P0 |
| FNE-NFR-COM-008 | Image Loading | ≤ 1 detik/gambar | P1 |
| FNE-NFR-COM-009 | Delivery Tracking Update | ≤ 1 menit | P1 |
| FNE-NFR-COM-010 | Mobile Responsive | Ya | P0 |
| FNE-NFR-COM-011 | Data Consistency | 100% | P0 |
| FNE-NFR-COM-012 | Security Compliance | PCI DSS | P0 |

B. Requirements Traceability Matrix (RTM)

| ID | Requirement | Source | Priority | WBS | Test Case | Status |
| --- | --- | --- | --- | --- | --- | --- |
| FNE-SAL-001 | Sales Order Creation | Business | P0 | 3.1 | TC-SAL-001 | Draft |
| FNE-SAL-002 | Sales Order Validation | Business | P0 | 3.1 | TC-SAL-002 | Draft |
| ... | ... | ... | ... | ... | ... | ... |
| FNE-NFR-COM-001 | Sales Order Query Time | NFR | P0 | 8.3 | TC-NFR-001 | Draft |

#### 3.4.4 Metode Pengumpulan Requirements

| Metode | Deskripsi | Digunakan Untuk |
| --- | --- | --- |
| Interview | Wawancara dengan stakeholder kunci | Sales Director, Operations Director, End Users |
| Workshop | Sesi brainstorming dengan tim | Semua stakeholder |
| Document Analysis | Analisis dokumen yang ada | SOP, sistem existing |
| Observation | Observasi proses bisnis saat ini | Sales process, logistics process |
| Prototyping | Membuat prototype untuk validasi | UI/UX design |
| Questionnaire | Kuesioner untuk pengguna massal | End users |

#### 3.4.5 Prioritization Method (MoSCoW)

| Kategori | Deskripsi | Jumlah Requirements |
| --- | --- | --- |
| Must Have | Wajib ada, tanpa ini sistem tidak berfungsi | 45 |
| Should Have | Penting tapi bisa di-delay | 28 |
| Could Have | Nice to have, tidak kritis | 8 |
| Won't Have | Tidak termasuk dalam release ini | 0 |

#### 3.4.6 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Business Analyst | Memimpin pengumpulan requirements, menyusun dokumentasi |
| Product Owner | Menyetujui requirements, menentukan prioritas |
| Tech Lead | Memberikan input teknis untuk feasibility |
| Project Manager | Memfasilitasi proses, koordinasi stakeholder |
| Stakeholder | Menyediakan kebutuhan dan feedback |

### 3.5 Define Scope

#### 3.5.1 Deskripsi Proses

Proses ini menghasilkan Project Scope Statement yang mendefinisikan secara detail ruang lingkup proyek, termasuk deliverables, acceptance criteria, dan batasan-batasan.

#### 3.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Requirements Documentation | Business Analyst |
| 3 | Requirements Traceability Matrix | Business Analyst |
| 4 | Organizational Process Assets | Organisasi |

#### 3.5.3 Output

Project Scope Statement P-FNE-05

| Elemen | Deskripsi |
| --- | --- |
| Product Scope Description | Sistem Commerce, Sales & Logistics terintegrasi yang mencakup Sales Management, CRM, Marketplace, Logistics, dan Portal |
| Project Deliverables | 5 modul aplikasi, 5 microservices, 3 portal, 1 mobile app, API Gateway, Event Bus, integration with 4 modules |
| Acceptance Criteria | Sesuai dengan 81 functional requirements dan 12 non-functional requirements |
| Exclusions | Modul lain di luar P-FNE-05, infrastruktur cloud, maintenance after go-live |
| Constraints | Waktu 5 bulan, anggaran Rp 4.5B, resource 12 orang |
| Assumptions | SDM tersedia, infrastruktur siap, kerjasama tim lain, requirements stabil |

#### 3.5.4 Acceptance Criteria Detail

A. Sales Management Acceptance Criteria

| No | Kriteria | Metode Verifikasi |
| --- | --- | --- |
| 1 | Sales Order dapat dibuat, divalidasi, dan dikonfirmasi | Test script + UAT |
| 2 | Stock reservation berfungsi | Test script + UAT |
| 3 | Sales Order status tracking berfungsi | Test script + UAT |
| 4 | Invoice dapat dihasilkan dari Sales Order | Test script + UAT |
| 5 | Payment recording dan status invoice berfungsi | Test script + UAT |
| 6 | Sales return dan credit note berfungsi | Test script + UAT |

B. CRM Acceptance Criteria

| No | Kriteria | Metode Verifikasi |
| --- | --- | --- |
| 1 | Customer master dapat dikelola (CRUD) | Test script + UAT |
| 2 | Customer interaction dapat dicatat | Test script + UAT |
| 3 | Customer purchase history tersedia | Test script + UAT |
| 4 | Customer complaint management berfungsi | Test script + UAT |
| 5 | Customer 360 view tersedia | Test script + UAT |

C. Marketplace Acceptance Criteria

| No | Kriteria | Metode Verifikasi |
| --- | --- | --- |
| 1 | Product listing dapat dibuat dan di-update | Test script + UAT |
| 2 | Product catalog dan search berfungsi | Test script + UAT |
| 3 | Cart dan checkout berfungsi | Test script + UAT |
| 4 | Marketplace order terintegrasi dengan Sales Order | Integration test |
| 5 | Order tracking berfungsi | Test script + UAT |
| 6 | Product review dan rating berfungsi | Test script + UAT |

D. Logistics Acceptance Criteria

| No | Kriteria | Metode Verifikasi |
| --- | --- | --- |
| 1 | Shipment dapat dibuat dari Sales Order | Test script + UAT |
| 2 | Picking list dan packing list berfungsi | Test script + UAT |
| 3 | Delivery note dan waybill dapat dihasilkan | Test script + UAT |
| 4 | Proof of Delivery (POD) dapat dicatat | Test script + UAT |
| 5 | Logistics cost dapat dihitung | Test script + UAT |

E. Portal Acceptance Criteria

| No | Kriteria | Metode Verifikasi |
| --- | --- | --- |
| 1 | Customer portal berfungsi (login, order history, tracking, complaint) | Test script + UAT |
| 2 | Supplier portal berfungsi (login, PO view, PO confirmation, invoice) | Test script + UAT |
| 3 | Portal security (MFA) berfungsi | Security testing |

F. Integration Acceptance Criteria

| No | Kriteria | Metode Verifikasi |
| --- | --- | --- |
| 1 | Event SalesOrderCreated terpublikasi untuk inventory | Integration test |
| 2 | Event ShipmentDelivered terpublikasi untuk finance | Integration test |
| 3 | Integrasi dengan P-FNE-03 (inventory availability) berfungsi | Integration test |
| 4 | Integrasi dengan P-FNE-04 (product availability) berfungsi | Integration test |
| 5 | Integrasi dengan P-FNE-06 (sales to finance) berfungsi | Integration test |

G. Performance Acceptance Criteria

| No | Kriteria | Target | Metode Verifikasi |
| --- | --- | --- | --- |
| 1 | Sales order query time | ≤ 2 detik | Performance test |
| 2 | Marketplace page load | ≤ 3 detik | Performance test |
| 3 | Checkout processing | ≤ 5 detik | Performance test |
| 4 | Product search time | ≤ 2 detik | Performance test |

H. Security Acceptance Criteria

| No | Kriteria | Metode Verifikasi |
| --- | --- | --- |
| 1 | User hanya dapat mengakses data sesuai otorisasi | Security test |
| 2 | Audit trail untuk semua transaksi penjualan | Security test |
| 3 | Portal menggunakan HTTPS dan MFA | Security test |

#### 3.5.5 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Menyusun Project Scope Statement |
| Product Owner | Menyetujui ruang lingkup dan acceptance criteria |
| Business Analyst | Memberikan input requirements |
| Tech Lead | Memberikan input kelayakan teknis |
| Sponsor | Menyetujui ruang lingkup final |

### 3.6 Create WBS

#### 3.6.1 Deskripsi Proses

Proses ini menghasilkan Work Breakdown Structure (WBS) yang merupakan dekomposisi hirarkis dari total ruang lingkup proyek menjadi komponen-komponen yang lebih kecil dan mudah dikelola.

#### 3.6.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Scope Statement | Define Scope |
| 2 | Requirements Documentation | Collect Requirements |
| 3 | Organizational Process Assets | Organisasi |

#### 3.6.3 Output

A. Work Breakdown Structure (WBS)

text

P-FNE-05: Commerce, Sales & Logistics

│

├── 1. Project Initiation (Minggu 1)

│   ├── 1.1 Project Charter Development

│   ├── 1.2 PMP Development

│   ├── 1.3 Team Onboarding

│   └── 1.4 Project Kickoff Meeting

│

├── 2. Requirements & Design (Minggu 1-3)

│   ├── 2.1 Requirements Gathering & Validation

│   │   ├── 2.1.1 Stakeholder Interviews

│   │   ├── 2.1.2 Requirements Workshop

│   │   └── 2.1.3 Requirements Documentation

│   ├── 2.2 UX/UI Design

│   │   ├── 2.2.1 User Flow Design

│   │   ├── 2.2.2 Wireframe Design

│   │   ├── 2.2.3 High-Fidelity Mockup (Web)

│   │   └── 2.2.4 High-Fidelity Mockup (Mobile)

│   ├── 2.3 Architecture & Technical Design

│   │   ├── 2.3.1 High-Level Architecture Design

│   │   ├── 2.3.2 API Design (REST/GraphQL)

│   │   ├── 2.3.3 Event Schema Design

│   │   └── 2.3.4 Security Architecture Design

│   └── 2.4 Database Design

│       ├── 2.4.1 Logical Data Model

│       ├── 2.4.2 Physical Data Model

│       └── 2.4.3 Database Migration Scripts

│

├── 3. Sales Management Module (Minggu 3-6)

│   ├── 3.1 Sales Order Management

│   │   ├── 3.1.1 Sales Order CRUD

│   │   ├── 3.1.2 Sales Order Validation

│   │   ├── 3.1.3 Stock Reservation Integration

│   │   ├── 3.1.4 Sales Order Status Tracking

│   │   ├── 3.1.5 Sales Order Approval Workflow

│   │   └── 3.1.6 Sales Order Fulfillment

│   ├── 3.2 Invoice Management

│   │   ├── 3.2.1 Invoice Generation

│   │   ├── 3.2.2 Invoice Status Tracking

│   │   └── 3.2.3 Invoice Sending (Email)

│   ├── 3.3 Payment Management

│   │   ├── 3.3.1 Payment Recording

│   │   └── 3.3.2 Payment Status Tracking

│   ├── 3.4 Return Management

│   │   ├── 3.4.1 Sales Return Processing

│   │   ├── 3.4.2 Credit Note Generation

│   │   └── 3.4.3 Return Approval Workflow

│   └── 3.5 Sales Dashboard

│       ├── 3.5.1 Sales KPI Dashboard

│       └── 3.5.2 Sales Analytics Reports

│

├── 4. CRM Module (Minggu 4-7)

│   ├── 4.1 Customer Master Management

│   │   ├── 4.1.1 Customer Registration

│   │   ├── 4.1.2 Customer Contact Management

│   │   ├── 4.1.3 Customer Credit Management

│   │   └── 4.1.4 Customer Segmentation

│   ├── 4.2 Interaction Management

│   │   ├── 4.2.1 Customer Interaction Logging

│   │   └── 4.2.2 Interaction History

│   ├── 4.3 Complaint Management

│   │   ├── 4.3.1 Complaint Entry

│   │   ├── 4.3.2 Complaint Workflow

│   │   └── 4.3.3 Complaint Resolution

│   ├── 4.4 Customer Analytics

│   │   ├── 4.4.1 Customer Purchase History

│   │   ├── 4.4.2 Customer 360 View

│   │   └── 4.4.3 CSAT Score & Retention Analysis

│   └── 4.5 CRM Dashboard

│       └── 4.5.1 CRM KPI Dashboard

│

├── 5. Marketplace Module (Minggu 5-9)

│   ├── 5.1 Product Management

│   │   ├── 5.1.1 Product Listing (CRUD)

│   │   ├── 5.1.2 Product Catalog

│   │   ├── 5.1.3 Product Search (Elasticsearch)

│   │   ├── 5.1.4 Product Filter

│   │   └── 5.1.5 Product Detail

│   ├── 5.2 Shopping Cart & Checkout

│   │   ├── 5.2.1 Add to Cart

│   │   ├── 5.2.2 Cart Management

│   │   ├── 5.2.3 Checkout Process

│   │   └── 5.2.4 Order Integration (to Sales Service)

│   ├── 5.3 Review & Rating

│   │   ├── 5.3.1 Product Review

│   │   ├── 5.3.2 Product Rating

│   │   └── 5.3.3 Seller Rating

│   ├── 5.4 Promotion Management

│   │   ├── 5.4.1 Promotion Creation

│   │   ├── 5.4.2 Discount Management

│   │   └── 5.4.3 Flash Sale Management

│   └── 5.5 Marketplace Dashboard

│       ├── 5.5.1 Marketplace KPI Dashboard

│       └── 5.5.2 Marketplace Analytics

│

├── 6. Logistics Module (Minggu 8-11)

│   ├── 6.1 Shipment Management

│   │   ├── 6.1.1 Shipment Creation

│   │   ├── 6.1.2 Shipment Status Tracking

│   │   └── 6.1.3 Shipment Document Generation

│   │       ├── Picking List

│   │       ├── Packing List

│   │       └── Delivery Note

│   ├── 6.2 Tracking & POD

│   │   ├── 6.2.1 Delivery Tracking (Real-time)

│   │   ├── 6.2.2 Proof of Delivery (POD)

│   │   └── 6.2.3 Tracking History

│   ├── 6.3 Carrier Management

│   │   ├── 6.3.1 Carrier Registration

│   │   ├── 6.3.2 Rate Management

│   │   └── 6.3.3 Carrier API Integration

│   ├── 6.4 Route & Fleet Management

│   │   ├── 6.4.1 Route Optimization

│   │   └── 6.4.2 Fleet Management

│   └── 6.5 Logistics Dashboard

│       ├── 6.5.1 Logistics KPI Dashboard

│       ├── 6.5.2 Logistics Analytics

│       └── 6.5.3 Carrier Performance

│

├── 7. Portal Module (Minggu 10-13)

│   ├── 7.1 Customer Portal

│   │   ├── 7.1.1 Customer Login (MFA)

│   │   ├── 7.1.2 Customer Profile

│   │   ├── 7.1.3 Order History & Tracking

│   │   ├── 7.1.4 Product Catalog (B2B)

│   │   ├── 7.1.5 Place Order (B2B)

│   │   ├── 7.1.6 Invoice History

│   │   └── 7.1.7 Complaint Submission

│   ├── 7.2 Supplier Portal

│   │   ├── 7.2.1 Supplier Login (MFA)

│   │   ├── 7.2.2 Supplier Profile

│   │   ├── 7.2.3 PO View & Confirmation

│   │   ├── 7.2.4 Invoice Submission

│   │   ├── 7.2.5 Payment Status

│   │   └── 7.2.6 Performance Scorecard

│   └── 7.3 Portal Security

│       ├── 7.3.1 MFA Implementation

│       └── 7.3.2 Session Management

│

├── 8. Integration & Testing (Minggu 12-15)

│   ├── 8.1 System Integration

│   │   ├── 8.1.1 Integration with P-FNE-01 (Foundation)

│   │   ├── 8.1.2 Integration with P-FNE-03 (Supply Chain)

│   │   ├── 8.1.3 Integration with P-FNE-04 (Production)

│   │   └── 8.1.4 Integration with P-FNE-06 (Finance)

│   ├── 8.2 External Integration

│   │   ├── 8.2.1 Payment Gateway Integration

│   │   └── 8.2.2 Carrier API Integration

│   ├── 8.3 Performance Testing

│   │   ├── 8.3.1 Load Testing

│   │   ├── 8.3.2 Stress Testing

│   │   └── 8.3.3 Scalability Testing

│   ├── 8.4 Security Testing

│   │   ├── 8.4.1 Penetration Testing

│   │   ├── 8.4.2 Vulnerability Scanning

│   │   └── 8.4.3 Security Audit

│   └── 8.5 System Integration Testing

│       ├── 8.5.1 E2E Testing

│       └── 8.5.2 User Acceptance Testing

│

├── 9. Deployment & UAT (Minggu 16-18)

│   ├── 9.1 Deployment

│   │   ├── 9.1.1 Staging Environment Setup

│   │   ├── 9.1.2 Deployment to Staging

│   │   └── 9.1.3 Production Environment Setup

│   ├── 9.2 User Acceptance Testing

│   │   ├── 9.2.1 UAT Execution

│   │   └── 9.2.2 UAT Sign-off

│   ├── 9.3 Bug Fixing & Retest

│   │   ├── 9.3.1 Critical Bug Fixing

│   │   └── 9.3.2 Regression Testing

│   ├── 9.4 Production Deployment

│   │   ├── 9.4.1 Deployment to Production

│   │   └── 9.4.2 Go-Live Support

│   └── 9.5 Training

│       ├── 9.5.1 User Training Material

│       └── 9.5.2 End-User Training

│

└── 10. Project Closure (Minggu 19-20)

├── 10.1 Final Documentation

├── 10.2 Lessons Learned Workshop

├── 10.3 Project Closure Report

└── 10.4 Project Handover

B. WBS Dictionary

| WBS Code | Work Package | Description | Owner | Deliverable | Duration |
| --- | --- | --- | --- | --- | --- |
| 3.1.1 | Sales Order CRUD | Create, Read, Update, Delete Sales Order | Backend Dev | API endpoints + UI | 1 sprint |
| 3.1.2 | Sales Order Validation | Validasi customer, stock, credit limit | Backend Dev | Business logic | 0.5 sprint |
| 3.1.3 | Stock Reservation | Integrasi dengan Inventory Service | Backend Dev | Integration | 0.5 sprint |
| ... | ... | ... | ... | ... | ... |

#### 3.6.4 WBS Decomposition Guidelines

| Level | Deskripsi | Contoh |
| --- | --- | --- |
| Level 0 | Proyek secara keseluruhan | P-FNE-05 |
| Level 1 | Fase/Milestone utama | Sales Management Module |
| Level 2 | Komponen/Modul utama | Sales Order Management |
| Level 3 | Sub-komponen | Sales Order CRUD |
| Level 4 | Work Package | Create Sales Order API |

Rule: 100% Rule

- WBS mencakup 100% dari ruang lingkup proyek

- Tidak ada pekerjaan yang berada di luar WBS

- Setiap level mencakup 100% dari level di atasnya

#### 3.6.5 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Memimpin pembuatan WBS, memastikan completeness |
| Tech Lead | Memecah pekerjaan teknis ke level detail |
| Product Owner | Memastikan WBS mencakup semua fitur |
| Tim | Memberikan input untuk estimasi dan aktivitas |

### 3.7 Validate Scope

#### 3.7.1 Deskripsi Proses

Proses ini bertujuan untuk memvalidasi deliverables proyek dengan stakeholder untuk memastikan bahwa deliverables memenuhi kebutuhan dan ekspektasi. Proses ini terjadi di setiap Sprint Review dan UAT.

#### 3.7.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Management Plan | PMP |
| 2 | Requirements Documentation | Collect Requirements |
| 3 | Requirements Traceability Matrix | Collect Requirements |
| 4 | Validated Deliverables | Development & QA |

#### 3.7.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Accepted Deliverables | Deliverables yang disetujui oleh Product Owner |
| 2 | Change Requests | Permintaan perubahan berdasarkan feedback |
| 3 | Work Performance Information | Informasi kinerja validasi |
| 4 | Project Documents Updates | Update dokumen |

#### 3.7.4 Validation Process

A. Sprint Review Validation

| Elemen | Deskripsi |
| --- | --- |
| Waktu | Setiap akhir sprint (2 minggu) |
| Peserta | Product Owner, Stakeholder, Tim |
| Metode | Demo fitur yang selesai |
| Kriteria | Acceptance criteria terpenuhi |
| Output | Accepted/Rejected deliverables |

B. User Acceptance Testing (UAT)

| Elemen | Deskripsi |
| --- | --- |
| Waktu | Minggu 16-18 (Setelah integration testing) |
| Peserta | End users (Sales, Logistics, Customer Service) |
| Metode | Test execution by users |
| Kriteria | 100% critical path, 95% overall |
| Output | UAT Sign-off Report |

C. UAT Test Scenarios

| Modul | Test Scenarios | Jumlah Test Case |
| --- | --- | --- |
| Sales Management | End-to-end order process | 25 |
| CRM | Customer lifecycle management | 15 |
| Marketplace | Shopping journey | 20 |
| Logistics | Shipment process | 15 |
| Portal | User journeys | 20 |
| Total |  | 95 |

#### 3.7.5 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Product Owner | Memimpin sprint review, menyetujui deliverables |
| Project Manager | Memfasilitasi proses validasi |
| QA Lead | Menyiapkan UAT, mengelola testing |
| End Users | Melakukan UAT, memberikan feedback |
| Tech Lead | Memastikan readiness untuk demo/UAT |

### 3.8 Control Scope

#### 3.8.1 Deskripsi Proses

Proses ini bertujuan untuk mengendalikan perubahan terhadap ruang lingkup proyek. Proses ini memastikan bahwa hanya perubahan yang telah disetujui yang diimplementasikan.

#### 3.8.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Management Plan | PMP |
| 2 | Requirements Documentation | Collect Requirements |
| 3 | Work Performance Data | Monitoring |
| 4 | Change Requests | Siapapun |

#### 3.8.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Work Performance Information | Informasi kinerja scope |
| 2 | Change Requests | Permintaan perubahan scope |
| 3 | Project Management Plan Updates | Update baseline |
| 4 | Project Documents Updates | Update dokumen |

#### 3.8.4 Scope Control Process

Scope Change Request Process:

text

┌─────────────────────────────────────────────────────────────────────┐

│                    SCOPE CHANGE REQUEST PROCESS                    │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  [1] IDENTIFY CHANGE                                               │

│  │   - Siapapun dapat mengidentifikasi perubahan                   │

│  │   - Submit Scope Change Request Form                           │

│  │   - Berikan justifikasi dan dampak                             │

│  │   ↓                                                            │

│  [2] EVALUATE CHANGE                                              │

│  │   - PM & Tech Lead evaluasi dampak teknis                     │

│  │   - PO & BA evaluasi dampak bisnis                             │

│  │   - Estimasi dampak: scope, schedule, cost, quality           │

│  │   ↓                                                            │

│  [3] CCB REVIEW                                                   │

│  │   - CCB review change request                                 │

│  │   - Discussion dan voting                                     │

│  │   - Keputusan: Approved / Rejected / Deferred                 │

│  │   ↓                                                            │

│  [4] IMPLEMENT CHANGE                                             │

│  │   - Update baseline (scope, schedule, cost)                   │

│  │   - Update PMP dan dokumen terkait                            │

│  │   - Implementasi dalam pekerjaan proyek                       │

│  │   ↓                                                            │

│  [5] COMMUNICATE CHANGE                                          │

│      - Komunikasikan keputusan ke stakeholder                    │

│      - Update stakeholder expectations                           │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

#### 3.8.5 Scope Change Impact Assessment

| Aspek | Assessment Criteria | Decision Threshold |
| --- | --- | --- |
| Scope | % perubahan terhadap baseline | > 5% → CCB required |
| Schedule | Tambahan waktu (hari) | > 5 hari → CCB required |
| Cost | Tambahan biaya (Rp) | > Rp 50.000.000 → CCB required |
| Quality | Penurunan kualitas | Any decrease → CCB required |
| Risk | Risiko baru atau meningkat | Any new risk → CCB required |
| Resource | Sumber daya tambahan | Any new resource → CCB required |

#### 3.8.6 Scope Control Tools

| Tool | Fungsi |
| --- | --- |
| Requirements Traceability Matrix | Melacak requirements dari awal hingga delivery |
| WBS | Referensi untuk ruang lingkup yang disetujui |
| Change Request Form | Dokumentasi perubahan |
| CCB Meeting Minutes | Dokumentasi keputusan |
| JIRA | Tracking changes dan impact |

#### 3.8.7 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Mengelola scope control process, memfasilitasi evaluasi |
| Product Owner | Memastikan perubahan selaras dengan kebutuhan bisnis |
| Tech Lead | Mengevaluasi dampak teknis |
| CCB | Memutuskan perubahan |

## BAB 4: MANAJEMEN JADWAL PROYEK

### 4.1 Tujuan Manajemen Jadwal

Manajemen Jadwal Proyek bertujuan untuk memastikan bahwa proyek selesai tepat waktu dengan mengelola aktivitas, durasi, dan dependensi proyek secara efektif. Tujuan spesifiknya adalah:

- Mengidentifikasi semua aktivitas yang diperlukan untuk menyelesaikan proyek

- Mengurutkan aktivitas berdasarkan dependensi logis

- Mengestimasi durasi yang realistis untuk setiap aktivitas

- Mengembangkan jadwal proyek yang terintegrasi

- Mengendalikan jadwal untuk memastikan penyelesaian tepat waktu

### 4.2 Proses Manajemen Jadwal

Manajemen Jadwal Proyek terdiri dari 6 (enam) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Plan Schedule Management | Merencanakan bagaimana jadwal akan dikelola | Minggu 1-2 |
| 2 | Define Activities | Mengidentifikasi aktivitas spesifik | Minggu 2-3 |
| 3 | Sequence Activities | Mengurutkan aktivitas dengan dependensi | Minggu 2-3 |
| 4 | Estimate Activity Durations | Mengestimasi durasi setiap aktivitas | Minggu 2-3 |
| 5 | Develop Schedule | Mengembangkan jadwal proyek | Minggu 2-3 |
| 6 | Control Schedule | Mengendalikan perubahan jadwal | Berkelanjutan |

### 4.3 Plan Schedule Management

#### 4.3.1 Deskripsi Proses

Proses ini menghasilkan Schedule Management Plan yang mendefinisikan bagaimana jadwal akan dikembangkan, dimonitor, dan dikendalikan sepanjang proyek.

#### 4.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Scope Management Plan | PMP |
| 3 | Enterprise Environmental Factors | Organisasi |
| 4 | Organizational Process Assets | Organisasi |

#### 4.3.3 Output

Schedule Management Plan P-FNE-05

| Elemen | Deskripsi |
| --- | --- |
| Satuan Waktu | Minggu, Hari, Jam |
| Metode Estimasi | Story Points (Scrum) + Planning Poker |
| Baseline | Schedule Baseline yang disetujui |
| Tools | JIRA, Microsoft Project, Google Sheets |
| Jadwal Update | Harian (JIRA), Mingguan (Status Report) |
| Variance Threshold | > 10% deviation → Change Request |
| Reporting | Weekly Status Report, Monthly Report |
| Milestones | 11 milestones utama |

### 4.4 Define Activities

#### 4.4.1 Deskripsi Proses

Proses ini mengidentifikasi dan mendokumentasikan aktivitas-aktivitas spesifik yang harus dilakukan untuk menghasilkan deliverables proyek. Aktivitas dipecah dari WBS menjadi level work package.

#### 4.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Schedule Management Plan | PMP |
| 2 | Scope Baseline (WBS) | Create WBS |
| 3 | Enterprise Environmental Factors | Organisasi |
| 4 | Organizational Process Assets | Organisasi |

#### 4.4.3 Output

A. Activity List

| WBS | Activity ID | Activity Name | Description | Owner |
| --- | --- | --- | --- | --- |
| 1.1 | ACT-001 | Develop Project Charter | Menyusun dan mendapatkan approval project charter | PM |
| 1.2 | ACT-002 | Develop PMP | Menyusun Project Management Plan | PM |
| 1.3 | ACT-003 | Team Onboarding | Orientasi dan setup tim | PM |
| 1.4 | ACT-004 | Kickoff Meeting | Melakukan kickoff proyek | PM |
| 2.1.1 | ACT-005 | Stakeholder Interviews | Interview stakeholder kunci | BA |
| 2.1.2 | ACT-006 | Requirements Workshop | Workshop pengumpulan requirements | BA |
| 2.1.3 | ACT-007 | Requirements Documentation | Mendokumentasikan requirements | BA |
| 2.2.1 | ACT-008 | User Flow Design | Merancang user flow | UX |
| 2.2.2 | ACT-009 | Wireframe Design | Membuat wireframe | UX |
| 2.2.3 | ACT-010 | High-Fidelity Mockup (Web) | Desain web mockup | UX |
| 2.2.4 | ACT-011 | High-Fidelity Mockup (Mobile) | Desain mobile mockup | UX |
| 2.3.1 | ACT-012 | High-Level Architecture Design | Desain arsitektur sistem | Tech Lead |
| 2.3.2 | ACT-013 | API Design | Desain REST/GraphQL API | Tech Lead |
| 2.3.3 | ACT-014 | Event Schema Design | Desain event schema Kafka | Tech Lead |
| 2.3.4 | ACT-015 | Security Architecture Design | Desain arsitektur keamanan | Tech Lead |
| 2.4.1 | ACT-016 | Logical Data Model | Desain model data logis | Tech Lead |
| 2.4.2 | ACT-017 | Physical Data Model | Desain model data fisik | Tech Lead |
| 2.4.3 | ACT-018 | Database Migration Scripts | Script migrasi database | Tech Lead |
| 3.1.1 | ACT-019 | Sales Order CRUD | Implementasi CRUD Sales Order | Backend Dev |
| 3.1.2 | ACT-020 | Sales Order Validation | Implementasi validasi order | Backend Dev |
| 3.1.3 | ACT-021 | Stock Reservation Integration | Integrasi dengan Inventory Service | Backend Dev |
| 3.1.4 | ACT-022 | Sales Order Status Tracking | Implementasi status tracking | Backend Dev |
| 3.1.5 | ACT-023 | Sales Order Approval Workflow | Implementasi approval workflow | Backend Dev |
| 3.1.6 | ACT-024 | Sales Order Fulfillment | Implementasi fulfillment | Backend Dev |
| 3.2.1 | ACT-025 | Invoice Generation | Implementasi generate invoice | Backend Dev |
| 3.2.2 | ACT-026 | Invoice Status Tracking | Implementasi status invoice | Backend Dev |
| 3.2.3 | ACT-027 | Invoice Sending (Email) | Implementasi kirim invoice via email | Backend Dev |
| 3.3.1 | ACT-028 | Payment Recording | Implementasi pencatatan pembayaran | Backend Dev |
| 3.3.2 | ACT-029 | Payment Status Tracking | Implementasi status pembayaran | Backend Dev |
| 3.4.1 | ACT-030 | Sales Return Processing | Implementasi retur penjualan | Backend Dev |
| 3.4.2 | ACT-031 | Credit Note Generation | Implementasi credit note | Backend Dev |
| 3.4.3 | ACT-032 | Return Approval Workflow | Implementasi approval retur | Backend Dev |
| 3.5.1 | ACT-033 | Sales KPI Dashboard | Implementasi dashboard sales | Frontend Dev |
| 3.5.2 | ACT-034 | Sales Analytics Reports | Implementasi laporan analitik sales | Frontend/Backend |
| 4.1.1 | ACT-035 | Customer Registration | Implementasi registrasi customer | Backend Dev |
| 4.1.2 | ACT-036 | Customer Contact Management | Implementasi manajemen kontak | Backend Dev |
| 4.1.3 | ACT-037 | Customer Credit Management | Implementasi manajemen kredit | Backend Dev |
| 4.1.4 | ACT-038 | Customer Segmentation | Implementasi segmentasi customer | Backend Dev |
| 4.2.1 | ACT-039 | Customer Interaction Logging | Implementasi logging interaksi | Backend Dev |
| 4.2.2 | ACT-040 | Interaction History | Implementasi riwayat interaksi | Backend Dev |
| 4.3.1 | ACT-041 | Complaint Entry | Implementasi entry komplain | Backend Dev |
| 4.3.2 | ACT-042 | Complaint Workflow | Implementasi workflow komplain | Backend Dev |
| 4.3.3 | ACT-043 | Complaint Resolution | Implementasi resolusi komplain | Backend Dev |
| 4.4.1 | ACT-044 | Customer Purchase History | Implementasi riwayat pembelian | Backend Dev |
| 4.4.2 | ACT-045 | Customer 360 View | Implementasi Customer 360 View | Backend/Frontend |
| 4.4.3 | ACT-046 | CSAT Score & Retention Analysis | Implementasi CSAT dan retensi | Backend Dev |
| 4.5.1 | ACT-047 | CRM KPI Dashboard | Implementasi dashboard CRM | Frontend Dev |
| 5.1.1 | ACT-048 | Product Listing (CRUD) | Implementasi CRUD listing produk | Backend Dev |
| 5.1.2 | ACT-049 | Product Catalog | Implementasi katalog produk | Backend Dev |
| 5.1.3 | ACT-050 | Product Search (Elasticsearch) | Implementasi search dengan ES | Backend Dev |
| 5.1.4 | ACT-051 | Product Filter | Implementasi filter produk | Backend/Frontend |
| 5.1.5 | ACT-052 | Product Detail | Implementasi detail produk | Backend/Frontend |
| 5.2.1 | ACT-053 | Add to Cart | Implementasi tambah ke keranjang | Backend Dev |
| 5.2.2 | ACT-054 | Cart Management | Implementasi manajemen keranjang | Backend Dev |
| 5.2.3 | ACT-055 | Checkout Process | Implementasi proses checkout | Backend Dev |
| 5.2.4 | ACT-056 | Order Integration (to Sales Service) | Integrasi ke Sales Service | Backend Dev |
| 5.3.1 | ACT-057 | Product Review | Implementasi review produk | Backend Dev |
| 5.3.2 | ACT-058 | Product Rating | Implementasi rating produk | Backend Dev |
| 5.3.3 | ACT-059 | Seller Rating | Implementasi rating seller | Backend Dev |
| 5.4.1 | ACT-060 | Promotion Creation | Implementasi pembuatan promosi | Backend Dev |
| 5.4.2 | ACT-061 | Discount Management | Implementasi manajemen diskon | Backend Dev |
| 5.4.3 | ACT-062 | Flash Sale Management | Implementasi flash sale | Backend Dev |
| 5.5.1 | ACT-063 | Marketplace KPI Dashboard | Implementasi dashboard marketplace | Frontend Dev |
| 5.5.2 | ACT-064 | Marketplace Analytics | Implementasi analitik marketplace | Frontend/Backend |
| 6.1.1 | ACT-065 | Shipment Creation | Implementasi pembuatan shipment | Backend Dev |
| 6.1.2 | ACT-066 | Shipment Status Tracking | Implementasi status tracking | Backend Dev |
| 6.1.3 | ACT-067 | Shipment Document Generation | Implementasi dokumen pengiriman | Backend Dev |
| 6.2.1 | ACT-068 | Delivery Tracking (Real-time) | Implementasi tracking real-time | Backend Dev |
| 6.2.2 | ACT-069 | Proof of Delivery (POD) | Implementasi POD | Backend/Mobile |
| 6.2.3 | ACT-070 | Tracking History | Implementasi riwayat tracking | Backend Dev |
| 6.3.1 | ACT-071 | Carrier Registration | Implementasi registrasi carrier | Backend Dev |
| 6.3.2 | ACT-072 | Rate Management | Implementasi manajemen tarif | Backend Dev |
| 6.3.3 | ACT-073 | Carrier API Integration | Integrasi dengan API carrier | Backend Dev |
| 6.4.1 | ACT-074 | Route Optimization | Implementasi optimasi rute | Backend Dev |
| 6.4.2 | ACT-075 | Fleet Management | Implementasi manajemen armada | Backend Dev |
| 6.5.1 | ACT-076 | Logistics KPI Dashboard | Implementasi dashboard logistik | Frontend Dev |
| 6.5.2 | ACT-077 | Logistics Analytics | Implementasi analitik logistik | Frontend/Backend |
| 6.5.3 | ACT-078 | Carrier Performance | Implementasi performa carrier | Frontend/Backend |
| 7.1.1 | ACT-079 | Customer Login (MFA) | Implementasi login customer | Backend Dev |
| 7.1.2 | ACT-080 | Customer Profile | Implementasi profil customer | Backend/Frontend |
| 7.1.3 | ACT-081 | Order History & Tracking | Implementasi riwayat order | Backend/Frontend |
| 7.1.4 | ACT-082 | Product Catalog (B2B) | Implementasi katalog B2B | Backend/Frontend |
| 7.1.5 | ACT-083 | Place Order (B2B) | Implementasi pemesanan B2B | Backend/Frontend |
| 7.1.6 | ACT-084 | Invoice History | Implementasi riwayat invoice | Backend/Frontend |
| 7.1.7 | ACT-085 | Complaint Submission | Implementasi submit komplain | Backend/Frontend |
| 7.2.1 | ACT-086 | Supplier Login (MFA) | Implementasi login supplier | Backend Dev |
| 7.2.2 | ACT-087 | Supplier Profile | Implementasi profil supplier | Backend/Frontend |
| 7.2.3 | ACT-088 | PO View & Confirmation | Implementasi PO supplier | Backend/Frontend |
| 7.2.4 | ACT-089 | Invoice Submission | Implementasi submit invoice | Backend/Frontend |
| 7.2.5 | ACT-090 | Payment Status | Implementasi status pembayaran | Backend/Frontend |
| 7.2.6 | ACT-091 | Performance Scorecard | Implementasi scorecard supplier | Backend/Frontend |
| 7.3.1 | ACT-092 | MFA Implementation | Implementasi MFA | Backend Dev |
| 7.3.2 | ACT-093 | Session Management | Implementasi manajemen session | Backend Dev |
| 8.1.1 | ACT-094 | Integration with P-FNE-01 | Integrasi dengan Foundation | Backend Dev |
| 8.1.2 | ACT-095 | Integration with P-FNE-03 | Integrasi dengan Supply Chain | Backend Dev |
| 8.1.3 | ACT-096 | Integration with P-FNE-04 | Integrasi dengan Production | Backend Dev |
| 8.1.4 | ACT-097 | Integration with P-FNE-06 | Integrasi dengan Finance | Backend Dev |
| 8.2.1 | ACT-098 | Payment Gateway Integration | Integrasi payment gateway | Backend Dev |
| 8.2.2 | ACT-099 | Carrier API Integration | Integrasi API carrier | Backend Dev |
| 8.3.1 | ACT-100 | Load Testing | Melakukan load testing | QA |
| 8.3.2 | ACT-101 | Stress Testing | Melakukan stress testing | QA |
| 8.3.3 | ACT-102 | Scalability Testing | Melakukan scalability testing | QA |
| 8.4.1 | ACT-103 | Penetration Testing | Melakukan penetration testing | QA/Security |
| 8.4.2 | ACT-104 | Vulnerability Scanning | Melakukan vulnerability scan | QA/Security |
| 8.4.3 | ACT-105 | Security Audit | Melakukan audit keamanan | QA/Security |
| 8.5.1 | ACT-106 | E2E Testing | Melakukan end-to-end testing | QA |
| 8.5.2 | ACT-107 | UAT Execution | Menjalankan UAT dengan user | QA/Users |
| 9.1.1 | ACT-108 | Staging Environment Setup | Setup environment staging | DevOps |
| 9.1.2 | ACT-109 | Deployment to Staging | Deploy ke staging | DevOps |
| 9.1.3 | ACT-110 | Production Environment Setup | Setup environment production | DevOps |
| 9.2.1 | ACT-111 | UAT Execution (User) | UAT oleh end user | Users/QA |
| 9.2.2 | ACT-112 | UAT Sign-off | Tanda tangan UAT | PO/Users |
| 9.3.1 | ACT-113 | Critical Bug Fixing | Perbaikan bug critical | Dev |
| 9.3.2 | ACT-114 | Regression Testing | Testing regresi | QA |
| 9.4.1 | ACT-115 | Deployment to Production | Deploy ke production | DevOps |
| 9.4.2 | ACT-116 | Go-Live Support | Support saat go-live | All Team |
| 9.5.1 | ACT-117 | User Training Material | Materi pelatihan user | BA |
| 9.5.2 | ACT-118 | End-User Training | Pelatihan end user | BA/Trainer |
| 10.1 | ACT-119 | Final Documentation | Dokumentasi final | PM/Tech Lead |
| 10.2 | ACT-120 | Lessons Learned Workshop | Workshop lessons learned | PM |
| 10.3 | ACT-121 | Project Closure Report | Laporan penutupan proyek | PM |
| 10.4 | ACT-122 | Project Handover | Serah terima proyek | PM/Tech Lead |

B. Milestone List

| Milestone ID | Milestone Name | Deskripsi | Estimated Date |
| --- | --- | --- | --- |
| M1 | Project Kickoff | Kickoff proyek selesai | 16 Sep 2026 |
| M2 | Design Phase Complete | Requirements & Design selesai | 7 Okt 2026 |
| M3 | Sales Module Complete | Modul Sales selesai dikembangkan | 28 Okt 2026 |
| M4 | CRM Module Complete | Modul CRM selesai dikembangkan | 18 Nov 2026 |
| M5 | Marketplace Module Complete | Modul Marketplace selesai | 16 Des 2026 |
| M6 | Logistics Module Complete | Modul Logistics selesai | 6 Jan 2027 |
| M7 | Portal Module Complete | Modul Portal selesai | 27 Jan 2027 |
| M8 | Integration & Testing Complete | Integrasi & testing selesai | 17 Feb 2027 |
| M9 | UAT Complete | User Acceptance Testing selesai | 3 Mar 2027 |
| M10 | Production Deployment | Deploy ke production | 10 Mar 2027 |
| M11 | Project Closure | Proyek ditutup | 17 Mar 2027 |

#### 4.4.4 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Memastikan semua aktivitas teridentifikasi |
| Tech Lead | Memecah pekerjaan teknis ke level aktivitas |
| QA Lead | Mengidentifikasi aktivitas testing |
| Tim | Memberikan input aktivitas dari perspektif teknis |

### 4.5 Sequence Activities

#### 4.5.1 Deskripsi Proses

Proses ini mengidentifikasi dan mendokumentasikan hubungan ketergantungan (dependensi) antar aktivitas proyek. Urutan aktivitas menentukan jalur kritis proyek.

#### 4.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Schedule Management Plan | PMP |
| 2 | Activity List | Define Activities |
| 3 | Activity Attributes | Define Activities |
| 4 | Milestone List | Define Activities |

#### 4.5.3 Output

A. Activity Dependencies

| Aktivitas | Dependensi (Predecessor) | Jenis | Keterangan |
| --- | --- | --- | --- |
| ACT-001 (Project Charter) | - | Start | Tidak ada dependensi |
| ACT-002 (PMP) | ACT-001 | FS | PMP dibuat setelah Charter |
| ACT-004 (Kickoff) | ACT-001, ACT-002, ACT-003 | FS | Kickoff setelah semua siap |
| ACT-005 (Interviews) | ACT-004 | FS | Interview setelah kickoff |
| ACT-008 (User Flow) | ACT-007 | FS | User flow setelah requirements |
| ACT-009 (Wireframe) | ACT-008 | FS | Wireframe setelah user flow |
| ACT-010 (Web Mockup) | ACT-009 | FS | Mockup setelah wireframe |
| ACT-012 (Architecture) | ACT-007 | FS | Arsitektur setelah requirements |
| ACT-016 (Data Model) | ACT-012 | FS | Data model setelah arsitektur |
| ACT-019 (Sales Order CRUD) | ACT-010, ACT-016 | FS | Development setelah design |
| ACT-035 (Customer Registration) | ACT-010, ACT-016 | FS | Development setelah design |
| ACT-048 (Product Listing) | ACT-010, ACT-016 | FS | Development setelah design |
| ACT-065 (Shipment Creation) | ACT-010, ACT-016 | FS | Development setelah design |
| ACT-079 (Customer Login) | ACT-010, ACT-016 | FS | Development setelah design |
| ACT-094 (Integration P-FNE-01) | ACT-019, ACT-035, ACT-048, ACT-065 | FS | Setelah modul siap |
| ACT-100 (Load Testing) | ACT-106 | FS | Setelah E2E testing |
| ACT-111 (UAT Execution) | ACT-106 | FS | Setelah E2E testing |
| ACT-115 (Production Deployment) | ACT-112 | FS | Setelah UAT sign-off |
| ACT-120 (Lessons Learned) | ACT-115 | FS | Setelah deployment |

B. Dependency Types

| Jenis | Deskripsi | Contoh |
| --- | --- | --- |
| FS (Finish-to-Start) | Aktivitas B dimulai setelah Aktivitas A selesai | Design → Development |
| FF (Finish-to-Finish) | Aktivitas B selesai setelah Aktivitas A selesai | Development → Testing |
| SS (Start-to-Start) | Aktivitas B dimulai setelah Aktivitas A dimulai | Development → Documentation |
| SF (Start-to-Finish) | Aktivitas B selesai setelah Aktivitas A dimulai | Jarang digunakan |

C. Critical Path

Jalur kritis (Critical Path) adalah urutan aktivitas dengan total float = 0. Keterlambatan pada jalur kritis akan menunda penyelesaian proyek.

text

Critical Path:

M1 (Kickoff) → Design → Sales Module → CRM Module → Marketplace Module →

Logistics Module → Portal Module → Integration → Testing → UAT → Deployment → M11 (Closure)

Total Duration: 22 Minggu

#### 4.5.4 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Mengidentifikasi dependensi, menyusun network diagram |
| Tech Lead | Mengidentifikasi dependensi teknis |
| QA Lead | Mengidentifikasi dependensi testing |

### 4.6 Estimate Activity Durations

#### 4.6.1 Deskripsi Proses

Proses ini mengestimasi durasi yang dibutuhkan untuk menyelesaikan setiap aktivitas. Estimasi menggunakan kombinasi teknik: Planning Poker (untuk story points) dan Analogous Estimating (untuk aktivitas non-development).

#### 4.6.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Schedule Management Plan | PMP |
| 2 | Activity List | Define Activities |
| 3 | Activity Attributes | Define Activities |
| 4 | Resource Requirements | Resource Management |
| 5 | Project Calendars | Organisasi |

#### 4.6.3 Output

A. Activity Duration Estimates

| Activity ID | Activity Name | Story Points | Duration (Days) | Resource |
| --- | --- | --- | --- | --- |
| ACT-001 | Develop Project Charter | - | 3 | PM |
| ACT-002 | Develop PMP | - | 5 | PM |
| ACT-003 | Team Onboarding | - | 3 | PM, HR |
| ACT-004 | Kickoff Meeting | - | 1 | All |
| ACT-005 | Stakeholder Interviews | - | 3 | BA |
| ACT-006 | Requirements Workshop | - | 2 | BA, PO, Stakeholder |
| ACT-007 | Requirements Documentation | - | 5 | BA |
| ACT-008 | User Flow Design | - | 3 | UX |
| ACT-009 | Wireframe Design | - | 5 | UX |
| ACT-010 | High-Fidelity Mockup (Web) | - | 5 | UX |
| ACT-011 | High-Fidelity Mockup (Mobile) | - | 3 | UX |
| ACT-012 | High-Level Architecture | - | 3 | Tech Lead |
| ACT-013 | API Design | - | 5 | Tech Lead |
| ACT-014 | Event Schema Design | - | 3 | Tech Lead |
| ACT-015 | Security Architecture | - | 3 | Tech Lead |
| ACT-016 | Logical Data Model | - | 3 | Tech Lead |
| ACT-017 | Physical Data Model | - | 3 | Tech Lead |
| ACT-018 | Database Migration Scripts | - | 3 | Backend Dev |
| ACT-019 | Sales Order CRUD | 8 | 3 | Backend Dev |
| ACT-020 | Sales Order Validation | 5 | 2 | Backend Dev |
| ACT-021 | Stock Reservation Integration | 5 | 2 | Backend Dev |
| ACT-022 | Sales Order Status Tracking | 5 | 2 | Backend Dev |
| ACT-023 | Sales Order Approval Workflow | 8 | 3 | Backend Dev |
| ACT-024 | Sales Order Fulfillment | 5 | 2 | Backend Dev |
| ACT-025 | Invoice Generation | 8 | 3 | Backend Dev |
| ACT-026 | Invoice Status Tracking | 3 | 1 | Backend Dev |
| ACT-027 | Invoice Sending (Email) | 3 | 1 | Backend Dev |
| ACT-028 | Payment Recording | 5 | 2 | Backend Dev |
| ACT-029 | Payment Status Tracking | 3 | 1 | Backend Dev |
| ACT-030 | Sales Return Processing | 5 | 2 | Backend Dev |
| ACT-031 | Credit Note Generation | 5 | 2 | Backend Dev |
| ACT-032 | Return Approval Workflow | 5 | 2 | Backend Dev |
| ACT-033 | Sales KPI Dashboard | 8 | 3 | Frontend Dev |
| ACT-034 | Sales Analytics Reports | 8 | 3 | Frontend/Backend |
| ACT-035 | Customer Registration | 8 | 3 | Backend Dev |
| ACT-036 | Customer Contact Management | 5 | 2 | Backend Dev |
| ACT-037 | Customer Credit Management | 5 | 2 | Backend Dev |
| ACT-038 | Customer Segmentation | 5 | 2 | Backend Dev |
| ACT-039 | Customer Interaction Logging | 5 | 2 | Backend Dev |
| ACT-040 | Interaction History | 5 | 2 | Backend Dev |
| ACT-041 | Complaint Entry | 5 | 2 | Backend Dev |
| ACT-042 | Complaint Workflow | 8 | 3 | Backend Dev |
| ACT-043 | Complaint Resolution | 5 | 2 | Backend Dev |
| ACT-044 | Customer Purchase History | 5 | 2 | Backend Dev |
| ACT-045 | Customer 360 View | 13 | 5 | Backend/Frontend |
| ACT-046 | CSAT Score & Retention | 5 | 2 | Backend Dev |
| ACT-047 | CRM KPI Dashboard | 8 | 3 | Frontend Dev |
| ACT-048 | Product Listing (CRUD) | 8 | 3 | Backend Dev |
| ACT-049 | Product Catalog | 8 | 3 | Backend Dev |
| ACT-050 | Product Search (ES) | 13 | 5 | Backend Dev |
| ACT-051 | Product Filter | 5 | 2 | Backend/Frontend |
| ACT-052 | Product Detail | 5 | 2 | Backend/Frontend |
| ACT-053 | Add to Cart | 5 | 2 | Backend Dev |
| ACT-054 | Cart Management | 5 | 2 | Backend Dev |
| ACT-055 | Checkout Process | 8 | 3 | Backend Dev |
| ACT-056 | Order Integration | 5 | 2 | Backend Dev |
| ACT-057 | Product Review | 5 | 2 | Backend Dev |
| ACT-058 | Product Rating | 3 | 1 | Backend Dev |
| ACT-059 | Seller Rating | 3 | 1 | Backend Dev |
| ACT-060 | Promotion Creation | 5 | 2 | Backend Dev |
| ACT-061 | Discount Management | 5 | 2 | Backend Dev |
| ACT-062 | Flash Sale Management | 5 | 2 | Backend Dev |
| ACT-063 | Marketplace KPI Dashboard | 8 | 3 | Frontend Dev |
| ACT-064 | Marketplace Analytics | 8 | 3 | Frontend/Backend |
| ACT-065 | Shipment Creation | 8 | 3 | Backend Dev |
| ACT-066 | Shipment Status Tracking | 5 | 2 | Backend Dev |
| ACT-067 | Shipment Document Generation | 8 | 3 | Backend Dev |
| ACT-068 | Delivery Tracking (Real-time) | 8 | 3 | Backend Dev |
| ACT-069 | Proof of Delivery (POD) | 8 | 3 | Backend/Mobile |
| ACT-070 | Tracking History | 5 | 2 | Backend Dev |
| ACT-071 | Carrier Registration | 5 | 2 | Backend Dev |
| ACT-072 | Rate Management | 5 | 2 | Backend Dev |
| ACT-073 | Carrier API Integration | 8 | 3 | Backend Dev |
| ACT-074 | Route Optimization | 13 | 5 | Backend Dev |
| ACT-075 | Fleet Management | 5 | 2 | Backend Dev |
| ACT-076 | Logistics KPI Dashboard | 8 | 3 | Frontend Dev |
| ACT-077 | Logistics Analytics | 8 | 3 | Frontend/Backend |
| ACT-078 | Carrier Performance | 8 | 3 | Frontend/Backend |
| ACT-079 | Customer Login (MFA) | 8 | 3 | Backend Dev |
| ACT-080 | Customer Profile | 5 | 2 | Backend/Frontend |
| ACT-081 | Order History & Tracking | 8 | 3 | Backend/Frontend |
| ACT-082 | Product Catalog (B2B) | 5 | 2 | Backend/Frontend |
| ACT-083 | Place Order (B2B) | 8 | 3 | Backend/Frontend |
| ACT-084 | Invoice History | 5 | 2 | Backend/Frontend |
| ACT-085 | Complaint Submission | 5 | 2 | Backend/Frontend |
| ACT-086 | Supplier Login (MFA) | 8 | 3 | Backend Dev |
| ACT-087 | Supplier Profile | 5 | 2 | Backend/Frontend |
| ACT-088 | PO View & Confirmation | 8 | 3 | Backend/Frontend |
| ACT-089 | Invoice Submission | 5 | 2 | Backend/Frontend |
| ACT-090 | Payment Status | 3 | 1 | Backend/Frontend |
| ACT-091 | Performance Scorecard | 8 | 3 | Backend/Frontend |
| ACT-092 | MFA Implementation | 5 | 2 | Backend Dev |
| ACT-093 | Session Management | 5 | 2 | Backend Dev |
| ACT-094 | Integration P-FNE-01 | 8 | 3 | Backend Dev |
| ACT-095 | Integration P-FNE-03 | 8 | 3 | Backend Dev |
| ACT-096 | Integration P-FNE-04 | 5 | 2 | Backend Dev |
| ACT-097 | Integration P-FNE-06 | 5 | 2 | Backend Dev |
| ACT-098 | Payment Gateway Integration | 8 | 3 | Backend Dev |
| ACT-099 | Carrier API Integration | 8 | 3 | Backend Dev |
| ACT-100 | Load Testing | - | 3 | QA |
| ACT-101 | Stress Testing | - | 2 | QA |
| ACT-102 | Scalability Testing | - | 2 | QA |
| ACT-103 | Penetration Testing | - | 3 | QA/Security |
| ACT-104 | Vulnerability Scanning | - | 2 | QA/Security |
| ACT-105 | Security Audit | - | 2 | QA/Security |
| ACT-106 | E2E Testing | - | 5 | QA |
| ACT-107 | UAT Execution | - | 5 | QA/Users |
| ACT-108 | Staging Environment Setup | - | 2 | DevOps |
| ACT-109 | Deployment to Staging | - | 1 | DevOps |
| ACT-110 | Production Environment Setup | - | 3 | DevOps |
| ACT-111 | UAT Execution (User) | - | 5 | Users/QA |
| ACT-112 | UAT Sign-off | - | 1 | PO/Users |
| ACT-113 | Critical Bug Fixing | - | 5 | Dev |
| ACT-114 | Regression Testing | - | 3 | QA |
| ACT-115 | Deployment to Production | - | 2 | DevOps |
| ACT-116 | Go-Live Support | - | 3 | All Team |
| ACT-117 | User Training Material | - | 5 | BA |
| ACT-118 | End-User Training | - | 3 | BA/Trainer |
| ACT-119 | Final Documentation | - | 5 | PM/Tech Lead |
| ACT-120 | Lessons Learned Workshop | - | 1 | PM |
| ACT-121 | Project Closure Report | - | 3 | PM |
| ACT-122 | Project Handover | - | 2 | PM/Tech Lead |

B. Total Story Points per Modul

| Modul | Story Points |
| --- | --- |
| Sales Management | 120 |
| CRM | 90 |
| Marketplace | 180 |
| Logistics | 160 |
| Portal | 110 |
| Integration & Testing | 80 |
| Total | 740 |

C. Velocity Estimation

| Sprint | Velocity (Story Points) |
| --- | --- |
| Sprint 1 | 50 |
| Sprint 2 | 70 |
| Sprint 3 | 80 |
| Sprint 4 | 85 |
| Sprint 5 | 85 |
| Sprint 6 | 85 |
| Sprint 7 | 85 |
| Sprint 8 | 85 |
| Sprint 9 | 80 |
| Total | 705 |

#### 4.6.4 Estimasi Teknik

| Teknik | Deskripsi | Digunakan Untuk |
| --- | --- | --- |
| Planning Poker | Tim memberikan estimasi story points | Development activities |
| Analogous Estimating | Estimasi berdasarkan proyek sebelumnya | Non-development activities |
| Three-Point Estimating | Optimistic, Pessimistic, Most Likely | High-uncertainty activities |
| Expert Judgment | Konsultasi dengan expert | Complex activities |

#### 4.6.5 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Memfasilitasi proses estimasi, memastikan konsistensi |
| Tech Lead | Memberikan estimasi teknis |
| Tim | Memberikan estimasi untuk aktivitas yang dikerjakan |

### 4.7 Develop Schedule

#### 4.7.1 Deskripsi Proses

Proses ini mengembangkan jadwal proyek yang terintegrasi dengan mengkombinasikan aktivitas, durasi, dependensi, dan sumber daya. Hasilnya adalah Schedule Baseline yang akan digunakan untuk monitoring dan kontrol.

#### 4.7.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Schedule Management Plan | PMP |
| 2 | Activity List | Define Activities |
| 3 | Activity Attributes | Define Activities |
| 4 | Project Network Diagrams | Sequence Activities |
| 5 | Activity Duration Estimates | Estimate Activity Durations |
| 6 | Resource Requirements | Resource Management |
| 7 | Project Calendars | Organisasi |

#### 4.7.3 Output

A. Project Schedule

Gantt Chart (Ringkasan 5 Bulan):

text

Task                          | Sep  | Okt  | Nov  | Des  | Jan  | Feb  | Mar  |

------------------------------|------|------|------|------|------|------|------|

1. Project Initiation         | ████ |      |      |      |      |      |      |

M1: Kickoff (16/9)         |  ●   |      |      |      |      |      |      |

|      |      |      |      |      |      |      |

2. Requirements & Design      | ████████ |      |      |      |      |      |      |

M2: Design Complete (7/10) |      |  ●   |      |      |      |      |      |

|      |      |      |      |      |      |      |

3. Sales Module               |      | ████████ |      |      |      |      |      |

M3: Sales Complete (28/10) |      |      |  ●   |      |      |      |      |

|      |      |      |      |      |      |      |

4. CRM Module                 |      | ████████ |      |      |      |      |      |

M4: CRM Complete (18/11)   |      |      |      |  ●   |      |      |      |

|      |      |      |      |      |      |      |

5. Marketplace Module         |      |      | ██████████ |      |      |      |      |

M5: Marketplace Complete   |      |      |      |      |  ●   |      |      |

|      |      |      |      |      |      |      |

6. Logistics Module           |      |      |      | ████████ |      |      |      |

M6: Logistics Complete     |      |      |      |      |      |  ●   |      |

|      |      |      |      |      |      |      |

7. Portal Module              |      |      |      | ████████ |      |      |      |

M7: Portal Complete        |      |      |      |      |      |  ●   |      |

|      |      |      |      |      |      |      |

8. Integration & Testing      |      |      |      |      | ████████ |      |      |

M8: Test Complete          |      |      |      |      |      |      |  ●   |

|      |      |      |      |      |      |      |

9. UAT & Deployment           |      |      |      |      |      | ██████████ |      |

M9: UAT Complete (3/3)     |      |      |      |      |      |      |  ●   |

M10: Prod Deploy (10/3)    |      |      |      |      |      |      |      |●

|      |      |      |      |      |      |      |

10. Project Closure           |      |      |      |      |      |      | ████ |

M11: Closure (17/3)        |      |      |      |      |      |      |     ●

B. Sprint Schedule

| Sprint | Date Range | Focus | Story Points | Owner |
| --- | --- | --- | --- | --- |
| Sprint 0 | 16-27 Sep 2026 | Setup & Foundation | - | All |
| Sprint 1 | 28 Sep - 9 Okt 2026 | Sales Module - Part 1 | 50 | Backend |
| Sprint 2 | 12-23 Okt 2026 | Sales Module - Part 2 | 70 | Backend |
| Sprint 3 | 26 Okt - 6 Nov 2026 | CRM Module | 80 | Backend |
| Sprint 4 | 9-20 Nov 2026 | Marketplace - Part 1 | 85 | Backend/Frontend |
| Sprint 5 | 23 Nov - 4 Des 2026 | Marketplace - Part 2 | 85 | Backend/Frontend |
| Sprint 6 | 7-18 Des 2026 | Logistics Module | 85 | Backend/Frontend |
| Sprint 7 | 4-15 Jan 2027 | Portal Module | 85 | Backend/Frontend |
| Sprint 8 | 18-29 Jan 2027 | Integration | 85 | All |
| Sprint 9 | 1-12 Feb 2027 | Testing & UAT | 80 | All |

C. Resource Histogram

text

Resource Usage Over Time:

| Minggu | PM | BA | UX | TL | BE | FE | MB | QA | DevOps |

|--------|----|----|----|----|----|----|----|----|--------|

| 1-2    | 100| 100| 100| 100| 50 | 50 | 0  | 50 | 50     |

| 3-5    | 100| 100| 100| 100| 100| 100| 50 | 50 | 50     |

| 6-8    | 100| 80 | 80 | 100| 100| 100| 100| 50 | 50     |

| 9-11   | 100| 60 | 50 | 100| 100| 100| 100| 100| 50     |

| 12-14  | 100| 50 | 0  | 100| 100| 100| 100| 100| 50     |

| 15-17  | 100| 50 | 0  | 100| 80 | 80 | 50 | 100| 100    |

| 18-20  | 100| 100| 0  | 100| 50 | 50 | 0  | 100| 100    |

| 21-22  | 100| 50 | 0  | 80 | 0  | 0  | 0  | 50 | 50     |

D. Schedule Baseline

Schedule Baseline adalah jadwal yang disetujui yang akan digunakan sebagai acuan untuk mengukur kinerja proyek. Baseline mencakup:

- Start Date: 16 September 2026

- End Date: 17 Maret 2027

- Total Duration: 22 Minggu (5 Bulan)

- Milestones: 11 milestones

- Critical Path: Seperti yang telah didefinisikan

#### 4.7.4 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Menyusun jadwal terintegrasi, mendapatkan approval |
| Tech Lead | Memastikan jadwal teknis realistis |
| Product Owner | Menyetujui jadwal berdasarkan prioritas |
| Tim | Berkomitmen pada jadwal sprint |

### 4.8 Control Schedule

#### 4.8.1 Deskripsi Proses

Proses ini bertujuan untuk memonitor status proyek dan mengendalikan perubahan terhadap schedule baseline. Proses ini memastikan bahwa proyek tetap on-track dan mengambil tindakan korektif jika diperlukan.

#### 4.8.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Management Plan | PMP |
| 2 | Schedule Baseline | Develop Schedule |
| 3 | Work Performance Data | Monitoring |
| 4 | Change Requests | CCB |

#### 4.8.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Work Performance Information | Informasi kinerja jadwal |
| 2 | Schedule Forecasts | Prediksi kinerja jadwal |
| 3 | Change Requests | Permintaan perubahan jadwal |
| 4 | Project Management Plan Updates | Update baseline |

#### 4.8.4 Schedule Monitoring Tools

A. Sprint Burndown Chart

Sprint Burndown Chart digunakan untuk memonitor progress setiap sprint:

text

Burndown Chart - Sprint X

│

│  Points

│  80 │  ●

│     │     ●

│  60 │        ●

│     │           ●

│  40 │              ●

│     │                 ●

│  20 │                    ●

│     │                       ●

│   0 │────────────────────────●

│     └──────────────────────────

│      Mon Tue Wed Thu Fri Mon Tue Wed Thu Fri

│

│  ─── Ideal Burndown

│  ●●● Actual Burndown

B. Velocity Tracking

| Sprint | Planned Velocity | Actual Velocity | Variance |
| --- | --- | --- | --- |
| Sprint 1 | 50 | 45 | -10% |
| Sprint 2 | 70 | 72 | +3% |
| Sprint 3 | 80 | 78 | -2.5% |
| Sprint 4 | 85 | 88 | +3.5% |
| Sprint 5 | 85 | 82 | -3.5% |
| Sprint 6 | 85 | 86 | +1% |
| Sprint 7 | 85 | 84 | -1% |
| Sprint 8 | 85 | 83 | -2% |
| Sprint 9 | 80 | 80 | 0% |

C. Critical Path Monitoring

| Aktivitas | Planned Start | Actual Start | Planned End | Actual End | Variance |
| --- | --- | --- | --- | --- | --- |
| ACT-019 (Sales Order CRUD) | 28/9 | 28/9 | 30/9 | 30/9 | 0 |
| ACT-035 (Customer Registration) | 26/10 | 26/10 | 28/10 | 28/10 | 0 |
| ACT-048 (Product Listing) | 9/11 | 9/11 | 11/11 | 11/11 | 0 |
| ACT-065 (Shipment Creation) | 7/12 | 7/12 | 9/12 | 9/12 | 0 |
| ACT-079 (Customer Login) | 4/1 | 4/1 | 6/1 | 6/1 | 0 |
| ACT-094 (Integration) | 18/1 | 18/1 | 20/1 | 20/1 | 0 |

#### 4.8.5 Schedule Variance Thresholds

| Kategori | Threshold | Tindakan |
| --- | --- | --- |
| Green | Variance < 5% | Monitoring normal |
| Yellow | Variance 5-15% | Analisis penyebab, mitigasi |
| Red | Variance > 15% | Formal Change Request, escalation |

#### 4.8.6 Schedule Recovery Strategies

| Strategi | Deskripsi | Dampak |
| --- | --- | --- |
| Crashing | Menambah sumber daya | Meningkatkan biaya |
| Fast Tracking | Melakukan aktivitas paralel | Meningkatkan risiko |
| Scope Reduction | Mengurangi fitur non-esensial | Mengurangi ruang lingkup |
| Overtime | Lembur | Meningkatkan biaya, risiko burnout |
| Resource Leveling | Mengoptimalkan alokasi sumber daya | Minimal |

#### 4.8.7 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Memonitor jadwal, menganalisis variance, mengambil tindakan |
| Tech Lead | Memonitor progress teknis |
| Tim | Melaporkan progress harian, mengidentifikasi delay |
| QA Lead | Memonitor progress testing |

## BAB 5: MANAJEMEN BIAYA PROYEK

### 5.1 Tujuan Manajemen Biaya

Manajemen Biaya Proyek bertujuan untuk memastikan bahwa proyek selesai dalam anggaran yang disetujui dengan mengelola perencanaan, estimasi, penganggaran, dan pengendalian biaya secara efektif. Tujuan spesifiknya adalah:

- Mengestimasi biaya yang realistis untuk setiap aktivitas proyek

- Mengembangkan anggaran proyek yang komprehensif

- Mengendalikan biaya untuk memastikan tidak melebihi anggaran

- Memberikan laporan keuangan yang akurat kepada stakeholder

- Mengoptimalkan penggunaan sumber daya untuk efisiensi biaya

### 5.2 Metodologi Estimasi Biaya

Proyek ini menggunakan Activity Based Costing (ABC) untuk mengestimasi biaya secara akurat dengan mengalokasikan biaya ke setiap aktivitas berdasarkan konsumsi sumber daya. Tarif personil mengacu pada Standar Tarif Inkindo 2026 untuk industri konsultan dan pengembangan perangkat lunak.

#### 5.2.1 Tarif Personil Berdasarkan Inkindo 2026

Berdasarkan Standar Tarif Inkindo 2026 untuk jasa konsultansi dan pengembangan sistem, berikut adalah tarif personil yang digunakan:

| No | Level Personil | Kualifikasi | Tarif/Jam (Rp) | Tarif/Hari (Rp) | Tarif/Bulan (Rp) |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Manager | S2/S1 dengan pengalaman 8+ tahun di manajemen proyek IT | 750.000 | 6.000.000 | 120.000.000 |
| 2 | Tech Lead / Arsitek | S2/S1 dengan pengalaman 10+ tahun di arsitektur software | 850.000 | 6.800.000 | 136.000.000 |
| 3 | Senior Backend Developer | S1 dengan pengalaman 5-8 tahun di backend development | 600.000 | 4.800.000 | 96.000.000 |
| 4 | Senior Frontend Developer | S1 dengan pengalaman 5-8 tahun di frontend development | 575.000 | 4.600.000 | 92.000.000 |
| 5 | Mid Backend Developer | S1 dengan pengalaman 3-5 tahun di backend development | 400.000 | 3.200.000 | 64.000.000 |
| 6 | Mid Frontend Developer | S1 dengan pengalaman 3-5 tahun di frontend development | 375.000 | 3.000.000 | 60.000.000 |
| 7 | Mobile Developer | S1 dengan pengalaman 3-5 tahun di mobile development | 425.000 | 3.400.000 | 68.000.000 |
| 8 | Senior QA Engineer | S1 dengan pengalaman 5-8 tahun di quality assurance | 500.000 | 4.000.000 | 80.000.000 |
| 9 | Mid QA Engineer | S1 dengan pengalaman 3-5 tahun di quality assurance | 350.000 | 2.800.000 | 56.000.000 |
| 10 | Business Analyst | S1 dengan pengalaman 4-6 tahun di analisis bisnis IT | 475.000 | 3.800.000 | 76.000.000 |
| 11 | UX/UI Designer | S1 dengan pengalaman 4-6 tahun di UX/UI design | 450.000 | 3.600.000 | 72.000.000 |
| 12 | DevOps Engineer | S1 dengan pengalaman 4-6 tahun di DevOps | 500.000 | 4.000.000 | 80.000.000 |

#### 5.2.2 Komponen Biaya Proyek

Komponen biaya proyek dibagi menjadi beberapa kategori:

| Kategori | Komponen | Metode Perhitungan |
| --- | --- | --- |
| Direct Labor | Gaji personil berdasarkan role dan durasi | Tarif × Durasi (Jam/Hari/Bulan) |
| Overhead | Fasilitas, utilitas, administrasi | 20% dari Direct Labor |
| Infrastructure | Cloud, server, software licenses | Biaya aktual vendor |
| Third-party Services | Payment gateway, carrier API | Biaya aktual vendor |
| Travel & Meeting | Transportasi, akomodasi | Biaya aktual |
| Training | Pelatihan tim dan user | Biaya aktual |
| Contingency | Cadangan untuk risiko | 10% dari total |

### 5.3 Proses Manajemen Biaya

Manajemen Biaya Proyek terdiri dari 4 (empat) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Plan Cost Management | Merencanakan bagaimana biaya akan dikelola | Minggu 1-2 |
| 2 | Estimate Costs | Mengestimasi biaya setiap aktivitas | Minggu 2-3 |
| 3 | Determine Budget | Menentukan anggaran proyek secara keseluruhan | Minggu 2-3 |
| 4 | Control Costs | Mengendalikan biaya selama proyek berjalan | Berkelanjutan |

### 5.4 Plan Cost Management

#### 5.4.1 Deskripsi Proses

Proses ini menghasilkan Cost Management Plan yang mendefinisikan bagaimana biaya akan direncanakan, diestimasi, dianggarkan, dan dikendalikan.

#### 5.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Schedule Management Plan | PMP |
| 3 | Resource Management Plan | PMP |
| 4 | Risk Management Plan | PMP |
| 5 | Enterprise Environmental Factors | Organisasi |

#### 5.4.3 Output

Cost Management Plan P-FNE-05

| Elemen | Deskripsi |
| --- | --- |
| Satuan Biaya | Rupiah (IDR) |
| Akurasi Estimasi | ± 10% |
| Metode Estimasi | Activity Based Costing (ABC) |
| Tarif Personil | Inkindo 2026 |
| Baseline | Cost Baseline yang disetujui |
| Tools | Microsoft Excel, JIRA Time Tracking |
| Pengendalian | Monthly cost review, variance analysis |
| Variance Threshold | > 10% deviation → Change Request |
| Reporting | Monthly Financial Report |

### 5.5 Estimate Costs - Activity Based Costing (ABC)

#### 5.5.1 Deskripsi Proses

Proses ini mengestimasi biaya untuk setiap aktivitas berdasarkan konsumsi sumber daya (personil, material, peralatan). Estimasi menggunakan Activity Based Costing (ABC) untuk alokasi biaya yang lebih akurat.

#### 5.5.2 Metode Estimasi ABC

Langkah 1: Identifikasi Aktivitas

Semua aktivitas telah diidentifikasi dalam Activity List (BAB 4).

Langkah 2: Identifikasi Sumber Daya untuk Setiap Aktivitas

Setiap aktivitas membutuhkan sumber daya personil dengan level tertentu dan durasi tertentu.

Langkah 3: Alokasi Biaya ke Aktivitas

Biaya aktivitas = (Tarif personil × Durasi) + Biaya material/peralatan

Langkah 4: Akumulasi Biaya

Akumulasi semua biaya aktivitas menjadi total biaya proyek.

#### 5.5.3 Estimasi Biaya Personil per Aktivitas

Berikut adalah estimasi biaya personil untuk setiap aktivitas utama menggunakan metode ABC dengan tarif Inkindo 2026:

A. Project Initiation

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-001: Develop Project Charter | PM | Project Manager | 3 | 6.000.000 | 18.000.000 |
| ACT-002: Develop PMP | PM | Project Manager | 5 | 6.000.000 | 30.000.000 |
| ACT-003: Team Onboarding | PM | Project Manager | 3 | 6.000.000 | 18.000.000 |
| ACT-004: Kickoff Meeting | PM | Project Manager | 1 | 6.000.000 | 6.000.000 |
| Subtotal Initiation |  |  |  |  | 72.000.000 |

B. Requirements & Design

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-005: Stakeholder Interviews | BA | Business Analyst | 3 | 3.800.000 | 11.400.000 |
| ACT-006: Requirements Workshop | BA | Business Analyst | 2 | 3.800.000 | 7.600.000 |
| ACT-007: Requirements Documentation | BA | Business Analyst | 5 | 3.800.000 | 19.000.000 |
| ACT-008: User Flow Design | UX | UX/UI Designer | 3 | 3.600.000 | 10.800.000 |
| ACT-009: Wireframe Design | UX | UX/UI Designer | 5 | 3.600.000 | 18.000.000 |
| ACT-010: High-Fidelity Mockup (Web) | UX | UX/UI Designer | 5 | 3.600.000 | 18.000.000 |
| ACT-011: High-Fidelity Mockup (Mobile) | UX | UX/UI Designer | 3 | 3.600.000 | 10.800.000 |
| ACT-012: High-Level Architecture | TL | Tech Lead/Arsitek | 3 | 6.800.000 | 20.400.000 |
| ACT-013: API Design | TL | Tech Lead/Arsitek | 5 | 6.800.000 | 34.000.000 |
| ACT-014: Event Schema Design | TL | Tech Lead/Arsitek | 3 | 6.800.000 | 20.400.000 |
| ACT-015: Security Architecture | TL | Tech Lead/Arsitek | 3 | 6.800.000 | 20.400.000 |
| ACT-016: Logical Data Model | TL | Tech Lead/Arsitek | 3 | 6.800.000 | 20.400.000 |
| ACT-017: Physical Data Model | TL | Tech Lead/Arsitek | 3 | 6.800.000 | 20.400.000 |
| ACT-018: Database Migration Scripts | BE | Mid Backend Dev | 3 | 3.200.000 | 9.600.000 |
| Subtotal Design |  |  |  |  | 241.200.000 |

C. Sales Management Module

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-019: Sales Order CRUD | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-020: Sales Order Validation | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-021: Stock Reservation Integration | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-022: Sales Order Status Tracking | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-023: Sales Order Approval Workflow | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-024: Sales Order Fulfillment | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-025: Invoice Generation | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-026: Invoice Status Tracking | BE | Mid Backend Dev | 1 | 3.200.000 | 3.200.000 |
| ACT-027: Invoice Sending (Email) | BE | Mid Backend Dev | 1 | 3.200.000 | 3.200.000 |
| ACT-028: Payment Recording | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-029: Payment Status Tracking | BE | Mid Backend Dev | 1 | 3.200.000 | 3.200.000 |
| ACT-030: Sales Return Processing | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-031: Credit Note Generation | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-032: Return Approval Workflow | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-033: Sales KPI Dashboard | FE | Senior Frontend Dev | 3 | 4.600.000 | 13.800.000 |
| ACT-034: Sales Analytics Reports | FE/BE | Senior Frontend + Backend | 3 | 4.600.000 + 4.800.000 | 28.200.000 |
| Subtotal Sales Module |  |  |  |  | 165.600.000 |

D. CRM Module

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-035: Customer Registration | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-036: Customer Contact Management | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-037: Customer Credit Management | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-038: Customer Segmentation | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-039: Customer Interaction Logging | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-040: Interaction History | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-041: Complaint Entry | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-042: Complaint Workflow | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-043: Complaint Resolution | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-044: Customer Purchase History | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-045: Customer 360 View | BE/FE | Senior Backend + Frontend | 5 | 4.800.000 + 4.600.000 | 47.000.000 |
| ACT-046: CSAT Score & Retention | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-047: CRM KPI Dashboard | FE | Senior Frontend Dev | 3 | 4.600.000 | 13.800.000 |
| Subtotal CRM Module |  |  |  |  | 156.800.000 |

E. Marketplace Module

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-048: Product Listing (CRUD) | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-049: Product Catalog | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-050: Product Search (Elasticsearch) | BE | Senior Backend Dev | 5 | 4.800.000 | 24.000.000 |
| ACT-051: Product Filter | BE/FE | Mid Backend + Frontend | 2 | 3.200.000 + 3.000.000 | 12.400.000 |
| ACT-052: Product Detail | BE/FE | Mid Backend + Frontend | 2 | 3.200.000 + 3.000.000 | 12.400.000 |
| ACT-053: Add to Cart | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-054: Cart Management | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-055: Checkout Process | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-056: Order Integration | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-057: Product Review | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-058: Product Rating | BE | Mid Backend Dev | 1 | 3.200.000 | 3.200.000 |
| ACT-059: Seller Rating | BE | Mid Backend Dev | 1 | 3.200.000 | 3.200.000 |
| ACT-060: Promotion Creation | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-061: Discount Management | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-062: Flash Sale Management | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-063: Marketplace KPI Dashboard | FE | Senior Frontend Dev | 3 | 4.600.000 | 13.800.000 |
| ACT-064: Marketplace Analytics | FE/BE | Senior Frontend + Backend | 3 | 4.600.000 + 4.800.000 | 28.200.000 |
| Subtotal Marketplace Module |  |  |  |  | 198.000.000 |

F. Logistics Module

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-065: Shipment Creation | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-066: Shipment Status Tracking | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-067: Shipment Document Generation | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-068: Delivery Tracking (Real-time) | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-069: Proof of Delivery (POD) | BE/MB | Senior Backend + Mobile | 3 | 4.800.000 + 3.400.000 | 24.600.000 |
| ACT-070: Tracking History | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-071: Carrier Registration | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-072: Rate Management | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-073: Carrier API Integration | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-074: Route Optimization | BE | Senior Backend Dev | 5 | 4.800.000 | 24.000.000 |
| ACT-075: Fleet Management | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-076: Logistics KPI Dashboard | FE | Senior Frontend Dev | 3 | 4.600.000 | 13.800.000 |
| ACT-077: Logistics Analytics | FE/BE | Senior Frontend + Backend | 3 | 4.600.000 + 4.800.000 | 28.200.000 |
| ACT-078: Carrier Performance | FE/BE | Senior Frontend + Backend | 3 | 4.600.000 + 4.800.000 | 28.200.000 |
| Subtotal Logistics Module |  |  |  |  | 208.600.000 |

G. Portal Module

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-079: Customer Login (MFA) | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-080: Customer Profile | BE/FE | Mid Backend + Frontend | 2 | 3.200.000 + 3.000.000 | 12.400.000 |
| ACT-081: Order History & Tracking | BE/FE | Senior Backend + Frontend | 3 | 4.800.000 + 4.600.000 | 28.200.000 |
| ACT-082: Product Catalog (B2B) | BE/FE | Mid Backend + Frontend | 2 | 3.200.000 + 3.000.000 | 12.400.000 |
| ACT-083: Place Order (B2B) | BE/FE | Senior Backend + Frontend | 3 | 4.800.000 + 4.600.000 | 28.200.000 |
| ACT-084: Invoice History | BE/FE | Mid Backend + Frontend | 2 | 3.200.000 + 3.000.000 | 12.400.000 |
| ACT-085: Complaint Submission | BE/FE | Mid Backend + Frontend | 2 | 3.200.000 + 3.000.000 | 12.400.000 |
| ACT-086: Supplier Login (MFA) | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-087: Supplier Profile | BE/FE | Mid Backend + Frontend | 2 | 3.200.000 + 3.000.000 | 12.400.000 |
| ACT-088: PO View & Confirmation | BE/FE | Senior Backend + Frontend | 3 | 4.800.000 + 4.600.000 | 28.200.000 |
| ACT-089: Invoice Submission | BE/FE | Mid Backend + Frontend | 2 | 3.200.000 + 3.000.000 | 12.400.000 |
| ACT-090: Payment Status | BE/FE | Mid Backend + Frontend | 1 | 3.200.000 + 3.000.000 | 6.200.000 |
| ACT-091: Performance Scorecard | BE/FE | Senior Backend + Frontend | 3 | 4.800.000 + 4.600.000 | 28.200.000 |
| ACT-092: MFA Implementation | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| ACT-093: Session Management | BE | Senior Backend Dev | 2 | 4.800.000 | 9.600.000 |
| Subtotal Portal Module |  |  |  |  | 241.400.000 |

H. Integration & Testing

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-094: Integration P-FNE-01 | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-095: Integration P-FNE-03 | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-096: Integration P-FNE-04 | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-097: Integration P-FNE-06 | BE | Mid Backend Dev | 2 | 3.200.000 | 6.400.000 |
| ACT-098: Payment Gateway Integration | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-099: Carrier API Integration | BE | Senior Backend Dev | 3 | 4.800.000 | 14.400.000 |
| ACT-100: Load Testing | QA | Senior QA Engineer | 3 | 4.000.000 | 12.000.000 |
| ACT-101: Stress Testing | QA | Senior QA Engineer | 2 | 4.000.000 | 8.000.000 |
| ACT-102: Scalability Testing | QA | Senior QA Engineer | 2 | 4.000.000 | 8.000.000 |
| ACT-103: Penetration Testing | QA | Senior QA Engineer | 3 | 4.000.000 | 12.000.000 |
| ACT-104: Vulnerability Scanning | QA | Mid QA Engineer | 2 | 2.800.000 | 5.600.000 |
| ACT-105: Security Audit | QA | Senior QA Engineer | 2 | 4.000.000 | 8.000.000 |
| ACT-106: E2E Testing | QA | Senior QA Engineer | 5 | 4.000.000 | 20.000.000 |
| ACT-107: UAT Execution | QA | Senior QA Engineer | 5 | 4.000.000 | 20.000.000 |
| Subtotal Integration & Testing |  |  |  |  | 164.400.000 |

I. Deployment & UAT

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-108: Staging Environment Setup | DevOps | DevOps Engineer | 2 | 4.000.000 | 8.000.000 |
| ACT-109: Deployment to Staging | DevOps | DevOps Engineer | 1 | 4.000.000 | 4.000.000 |
| ACT-110: Production Environment Setup | DevOps | DevOps Engineer | 3 | 4.000.000 | 12.000.000 |
| ACT-111: UAT Execution (User) | QA | Senior QA Engineer | 5 | 4.000.000 | 20.000.000 |
| ACT-112: UAT Sign-off | PM | Project Manager | 1 | 6.000.000 | 6.000.000 |
| ACT-113: Critical Bug Fixing | BE/FE | Senior Backend + Frontend | 5 | 4.800.000 + 4.600.000 | 47.000.000 |
| ACT-114: Regression Testing | QA | Senior QA Engineer | 3 | 4.000.000 | 12.000.000 |
| ACT-115: Deployment to Production | DevOps | DevOps Engineer | 2 | 4.000.000 | 8.000.000 |
| ACT-116: Go-Live Support | All | All Team | 3 | Various | 60.000.000 |
| ACT-117: User Training Material | BA | Business Analyst | 5 | 3.800.000 | 19.000.000 |
| ACT-118: End-User Training | BA | Business Analyst | 3 | 3.800.000 | 11.400.000 |
| Subtotal Deployment & UAT |  |  |  |  | 207.400.000 |

J. Project Closure

| Activity | Personil | Level | Durasi (Hari) | Tarif/Hari (Rp) | Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| ACT-119: Final Documentation | PM/TL | PM + Tech Lead | 5 | 6.000.000 + 6.800.000 | 64.000.000 |
| ACT-120: Lessons Learned Workshop | PM | Project Manager | 1 | 6.000.000 | 6.000.000 |
| ACT-121: Project Closure Report | PM | Project Manager | 3 | 6.000.000 | 18.000.000 |
| ACT-122: Project Handover | PM/TL | PM + Tech Lead | 2 | 6.000.000 + 6.800.000 | 25.600.000 |
| Subtotal Project Closure |  |  |  |  | 113.600.000 |

### 5.6 Determine Budget

#### 5.6.1 Deskripsi Proses

Proses ini mengakumulasi semua biaya aktivitas dan menentukan anggaran proyek secara keseluruhan, termasuk biaya langsung, biaya tidak langsung, dan kontingensi.

#### 5.6.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Cost Estimates | Estimate Costs |
| 2 | Scope Baseline | PMP |
| 3 | Project Schedule | PMP |
| 4 | Resource Calendars | Resource Management |

#### 5.6.3 Output

A. Total Estimasi Biaya Proyek

| Kategori | Biaya (Rp) | Persentase |
| --- | --- | --- |
| Direct Labor | 1.769.000.000 | 52.0% |
| Overhead (20%) | 353.800.000 | 10.4% |
| Infrastructure & Software | 750.000.000 | 22.1% |
| Third-party Services | 350.000.000 | 10.3% |
| Travel & Meeting | 50.000.000 | 1.5% |
| Training | 100.000.000 | 2.9% |
| Subtotal | 3.372.800.000 | 99.2% |
| Contingency (10%) | 337.280.000 | 9.9% |
| Grand Total | 3.710.080.000 | ~109% |

B. Detail Biaya per Fase

| Fase | Biaya Personil (Rp) | Biaya Lain (Rp) | Total (Rp) | Persentase |
| --- | --- | --- | --- | --- |
| Project Initiation | 72.000.000 | 10.000.000 | 82.000.000 | 2.2% |
| Requirements & Design | 241.200.000 | 15.000.000 | 256.200.000 | 6.9% |
| Sales Management | 165.600.000 | 20.000.000 | 185.600.000 | 5.0% |
| CRM Module | 156.800.000 | 15.000.000 | 171.800.000 | 4.6% |
| Marketplace Module | 198.000.000 | 30.000.000 | 228.000.000 | 6.2% |
| Logistics Module | 208.600.000 | 25.000.000 | 233.600.000 | 6.3% |
| Portal Module | 241.400.000 | 20.000.000 | 261.400.000 | 7.0% |
| Integration & Testing | 164.400.000 | 50.000.000 | 214.400.000 | 5.8% |
| Deployment & UAT | 207.400.000 | 80.000.000 | 287.400.000 | 7.7% |
| Project Closure | 113.600.000 | 15.000.000 | 128.600.000 | 3.5% |
| Subtotal Personil | 1.769.000.000 | -280.000.000 | 1.489.000.000 | 55.0% |
| Overhead (20%) | - | 353.800.000 | 353.800.000 | 9.5% |
| Infrastructure & Software | - | 750.000.000 | 750.000.000 | 20.2% |
| Third-party Services | - | 350.000.000 | 350.000.000 | 9.4% |
| Travel & Meeting | - | 50.000.000 | 50.000.000 | 1.3% |
| Training | - | 100.000.000 | 100.000.000 | 2.7% |
| Subtotal | 1.769.000.000 | 1.603.800.000 | 3.372.800.000 | 90.8% |
| Contingency (10%) | - | 337.280.000 | 337.280.000 | 9.1% |
| Grand Total | 1.769.000.000 | 1.941.080.000 | 3.710.080.000 | 100% |

C. Detail Biaya per Personil

| Role | Tarif/Hari (Rp) | Total Hari | Total Biaya (Rp) | Persentase |
| --- | --- | --- | --- | --- |
| Project Manager | 6.000.000 | 100 | 600.000.000 | 33.9% |
| Tech Lead/Arsitek | 6.800.000 | 80 | 544.000.000 | 30.8% |
| Senior Backend Dev | 4.800.000 | 120 | 576.000.000 | 32.6% |
| Senior Frontend Dev | 4.600.000 | 80 | 368.000.000 | 20.8% |
| Mid Backend Dev | 3.200.000 | 120 | 384.000.000 | 21.7% |
| Mid Frontend Dev | 3.000.000 | 80 | 240.000.000 | 13.6% |
| Mobile Developer | 3.400.000 | 40 | 136.000.000 | 7.7% |
| Senior QA Engineer | 4.000.000 | 80 | 320.000.000 | 18.1% |
| Mid QA Engineer | 2.800.000 | 40 | 112.000.000 | 6.3% |
| Business Analyst | 3.800.000 | 60 | 228.000.000 | 12.9% |
| UX/UI Designer | 3.600.000 | 50 | 180.000.000 | 10.2% |
| DevOps Engineer | 4.000.000 | 40 | 160.000.000 | 9.0% |
| Total |  |  | 3.848.000.000 | 100% |

D. Detail Infrastructure & Software

| Komponen | Vendor/Platform | Estimasi Biaya (Rp) | Durasi | Keterangan |
| --- | --- | --- | --- | --- |
| Cloud Infrastructure | AWS/GCP | 400.000.000 | 5 bulan | EC2, RDS, S3, EKS |
| Database License | PostgreSQL Enterprise | 50.000.000 | - | Premium support |
| CI/CD Tools | GitLab Premium | 30.000.000 | - | 1 tahun |
| Monitoring Tools | Datadog/New Relic | 60.000.000 | 5 bulan | APM, Logging |
| Security Tools | SonarQube, Snyk | 40.000.000 | - | Code security |
| Elasticsearch | Elastic Cloud | 50.000.000 | 5 bulan | Search engine |
| Kafka | Confluent Cloud | 60.000.000 | 5 bulan | Event streaming |
| Redis | Redis Enterprise | 30.000.000 | 5 bulan | Caching |
| Design Tools | Figma | 10.000.000 | - | UX/UI design |
| SSL Certificate | DigiCert | 20.000.000 | - | Security |
| Subtotal |  | 750.000.000 |  |  |

E. Detail Third-party Services

| Komponen | Vendor | Estimasi Biaya (Rp) | Keterangan |
| --- | --- | --- | --- |
| Payment Gateway | Midtrans/Xendit | 150.000.000 | Setup + 3 bulan subscription |
| Carrier API (JNE) | JNE | 60.000.000 | API integration + subscription |
| Carrier API (SiCepat) | SiCepat | 50.000.000 | API integration + subscription |
| Carrier API (J&T) | J&T | 50.000.000 | API integration + subscription |
| SMS Gateway | Twilio | 40.000.000 | OTP, notification |
| Subtotal |  | 350.000.000 |  |

F. Detail Training Cost

| Komponen | Durasi | Peserta | Biaya (Rp) |
| --- | --- | --- | --- |
| Technical Training (Backend) | 3 hari | 4 peserta | 40.000.000 |
| Technical Training (Frontend) | 3 hari | 3 peserta | 30.000.000 |
| Mobile App Training | 2 hari | 2 peserta | 15.000.000 |
| End-User Training (Sales) | 2 hari | 15 peserta | 15.000.000 |
| End-User Training (CRM) | 2 hari | 10 peserta | 10.000.000 |
| End-User Training (Logistics) | 2 hari | 10 peserta | 10.000.000 |
| Subtotal |  |  | 100.000.000 |

G. Cost Baseline

Cost Baseline adalah anggaran yang disetujui dan akan digunakan sebagai acuan untuk mengukur kinerja biaya proyek.

| Komponen | Biaya (Rp) |
| --- | --- |
| Direct Labor | 1.769.000.000 |
| Overhead (20%) | 353.800.000 |
| Infrastructure & Software | 750.000.000 |
| Third-party Services | 350.000.000 |
| Travel & Meeting | 50.000.000 |
| Training | 100.000.000 |
| Subtotal | 3.372.800.000 |
| Contingency (10%) | 337.280.000 |
| Cost Baseline | 3.710.080.000 |
| Management Reserve | 789.920.000 |
| Total Budget | 4.500.000.000 |

### 5.7 Control Costs

#### 5.7.1 Deskripsi Proses

Proses ini bertujuan untuk memonitor kinerja biaya proyek dan mengendalikan perubahan terhadap cost baseline. Proses ini menggunakan Earned Value Management (EVM) untuk mengukur kinerja biaya secara objektif.

#### 5.7.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Management Plan | PMP |
| 2 | Cost Baseline | Determine Budget |
| 3 | Work Performance Data | Monitoring |
| 4 | Change Requests | CCB |

#### 5.7.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Work Performance Information | Informasi kinerja biaya |
| 2 | Cost Forecasts | Prediksi biaya akhir |
| 3 | Change Requests | Permintaan perubahan biaya |
| 4 | Project Management Plan Updates | Update baseline |

#### 5.7.4 Earned Value Management (EVM)

Proyek menggunakan EVM untuk mengukur kinerja biaya secara objektif:

| Metrik | Formula | Target |
| --- | --- | --- |
| PV (Planned Value) | Total anggaran × % rencana | - |
| EV (Earned Value) | Total anggaran × % actual | - |
| AC (Actual Cost) | Biaya aktual yang dikeluarkan | - |
| CV (Cost Variance) | EV - AC | ≥ 0 |
| SV (Schedule Variance) | EV - PV | ≥ 0 |
| CPI (Cost Performance Index) | EV / AC | ≥ 0.9 |
| SPI (Schedule Performance Index) | EV / PV | ≥ 1.0 |
| EAC (Estimate at Completion) | BAC / CPI | ≤ Rp 4.5B |
| ETC (Estimate to Complete) | EAC - AC | - |
| VAC (Variance at Completion) | BAC - EAC | ≥ 0 |

#### 5.7.5 Monthly Cost Tracking

| Bulan | PV | EV | AC | CV | SV | CPI | SPI | EAC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bulan 1 (Sep) | 100.000.000 | 95.000.000 | 105.000.000 | -10.000.000 | -5.000.000 | 0.90 | 0.95 | 4.000.000.000 |
| Bulan 2 (Okt) | 400.000.000 | 380.000.000 | 390.000.000 | -10.000.000 | -20.000.000 | 0.97 | 0.95 | 3.800.000.000 |
| Bulan 3 (Nov) | 800.000.000 | 780.000.000 | 790.000.000 | -10.000.000 | -20.000.000 | 0.99 | 0.98 | 3.700.000.000 |
| Bulan 4 (Des) | 1.400.000.000 | 1.380.000.000 | 1.350.000.000 | +30.000.000 | -20.000.000 | 1.02 | 0.99 | 3.600.000.000 |
| Bulan 5 (Jan) | 2.000.000.000 | 1.980.000.000 | 1.950.000.000 | +30.000.000 | -20.000.000 | 1.02 | 0.99 | 3.600.000.000 |
| Bulan 6 (Feb) | 2.800.000.000 | 2.750.000.000 | 2.700.000.000 | +50.000.000 | -50.000.000 | 1.02 | 0.98 | 3.500.000.000 |
| Bulan 7 (Mar) | 3.710.080.000 | 3.710.080.000 | 3.650.000.000 | +60.080.000 | 0 | 1.02 | 1.00 | 3.500.000.000 |

#### 5.7.6 Cost Variance Thresholds

| Kategori | Threshold | Tindakan |
| --- | --- | --- |
| Green | Variance < 5% | Monitoring normal |
| Yellow | Variance 5-15% | Analisis penyebab, mitigasi |
| Red | Variance > 15% | Formal Change Request, escalation |

#### 5.7.7 Cost Control Tools

| Tool | Fungsi |
| --- | --- |
| JIRA Time Tracking | Melacak waktu yang dihabiskan per aktivitas |
| Excel Dashboard | Monitoring biaya aktual vs budget |
| EVM Calculator | Menghitung metrik EVM secara otomatis |
| Monthly Financial Report | Laporan keuangan bulanan |
| Change Request Form | Dokumentasi perubahan biaya |

#### 5.7.8 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Memonitor biaya, menganalisis variance, mengambil tindakan |
| Finance | Memverifikasi biaya aktual, menyusun laporan keuangan |
| Tech Lead | Memonitor resource utilization |
| Tim | Melaporkan waktu dan biaya yang dikeluarkan |

### 5.8 Ringkasan Anggaran Proyek

| No | Komponen | Estimasi (Rp) | Keterangan |
| --- | --- | --- | --- |
| 1 | Direct Labor | 1.769.000.000 | 12 personil × 5 bulan |
| 2 | Overhead (20%) | 353.800.000 | Fasilitas, administrasi |
| 3 | Infrastructure & Software | 750.000.000 | Cloud, tools, licenses |
| 4 | Third-party Services | 350.000.000 | Payment gateway, carrier API |
| 5 | Travel & Meeting | 50.000.000 | Transportasi, akomodasi |
| 6 | Training | 100.000.000 | Team training, user training |
| 7 | Contingency (10%) | 337.280.000 | Cadangan risiko |
| 8 | Management Reserve | 789.920.000 | Cadangan manajemen |
| Grand Total |  | 4.500.000.000 | Anggaran Maksimum |

## BAB 6: MANAJEMEN KUALITAS PROYEK

### 6.1 Tujuan Manajemen Kualitas

Manajemen Kualitas Proyek bertujuan untuk memastikan bahwa proyek menghasilkan deliverables yang memenuhi standar kualitas yang ditentukan dan memuaskan kebutuhan stakeholder. Tujuan spesifiknya adalah:

- Menentukan standar kualitas yang akan digunakan dalam proyek

- Merencanakan aktivitas kualitas untuk memastikan kepatuhan terhadap standar

- Melaksanakan quality assurance dan quality control

- Mengukur dan melaporkan kinerja kualitas secara berkelanjutan

- Meningkatkan kualitas melalui proses perbaikan berkelanjutan

### 6.2 Proses Manajemen Kualitas

Manajemen Kualitas Proyek terdiri dari 3 (tiga) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Plan Quality Management | Merencanakan standar dan metrik kualitas | Minggu 1-3 |
| 2 | Manage Quality | Melaksanakan quality assurance | Setiap Sprint |
| 3 | Control Quality | Melaksanakan quality control dan testing | Setiap Sprint + UAT |

### 6.3 Plan Quality Management

#### 6.3.1 Deskripsi Proses

Proses ini menghasilkan Quality Management Plan yang mendefinisikan standar kualitas, metrik, dan pendekatan untuk menjamin kualitas deliverables proyek.

#### 6.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Scope Management Plan | PMP |
| 3 | Requirements Documentation | Collect Requirements |
| 4 | Stakeholder Register | Manajemen Stakeholder |
| 5 | Organizational Process Assets | Organisasi |

#### 6.3.3 Output

A. Quality Management Plan P-FNE-05

| Elemen | Deskripsi |
| --- | --- |
| Standar Kualitas | ISO 25010 (Software Quality), OWASP Top 10 (Security), WCAG 2.1 (Accessibility) |
| Metrik Kualitas | Code coverage, defect density, response time, availability |
| Quality Assurance | Code review, static analysis, automated testing |
| Quality Control | Unit testing, integration testing, E2E testing, UAT |
| Quality Tools | SonarQube, JIRA, Selenium, JMeter, OWASP ZAP |
| Improvement | Sprint retrospective, lessons learned |

B. Quality Standards

| Standar | Deskripsi | Diterapkan Pada |
| --- | --- | --- |
| ISO 25010 | Software Quality Model (8 characteristics) | Code, Performance, Security |
| OWASP Top 10 | Web Application Security Risks | Security, Code |
| WCAG 2.1 | Web Content Accessibility Guidelines | UI/UX, Frontend |
| PCI DSS | Payment Card Industry Data Security Standard | Payment Module |

C. Quality Metrics

| No | Metrik | Deskripsi | Target | Alat Ukur |
| --- | --- | --- | --- | --- |
| 1 | Code Coverage | Persentase kode yang diuji oleh unit test | ≥ 80% | SonarQube |
| 2 | Defect Density | Jumlah bug per KLOC (1000 baris kode) | ≤ 1 per KLOC | SonarQube |
| 3 | Critical Bugs | Jumlah bug dengan severity P1 | 0 | JIRA |
| 4 | Test Pass Rate | Persentase test case yang lulus | ≥ 98% | Test Automation |
| 5 | Response Time | Waktu respons API | ≤ 2 detik | JMeter |
| 6 | Availability | Uptime portal | ≥ 99.5% | Grafana |
| 7 | UAT Satisfaction | Skor kepuasan dari UAT | ≥ 4.5/5 | Survey |
| 8 | Technical Debt | Technical debt ratio | ≤ 5% | SonarQube |
| 9 | Security Vulnerability | Jumlah vulnerability kritis | 0 | OWASP ZAP, Snyk |
| 10 | Defect Removal Efficiency | % bug ditemukan sebelum production | ≥ 95% | JIRA |

D. Quality Roles & Responsibilities

| Peran | Tanggung Jawab Kualitas |
| --- | --- |
| Project Manager | Memastikan proses kualitas diikuti, menyetujui quality plan |
| QA Lead | Memimpin strategi testing, quality assurance |
| Tech Lead | Memastikan code quality, code review, technical standards |
| Developer | Unit testing, code review, fixing bugs |
| QA Engineer | Test case creation, execution, bug reporting |
| Product Owner | Menyetujui acceptance criteria, UAT sign-off |
| UX Designer | Memastikan accessibility dan usability |

### 6.4 Manage Quality

#### 6.4.1 Deskripsi Proses

Proses ini bertujuan untuk melaksanakan quality assurance dengan memastikan bahwa proses dan standar kualitas diikuti sepanjang proyek.

#### 6.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Quality Management Plan | Plan Quality Management |
| 2 | Project Documents | Semua dokumen |
| 3 | Work Performance Data | Monitoring |

#### 6.4.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Quality Reports | Laporan kualitas |
| 2 | Test Results | Hasil pengujian |
| 3 | Change Requests | Permintaan perubahan untuk perbaikan kualitas |
| 4 | Process Improvements | Perbaikan proses |

#### 6.4.4 Quality Assurance Activities

A. Code Review

| Elemen | Deskripsi |
| --- | --- |
| Metode | Pull Request Review dengan minimal 2 approvals |
| Tools | GitLab Merge Request, GitLab Code Review |
| Checklist | Coding standards, performance, security, test coverage |
| Frequency | Setiap pull request |

B. Static Code Analysis

| Elemen | Deskripsi |
| --- | --- |
| Tools | SonarQube, ESLint, Pylint |
| Check | Code smells, bugs, vulnerabilities, duplication |
| Frequency | Setiap commit / CI pipeline |
| Threshold | Quality gate: No blocker/critical issues, coverage ≥ 80% |

C. Automated Testing

| Elemen | Deskripsi |
| --- | --- |
| Unit Testing | JUnit (Java), Jest (JS), pytest (Python) |
| Integration Testing | Testcontainers, Postman/Newman |
| E2E Testing | Cypress, Selenium |
| Frequency | Setiap commit / CI pipeline |

D. Performance Testing

| Elemen | Deskripsi |
| --- | --- |
| Tools | JMeter, K6 |
| Scenarios | Load testing, stress testing, scalability testing |
| Target | ≥ 50 transactions/second, response time ≤ 2 seconds |
| Frequency | Akhir setiap modul, sebelum release |

E. Security Testing

| Elemen | Deskripsi |
| --- | --- |
| Tools | OWASP ZAP, Snyk, SonarQube (Security) |
| Scenarios | Penetration testing, vulnerability scanning |
| Target | Zero critical vulnerability |
| Frequency | Akhir setiap modul, sebelum release |

#### 6.4.5 Quality Assurance Process

text

┌─────────────────────────────────────────────────────────────────────┐

│                    QUALITY ASSURANCE PROCESS                       │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  [1] Code Commit ──► [2] CI Pipeline ──► [3] Static Analysis     │

│        │                  │                  │                     │

│        ▼                  ▼                  ▼                     │

│  [4] Unit Tests ──► [5] Integration Tests ──► [6] Code Review     │

│        │                  │                  │                     │

│        ▼                  ▼                  ▼                     │

│  [7] Quality Gate ──► [8] Merge ──► [9] Deploy to Staging        │

│        │                                                           │

│        ▼                                                           │

│  [10] E2E Tests ──► [11] Performance Tests ──► [12] UAT          │

│                                                                     │

│  Quality Gate Criteria:                                            │

│  - No blocker/critical issues                                     │

│  - Code coverage ≥ 80%                                            │

│  - All unit tests passing                                         │

│  - All integration tests passing                                 │

│  - No security vulnerabilities                                    │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

### 6.5 Control Quality

#### 6.5.1 Deskripsi Proses

Proses ini bertujuan untuk memonitor dan mencatat hasil pelaksanaan kegiatan quality control untuk menilai kinerja kualitas dan memastikan bahwa deliverables memenuhi standar kualitas.

#### 6.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Quality Management Plan | PMP |
| 2 | Quality Metrics | Manage Quality |
| 3 | Test Results | Manage Quality |
| 4 | Work Performance Data | Monitoring |

#### 6.5.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Quality Control Measurements | Hasil pengukuran kualitas |
| 2 | Validated Deliverables | Deliverables yang telah divalidasi |
| 3 | Verified Deliverables | Deliverables yang telah diverifikasi |
| 4 | Change Requests | Permintaan perubahan untuk perbaikan |

#### 6.5.4 Test Strategy

A. Unit Testing

| Elemen | Deskripsi |
| --- | --- |
| Tools | JUnit 5 (Java), Jest (JavaScript/TypeScript), pytest (Python) |
| Scope | Semua kelas, metode, dan fungsi |
| Coverage Target | ≥ 80% |
| Framework | TDD (Test-Driven Development) |
| Responsibility | Developer |

B. Integration Testing

| Elemen | Deskripsi |
| --- | --- |
| Tools | Testcontainers, Postman/Newman, REST Assured |
| Scope | API endpoints, database integration, external services |
| Coverage Target | 100% API endpoints |
| Responsibility | Backend Developer + QA |

C. System Testing

| Elemen | Deskripsi |
| --- | --- |
| Tools | Selenium, Cypress, Postman |
| Scope | End-to-end user scenarios |
| Coverage Target | Critical paths |
| Responsibility | QA Engineer |

D. Performance Testing

| Elemen | Deskripsi |
| --- | --- |
| Tools | JMeter, K6 |
| Scope | API endpoints, UI loading |
| Target | Response time ≤ 2 seconds, 50+ TPS |
| Responsibility | QA Engineer + DevOps |

E. Security Testing

| Elemen | Deskripsi |
| --- | --- |
| Tools | OWASP ZAP, Snyk, SonarQube |
| Scope | All endpoints, authentication, authorization |
| Target | Zero critical vulnerability |
| Responsibility | QA Engineer + Security |

F. User Acceptance Testing (UAT)

| Elemen | Deskripsi |
| --- | --- |
| Peserta | End users (Sales, Logistics, Customer Service) |
| Scope | All user stories and scenarios |
| Acceptance Criteria | Acceptance criteria per requirements |
| SLA | 100% critical path, 95% overall |
| Sign-off | PO + User Representative |

#### 6.5.5 Testing Levels

text

┌─────────────────────────────────────────────────────────────────────┐

│                        TESTING LEVELS                              │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│                         ┌──────────────┐                           │

│                  ┌─────►│    UAT       │◄────┐                     │

│                  │      │  (User)      │     │                     │

│                  │      └──────────────┘     │                     │

│                  │         ▲                 │                     │

│                  │         │                 │                     │

│                  │      ┌──────────────┐     │                     │

│                  ├─────►│ E2E Testing  │◄────┤                     │

│                  │      │  (QA Team)   │     │                     │

│                  │      └──────────────┘     │                     │

│                  │         ▲                 │                     │

│                  │         │                 │                     │

│                  │      ┌──────────────┐     │                     │

│                  ├─────►│ Integration  │◄────┤                     │

│                  │      │  Testing     │     │                     │

│                  │      └──────────────┘     │                     │

│                  │         ▲                 │                     │

│                  │         │                 │                     │

│                  │      ┌──────────────┐     │                     │

│                  └─────►│   Unit       │◄────┘                     │

│                         │   Testing    │                           │

│                         └──────────────┘                           │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

#### 6.5.6 Defect Management

A. Defect Severity Classification

| Severity | Deskripsi | SLA Resolution | Contoh |
| --- | --- | --- | --- |
| Critical (P1) | System down, data loss, major functionality broken | ≤ 4 jam | Payment gateway not working |
| High (P2) | Major function broken, but workaround exists | ≤ 24 jam | Unable to create sales order |
| Medium (P3) | Minor function broken, workaround exists | ≤ 3 hari | UI misalignment |
| Low (P4) | Cosmetic issues, typo, minor UI issues | ≤ 5 hari | Spelling error in label |

B. Defect Lifecycle

text

┌─────────────────────────────────────────────────────────────────────┐

│                        DEFECT LIFECYCLE                            │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│   [NEW] ──► [ASSIGNED] ──► [IN PROGRESS] ──► [FIXED]             │

│                         │                    │                     │

│                         ▼                    ▼                     │

│                   [REJECTED]           [VERIFIED]                  │

│                         │                    │                     │

│                         ▼                    ▼                     │

│                   [CLOSED]             [REOPENED]                  │

│                                              │                     │

│                                              ▼                     │

│                                        [ASSIGNED]                  │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

C. Defect Reporting

| Elemen | Deskripsi |
| --- | --- |
| Tools | JIRA |
| Template | Summary, Description, Steps to Reproduce, Expected/Actual Result, Severity, Priority, Environment, Screenshots |
| Frequency | Real-time |

#### 6.5.7 Quality Gates

| Quality Gate | Checkpoints | Criteria |
| --- | --- | --- |
| Gate 1: Code Quality | Setiap pull request | No blocker issues, coverage ≥ 80%, all tests passing |
| Gate 2: Integration | Akhir setiap modul | Integration tests passing, no critical bugs |
| Gate 3: Performance | Akhir setiap modul | Response time ≤ 2 sec, throughput ≥ 50 TPS |
| Gate 4: Security | Akhir setiap modul | Zero critical vulnerability |
| Gate 5: UAT | Pra-deployment | UAT sign-off, no critical bugs |
| Gate 6: Production | Pra-deployment | All gates passed, deployment approved |

#### 6.5.8 Quality Reporting

A. Weekly Quality Report

| Elemen | Isi |
| --- | --- |
| Code Coverage | % coverage per module |
| Defect Summary | Open/Closed bugs, severity distribution |
| Test Summary | Pass/Fail rate per test type |
| Quality Gate Status | Pass/Fail per quality gate |
| Trend | Coverage trend, defect trend |

B. Sprint Quality Report

| Elemen | Isi |
| --- | --- |
| Defects Found | Jumlah bug per sprint |
| Defects Fixed | Jumlah bug yang diperbaiki |
| Coverage Change | Perubahan code coverage |
| Technical Debt | Perubahan technical debt |
| Action Items | Perbaikan yang diperlukan |

#### 6.5.9 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| QA Lead | Memimpin testing strategy, mengelola quality control |
| QA Engineer | Menjalankan test cases, melaporkan bugs |
| Developer | Unit testing, code quality, fixing bugs |
| Tech Lead | Memastikan code quality, memimpin code review |
| Product Owner | Menyetujui acceptance criteria, UAT sign-off |
| Project Manager | Memastikan quality process diikuti |

### 6.6 Continuous Improvement

#### 6.6.1 Sprint Retrospective

| Elemen | Deskripsi |
| --- | --- |
| Frequency | Setiap akhir sprint |
| Format | 4L (Liked, Learned, Lacked, Longed For) |
| Output | Action items untuk perbaikan |
| Owner | Scrum Master / Tech Lead |

#### 6.6.2 Quality Improvement Plan

| Area | Tindakan Perbaikan | Timeline | Owner |
| --- | --- | --- | --- |
| Code Coverage | Mengidentifikasi area dengan coverage rendah, tambahkan unit test | Sprint | Developer |
| Defect Density | Root cause analysis, improve code review process | Sprint | Tech Lead |
| Test Automation | Meningkatkan automation coverage | Sprint | QA |
| Performance | Optimasi kueri, caching, code optimization | Sprint | Backend Dev |
| Security | Security training, code review for security | Sprint | Tech Lead |

## BAB 7: MANAJEMEN SUMBER DAYA PROYEK

### 7.1 Tujuan Manajemen Sumber Daya

Manajemen Sumber Daya Proyek bertujuan untuk mengoptimalkan penggunaan sumber daya manusia, material, dan peralatan dalam proyek. Tujuan spesifiknya adalah:

- Mengidentifikasi sumber daya yang dibutuhkan untuk setiap aktivitas

- Mengakuisisi sumber daya yang diperlukan tepat waktu

- Mengembangkan tim proyek yang kompeten dan kolaboratif

- Mengelola tim untuk mencapai kinerja optimal

- Mengendalikan penggunaan sumber daya agar efisien

### 7.2 Proses Manajemen Sumber Daya

Manajemen Sumber Daya Proyek terdiri dari 5 (lima) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Plan Resource Management | Merencanakan sumber daya yang dibutuhkan | Minggu 1-2 |
| 2 | Estimate Activity Resources | Mengestimasi kebutuhan sumber daya per aktivitas | Minggu 2-3 |
| 3 | Acquire Resources | Mengakuisisi sumber daya yang dibutuhkan | Minggu 1-3 |
| 4 | Develop Team | Mengembangkan kompetensi tim | Berkelanjutan |
| 5 | Manage Team | Mengelola kinerja dan konflik tim | Berkelanjutan |
| 6 | Control Resources | Mengendalikan penggunaan sumber daya | Berkelanjutan |

### 7.3 Plan Resource Management

#### 7.3.1 Deskripsi Proses

Proses ini menghasilkan Resource Management Plan yang mendefinisikan bagaimana sumber daya akan diidentifikasi, diakuisisi, dikembangkan, dan dikelola.

#### 7.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Scope Baseline | PMP |
| 3 | Activity List | Define Activities |
| 4 | Enterprise Environmental Factors | Organisasi |
| 5 | Organizational Process Assets | Organisasi |

#### 7.3.3 Output

A. Resource Management Plan P-FNE-05

| Elemen | Deskripsi |
| --- | --- |
| Resource Requirements | 12 personil dengan peran spesifik |
| Acquisition Strategy | Internal hiring (80%), external hiring (20%) |
| Staffing Schedule | Timeline per role (lihat di bawah) |
| Training Plan | Tech training, Agile training, Security training |
| Recognition & Rewards | Bonus, public recognition, performance review |
| Conflict Resolution | Open communication, mediation, escalation |
| Team Development | Pair programming, tech sharing, team building |

B. Resource Requirements Matrix

| Role | Jumlah | Level | Kualifikasi | Tanggal Mulai | Tanggal Selesai | Sumber |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager | 1 | Senior | S2/S1, 8+ tahun PM IT | M1 | M5 | Internal |
| Tech Lead/Arsitek | 1 | Senior | S2/S1, 10+ tahun arsitektur | M1 | M5 | Internal |
| Senior Backend Dev | 2 | Senior | S1, 5-8 tahun backend | M1 | M5 | Internal (1) + External (1) |
| Senior Frontend Dev | 1 | Senior | S1, 5-8 tahun frontend | M1 | M5 | Internal |
| Mid Backend Dev | 2 | Mid | S1, 3-5 tahun backend | M1 | M5 | Internal (1) + External (1) |
| Mid Frontend Dev | 2 | Mid | S1, 3-5 tahun frontend | M1 | M5 | External |
| Mobile Developer | 2 | Mid | S1, 3-5 tahun mobile | M2 | M5 | External |
| Senior QA Engineer | 1 | Senior | S1, 5-8 tahun QA | M1 | M5 | Internal |
| Mid QA Engineer | 1 | Mid | S1, 3-5 tahun QA | M1 | M5 | Internal |
| Business Analyst | 1 | Mid | S1, 4-6 tahun BA | M1 | M5 | Internal |
| UX/UI Designer | 1 | Mid | S1, 4-6 tahun UX/UI | M1 | M4 | Internal |
| DevOps Engineer | 1 | Mid | S1, 4-6 tahun DevOps | M1 | M5 | Internal |
| Total | 16 |  |  |  |  |  |

#### 7.3.4 Organisasi Tim Proyek

A. Struktur Organisasi Tim

text

┌─────────────────────────────────────────────────────────────────────┐

│                         PROJECT ORGANIZATION                       │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│                        ┌──────────────────┐                        │

│                        │  Project Sponsor │                        │

│                        │   (CEO FNE)      │                        │

│                        └────────┬─────────┘                        │

│                                 │                                   │

│                        ┌────────▼─────────┐                        │

│                        │  Project Manager │                        │

│                        │   [Nama PM]      │                        │

│                        └────────┬─────────┘                        │

│                                 │                                   │

│              ┌──────────────────┼──────────────────┐               │

│              │                  │                  │               │

│    ┌─────────▼─────────┐ ┌──────▼──────┐ ┌────────▼────────┐      │

│    │   Tech Lead       │ │  Product    │ │    QA Lead      │      │

│    │   [Nama TL]       │ │  Owner      │ │    [Nama QA]    │      │

│    │                   │ │  [Nama PO]  │ │                 │      │

│    └─────────┬─────────┘ └──────┬──────┘ └────────┬────────┘      │

│              │                  │                  │               │

│    ┌─────────┼──────────────────┼──────────────────┼────────┐      │

│    │         │                  │                  │        │      │

│ ┌──▼───┐ ┌───▼───┐ ┌───────────▼──────────┐ ┌────▼────┐ ┌──▼───┐ │

│ │Backend│ │Frontend│ │   Mobile Dev        │ │  QA     │ │  BA  │ │

│ │(4 org)│ │(3 org) │ │   (2 org)           │ │(2 org)  │ │(1 org)│ │

│ └──────┘ └───────┘ └──────────────────────┘ └─────────┘ └──────┘ │

│                                                                     │

│                        ┌──────────────────┐                        │

│                        │   UX Designer    │                        │

│                        │   (1 person)     │                        │

│                        └──────────────────┘                        │

│                                                                     │

│                        ┌──────────────────┐                        │

│                        │  DevOps Engineer │                        │

│                        │   (1 person)     │                        │

│                        └──────────────────┘                        │

└─────────────────────────────────────────────────────────────────────┘

B. Role Descriptions

| Role | Deskripsi | Kompetensi Kunci |
| --- | --- | --- |
| Project Manager | Memimpin seluruh aspek proyek, koordinasi stakeholder | PMP/Agile certified, leadership, communication |
| Tech Lead/Arsitek | Mengarahkan arsitektur teknis, code quality, technical decisions | Microservices, Cloud, API design, Security |
| Product Owner | Menentukan prioritas fitur, validasi requirement | Domain knowledge, Agile, stakeholder management |
| Senior Backend Dev | Mengimplementasikan backend microservices | Spring Boot, Node.js, Kafka, PostgreSQL |
| Senior Frontend Dev | Mengimplementasikan web portal | React, Next.js, TypeScript, GraphQL |
| Mid Backend Dev | Mendukung backend development | Spring Boot, Node.js, REST API |
| Mid Frontend Dev | Mendukung frontend development | React, TypeScript, CSS |
| Mobile Developer | Mengimplementasikan mobile app | Flutter, React Native |
| Senior QA Engineer | Memimpin strategi testing, quality assurance | Test automation, performance testing, security testing |
| Mid QA Engineer | Menjalankan testing | Manual testing, test automation |
| Business Analyst | Menjembatani bisnis dan teknis | Domain knowledge, requirements engineering |
| UX/UI Designer | Merancang antarmuka pengguna | Figma, user research, interaction design |
| DevOps Engineer | Mengelola infrastructure, CI/CD | Docker, Kubernetes, AWS/GCP, Terraform |

#### 7.3.5 Staffing Schedule

Timeline Penggunaan Sumber Daya

| Role | M1 | M2 | M3 | M4 | M5 |
| --- | --- | --- | --- | --- | --- |
| Project Manager | 100% | 100% | 100% | 100% | 100% |
| Tech Lead/Arsitek | 100% | 100% | 100% | 100% | 100% |
| Product Owner | 100% | 100% | 100% | 100% | 100% |
| Senior Backend Dev (2) | 100% | 100% | 100% | 100% | 80% |
| Senior Frontend Dev (1) | 50% | 100% | 100% | 100% | 80% |
| Mid Backend Dev (2) | 50% | 100% | 100% | 100% | 80% |
| Mid Frontend Dev (2) | - | 80% | 100% | 100% | 80% |
| Mobile Developer (2) | - | 50% | 100% | 100% | 50% |
| Senior QA Engineer (1) | 50% | 50% | 100% | 100% | 100% |
| Mid QA Engineer (1) | 50% | 50% | 100% | 100% | 100% |
| Business Analyst (1) | 100% | 100% | 50% | 50% | 50% |
| UX/UI Designer (1) | 100% | 100% | 50% | - | - |
| DevOps Engineer (1) | 50% | 50% | 50% | 100% | 100% |

### 7.4 Acquire Resources

#### 7.4.1 Deskripsi Proses

Proses ini bertujuan untuk mengakuisisi sumber daya yang dibutuhkan proyek, baik melalui rekrutmen internal maupun eksternal.

#### 7.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Resource Management Plan | Plan Resource Management |
| 2 | Staffing Schedule | Plan Resource Management |
| 3 | Enterprise Environmental Factors | Organisasi |

#### 7.4.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Project Team Assignments | Penugasan tim proyek |
| 2 | Physical Resource Assignments | Alokasi infrastruktur |
| 3 | Resource Calendars | Kalender ketersediaan sumber daya |

#### 7.4.4 Akuisisi Sumber Daya

A. Internal Hiring (80%)

| Peran | Sumber | Status |
| --- | --- | --- |
| Project Manager | Internal | Tersedia |
| Tech Lead | Internal | Tersedia |
| Product Owner | Internal | Tersedia |
| Senior Backend Dev (1) | Internal | Tersedia |
| Senior Frontend Dev (1) | Internal | Tersedia |
| Mid Backend Dev (1) | Internal | Tersedia |
| Senior QA Engineer (1) | Internal | Tersedia |
| Mid QA Engineer (1) | Internal | Tersedia |
| Business Analyst (1) | Internal | Tersedia |
| UX/UI Designer (1) | Internal | Tersedia |
| DevOps Engineer (1) | Internal | Tersedia |

B. External Hiring (20%)

| Peran | Sumber | Status | Timeline |
| --- | --- | --- | --- |
| Senior Backend Dev (1) | Freelance/Konsultan | Dalam proses rekrutmen | M1 |
| Mid Backend Dev (1) | Freelance/Konsultan | Dalam proses rekrutmen | M1 |
| Mid Frontend Dev (2) | Freelance/Konsultan | Dalam proses rekrutmen | M1 |
| Mobile Developer (2) | Freelance/Konsultan | Dalam proses rekrutmen | M1 |

C. Infrastructure Resources

| Resource | Spesifikasi | Ketersediaan |
| --- | --- | --- |
| Development Environment | Cloud-based (GitPod/Codespaces) | M1 |
| CI/CD Pipeline | GitLab CI | M1 |
| Staging Environment | Kubernetes cluster | M1 |
| Production Environment | Kubernetes cluster | M1 |
| Development Database | PostgreSQL, Redis, Elasticsearch | M1 |
| Monitoring | Prometheus, Grafana, ELK | M1 |

### 7.5 Develop Team

#### 7.5.1 Deskripsi Proses

Proses ini bertujuan untuk mengembangkan kompetensi dan kolaborasi tim proyek melalui pelatihan, coaching, dan team building.

#### 7.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Resource Management Plan | Plan Resource Management |
| 2 | Project Team Assignments | Acquire Resources |
| 3 | Organizational Process Assets | Organisasi |

#### 7.5.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Team Performance Assessments | Evaluasi kinerja tim |
| 2 | Change Requests | Perubahan pada sumber daya |
| 3 | Project Management Plan Updates | Update rencana |

#### 7.5.4 Team Development Activities

A. Onboarding Program

| Aktivitas | Durasi | Deskripsi |
| --- | --- | --- |
| Project Introduction | 1 hari | Overview proyek, tujuan, roadmap |
| Technology Stack Training | 3 hari | Spring Boot, React, Flutter, Docker, Kafka |
| Development Environment Setup | 1 hari | Setup IDE, Git, CI/CD |
| Agile/Scrum Training | 1 hari | Framework Scrum, JIRA |
| Domain Training | 1 hari | Business process FNE, Sales, Logistics |

B. Continuous Development

| Aktivitas | Frekuensi | Deskripsi |
| --- | --- | --- |
| Tech Sharing Session | 2 minggu | Berbagi pengetahuan antar tim |
| Pair Programming | 2 hari/minggu | Kolaborasi coding antara 2 developer |
| Code Review | Setiap PR | Review kode oleh peer |
| Sprint Retrospective | 2 minggu | Evaluasi dan perbaikan proses |
| External Training | Sesuai kebutuhan | Pelatihan dari vendor |

C. Team Building Activities

| Aktivitas | Frekuensi | Deskripsi |
| --- | --- | --- |
| Kickoff Lunch | M1 | Perkenalan dan bonding tim |
| Monthly Team Lunch | Bulanan | Makan siang bersama |
| Team Outing | M3 | Aktivitas di luar kantor |
| Fun Friday Games | 2 minggu | Ice breaking dan games |

D. Recognition & Rewards

| No | Kategori | Reward | Keterangan |
| --- | --- | --- | --- |
| 1 | Best Developer | Bonus + Certificate | Per sprint |
| 2 | Best QA | Bonus + Certificate | Per sprint |
| 3 | Best Team Player | Bonus + Certificate | Per sprint |
| 4 | Innovation Award | Bonus + Certificate | Per bulan |
| 5 | Project Success Bonus | Bonus 1 bulan gaji | End of project |

### 7.6 Manage Team

#### 7.6.1 Deskripsi Proses

Proses ini bertujuan untuk mengelola kinerja tim dan menyelesaikan konflik yang mungkin muncul selama proyek berlangsung.

#### 7.6.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Resource Management Plan | Plan Resource Management |
| 2 | Team Performance Assessments | Develop Team |
| 3 | Work Performance Data | Monitoring |
| 4 | Issue Log | Project Documents |

#### 7.6.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Change Requests | Perubahan pada tim |
| 2 | Project Management Plan Updates | Update rencana |
| 3 | Project Documents Updates | Update issue log |

#### 7.6.4 Team Management Activities

A. Performance Management

| Aktivitas | Frekuensi | Deskripsi |
| --- | --- | --- |
| Daily Stand-up | Harian | Progress harian dan hambatan |
| 1-on-1 Meeting | 2 minggu | Diskusi individual dengan PM |
| Sprint Review | 2 minggu | Review deliverable tim |
| Performance Review | 3 bulan | Evaluasi kinerja formal |

B. Conflict Resolution

| Level | Konflik | Pendekatan | Escalation |
| --- | --- | --- | --- |
| Level 1 | Perbedaan pendapat teknis | Diskusi tim, voting | Tech Lead |
| Level 2 | Konflik interpersonal | Mediasi PM | PM |
| Level 3 | Konflik serius (tidak terselesaikan) | Formal mediation | HR/Sponsor |

Conflict Resolution Process:

text

┌─────────────────────────────────────────────────────────────────────┐

│                    CONFLICT RESOLUTION PROCESS                     │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  [1] IDENTIFY CONFLICT                                             │

│  │   - Terjadi perbedaan pendapat atau ketegangan antar tim        │

│  │   ↓                                                            │

│  [2] INITIAL DISCUSSION                                            │

│  │   - Pihak yang berkonflik berdiskusi secara langsung           │

│  │   - Mediasi oleh PM jika diperlukan                            │

│  │   ↓                                                            │

│  [3] RESOLUTION ATTEMPT                                            │

│  │   - Mencari solusi yang disepakati bersama                     │

│  │   - Dokumentasi kesepakatan                                    │

│  │   ↓                                                            │

│  [4] ESCALATION                                                   │

│  │   - Jika tidak terselesaikan, eskalasi ke HR/Sponsor           │

│  │   ↓                                                            │

│  [5] FINAL DECISION                                               │

│      - Keputusan akhir dari HR/Sponsor                            │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

C. Motivation Strategies

| No | Strategi | Deskripsi |
| --- | --- | --- |
| 1 | Autonomy | Memberikan kebebasan dalam mengerjakan task |
| 2 | Mastery | Memberikan kesempatan belajar dan berkembang |
| 3 | Purpose | Menjelaskan dampak positif proyek |
| 4 | Recognition | Memberikan apresiasi atas kontribusi |
| 5 | Growth | Memberikan jalur karir yang jelas |
| 6 | Work-Life Balance | Menghindari burnout, flexi time |

### 7.7 Control Resources

#### 7.7.1 Deskripsi Proses

Proses ini bertujuan untuk mengendalikan penggunaan sumber daya proyek agar tetap sesuai dengan rencana.

#### 7.7.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Resource Management Plan | Plan Resource Management |
| 2 | Work Performance Data | Monitoring |
| 3 | Resource Calendars | Acquire Resources |

#### 7.7.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Work Performance Information | Informasi kinerja sumber daya |
| 2 | Change Requests | Perubahan alokasi sumber daya |
| 3 | Project Management Plan Updates | Update rencana |

#### 7.7.4 Resource Monitoring

A. Resource Utilization Tracking

| Role | Planned Days | Actual Days | Variance | Utilization |
| --- | --- | --- | --- | --- |
| Project Manager | 22 | 22 | 0 | 100% |
| Tech Lead | 22 | 20 | -2 | 91% |
| Product Owner | 22 | 22 | 0 | 100% |
| Senior Backend Dev | 22 | 24 | +2 | 109% |
| Senior Frontend Dev | 22 | 20 | -2 | 91% |
| Mid Backend Dev | 22 | 22 | 0 | 100% |
| Mid Frontend Dev | 22 | 22 | 0 | 100% |
| Mobile Developer | 22 | 18 | -4 | 82% |
| Senior QA Engineer | 22 | 20 | -2 | 91% |
| Mid QA Engineer | 22 | 22 | 0 | 100% |
| Business Analyst | 22 | 18 | -4 | 82% |
| UX/UI Designer | 22 | 12 | -10 | 55% |
| DevOps Engineer | 22 | 14 | -8 | 64% |

B. Resource Leveling

Jika ada sumber daya yang overloaded (>100% utilization), dilakukan resource leveling:

| Resource | Overload | Tindakan Leveling |
| --- | --- | --- |
| Senior Backend Dev | 109% | Shift sebagian task ke Mid Backend Dev |
| Mid Frontend Dev | 100% | Optimalkan workload, prioritize task |

C. Resource Change Management

| Perubahan | Dampak | Approval |
| --- | --- | --- |
| Perubahan personil | Delay 1-2 minggu | CCB |
| Perubahan alokasi waktu | Dampak pada jadwal | PM |
| Penambahan sumber daya | Dampak pada biaya | Sponsor |

#### 7.7.5 Tanggung Jawab

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Memonitor alokasi sumber daya, mengambil tindakan |
| Tech Lead | Memonitor alokasi teknis |
| HR | Mendukung rekrutmen dan pengembangan |
| Tim | Melaporkan waktu dan aktivitas |

## BAB 8: MANAJEMEN KOMUNIKASI PROYEK

### 8.1 Tujuan Manajemen Komunikasi

Manajemen Komunikasi Proyek bertujuan untuk memastikan bahwa informasi proyek dikomunikasikan secara efektif dan tepat waktu kepada semua stakeholder. Tujuan spesifiknya adalah:

- Mengidentifikasi kebutuhan informasi setiap stakeholder

- Merencanakan strategi komunikasi yang efektif

- Menyampaikan informasi yang tepat kepada stakeholder yang tepat

- Memastikan pemahaman yang sama di antara stakeholder

- Memonitor efektivitas komunikasi

### 8.2 Proses Manajemen Komunikasi

Manajemen Komunikasi Proyek terdiri dari 3 (tiga) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Plan Communications Management | Merencanakan strategi komunikasi | Minggu 1-2 |
| 2 | Manage Communications | Melaksanakan komunikasi | Berkelanjutan |
| 3 | Monitor Communications | Memonitor efektivitas komunikasi | Berkelanjutan |

### 8.3 Plan Communications Management

#### 8.3.1 Deskripsi Proses

Proses ini menghasilkan Communications Management Plan yang mendefinisikan kebutuhan informasi stakeholder, metode komunikasi, dan frekuensi komunikasi.

#### 8.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Stakeholder Register | Manajemen Stakeholder |
| 3 | Resource Management Plan | PMP |
| 4 | Enterprise Environmental Factors | Organisasi |

#### 8.3.3 Output

A. Communications Management Plan P-FNE-05

| Elemen | Deskripsi |
| --- | --- |
| Communication Channels | 16 stakeholder → 120 channel (n(n-1)/2) |
| Communication Methods | Meeting, Email, Dashboard, Report |
| Frequency | Harian, Mingguan, Bulanan, Ad-hoc |
| Tools | Google Meet, Slack, JIRA, Confluence |
| Escalation | PM → Sponsor untuk critical issues |
| Reporting | Status Report, Dashboard, Financial Report |

B. Stakeholder Communication Matrix

| Stakeholder | Kebutuhan Informasi | Frekuensi | Metode | Penerima | Format |
| --- | --- | --- | --- | --- | --- |
| Project Sponsor | Status proyek, milestone, risiko, keputusan strategis | Bulanan | Laporan Bulanan | PM | PowerPoint + Laporan |
| Steering Committee | Progress, keputusan strategis, budget | 2 Minggu | Meeting | PM | Meeting + Minutes |
| Product Owner | Sprint progress, backlog, feature complete | 2 Minggu | Sprint Review | Tim | Demo + Dokumentasi |
| Development Team | Task assignment, daily progress, technical issues | Harian | Daily Stand-up | Seluruh Tim | Verbal + JIRA |
| End Users | Fitur baru, UAT schedule, feedback | Sesuai kebutuhan | Email, Portal, UAT | BA | Email + Notification |
| External Vendors | API integration progress | Mingguan | Email, Meeting | Tech Lead | Email + Meeting |
| Internal P-FNE Teams | Integrasi progress | 2 Minggu | Meeting | Tech Lead | Meeting + API Docs |
| QA Team | Test progress, bugs, quality metrics | Harian | Daily Stand-up | QA Lead | JIRA + Test Reports |
| UX Designer | Design feedback, implementation progress | Mingguan | Meeting | FE Lead | Figma + Meeting |

C. Communication Methods

| Metode | Deskripsi | Contoh |
| --- | --- | --- |
| Interactive Communication | Two-way communication, real-time | Meeting, Daily Stand-up |
| Push Communication | One-way, sender to receiver | Email, Slack, Report |
| Pull Communication | Receiver retrieves information | Confluence, Dashboard, Wiki |

D. Meeting Schedule

| Meeting | Peserta | Frekuensi | Durasi | Tujuan |
| --- | --- | --- | --- | --- |
| Daily Stand-up | Tim | Harian | 15 menit | Sinkronisasi tim |
| Sprint Planning | Tim + PO | 2 minggu | 2-4 jam | Perencanaan sprint |
| Sprint Review | Tim + PO + Stakeholder | 2 minggu | 1-2 jam | Demo dan feedback |
| Sprint Retrospective | Tim | 2 minggu | 1 jam | Evaluasi dan perbaikan |
| Weekly Status Meeting | PM + Leads | Mingguan | 1 jam | Sinkronisasi lead |
| Bi-weekly Steering | Steering Committee | 2 minggu | 2 jam | Laporan steering |
| Monthly Board Meeting | Sponsor + Steering | Bulanan | 2 jam | Laporan board |
| Tech Sharing | Tim | 2 minggu | 1 jam | Berbagi pengetahuan |

### 8.4 Manage Communications

#### 8.4.1 Deskripsi Proses

Proses ini bertujuan untuk melaksanakan komunikasi sesuai dengan Communications Management Plan.

#### 8.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Communications Management Plan | Plan Communications Management |
| 2 | Work Performance Information | Monitoring |
| 3 | Project Documents | Semua dokumen |
| 4 | Stakeholder Register | Manajemen Stakeholder |

#### 8.4.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Project Communications | Komunikasi yang telah dilakukan |
| 2 | Project Management Plan Updates | Update rencana |
| 3 | Project Documents Updates | Update dokumen |
| 4 | Change Requests | Permintaan perubahan dari komunikasi |

#### 8.4.4 Communication Templates

A. Daily Stand-up Report (15 menit)

| Elemen | Isi |
| --- | --- |
| Yesterday | Apa yang saya kerjakan kemarin? |
| Today | Apa yang akan saya kerjakan hari ini? |
| Impediments | Apa hambatan yang saya hadapi? |

B. Weekly Status Report

Template:

text

┌─────────────────────────────────────────────────────────────────────┐

│                    WEEKLY STATUS REPORT                            │

│                    P-FNE-05: Commerce, Sales & Logistics           │

│                    Week: [X] (Date: DD/MM/YYYY)                   │

├─────────────────────────────────────────────────────────────────────┤

│ 1. OVERALL STATUS                                                  │

│    ☐ On Track  ☐ At Risk  ☐ Off Track                             │

│    Health: 🟢 Green  🟡 Yellow  🔴 Red                            │

│                                                                     │

│ 2. PROGRESS SUMMARY                                                │

│    - Sprint [X] Progress: [XX]%                                    │

│    - Story Points Completed: [X] / [Y]                            │

│    - Story Points Remaining: [X]                                  │

│                                                                     │

│ 3. KEY ACCOMPLISHMENTS                                             │

│    - [Feature/Module] - [Status]                                  │

│    - [Feature/Module] - [Status]                                  │

│                                                                     │

│ 4. KEY RISKS & ISSUES                                              │

│    - [Risk/Issue] - [Impact] - [Mitigation]                       │

│    - [Risk/Issue] - [Impact] - [Mitigation]                       │

│                                                                     │

│ 5. UPCOMING ACTIVITIES                                             │

│    - [Activity] - [Timeline]                                      │

│    - [Activity] - [Timeline]                                      │

│                                                                     │

│ 6. DECISIONS NEEDED                                                │

│    - [Decision] - [Deadline] - [Owner]                            │

│                                                                     │

│ 7. KPIs                                                            │

│    - Schedule: [SPI] [SV]                                         │

│    - Budget: [CPI] [CV]                                           │

│    - Quality: [Coverage] [Defects]                                │

│    - Risk: [Open Risks] [Mitigated]                               │

│                                                                     │

│ 8. NEXT WEEK PLAN                                                  │

│    - [Plan]                                                        │

│                                                                     │

│ Prepared By: [PM Name]                                             │

│ Date: DD/MM/YYYY                                                  │

└─────────────────────────────────────────────────────────────────────┘

C. Monthly Report

Template:

text

┌─────────────────────────────────────────────────────────────────────┐

│                    MONTHLY PROGRESS REPORT                         │

│                    P-FNE-05: Commerce, Sales & Logistics           │

│                    Period: [Month] [Year]                          │

├─────────────────────────────────────────────────────────────────────┤

│ 1. EXECUTIVE SUMMARY                                               │

│    [Ringkasan 1-2 paragraf]                                       │

│                                                                     │

│ 2. SCHEDULE PERFORMANCE                                            │

│    - Planned Completion: [X]%                                     │

│    - Actual Completion: [X]%                                      │

│    - SPI: [X]                                                     │

│    - SV: [X]                                                      │

│                                                                     │

│ 3. BUDGET PERFORMANCE                                              │

│    - Budget Plan: Rp [X]                                          │

│    - Actual Cost: Rp [X]                                          │

│    - CPI: [X]                                                     │

│    - CV: [X]                                                      │

│    - EAC: Rp [X]                                                  │

│                                                                     │

│ 4. SCOPE PERFORMANCE                                               │

│    - Planned Scope: [X]                                          │

│    - Completed Scope: [X]                                        │

│    - Scope Changes: [X]                                          │

│                                                                     │

│ 5. QUALITY PERFORMANCE                                             │

│    - Code Coverage: [X]%                                          │

│    - Defects Found: [X]                                          │

│    - Defects Closed: [X]                                         │

│    - Critical Bugs: [X]                                          │

│                                                                     │

│ 6. RISK PERFORMANCE                                                │

│    - Open Risks: [X]                                             │

│    - Closed Risks: [X]                                           │

│    - New Risks: [X]                                              │

│                                                                     │

│ 7. KEY ACCOMPLISHMENTS                                             │

│    - [Accomplishment 1]                                           │

│    - [Accomplishment 2]                                           │

│                                                                     │

│ 8. PLANS FOR NEXT MONTH                                            │

│    - [Plan 1]                                                     │

│    - [Plan 2]                                                     │

│                                                                     │

│ 9. RECOMMENDATIONS                                                 │

│    - [Recommendation 1]                                           │

│                                                                     │

│ Prepared By: [PM Name]                                             │

│ Approved By: [Sponsor Name]                                        │

│ Date: DD/MM/YYYY                                                  │

└─────────────────────────────────────────────────────────────────────┘

D. Change Request Communication

Template:

text

┌─────────────────────────────────────────────────────────────────────┐

│                    CHANGE REQUEST COMMUNICATION                    │

│                    CR-YYYYMMDD-XXX                                │

├─────────────────────────────────────────────────────────────────────┤

│ 1. CHANGE REQUEST ID                                               │

│    CR-20260909-001                                                 │

│                                                                     │

│ 2. REQUESTED BY                                                    │

│    [Name] - [Role] - [Date]                                       │

│                                                                     │

│ 3. CHANGE DESCRIPTION                                              │

│    [Deskripsi perubahan]                                           │

│                                                                     │

│ 4. BUSINESS JUSTIFICATION                                          │

│    [Alasan perubahan]                                              │

│                                                                     │

│ 5. IMPACT ASSESSMENT                                               │

│    - Scope Impact: [X]                                            │

│    - Schedule Impact: [X] hari                                    │

│    - Cost Impact: Rp [X]                                          │

│    - Quality Impact: [X]                                          │

│    - Risk Impact: [X]                                             │

│                                                                     │

│ 6. CCB DECISION                                                    │

│    ☐ Approved   ☐ Rejected   ☐ Deferred   ☐ More Info            │

│    - Approval Date: DD/MM/YYYY                                    │

│    - Signed By: [CCB Members]                                     │

│                                                                     │

│ 7. COMMUNICATION PLAN                                              │

│    - Stakeholders Informed: [List]                                │

│    - Communication Date: DD/MM/YYYY                               │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

#### 8.4.5 Communication Tools

| Tool | Fungsi | Pengguna |
| --- | --- | --- |
| Slack | Komunikasi real-time, notifikasi | Seluruh tim |
| Google Meet / Zoom | Video conference, meeting | Seluruh tim |
| JIRA | Task tracking, sprint management | Seluruh tim |
| Confluence | Dokumentasi, knowledge base | Seluruh tim |
| Email | Formal communication | PM, Stakeholder |
| GitLab | Code review, CI/CD | Tim teknis |
| Figma | Design collaboration | UX, FE |
| PowerPoint | Presentasi | PM |
| Google Drive | Dokumen bersama | Seluruh tim |

### 8.5 Monitor Communications

#### 8.5.1 Deskripsi Proses

Proses ini bertujuan untuk memonitor efektivitas komunikasi proyek dan mengambil tindakan jika diperlukan.

#### 8.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Communications Management Plan | Plan Communications Management |
| 2 | Work Performance Data | Monitoring |
| 3 | Project Communications | Manage Communications |
| 4 | Issue Log | Project Documents |

#### 8.5.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Work Performance Information | Informasi kinerja komunikasi |
| 2 | Change Requests | Permintaan perubahan komunikasi |
| 3 | Project Management Plan Updates | Update rencana |

#### 8.5.4 Communication Effectiveness Metrics

| Metrik | Deskripsi | Target | Metode Pengukuran |
| --- | --- | --- | --- |
| Response Time | Waktu respons email/komunikasi | ≤ 24 jam | Email tracking |
| Meeting Effectiveness | Efektivitas meeting | ≥ 4/5 | Survey |
| Information Clarity | Kejelasan informasi | ≥ 4/5 | Survey |
| Stakeholder Satisfaction | Kepuasan stakeholder | ≥ 4/5 | Survey |
| Report Timeliness | Ketepatan waktu laporan | 100% | Tracking |
| Meeting Attendance | Kehadiran meeting | ≥ 90% | Tracking |

#### 8.5.5 Communication Feedback Loop

text

┌─────────────────────────────────────────────────────────────────────┐

│                    COMMUNICATION FEEDBACK LOOP                     │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  [1] PLAN COMMUNICATION                                            │

│  │   - Rencana komunikasi sesuai dengan plan                      │

│  │   ↓                                                            │

│  [2] EXECUTE COMMUNICATION                                         │

│  │   - Kirim komunikasi sesuai schedule                          │

│  │   ↓                                                            │

│  [3] COLLECT FEEDBACK                                              │

│  │   - Survei stakeholder, meeting evaluation                    │

│  │   ↓                                                            │

│  [4] ANALYZE EFFECTIVENESS                                         │

│  │   - Bandingkan dengan metrik                                  │

│  │   - Identifikasi area perbaikan                               │

│  │   ↓                                                            │

│  [5] IMPROVE COMMUNICATION                                         │

│      - Adjust plan, method, atau frequency                       │

│      - Update Communications Management Plan                     │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

#### 8.5.6 Communication Issue Resolution

| Issue | Dampak | Resolusi | Owner |
| --- | --- | --- | --- |
| Miscommunication | Kesalahan interpretasi | Clarification meeting | PM |
| Information Delay | Keterlambatan keputusan | Reminder, follow-up | PM |
| Wrong Recipient | Informasi tidak sampai | Update stakeholder list | PM |
| Unclear Message | Kebingungan | Rephrase, summary | PM |
| Too Much Information | Overload | Ringkas, prioritize | PM |

#### 8.5.7 Tanggung Jawab

| Peran | Tanggung Jawab Komunikasi |
| --- | --- |
| Project Manager | Memimpin seluruh komunikasi proyek |
| Tech Lead | Komunikasi teknis dengan tim dan vendor |
| Product Owner | Komunikasi bisnis dengan stakeholder |
| BA | Komunikasi requirements dan UAT |
| QA Lead | Komunikasi quality dan test results |
| Tim | Komunikasi daily progress, issue |

### 8.6 Escalation Process

#### 8.6.1 Escalation Levels

| Level | Deskripsi | Penerima | Respons Time |
| --- | --- | --- | --- |
| Level 1 | Masalah teknis rutin | Tech Lead | ≤ 4 jam |
| Level 2 | Masalah teknis kompleks, resource conflict | PM | ≤ 8 jam |
| Level 3 | Masalah bisnis, scope change, budget | PM + PO | ≤ 24 jam |
| Level 4 | Masalah strategis, sponsor decision | Sponsor | ≤ 48 jam |
| Level 5 | Masalah enterprise, CEO/Board decision | CEO/Board | ≤ 72 jam |

#### 8.6.2 Escalation Path

text

┌─────────────────────────────────────────────────────────────────────┐

│                         ESCALATION PATH                            │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│   Level 1: Tech Lead                                               │

│     │   - Technical issues                                        │

│     │   - Code quality issues                                     │

│     │   - Resource allocation technical                           │

│     ▼                                                              │

│   Level 2: Project Manager                                        │

│     │   - Cross-team coordination                                 │

│     │   - Resource conflict                                       │

│     │   - Schedule delay                                          │

│     ▼                                                              │

│   Level 3: PM + PO                                                │

│     │   - Scope change                                           │

│     │   - Budget issue                                           │

│     │   - Stakeholder conflict                                   │

│     ▼                                                              │

│   Level 4: Project Sponsor                                        │

│     │   - Strategic decision                                     │

│     │   - Major budget change                                    │

│     │   - Partnership decision                                   │

│     ▼                                                              │

│   Level 5: CEO / Board                                            │

│         - Enterprise decision                                    │

│         - Organizational change                                  │

│         - Major strategic pivot                                  │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

## BAB 9: MANAJEMEN RISIKO PROYEK

### 9.1 Tujuan Manajemen Risiko

Manajemen Risiko Proyek bertujuan untuk mengidentifikasi, menganalisis, dan merespons risiko proyek secara proaktif. Tujuan spesifiknya adalah:

- Mengidentifikasi risiko yang dapat mempengaruhi proyek

- Menganalisis probabilitas dan dampak risiko

- Merencanakan respons yang tepat untuk setiap risiko

- Mengimplementasikan respons risiko

- Memonitor risiko secara berkelanjutan

### 9.2 Proses Manajemen Risiko

Manajemen Risiko Proyek terdiri dari 6 (enam) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Plan Risk Management | Merencanakan bagaimana risiko akan dikelola | Minggu 1-2 |
| 2 | Identify Risks | Mengidentifikasi risiko potensial | Minggu 1-3 |
| 3 | Perform Qualitative Risk Analysis | Menganalisis probabilitas dan dampak risiko | Minggu 2-3 |
| 4 | Perform Quantitative Risk Analysis | Menganalisis dampak kuantitatif risiko | Minggu 3-4 |
| 5 | Plan Risk Responses | Merencanakan respons terhadap risiko | Minggu 3-4 |
| 6 | Implement Risk Responses | Melaksanakan respons risiko | Berkelanjutan |
| 7 | Monitor Risks | Memonitor risiko secara berkelanjutan | Berkelanjutan |

### 9.3 Plan Risk Management

#### 9.3.1 Deskripsi Proses

Proses ini menghasilkan Risk Management Plan yang mendefinisikan bagaimana risiko akan diidentifikasi, dianalisis, dan dikelola.

#### 9.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Scope Management Plan | PMP |
| 3 | Schedule Management Plan | PMP |
| 4 | Cost Management Plan | PMP |
| 5 | Enterprise Environmental Factors | Organisasi |

#### 9.3.3 Output

Risk Management Plan P-FNE-05

| Elemen | Deskripsi |
| --- | --- |
| Risk Categories | Technical, Schedule, Cost, Resource, Quality, External |
| Probability Definition | Very Low (5%), Low (20%), Medium (50%), High (70%), Very High (90%) |
| Impact Definition | Insignificant, Minor, Moderate, Major, Catastrophic |
| Risk Tolerance | Moderat |
| Threshold | Dampak > Moderate memerlukan mitigasi |
| Tools | Risk Register (Excel/JIRA), Risk Matrix |
| Frequency | Risk review setiap sprint / 2 minggu |

Risk Probability & Impact Matrix:

text

Dampak

│ Insignif │ Minor │ Moderate │ Major │ Catastrophic

──────────────┼──────────┼───────┼──────────┼───────┼─────────────

Very High (90%)│  Medium  │ High  │   High   │ High  │  Very High

──────────────┼──────────┼───────┼──────────┼───────┼─────────────

High (70%)    │  Medium  │ High  │   High   │ High  │  Very High

──────────────┼──────────┼───────┼──────────┼───────┼─────────────

Medium (50%)  │  Low     │ Medium│   High   │ High  │  High

──────────────┼──────────┼───────┼──────────┼───────┼─────────────

Low (20%)     │  Low     │ Low   │  Medium  │ Medium│  High

──────────────┼──────────┼───────┼──────────┼───────┼─────────────

Very Low (5%) │  Low     │ Low   │  Low     │ Medium│  Medium

──────────────┴──────────┴───────┴──────────┴───────┴─────────────

Risk Response Strategy:

- Very High: Immediate action required

- High: Action plan required

- Medium: Monitor and contingency plan

- Low: Accept and monitor

### 9.4 Identify Risks

#### 9.4.1 Deskripsi Proses

Proses ini mengidentifikasi risiko potensial yang dapat mempengaruhi proyek. Identifikasi dilakukan melalui brainstorming, expert judgment, dan analisis dokumen.

#### 9.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Risk Management Plan | Plan Risk Management |
| 2 | Project Documents | Semua dokumen |
| 3 | Activity List | Define Activities |
| 4 | Scope Baseline | PMP |
| 5 | Schedule Baseline | PMP |
| 6 | Cost Baseline | PMP |

#### 9.4.3 Output

Risk Register P-FNE-05

A. Teknis (Technical Risks)

| ID | Risiko | Deskripsi | Kategori | Probabilitas | Dampak |
| --- | --- | --- | --- | --- | --- |
| R-001 | Integrasi dengan sistem eksternal gagal | Payment gateway atau carrier API tidak terintegrasi dengan baik | Technical | Medium (50%) | Major |
| R-002 | Performance tidak mencapai target | Response time dan throughput tidak sesuai NFR | Technical | Medium (50%) | Major |
| R-003 | API Gateway bottleneck | API Gateway menjadi single point of failure | Technical | Medium (50%) | Major |
| R-004 | Security vulnerability | Celah keamanan ditemukan setelah deployment | Technical | Low (20%) | Catastrophic |
| R-005 | Data migration error | Data yang dimigrasi tidak akurat atau hilang | Technical | Medium (50%) | Major |
| R-006 | Database performance issue | Query lambat, locking, deadlock | Technical | Medium (50%) | Moderate |
| R-007 | Third-party API changes | API vendor berubah tanpa notifikasi | Technical | Low (20%) | Moderate |
| R-008 | Technical debt accumulation | Code quality menurun karena terburu-buru | Technical | Medium (50%) | Moderate |
| R-009 | Microservices communication failure | Kafka down, service discovery issue | Technical | Low (20%) | Major |
| R-010 | Container orchestration issue | Kubernetes deployment failure | Technical | Low (20%) | Moderate |

B. Jadwal (Schedule Risks)

| ID | Risiko | Deskripsi | Kategori | Probabilitas | Dampak |
| --- | --- | --- | --- | --- | --- |
| R-011 | Scope creep | Perubahan scope yang tidak terkendali | Schedule | High (70%) | Moderate |
| R-012 | Dependency with other projects | P-FNE-01,03,04,06 terlambat | Schedule | Medium (50%) | Moderate |
| R-013 | Estimasi tidak akurat | Story points tidak sesuai kemampuan tim | Schedule | Medium (50%) | Moderate |
| R-014 | Resource unavailability | Anggota tim sakit, cuti, keluar | Schedule | Low (20%) | Major |
| R-015 | Integration delay | Integrasi dengan sistem lain lebih lama | Schedule | Medium (50%) | Moderate |
| R-016 | UAT delay | End user tidak tersedia untuk UAT | Schedule | Medium (50%) | Moderate |
| R-017 | Requirement changes | Perubahan requirement dari stakeholder | Schedule | High (70%) | Moderate |

C. Biaya (Cost Risks)

| ID | Risiko | Deskripsi | Kategori | Probabilitas | Dampak |
| --- | --- | --- | --- | --- | --- |
| R-018 | Over budget | Biaya aktual melebihi budget | Cost | Medium (50%) | Moderate |
| R-019 | Currency fluctuation | Perubahan kurs untuk software license | Cost | Low (20%) | Minor |
| R-020 | Vendor cost increase | Kenaikan biaya dari vendor | Cost | Low (20%) | Moderate |
| R-021 | Infrastructure cost overrun | Biaya cloud lebih tinggi dari estimasi | Cost | Medium (50%) | Moderate |
| R-022 | Resource cost increase | Kenaikan tarif personil | Cost | Low (20%) | Minor |

D. Sumber Daya (Resource Risks)

| ID | Risiko | Deskripsi | Kategori | Probabilitas | Dampak |
| --- | --- | --- | --- | --- | --- |
| R-023 | Kehilangan key developer | Developer kunci keluar dari proyek | Resource | Low (20%) | Major |
| R-024 | Skill gap | Tim tidak memiliki skill yang dibutuhkan | Resource | Medium (50%) | Moderate |
| R-025 | Team conflict | Konflik antar anggota tim | Resource | Low (20%) | Moderate |
| R-026 | Burnout | Tim kelelahan karena beban kerja berlebih | Resource | Medium (50%) | Moderate |

E. Kualitas (Quality Risks)

| ID | Risiko | Deskripsi | Kategori | Probabilitas | Dampak |
| --- | --- | --- | --- | --- | --- |
| R-027 | Code quality issue | Code quality tidak memenuhi standar | Quality | Medium (50%) | Moderate |
| R-028 | Testing coverage rendah | Unit test coverage di bawah target | Quality | Medium (50%) | Moderate |
| R-029 | Critical bug di production | Bug kritis ditemukan setelah go-live | Quality | Low (20%) | Major |
| R-030 | UAT tidak lulus | End user tidak menyetujui sistem | Quality | Low (20%) | Major |

F. Eksternal (External Risks)

| ID | Risiko | Deskripsi | Kategori | Probabilitas | Dampak |
| --- | --- | --- | --- | --- | --- |
| R-031 | Regulasi baru | Perubahan regulasi yang mempengaruhi sistem | External | Low (20%) | Major |
| R-032 | Cloud service outage | AWS/GCP downtime | External | Low (20%) | Major |
| R-033 | Natural disaster | Bencana alam yang mempengaruhi tim/operasi | External | Very Low (5%) | Catastrophic |
| R-034 | Pandemi/wabah | Wabah yang mempengaruhi tim | External | Low (20%) | Major |
| R-035 | Vendor bankruptcy | Vendor payment gateway/carrier bangkrut | External | Very Low (5%) | Major |
| R-036 | Cybersecurity attack | Serangan keamanan siber | External | Low (20%) | Catastrophic |

### 9.5 Perform Qualitative Risk Analysis

#### 9.5.1 Deskripsi Proses

Proses ini menganalisis probabilitas dan dampak risiko secara kualitatif untuk menentukan prioritas risiko.

#### 9.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Risk Register (Identified Risks) | Identify Risks |
| 2 | Risk Management Plan | Plan Risk Management |

#### 9.5.3 Output

Prioritized Risk Register

Top 10 Risiko Berdasarkan Skor:

| Rank | ID | Risiko | Probabilitas | Dampak | Skor | Strategi |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | R-001 | Integrasi dengan sistem eksternal gagal | Medium (50%) | Major | 25 | Mitigate |
| 2 | R-002 | Performance tidak mencapai target | Medium (50%) | Major | 25 | Mitigate |
| 3 | R-003 | API Gateway bottleneck | Medium (50%) | Major | 25 | Mitigate |
| 4 | R-011 | Scope creep | High (70%) | Moderate | 21 | Avoid |
| 5 | R-004 | Security vulnerability | Low (20%) | Catastrophic | 18 | Mitigate |
| 6 | R-005 | Data migration error | Medium (50%) | Major | 25 | Mitigate |
| 7 | R-023 | Kehilangan key developer | Low (20%) | Major | 16 | Mitigate |
| 8 | R-018 | Over budget | Medium (50%) | Moderate | 15 | Accept |
| 9 | R-012 | Dependency with other projects | Medium (50%) | Moderate | 15 | Mitigate |
| 10 | R-032 | Cloud service outage | Low (20%) | Major | 16 | Accept |

Risk Matrix Visualization:

text

Probabilitas │

│

Very High    │          R-011    │

│                  │

High         │                  │

│                  │

Medium       │ R-001 R-002 R-003│ R-005

│ R-018 R-012      │

Low          │ R-032     R-023  │ R-004

│                  │

Very Low     │                  │

└──────────────────┴──────────────────

Insignif   Minor  Moderate   Major   Catastrophic

Dampak

### 9.6 Plan Risk Responses

#### 9.6.1 Deskripsi Proses

Proses ini merencanakan respons untuk setiap risiko yang telah diprioritaskan.

#### 9.6.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Prioritized Risk Register | Qualitative Risk Analysis |
| 2 | Risk Management Plan | Plan Risk Management |
| 3 | Resource Management Plan | PMP |

#### 9.6.3 Output

Risk Response Plan

| ID | Risiko | Strategi | Tindakan Mitigasi | Kontingensi | Owner | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Integrasi eksternal gagal | Mitigate | - Mock testing dengan stub - Contract testing - Fallback mechanism | Manual fallback process | Tech Lead | M1-M5 |
| R-002 | Performance tidak mencapai target | Mitigate | - Performance testing sejak awal - Profiling & optimization - Caching implementation | Infrastruktur scaling | Tech Lead | M3-M5 |
| R-003 | API Gateway bottleneck | Mitigate | - Load testing API Gateway - Implement caching - Auto-scaling configuration | Manual scaling | Tech Lead | M1-M5 |
| R-004 | Security vulnerability | Mitigate | - Security code review - OWASP training - Penetration testing | Incident response plan | Tech Lead | M1-M5 |
| R-005 | Data migration error | Mitigate | - Data validation script - Backup & rollback plan | Restore from backup | QA Lead | M3-M5 |
| R-011 | Scope creep | Avoid | - Strict change control - Scope management - Change Request Process | Escalation to sponsor | PM | M1-M5 |
| R-023 | Kehilangan key developer | Mitigate | - Cross-training - Documentation - Pair programming | Hire replacement | PM | M1-M5 |
| R-018 | Over budget | Accept | - Budget contingency 10% - Monthly cost review | Cost cutting | PM | M1-M5 |
| R-012 | Dependency with other projects | Mitigate | - Early coordination - API contract - Integration testing | Prioritization | PM | M3-M5 |
| R-032 | Cloud service outage | Accept | - Multi-region deployment - Monitoring & alert | Manual failover | DevOps | M1-M5 |

#### 9.6.4 Response Strategy Definitions

| Strategi | Deskripsi | Contoh |
| --- | --- | --- |
| Avoid | Menghilangkan risiko dengan mengubah rencana | Scope change control |
| Mitigate | Mengurangi probabilitas atau dampak | Performance testing |
| Transfer | Mengalihkan risiko ke pihak ketiga | Insurance, warranty |
| Accept | Menerima risiko, dengan atau tanpa contingency | Budget contingency |
| Exploit | Memanfaatkan risiko positif | Opportunity for innovation |

### 9.7 Implement Risk Responses

#### 9.7.1 Deskripsi Proses

Proses ini melaksanakan respons risiko yang telah direncanakan.

#### 9.7.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Risk Response Plan | Plan Risk Responses |
| 2 | Project Documents | Semua dokumen |

#### 9.7.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Change Requests | Permintaan perubahan dari implementasi respons |
| 2 | Project Documents Updates | Update dokumen |
| 3 | Risk Register Updates | Update status risiko |

#### 9.7.4 Risk Implementation Schedule

| ID | Risiko | Tindakan | Implementation Timeline | Status |
| --- | --- | --- | --- | --- |
| R-001 | Integrasi eksternal | Mock testing setup | M1 | Planned |
| R-002 | Performance | Performance testing setup | M2 | Planned |
| R-003 | API Gateway | Load testing | M3 | Planned |
| R-004 | Security | Security training | M1 | Planned |
| R-005 | Data migration | Validation script | M4 | Planned |
| R-011 | Scope creep | Change control process | M1 | Implemented |
| R-023 | Key developer | Cross-training | M1-M5 | Ongoing |
| R-018 | Over budget | Cost review monthly | M1-M5 | Ongoing |
| R-012 | Dependency | Coordination meeting | M2 | Planned |
| R-032 | Cloud outage | Multi-region setup | M1 | Planned |

### 9.8 Monitor Risks

#### 9.8.1 Deskripsi Proses

Proses ini memonitor risiko secara berkelanjutan dan mengidentifikasi risiko baru.

#### 9.8.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Risk Register | Plan Risk Responses |
| 2 | Risk Management Plan | Plan Risk Management |
| 3 | Work Performance Data | Monitoring |

#### 9.8.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Risk Register Updates | Update status, mitigasi |
| 2 | Change Requests | Permintaan perubahan |
| 3 | Project Management Plan Updates | Update rencana |

#### 9.8.4 Risk Monitoring Activities

A. Weekly Risk Review

| Elemen | Deskripsi |
| --- | --- |
| Waktu | Setiap minggu (dalam daily/weekly meeting) |
| Peserta | PM, Tech Lead, QA Lead |
| Agenda | Review status risiko, update mitigasi, identifikasi risiko baru |

B. Risk Report

Template:

text

┌─────────────────────────────────────────────────────────────────────┐

│                         RISK REPORT                                │

│                    P-FNE-05: Commerce, Sales & Logistics           │

│                    Date: DD/MM/YYYY                               │

├─────────────────────────────────────────────────────────────────────┤

│ 1. RISK SUMMARY                                                    │

│    - Total Open Risks: [X]                                        │

│    - High Priority: [X]                                           │

│    - Medium Priority: [X]                                         │

│    - Low Priority: [X]                                            │

│    - Mitigated: [X]                                               │

│                                                                     │

│ 2. TOP RISKS                                                       │

│    - [Risk ID] [Description] - [Status] - [Owner]                │

│    - [Risk ID] [Description] - [Status] - [Owner]                │

│                                                                     │

│ 3. NEW RISKS IDENTIFIED                                            │

│    - [Risk ID] [Description] - [Status] - [Owner]                │

│                                                                     │

│ 4. CLOSED RISKS                                                    │

│    - [Risk ID] [Description] - [Date] - [Reason]                  │

│                                                                     │

│ 5. MITIGATION STATUS                                               │

│    - [Risk ID] [Action] - [Status] - [Effectiveness]              │

│                                                                     │

│ Prepared By: [PM Name]                                             │

│ Reviewed By: [Risk Owners]                                        │

│ Date: DD/MM/YYYY                                                  │

└─────────────────────────────────────────────────────────────────────┘

C. Risk Trigger Monitoring

| Risiko | Trigger | Monitoring Method |
| --- | --- | --- |
| R-001 | API integration failed in test | Integration test result |
| R-002 | Response time > 2 seconds | Performance test result |
| R-003 | CPU/Memory > 80% | Grafana monitoring |
| R-004 | Security scan found vulnerability | Security scan result |
| R-011 | Change requests > 5 per month | Change request count |

#### 9.8.5 Risk Reserve Management

| Reserve Type | Amount | Owner | Usage |
| --- | --- | --- | --- |
| Contingency Reserve | 10% of budget (Rp 337.280.000) | PM | Untuk risiko yang sudah diidentifikasi |
| Management Reserve | Rp 789.920.000 | Sponsor | Untuk risiko tidak teridentifikasi |

Contingency Reserve Usage:

| Risiko | Biaya Kontingensi | Status |
| --- | --- | --- |
| R-005 | Rp 50.000.000 | Allocated |
| R-018 | Rp 100.000.000 | Reserve |
| R-023 | Rp 150.000.000 | Reserve |
| Total Used | Rp 50.000.000 |  |
| Remaining | Rp 287.280.000 |  |

#### 9.8.6 Tanggung Jawab

| Peran | Tanggung Jawab Risiko |
| --- | --- |
| Project Manager | Memimpin manajemen risiko, memonitor risiko |
| Tech Lead | Mengidentifikasi risiko teknis, mitigasi |
| QA Lead | Mengidentifikasi risiko kualitas |
| Product Owner | Mengidentifikasi risiko bisnis |
| Tim | Melaporkan risiko yang ditemukan |

## BAB 10: MANAJEMEN PENGADAAN PROYEK

### 10.1 Tujuan Manajemen Pengadaan

Manajemen Pengadaan Proyek bertujuan untuk mengelola pembelian dan akuisisi produk, layanan, atau hasil yang dibutuhkan proyek dari sumber eksternal. Tujuan spesifiknya adalah:

- Mengidentifikasi kebutuhan pengadaan proyek

- Memilih vendor yang tepat untuk setiap kebutuhan

- Mengelola kontrak dengan vendor secara efektif

- Memastikan barang/jasa diterima sesuai spesifikasi

- Menutup kontrak secara formal setelah selesai

### 10.2 Proses Manajemen Pengadaan

Manajemen Pengadaan Proyek terdiri dari 4 (empat) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Plan Procurement Management | Merencanakan kebutuhan pengadaan | Minggu 1-2 |
| 2 | Conduct Procurements | Melaksanakan pengadaan dan seleksi vendor | Minggu 2-4 |
| 3 | Control Procurements | Mengelola kontrak dan kinerja vendor | Berkelanjutan |
| 4 | Close Procurements | Menutup kontrak secara formal | Akhir proyek |

### 10.3 Plan Procurement Management

#### 10.3.1 Deskripsi Proses

Proses ini menghasilkan Procurement Management Plan yang mendefinisikan kebutuhan pengadaan, jenis kontrak, kriteria seleksi vendor, dan proses pengadaan.

#### 10.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Scope Baseline | PMP |
| 3 | Cost Baseline | PMP |
| 4 | Resource Management Plan | PMP |
| 5 | Risk Register | Risk Management |
| 6 | Enterprise Environmental Factors | Organisasi |

#### 10.3.3 Output

A. Procurement Management Plan P-FNE-05

| Elemen | Deskripsi |
| --- | --- |
| Procurement Items | Cloud infrastructure, software licenses, third-party services, external developers |
| Kontrak Types | Fixed Price, Time & Material, Subscription |
| Selection Criteria | Technical capability (30%), Cost (25%), Timeline (20%), Security (15%), References (10%) |
| Vendor Management | Monthly performance review, SLA monitoring |
| Payment Terms | 30% advance, 40% milestone, 30% completion |
| Legal Compliance | Sesuai dengan regulasi Indonesia |

B. Procurement Items Matrix

| No | Item | Tipe | Vendor Type | Estimasi Biaya | Kontrak Type | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Cloud Infrastructure | Service | AWS/GCP | Rp 400.000.000 | Subscription | 5 bulan |
| 2 | Payment Gateway | Service | Midtrans/Xendit | Rp 150.000.000 | Subscription + Transaction | 5 bulan |
| 3 | Carrier API Integration | Service | JNE, SiCepat, J&T | Rp 160.000.000 | Subscription | 5 bulan |
| 4 | Software Licenses | Product | JetBrains, SonarQube, Datadog | Rp 200.000.000 | Subscription | 5 bulan |
| 5 | SMS Gateway | Service | Twilio | Rp 40.000.000 | Pay-as-you-go | 5 bulan |
| 6 | External Backend Developer | Service | Freelance/Konsultan | Rp 150.000.000 | Time & Material | 4 bulan |
| 7 | External Frontend Developer | Service | Freelance/Konsultan | Rp 150.000.000 | Time & Material | 4 bulan |
| 8 | SSL Certificate | Product | DigiCert | Rp 20.000.000 | Fixed Price | 1 tahun |
| Total |  |  |  | Rp 1.270.000.000 |  |  |

C. Vendor Selection Criteria

| Kriteria | Bobot | Metode Penilaian |
| --- | --- | --- |
| Technical Capability | 30% | Portfolio, technical interview, reference check |
| Cost | 25% | Cost proposal analysis |
| Timeline & SLA | 20% | Implementation timeline, SLA commitment |
| Security & Compliance | 15% | Security certification, compliance audit |
| References & Reputation | 10% | Client references, market reputation |

D. Procurement Schedule

| No | Item | RFP Issued | Proposal Deadline | Vendor Selection | Contract Sign | Implementation Start |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Cloud Infrastructure | M1-W1 | M1-W2 | M1-W3 | M1-W3 | M1-W4 |
| 2 | Payment Gateway | M1-W1 | M1-W2 | M1-W3 | M1-W3 | M2-W1 |
| 3 | Carrier API Integration | M1-W1 | M1-W2 | M1-W3 | M1-W3 | M2-W1 |
| 4 | Software Licenses | M1-W1 | M1-W2 | M1-W3 | M1-W3 | M1-W4 |
| 5 | SMS Gateway | M1-W2 | M1-W3 | M1-W4 | M1-W4 | M2-W1 |
| 6 | External Developers | M1-W1 | M1-W2 | M1-W3 | M1-W3 | M1-W4 |

### 10.4 Conduct Procurements

#### 10.4.1 Deskripsi Proses

Proses ini melaksanakan pengadaan dengan mengeluarkan RFP, mengevaluasi proposal, dan memilih vendor.

#### 10.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Procurement Management Plan | Plan Procurement Management |
| 2 | Procurement SOW | Plan Procurement Management |
| 3 | Source Selection Criteria | Plan Procurement Management |
| 4 | Vendor Lists | Organisasi |

#### 10.4.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Selected Vendors | Vendor yang terpilih |
| 2 | Procurement Contracts | Kontrak yang ditandatangani |
| 3 | Change Requests | Permintaan perubahan dari proses pengadaan |

#### 10.4.4 RFP Process

A. RFP Template

text

┌─────────────────────────────────────────────────────────────────────┐

│                    REQUEST FOR PROPOSAL (RFP)                      │

│                    P-FNE-05: Commerce, Sales & Logistics           │

├─────────────────────────────────────────────────────────────────────┤

│ 1. INTRODUCTION                                                    │

│    - Project Background                                            │

│    - Project Objectives                                            │

│    - Scope of Work                                                 │

│                                                                     │

│ 2. SCOPE OF SERVICES                                               │

│    - Detailed requirements                                         │

│    - Technical specifications                                      │

│    - Deliverables                                                  │

│                                                                     │

│ 3. PROPOSAL REQUIREMENTS                                           │

│    - Company profile                                               │

│    - Technical solution                                            │

│    - Implementation timeline                                       │

│    - Cost proposal                                                 │

│    - Team composition                                              │

│    - References                                                    │

│                                                                     │

│ 4. EVALUATION CRITERIA                                             │

│    - Technical (30%)                                               │

│    - Cost (25%)                                                    │

│    - Timeline (20%)                                                │

│    - Security (15%)                                                │

│    - References (10%)                                              │

│                                                                     │

│ 5. PROPOSAL SUBMISSION                                             │

│    - Deadline: DD/MM/YYYY                                         │

│    - Format: PDF                                                  │

│    - Submission: [email]                                          │

│                                                                     │

│ 6. QUESTIONS & CLARIFICATIONS                                      │

│    - Contact: [PM Name]                                           │

│    - Email: [email]                                               │

│    - Deadline: DD/MM/YYYY                                         │

└─────────────────────────────────────────────────────────────────────┘

B. Vendor Shortlist

| No | Item | Vendor Shortlist | Selected | Alasan |
| --- | --- | --- | --- | --- |
| 1 | Cloud Infrastructure | AWS, GCP, Azure | AWS | Cost effective, services complete, local support |
| 2 | Payment Gateway | Midtrans, Xendit, Doku | Midtrans | Best rate, features complete, easy integration |
| 3 | Carrier API Integration | JNE, SiCepat, J&T, Lion | JNE, SiCepat, J&T | Market leader, API support, regional coverage |
| 4 | Software Licenses | JetBrains, SonarQube, Datadog | JetBrains, SonarQube, Datadog | Complete package, enterprise support |
| 5 | SMS Gateway | Twilio, Telkom, BTS | Twilio | Reliable, easy API, good coverage |
| 6 | External Developers | Freelance (Upwork), Konsultan | Konsultan | More reliable, better quality, but more expensive |

C. Contract Types

| No | Vendor | Kontrak Type | Durasi | Nilai Kontrak | Payment Terms |
| --- | --- | --- | --- | --- | --- |
| 1 | AWS | Subscription | 5 bulan | Rp 400.000.000 | Monthly billing |
| 2 | Midtrans | Subscription + Transaction | 5 bulan | Rp 150.000.000 | Advance + transaction fee |
| 3 | JNE, SiCepat, J&T | Subscription | 5 bulan | Rp 160.000.000 | Quarterly billing |
| 4 | JetBrains, SonarQube, Datadog | Subscription | 5 bulan | Rp 200.000.000 | Annual billing |
| 5 | Twilio | Pay-as-you-go | 5 bulan | Rp 40.000.000 | Monthly billing |
| 6 | Konsultan | Time & Material | 4 bulan | Rp 300.000.000 | Monthly billing |

D. Evaluation Process

text

┌─────────────────────────────────────────────────────────────────────┐

│                    VENDOR EVALUATION PROCESS                       │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  [1] RFP ISSUED                                                    │

│  │   - Kirim RFP ke vendor shortlist                              │

│  │   - Berikan waktu 5-7 hari untuk proposal                      │

│  │   ↓                                                            │

│  [2] PROPOSAL RECEIVED                                             │

│  │   - Kumpulkan proposal dari vendor                            │

│  │   - Dokumentasikan proposal yang diterima                     │

│  │   ↓                                                            │

│  [3] INITIAL SCREENING                                              │

│  │   - Screening berdasarkan kriteria minimum                    │

│  │   - Eliminasi vendor yang tidak memenuhi                      │

│  │   ↓                                                            │

│  [4] DETAILED EVALUATION                                           │

│  │   - Evaluasi berdasarkan 5 kriteria                            │

│  │   - Scoring dan ranking                                        │

│  │   - Technical interview/clarification                         │

│  │   ↓                                                            │

│  [5] VENDOR SELECTION                                              │

│  │   - Pilih vendor dengan skor tertinggi                        │

│  │   - Negosiasi final terms                                     │

│  │   ↓                                                            │

│  [6] CONTRACT SIGNING                                              │

│      - Finalisasi kontrak                                          │

│      - Penandatanganan kontrak                                    │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

E. Vendor Evaluation Scoring

| Vendor | Technical (30%) | Cost (25%) | Timeline (20%) | Security (15%) | References (10%) | Total |
| --- | --- | --- | --- | --- | --- | --- |
| AWS | 28 | 22 | 18 | 14 | 9 | 91 |
| GCP | 27 | 20 | 19 | 14 | 8 | 88 |
| Midtrans | 27 | 23 | 18 | 14 | 9 | 91 |
| Xendit | 26 | 22 | 19 | 13 | 9 | 89 |
| Konsultan A | 27 | 22 | 18 | 14 | 9 | 90 |
| Konsultan B | 25 | 24 | 17 | 13 | 8 | 87 |

### 10.5 Control Procurements

#### 10.5.1 Deskripsi Proses

Proses ini mengelola kontrak dan kinerja vendor selama proyek berlangsung.

#### 10.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Procurement Contracts | Conduct Procurements |
| 2 | Procurement Management Plan | Plan Procurement Management |
| 3 | Work Performance Data | Monitoring |

#### 10.5.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Work Performance Information | Informasi kinerja vendor |
| 2 | Change Requests | Permintaan perubahan kontrak |
| 3 | Procurement Documents Updates | Update dokumen |

#### 10.5.4 Vendor Performance Monitoring

A. Vendor SLA Matrix

| Vendor | SLA Parameter | Target | Actual | Status |
| --- | --- | --- | --- | --- |
| AWS | Uptime | 99.95% | 99.98% | ✅ |
| Midtrans | Transaction success | 99.9% | 99.92% | ✅ |
| Midtrans | Response time | ≤ 500ms | 350ms | ✅ |
| JNE | API uptime | 99.5% | 99.3% | ⚠️ |
| SiCepat | API uptime | 99.5% | 99.6% | ✅ |
| J&T | API uptime | 99.5% | 99.4% | ⚠️ |
| Konsultan | Delivery time | 100% | 95% | ⚠️ |
| Twilio | SMS delivery | 98% | 97.5% | ⚠️ |

B. Vendor Performance Review

| Vendor | Review Frequency | Next Review | Status | Action |
| --- | --- | --- | --- | --- |
| AWS | Bulanan | 15/10/2026 | Good | Continue |
| Midtrans | Bulanan | 15/10/2026 | Good | Continue |
| JNE | 2 Minggu | 23/09/2026 | Warning | Request improvement |
| SiCepat | 2 Minggu | 23/09/2026 | Good | Continue |
| J&T | 2 Minggu | 23/09/2026 | Warning | Request improvement |
| Konsultan | 2 Minggu | 23/09/2026 | Warning | Review resource allocation |
| Twilio | Bulanan | 15/10/2026 | Warning | Request improvement |

C. Vendor Invoice Management

| Vendor | Invoice Date | Amount | Payment Status | Due Date |
| --- | --- | --- | --- | --- |
| AWS | 01/09/2026 | Rp 80.000.000 | Paid | 15/09/2026 |
| Midtrans | 01/09/2026 | Rp 30.000.000 | Paid | 15/09/2026 |
| Konsultan | 01/09/2026 | Rp 75.000.000 | Paid | 15/09/2026 |
| JNE | 01/09/2026 | Rp 32.000.000 | Pending | 15/09/2026 |

### 10.6 Close Procurements

#### 10.6.1 Deskripsi Proses

Proses ini menutup kontrak secara formal setelah semua pekerjaan selesai dan deliverables telah diterima.

#### 10.6.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Procurement Contracts | Conduct Procurements |
| 2 | Procurement Documents | Control Procurements |
| 3 | Accepted Deliverables | Quality Management |

#### 10.6.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Closed Procurements | Kontrak yang telah ditutup |
| 2 | Organizational Process Assets Updates | Update aset organisasi |
| 3 | Lessons Learned | Pembelajaran dari pengadaan |

#### 10.6.4 Procurement Closure Checklist

| No | Item | Status | Owner | Tanggal |
| --- | --- | --- | --- | --- |
| 1 | All deliverables accepted | ☐ | PM |  |
| 2 | Final payment completed | ☐ | Finance |  |
| 3 | All warranties and guarantees | ☐ | PM |  |
| 4 | Vendor performance evaluation | ☐ | PM |  |
| 5 | Final invoice received | ☐ | Finance |  |
| 6 | All disputes resolved | ☐ | PM |  |
| 7 | Contract officially closed | ☐ | PM |  |
| 8 | Lessons learned documented | ☐ | PM |  |

### 10.7 Ringkasan Pengadaan Proyek

| No | Vendor | Item | Nilai Kontrak | Status | Keterangan |
| --- | --- | --- | --- | --- | --- |
| 1 | AWS | Cloud Infrastructure | Rp 400.000.000 | Active | Good performance |
| 2 | Midtrans | Payment Gateway | Rp 150.000.000 | Active | Good performance |
| 3 | JNE | Carrier API | Rp 60.000.000 | Active | Improvement needed |
| 4 | SiCepat | Carrier API | Rp 50.000.000 | Active | Good performance |
| 5 | J&T | Carrier API | Rp 50.000.000 | Active | Improvement needed |
| 6 | JetBrains | Software License | Rp 50.000.000 | Active | Good |
| 7 | SonarQube | Software License | Rp 30.000.000 | Active | Good |
| 8 | Datadog | Software License | Rp 60.000.000 | Active | Good |
| 9 | Twilio | SMS Gateway | Rp 40.000.000 | Active | Improvement needed |
| 10 | Konsultan | External Developers | Rp 300.000.000 | Active | Warning - delivery delay |
| 11 | DigiCert | SSL Certificate | Rp 20.000.000 | Active | Good |
| Total |  |  | Rp 1.210.000.000 |  |  |

## BAB 11: MANAJEMEN PEMANGKU KEPENTINGAN PROYEK

### 11.1 Tujuan Manajemen Pemangku Kepentingan

Manajemen Pemangku Kepentingan Proyek bertujuan untuk mengidentifikasi, menganalisis, dan mengelola stakeholder proyek untuk memastikan keterlibatan yang efektif dan dukungan terhadap proyek. Tujuan spesifiknya adalah:

- Mengidentifikasi semua stakeholder proyek

- Menganalisis kepentingan, pengaruh, dan ekspektasi stakeholder

- Merencanakan strategi engagement yang tepat

- Mengelola hubungan dan komunikasi dengan stakeholder

- Memonitor efektivitas engagement stakeholder

### 11.2 Proses Manajemen Pemangku Kepentingan

Manajemen Pemangku Kepentingan Proyek terdiri dari 4 (empat) proses utama sesuai dengan PMBOK:

| No | Proses | Deskripsi | Timeline |
| --- | --- | --- | --- |
| 1 | Identify Stakeholders | Mengidentifikasi semua stakeholder | Minggu 1-2 |
| 2 | Plan Stakeholder Engagement | Merencanakan strategi engagement | Minggu 1-2 |
| 3 | Manage Stakeholder Engagement | Melaksanakan engagement | Berkelanjutan |
| 4 | Monitor Stakeholder Engagement | Memonitor efektivitas engagement | Berkelanjutan |

### 11.3 Identify Stakeholders

#### 11.3.1 Deskripsi Proses

Proses ini mengidentifikasi semua individu, kelompok, atau organisasi yang dapat mempengaruhi atau dipengaruhi oleh proyek.

#### 11.3.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Project Charter | Project Sponsor |
| 2 | Procurement Documents | Procurement Management |
| 3 | Enterprise Environmental Factors | Organisasi |
| 4 | Organizational Process Assets | Organisasi |

#### 11.3.3 Output

Stakeholder Register P-FNE-05

| ID | Nama | Peran | Departemen | Pengaruh | Kepentingan | Keterlibatan |
| --- | --- | --- | --- | --- | --- | --- |
| S-001 | CEO FNE | Project Sponsor | Executive | High | High | Steering |
| S-002 | CFO FNE | Finance Approver | Finance | High | High | Steering |
| S-003 | CIO FNE | Technical Executive | IT | High | High | Steering |
| S-004 | Director of Sales | Domain Expert | Sales | Medium | High | Consulted |
| S-005 | Director of Operations | Domain Expert | Operations | Medium | High | Consulted |
| S-006 | Project Manager | PM | PMO | High | High | Leading |
| S-007 | Product Owner | PO | PMO | High | High | Leading |
| S-008 | Tech Lead | Technical Lead | IT | High | High | Leading |
| S-009 | Backend Team | Developers | IT | Medium | High | Participating |
| S-010 | Frontend Team | Developers | IT | Medium | High | Participating |
| S-011 | Mobile Team | Developers | IT | Medium | High | Participating |
| S-012 | QA Team | Testers | IT | Medium | High | Participating |
| S-013 | BA Team | Business Analysts | IT | Medium | High | Participating |
| S-014 | UX Designer | Designer | IT | Medium | Medium | Participating |
| S-015 | DevOps Team | Infrastructure | IT | Medium | Medium | Participating |
| S-016 | End Users (Sales) | Users | Sales | Low | Medium | Consulted |
| S-017 | End Users (Logistics) | Users | Operations | Low | Medium | Consulted |
| S-018 | End Users (CS) | Users | CS | Low | Medium | Consulted |
| S-019 | End Users (Finance) | Users | Finance | Low | Medium | Consulted |
| S-020 | Supplier Users | Users | External | Low | Low | Informed |
| S-021 | Customer Users | Users | External | Low | Low | Informed |
| S-022 | AWS | Vendor | External | Low | Low | Informed |
| S-023 | Midtrans | Vendor | External | Low | Low | Informed |
| S-024 | JNE, SiCepat, J&T | Vendors | External | Low | Low | Informed |
| S-025 | Konsultan | Vendor | External | Low | Low | Informed |
| S-026 | P-FNE-01 Team | Internal Team | IT | Medium | Medium | Consulted |
| S-027 | P-FNE-03 Team | Internal Team | IT | Medium | Medium | Consulted |
| S-028 | P-FNE-04 Team | Internal Team | IT | Medium | Medium | Consulted |
| S-029 | P-FNE-06 Team | Internal Team | IT | Medium | Medium | Consulted |

### 11.4 Plan Stakeholder Engagement

#### 11.4.1 Deskripsi Proses

Proses ini merencanakan strategi engagement untuk setiap stakeholder berdasarkan tingkat pengaruh dan kepentingannya.

#### 11.4.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Stakeholder Register | Identify Stakeholders |
| 2 | Project Management Plan | PMP |
| 3 | Communications Management Plan | PMP |

#### 11.4.3 Output

Stakeholder Engagement Plan P-FNE-05

A. Stakeholder Power-Interest Grid

text

Power │

│

High  │  S-001, S-002,     │  S-004, S-005, S-006

│  S-003             │  S-007, S-008

│  (Keep Satisfied)  │  (Manage Closely)

│                    │

│                    │

Low   │  S-020, S-021,     │  S-009, S-010, S-011

│  S-022, S-023,     │  S-012, S-013, S-014

│  S-024, S-025      │  S-015, S-016, S-017

│  (Monitor)         │  S-018, S-019, S-026

│                    │  S-027, S-028, S-029

│                    │  (Keep Informed)

│                    │

└────────────────────┴─────────────────────

Low Interest         High Interest

B. Engagement Strategies by Stakeholder Group

| Kelompok | Stakeholder | Engagement Level | Strategi | Metode |
| --- | --- | --- | --- | --- |
| Manage Closely | CEO, CFO, CIO, Director of Sales, Director of Operations | High | Regular reporting, steering meetings, involve in decisions | Monthly report, steering committee, 1-on-1 meetings |
| Manage Closely | PM, PO, Tech Lead | High | Daily coordination, sprint rituals, decision making | Daily stand-up, sprint planning, sprint review |
| Keep Satisfied | Sponsor, Steering Committee | High | Proactive communication, issue escalation | Monthly report, steering meeting, escalation process |
| Keep Informed | Dev Teams (BE, FE, Mobile), QA, BA, UX, DevOps | Medium | Transparent communication, involve in process | Daily stand-up, sprint rituals, JIRA, Confluence |
| Keep Informed | End Users (Sales, Logistics, CS, Finance) | Medium | UAT, training, feedback sessions | UAT sessions, user training, feedback survey |
| Consulted | P-FNE-01,03,04,06 Teams | Medium | Integration coordination, API design | Integration meetings, API docs, joint planning |
| Monitor | External Vendors, Suppliers, Customers | Low | SLA monitoring, status updates | SLA reports, email updates, portal |

C. Stakeholder Communication Plan

| Stakeholder | Communication Need | Frequency | Method | Owner |
| --- | --- | --- | --- | --- |
| CEO, CFO, CIO | Project status, budget, risks | Bulanan | Monthly Report | PM |
| Steering Committee | Progress, decisions | 2 Minggu | Steering Meeting | PM |
| Director of Sales | Feature prioritization, domain input | 2 Minggu | 1-on-1 Meeting | PO |
| Director of Operations | Logistics requirements | 2 Minggu | 1-on-1 Meeting | PO |
| PM, PO, Tech Lead | Daily coordination | Harian | Daily Stand-up | PM |
| Dev Teams | Task assignment, progress | Harian | Daily Stand-up, JIRA | Tech Lead |
| QA Team | Test progress, bugs | Harian | Daily Stand-up, JIRA | QA Lead |
| End Users | UAT, feedback | Sesuai kebutuhan | UAT Session, Survey | BA |
| P-FNE Teams | Integration status | 2 Minggu | Integration Meeting | Tech Lead |
| Vendors | SLA, technical issues | Mingguan | Email, Meeting | Tech Lead |

### 11.5 Manage Stakeholder Engagement

#### 11.5.1 Deskripsi Proses

Proses ini melaksanakan strategi engagement stakeholder sesuai dengan rencana.

#### 11.5.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Stakeholder Engagement Plan | Plan Stakeholder Engagement |
| 2 | Communications Management Plan | PMP |
| 3 | Project Documents | Semua dokumen |

#### 11.5.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Issue Log | Log isu yang muncul |
| 2 | Change Requests | Permintaan perubahan dari stakeholder |
| 3 | Project Management Plan Updates | Update rencana |
| 4 | Project Documents Updates | Update dokumen |

#### 11.5.4 Engagement Activities Schedule

A. Monthly Activities

| Aktivitas | Peserta | Tujuan | Waktu |
| --- | --- | --- | --- |
| Monthly Board Report | Sponsor + Steering | Laporan bulanan | Akhir bulan |
| Executive Dashboard Update | Sponsor + PM | Review KPI | Awal bulan |
| Steering Committee Meeting | Steering | Keputusan strategis | 2 minggu |

B. Bi-weekly Activities

| Aktivitas | Peserta | Tujuan | Waktu |
| --- | --- | --- | --- |
| Sprint Planning | Tim + PO | Perencanaan sprint | Awal sprint |
| Sprint Review | Tim + PO + Stakeholder | Demo dan feedback | Akhir sprint |
| Sprint Retrospective | Tim | Evaluasi dan perbaikan | Akhir sprint |
| Integration Meeting | P-FNE Teams | Koordinasi integrasi | 2 minggu |
| 1-on-1 with Directors | PO + Directors | Domain input | 2 minggu |

C. Daily Activities

| Aktivitas | Peserta | Tujuan | Waktu |
| --- | --- | --- | --- |
| Daily Stand-up | Tim | Sinkronisasi harian | 09:00 |
| JIRA Updates | Tim | Task progress tracking | Sepanjang hari |
| Slack Communication | Tim | Koordinasi real-time | Sepanjang hari |

D. UAT Activities

| Aktivitas | Peserta | Tujuan | Waktu |
| --- | --- | --- | --- |
| UAT Session | End Users + QA | Testing dan feedback | M4-M5 |
| Feedback Survey | End Users | Kepuasan pengguna | Pasca-UAT |
| User Training | End Users | Pelatihan penggunaan | M5 |

#### 11.5.5 Issue Log

Template Issue Log:

text

┌─────────────────────────────────────────────────────────────────────┐

│                           ISSUE LOG                                │

│                    P-FNE-05: Commerce, Sales & Logistics           │

├─────────────────────────────────────────────────────────────────────┤

│ Issue ID   : ISS-001                                               │

│ Date       : DD/MM/YYYY                                          │

│ Raised By  : [Name] - [Role]                                     │

│ Category   : Technical / Resource / Process / Stakeholder         │

│                                                                     │

│ DESCRIPTION:                                                       │

│ [Deskripsi issue]                                                  │

│                                                                     │

│ IMPACT:                                                            │

│ [Dampak pada proyek]                                              │

│                                                                     │

│ STATUS:                                                            │

│ ☐ Open   ☐ In Progress   ☐ Resolved   ☐ Closed                   │

│                                                                     │

│ RESOLUTION:                                                        │

│ [Tindakan penyelesaian]                                            │

│                                                                     │

│ ASSIGNED TO: [Name]                                                │

│ DUE DATE: DD/MM/YYYY                                              │

│ CLOSED DATE: DD/MM/YYYY                                           │

└─────────────────────────────────────────────────────────────────────┘

### 11.6 Monitor Stakeholder Engagement

#### 11.6.1 Deskripsi Proses

Proses ini memonitor efektivitas engagement stakeholder dan mengambil tindakan jika diperlukan.

#### 11.6.2 Input

| No | Input | Sumber |
| --- | --- | --- |
| 1 | Stakeholder Engagement Plan | Plan Stakeholder Engagement |
| 2 | Issue Log | Manage Stakeholder Engagement |
| 3 | Work Performance Data | Monitoring |

#### 11.6.3 Output

| No | Output | Deskripsi |
| --- | --- | --- |
| 1 | Work Performance Information | Informasi kinerja engagement |
| 2 | Change Requests | Permintaan perubahan strategi |
| 3 | Project Management Plan Updates | Update rencana |

#### 11.6.4 Engagement Effectiveness Metrics

| Metrik | Deskripsi | Target | Metode Pengukuran |
| --- | --- | --- | --- |
| Stakeholder Satisfaction | Tingkat kepuasan stakeholder | ≥ 4/5 | Survey (bulanan) |
| Meeting Attendance | Kehadiran dalam meeting | ≥ 90% | Tracking |
| Issue Resolution | Isu terselesaikan tepat waktu | ≥ 95% | Issue Log |
| Feedback Received | Jumlah feedback stakeholder | ≥ 80% respond | Survey |
| Communication Effectiveness | Efektivitas komunikasi | ≥ 4/5 | Survey |
| UAT Participation | Partisipasi UAT | ≥ 90% | Tracking |

#### 11.6.5 Stakeholder Feedback Survey

Template:

text

┌─────────────────────────────────────────────────────────────────────┐

│                    STAKEHOLDER FEEDBACK SURVEY                    │

│                    P-FNE-05: Commerce, Sales & Logistics           │

├─────────────────────────────────────────────────────────────────────┤

│ Stakeholder: [Name] - [Role]                                      │

│ Date: DD/MM/YYYY                                                  │

│                                                                     │

│ 1. SATISFACTION (1-5)                                             │

│    - Project Progress: [ ]                                       │

│    - Communication: [ ]                                          │

│    - Decision Making: [ ]                                        │

│    - Quality of Deliverables: [ ]                                │

│    - Overall Satisfaction: [ ]                                   │

│                                                                     │

│ 2. WHAT IS WORKING WELL?                                          │

│    [Open feedback]                                                │

│                                                                     │

│ 3. WHAT NEEDS IMPROVEMENT?                                        │

│    [Open feedback]                                                │

│                                                                     │

│ 4. SUGGESTIONS FOR IMPROVEMENT                                    │

│    [Open feedback]                                                │

│                                                                     │

│ 5. OTHER COMMENTS                                                 │

│    [Open feedback]                                                │

│                                                                     │

│ Signature: [ ]                                                    │

│ Date: DD/MM/YYYY                                                  │

└─────────────────────────────────────────────────────────────────────┘

#### 11.6.6 Stakeholder Engagement Dashboard

text

┌─────────────────────────────────────────────────────────────────────┐

│                 STAKEHOLDER ENGAGEMENT DASHBOARD                   │

│                    P-FNE-05: Commerce, Sales & Logistics           │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ STAKEHOLDER SATISFACTION                                           │

│ ┌────────────────────────────────────────────────────────────┐     │

│ │ Sponsor   │ ████████████████████▌  4.2/5                  │     │

│ │ Steering  │ █████████████████████▌  4.5/5                 │     │

│ │ Directors │ ████████████████████▌  4.0/5                  │     │

│ │ PM/PO     │ █████████████████████▌  4.6/5                 │     │

│ │ Dev Team  │ █████████████████████▌  4.3/5                 │     │

│ │ End Users │ ███████████████████▌   3.8/5                  │     │

│ └────────────────────────────────────────────────────────────┘     │

│                                                                     │

│ MEETING ATTENDANCE                                                 │

│ ┌────────────────────────────────────────────────────────────┐     │

│ │ Daily Stand-up │ ████████████████████████▌  95%          │     │

│ │ Sprint Planning│ ███████████████████████▌   92%          │     │

│ │ Sprint Review  │ ████████████████████████▌  94%          │     │

│ │ Steering Meet  │ ███████████████████████▌   90%          │     │

│ └────────────────────────────────────────────────────────────┘     │

│                                                                     │

│ OPEN ISSUES BY CATEGORY                                            │

│ ┌────────────────────────────────────────────────────────────┐     │

│ │ Technical   │ ████████████▌  4                            │     │

│ │ Resource    │ ███████▌       2                            │     │

│ │ Process     │ ████████▌      3                            │     │

│ │ Stakeholder │ ████▌          1                            │     │

│ └────────────────────────────────────────────────────────────┘     │

│                                                                     │

│ UAT PARTICIPATION                                                  │

│ ┌────────────────────────────────────────────────────────────┐     │

│ │ Sales Dept   │ ████████████████████████▌  100%           │     │

│ │ Logistics    │ ██████████████████████▌    85%            │     │

│ │ CS Dept      │ ████████████████████▌      80%            │     │

│ │ Finance Dept │ ███████████████████▌       75%            │     │

│ └────────────────────────────────────────────────────────────┘     │

└─────────────────────────────────────────────────────────────────────┘

#### 11.6.7 Stakeholder Engagement Improvement Plan

| Area | Issue | Tindakan Perbaikan | Timeline | Owner |
| --- | --- | --- | --- | --- |
| End User Engagement | UAT participation low (75-80%) | Personal invitation, flexible schedule, incentives | M4-M5 | BA |
| Communication | Technical jargon too heavy | Simplify communication, use layman terms | Ongoing | PM |
| Feedback | Low survey response | Shorter survey, reminders, incentives | Ongoing | PM |
| Decision Making | Slow decisions | Clear escalation path, empower PO | Ongoing | PM |

#### 11.6.8 Stakeholder Management Responsibilities

| Peran | Tanggung Jawab |
| --- | --- |
| Project Manager | Overall stakeholder management, primary contact |
| Product Owner | Manage business stakeholders, domain experts |
| Tech Lead | Manage technical stakeholders, vendors |
| QA Lead | Manage UAT stakeholders, end users |
| BA | Manage requirements stakeholders, feedback |
| Tim | Engage with stakeholders as needed |

### 11.7 Ringkasan Pemangku Kepentingan

A. Total Stakeholder: 29 stakeholder

B. Stakeholder Distribution by Category:

| Kategori | Jumlah | Persentase |
| --- | --- | --- |
| Internal - Executive | 5 | 17% |
| Internal - Project Team | 13 | 45% |
| Internal - End Users | 4 | 14% |
| Internal - Other P-FNE Teams | 4 | 14% |
| External - Vendors | 3 | 10% |

C. Stakeholder Engagement Status:

| Status | Jumlah | Persentase |
| --- | --- | --- |
| Leading | 3 | 10% |
| Participating | 10 | 34% |
| Consulted | 6 | 21% |
| Informed | 10 | 34% |

D. Critical Stakeholders (Manage Closely):

| ID | Nama | Peran |
| --- | --- | --- |
| S-001 | CEO FNE | Project Sponsor |
| S-002 | CFO FNE | Finance Approver |
| S-003 | CIO FNE | Technical Executive |
| S-004 | Director of Sales | Domain Expert |
| S-005 | Director of Operations | Domain Expert |
| S-006 | Project Manager | PM |
| S-007 | Product Owner | PO |
| S-008 | Tech Lead | Technical Lead |

== BAB 11 SELESAI ==

## BAB 12: PENUTUP

### 12.1 Ringkasan PMP

Project Management Plan (PMP) untuk Proyek P-FNE-05: Commerce, Sales & Logistics telah disusun secara komprehensif mencakup 11 (sebelas) area manajemen sesuai dengan PMBOK:

| No | Area Manajemen | Status |
| --- | --- | --- |
| 1 | Manajemen Integrasi Proyek | ✓ |
| 2 | Manajemen Ruang Lingkup Proyek | ✓ |
| 3 | Manajemen Jadwal Proyek | ✓ |
| 4 | Manajemen Biaya Proyek | ✓ |
| 5 | Manajemen Kualitas Proyek | ✓ |
| 6 | Manajemen Sumber Daya Proyek | ✓ |
| 7 | Manajemen Komunikasi Proyek | ✓ |
| 8 | Manajemen Risiko Proyek | ✓ |
| 9 | Manajemen Pengadaan Proyek | ✓ |
| 10 | Manajemen Pemangku Kepentingan Proyek | ✓ |

### 12.2 Key Deliverables

| No | Deliverable | Deskripsi | Target |
| --- | --- | --- | --- |
| 1 | Sales Management Module | Sales Order, Invoice, Payment, Return | M3 |
| 2 | CRM Module | Customer Master, Interaction, Complaint | M4 |
| 3 | Marketplace Module | Listing, Catalog, Cart, Checkout, Review | M5 |
| 4 | Logistics Module | Shipment, Tracking, POD, Carrier | M6 |
| 5 | Portal Module | Customer Portal, Supplier Portal | M7 |
| 6 | Integrated System | Integration with P-FNE-01,03,04,06 | M8 |

### 12.3 Success Criteria

Proyek dinyatakan BERHASIL apabila:

- Semua 81 functional requirements terpenuhi

- Semua 12 non-functional requirements tercapai

- UAT satisfaction ≥ 4.5/5

- Go-live dalam ≤ 5 bulan

- Budget variance ≤ 10%

### 12.4 Approval Sign-off

| Peran | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Sponsor | CEO FNE |  |  |
| Project Manager | [Nama PM] |  |  |
| Product Owner | [Nama PO] |  |  |
| Tech Lead | [Nama TL] |  |  |
| QA Lead | [Nama QA] |  |  |