# PROJECT MANAGEMENT PLAN (PMP) - DETAIL PER BAB

## PROYEK CORE AGRICULTURAL OPERATIONS (P-FNE-02)

### SUPER ERP FARM NATION ENTERPRISE (FNE)

## BAB 1: PENDAHULUAN

### 1.1. Tujuan Dokumen

Dokumen Project Management Plan (PMP) ini disusun dengan tujuan:

- Memberikan Panduan Komprehensif – Menjadi acuan utama bagi seluruh tim proyek dalam merencanakan, melaksanakan, memantau, dan mengendalikan seluruh aspek proyek P-FNE-02.

- Menjamin Keterpaduan – Mengintegrasikan seluruh rencana manajemen (scope, schedule, cost, quality, resource, communication, risk, procurement, stakeholder) ke dalam satu dokumen utuh.

- Memfasilitasi Komunikasi – Menyediakan informasi yang jelas dan terstruktur bagi seluruh stakeholder mengenai bagaimana proyek akan dikelola.

- Menjadi Baseline – Menjadi dasar pengukuran kinerja proyek dan alat kontrol perubahan.

- Memenuhi Standar PMBOK – Mengikuti kerangka kerja Project Management Body of Knowledge (PMBOK) edisi terbaru untuk memastikan praktik manajemen proyek yang terbaik.

### 1.2. Deskripsi Proyek

#### 1.2.1. Latar Belakang

Super ERP Farm Nation Enterprise (FNE) adalah platform digital terintegrasi yang dirancang untuk mengelola seluruh operasi pertanian skala besar. FNE terdiri dari 8 proyek turunan (P-FNE-01 s.d. P-FNE-08) yang saling terintegrasi dalam satu ekosistem digital yang kohesif.

Proyek P-FNE-02: Core Agricultural Operations merupakan jantung dari ekosistem FNE. Proyek ini bertanggung jawab atas digitalisasi seluruh siklus hidup pertanian, mulai dari perencanaan lahan, budidaya tanaman, pengelolaan ternak, hingga panen. Data yang dihasilkan oleh proyek ini menjadi sumber utama bagi modul-modul lain seperti Supply Chain (P-FNE-03), Production (P-FNE-04), Commerce (P-FNE-05), Finance (P-FNE-06), dan Intelligence (P-FNE-07).

#### 1.2.2. Visi Proyek

"Menjadi fondasi digital yang andal dan terintegrasi untuk pengelolaan operasi pertanian modern, yang memungkinkan peningkatan produktivitas, efisiensi, dan keberlanjutan melalui teknologi."

#### 1.2.3. Misi Proyek

- Menyediakan sistem manajemen farm dan lahan yang terintegrasi

- Mendigitalisasi siklus tanam dari perencanaan hingga panen

- Mengelola siklus ternak dari kelahiran hingga produksi

- Merekam semua aktivitas lapangan secara digital dengan dukungan offline

- Menyediakan visibilitas real-time terhadap kondisi pertanian

- Menjadi sumber data utama untuk modul-modul FNE lainnya

#### 1.2.4. Cakupan Proyek

| Komponen | Deskripsi | Modul |
| --- | --- | --- |
| Farm & Land Management | Manajemen data farm, land parcel, analisis tanah, dan fasilitas farm | Farm Service, Land Service |
| Crop Management | Siklus tanam, penanaman, growth stage, dan aktivitas budidaya | Crop Service |
| Harvest Management | Perencanaan panen, eksekusi, batch management, dan quality control | Harvest Service |
| Livestock Management | Manajemen ternak, pakan, kesehatan, reproduksi, dan produksi | Livestock Service |
| Activity Recording | Pencatatan aktivitas farm dengan dukungan mobile offline | Activity Service |
| Resource Management | Manajemen resource pertanian, alokasi, dan konsumsi | Resource Service |

#### 1.2.5. Arsitektur Teknologi

Proyek P-FNE-02 dibangun dengan arsitektur:

| Lapisan | Teknologi |
| --- | --- |
| Front-End Web | React 18, Next.js 14, TypeScript, Tailwind CSS |
| Front-End Mobile | Flutter 3.x, BLoC, SQLite |
| Back-End Services | Spring Boot 3 (Java 17) / NestJS, gRPC, REST |
| Database | PostgreSQL 15+ (PostGIS), TimescaleDB, Redis |
| Integration | Apache Kafka, REST APIs |
| Infrastructure | Docker, Kubernetes, AWS/GCP |

### 1.3. Tujuan Proyek

#### 1.3.1. Tujuan Utama

| Tujuan | Deskripsi | Metrik Keberhasilan |
| --- | --- | --- |
| Integrasi | Menyediakan sistem terintegrasi untuk seluruh operasi pertanian | 100% requirement P0 terimplementasi |
| Digitalisasi | Mendigitalisasi seluruh siklus hidup pertanian | Minimal 6 modul fungsional beroperasi |
| Efisiensi | Meningkatkan efisiensi operasional | Response time ≤ 3 detik |
| Skalabilitas | Mendukung operasi multi-farm | Mendukung unlimited farm |
| Resilien | Mendukung operasi offline | Minimal 100 transaksi offline |

#### 1.3.2. Tujuan SMART

Spesifik:

- Mengembangkan 6 modul utama (Farm, Land, Crop, Harvest, Livestock, Activity, Resource)

- Membangun 1 aplikasi web admin dan 1 aplikasi mobile

- Mengimplementasikan event-driven integration dengan 2 event utama

Measurable (Terukur):

- Minimal 5 farm dan 20 land parcel terdaftar

- Response time ≤ 3 detik untuk 90% request

- 95% UAT acceptance rate

- Minimal 100 transaksi offline support

Achievable (Dapat Dicapai):

- Tim terdiri dari 8-12 orang berpengalaman

- Durasi 5-6 bulan

- Teknologi yang digunakan sudah mature

Relevant (Relevan):

- Mendukung visi FNE sebagai platform pertanian terintegrasi

- Menjadi fondasi bagi modul-modul lainnya

Time-bound (Berbatas Waktu):

- Selesai dalam 6 bulan (Oktober 2026)

- Milestone setiap 3-4 minggu

#### 1.3.3. Key Performance Indicators (KPI)

| KPI | Target | Metode Pengukuran | Frekuensi |
| --- | --- | --- | --- |
| Sprint Velocity | ≥ 30 story points/sprint | Sprint Review | 2 minggu |
| Defect Density | ≤ 1 per KLOC | QA Report | Per sprint |
| Code Coverage | ≥ 80% | SonarQube | Per sprint |
| Response Time | ≤ 3 detik | Performance Test | Per milestone |
| UAT Acceptance | ≥ 95% | UAT Sign-off | Per milestone |
| User Satisfaction | NPS ≥ 70 | Survey | Akhir proyek |

### 1.4. Scope Statement

#### 1.4.1. In-Scope

A. Functional Requirements

| ID | Domain | Jumlah Requirement |
| --- | --- | --- |
| FNE-FRM-001 s.d. FNE-FRM-012 | Farm & Land Management | 12 requirements |
| FNE-CRP-001 s.d. FNE-CRP-014 | Crop Management | 14 requirements |
| FNE-HRV-001 s.d. FNE-HRV-010 | Harvest Management | 10 requirements |
| FNE-LIV-001 s.d. FNE-LIV-021 | Livestock Management | 21 requirements |
| FNE-ACT-001 s.d. FNE-ACT-010 | Activity Recording | 10 requirements |
| FNE-RES-001 s.d. FNE-RES-010 | Resource Management | 10 requirements |

B. Non-Functional Requirements

| ID | Requirement | Target |
| --- | --- | --- |
| FNE-NFR-FRM-001 | Farm Data Response | ≤ 3 detik |
| FNE-NFR-FRM-002 | Crop Cycle Query | ≤ 2 detik |
| FNE-NFR-FRM-003 | Mobile Offline Support | Minimal 100 transaksi |
| FNE-NFR-FRM-004 | Sync Time | ≤ 30 detik |
| FNE-NFR-FRM-005 | Geolocation Accuracy | ≤ 50 meter |
| FNE-NFR-FRM-006 | Photo Upload Size | ≤ 10 MB per foto |
| FNE-NFR-FRM-007 | Multi-Farm Support | Unlimited |
| FNE-NFR-FRM-008 | Historical Data Retention | Minimal 5 tahun |
| FNE-NFR-FRM-009 | Crop Data Integrity | 100% |
| FNE-NFR-FRM-010 | Seasonal Load | 3x normal load |

C. Deliverables

- Backend Services (6 microservices):

  - Farm Service

  - Crop Service

  - Harvest Service

  - Livestock Service

  - Activity Service

  - Resource Service

- Front-End Applications:

  - Web Admin Portal (React/Next.js)

  - Mobile Field App (Flutter)

  - Executive Dashboard (React)

- Database:

  - PostgreSQL (dengan PostGIS)

  - TimescaleDB (time-series)

  - Redis (cache)

- Integration:

  - Kafka event publishers

  - Kafka event consumers

  - REST APIs (BFF)

  - gRPC services (internal)

- Documentation:

  - Technical Architecture Document

  - API Specification

  - Database Design Document

  - User Manual

  - Deployment Guide

#### 1.4.2. Out-of-Scope

Tidak termasuk dalam cakupan proyek P-FNE-02:

| Domain | Alasan |
| --- | --- |
| Manajemen Keuangan & Akuntansi (P-FNE-06) | Ditangani oleh proyek terpisah |
| Manajemen Supply Chain (P-FNE-03) | Ditangani oleh proyek terpisah |
| Business Intelligence & AI (P-FNE-07) | Ditangani oleh proyek terpisah |
| IoT & Digital Twin (P-FNE-08) | Ditangani oleh proyek terpisah |
| Core & Foundation (P-FNE-01) | Ditangani oleh proyek terpisah |
| Manajemen Marketplace (P-FNE-05) | Ditangani oleh proyek terpisah |
| Hardware & Sensor IoT | Tanggung jawab tim IoT terpisah |
| Enterprise Integration (ERP lain) | Diluar scope FNE |

### 1.5. Stakeholder Proyek

#### 1.5.1. Daftar Stakeholder

| ID | Stakeholder | Peran | Organisasi | Harapan |
| --- | --- | --- | --- | --- |
| S-001 | Project Sponsor | Pendanaan & Dukungan | FNE Executive | Proyek selesai tepat waktu dan anggaran |
| S-002 | Steering Committee | Pengarah Strategis | FNE Management | Sistem sesuai visi FNE |
| S-003 | Project Manager | Manajemen Proyek | PMO | Proyek berjalan sesuai rencana |
| S-004 | Product Owner | Representasi Pengguna | Business Unit | Fitur sesuai kebutuhan bisnis |
| S-005 | Technical Lead | Arsitektur Teknis | Engineering | Solusi teknis yang scalable |
| S-006 | Development Team | Implementasi | Engineering | Tools dan requirement yang jelas |
| S-007 | QA Team | Pengujian | Engineering | Bug-free system |
| S-008 | Farm Manager | Pengguna Akhir | Operasional | Sistem mudah digunakan |
| S-009 | Operational Team | Pengguna Akhir | Operasional | Mendukung pekerjaan lapangan |
| S-010 | PMO | Governance | PMO | Dokumentasi dan kontrol proyek |
| S-011 | Agronomist | Pengguna Ahli | Operasional | Akurasi data pertanian |
| S-012 | Veteriner | Pengguna Ahli | Operasional | Manajemen kesehatan ternak |

#### 1.5.2. Stakeholder Analysis

Kekuasaan dan Kepentingan:

text

Kekuasaan

▲

│

H │  S-001   S-002

│  (Sponsor)(Steering)

│

M │  S-003   S-004   S-005

│  (PM)    (PO)    (Tech Lead)

│

L │  S-006   S-007   S-008

│  (Dev)   (QA)    (Farm Mgr)

│

│         S-009   S-010   S-011

│         (Ops)   (PMO)   (Agro)

└───────────────────────────────────►

L        M        H

Kepentingan

Strategi:

- S-001, S-002: Manage Closely (Libatkan intensif)

- S-003, S-004, S-005: Keep Satisfied (Jaga kepuasan)

- S-006, S-007, S-008: Keep Informed (Informasi teratur)

- S-009, S-010, S-011: Monitor (Pantau secara minimal)

#### 1.5.3. RACI Matrix

| Aktivitas | Sponsor | SC | PM | PO | Tech Lead | Dev | QA | Ops |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirement Definition | C | C | A | R | C | C | C | I |
| Sprint Planning | I | I | A | R | C | C | C | I |
| Development | I | I | I | C | R | R | I | I |
| Testing | I | I | A | C | C | C | R | I |
| Deployment | I | C | A | C | R | C | C | I |
| UAT | C | C | C | R | C | C | C | A |
| Go-Live | C | C | A | C | R | C | C | I |
| Reporting | I | I | R | C | C | I | I | I |

R = Responsible, A = Accountable, C = Consulted, I = Informed

### 1.6. Asumsi dan Batasan

#### 1.6.1. Asumsi

| No | Asumsi | Dampak jika Asumsi Salah |
| --- | --- | --- |
| 1 | Infrastruktur cloud (AWS/GCP) telah tersedia dari FNE | Perlu provisioning tambahan, delay 2-4 minggu |
| 2 | Tim P-FNE-01 (Foundation) selesai sebelum P-FNE-02 dimulai | Dependency blocking, delay signifikan |
| 3 | Ketersediaan user yang kompeten untuk UAT | UAT tidak optimal, risiko acceptance |
| 4 | Kerjasama tim lintas fungsional yang baik | Koordinasi sulit, risiko kualitas |
| 5 | Akses ke data historis untuk migrasi | Data migration incomplete |
| 6 | Ketersediaan perangkat mobile untuk testing | Testing mobile terbatas |
| 7 | Koneksi internet yang stabil untuk development | Produktivitas tim terganggu |
| 8 | Spesifikasi integrasi dengan modul lain sudah final | Integration rework signifikan |

#### 1.6.2. Batasan

| No | Batasan | Keterangan |
| --- | --- | --- |
| 1 | Durasi proyek | 5-6 bulan (sesuai proposal FNE) |
| 2 | Tim pengerjaan | 8-12 orang |
| 3 | Anggaran | Sesuai proposal yang disetujui (Rp 2.4 M) |
| 4 | Integrasi | Mengikuti timeline FNE secara keseluruhan |
| 5 | Teknologi | Menggunakan stack yang telah ditentukan |
| 6 | Keamanan | Harus mengikuti standar keamanan FNE |
| 7 | Regulasi | Harus mematuhi regulasi pertanian yang berlaku |
| 8 | Bahasa | Aplikasi dalam Bahasa Indonesia |
| 9 | Format Data | Mengikuti standar data FNE |

#### 1.6.3. Constraints Log

| Constraint | Type | Impact | Mitigation |
| --- | --- | --- | --- |
| Timeline 6 bulan | Hard | Kualitas terancam | Scope prioritization, parallel development |
| Budget fixed | Hard | Fitur terbatas | Efficient resource utilization |
| Stack teknologi | Hard | Fleksibilitas rendah | Memanfaatkan best practices |
| Dependency P-FNE-01 | Soft | Delay potensial | Parallel engineering, mock services |

### 1.7. Project Organization

#### 1.7.1. Struktur Organisasi Proyek

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                          PROJECT SPONSOR                                    │

│                        (FNE Executive)                                      │

└─────────────────────────────────────┬───────────────────────────────────────┘

│

┌─────────────────────────────────────▼───────────────────────────────────────┐

│                         STEERING COMMITTEE                                  │

│                   (FNE Management / PMO)                                    │

└─────────────────────────────────────┬───────────────────────────────────────┘

│

┌─────────────────────────────────────▼───────────────────────────────────────┐

│                           PROJECT MANAGER                                   │

│                     (Core Agricultural Ops)                                 │

└─────────────────────────────────────┬───────────────────────────────────────┘

│

┌────────────┬───────────────┼───────────────┬────────────┐

│            │               │               │            │

▼            ▼               ▼               ▼            ▼

┌─────────────┐ ┌─────────────┐ ┌─────────────┐ ┌─────────────┐ ┌─────────────┐

│  Product    │ │ Technical   │ │  QA Lead    │ │   DevOps    │ │ Business    │

│  Owner      │ │ Lead        │ │             │ │   Engineer  │ │ Analyst     │

└──────┬──────┘ └──────┬──────┘ └──────┬──────┘ └──────┬──────┘ └──────┬──────┘

│              │               │               │               │

▼              ▼               ▼               ▼               ▼

┌─────────────┐ ┌─────────────┐ ┌─────────────┐ ┌─────────────┐ ┌─────────────┐

│ Backend     │ │ Frontend    │ │ QA Engineer │ │ DevOps      │ │ Junior      │

│ Developers  │ │ Developers  │ │ (2)         │ │ (1)         │ │ BA          │

│ (4)         │ │ (2)         │ │             │ │             │ │ (1)         │

└─────────────┘ └─────────────┘ └─────────────┘ └─────────────┘ └─────────────┘

#### 1.7.2. Peran dan Tanggung Jawab

| Peran | Nama | Tanggung Jawab |
| --- | --- | --- |
| Project Sponsor | TBD | • Menyetujui charter dan PMP • Menyediakan pendanaan • Mengambil keputusan strategis • Menyetujui perubahan scope signifikan |
| Steering Committee | TBD | • Memberikan arahan strategis • Menyetujui milestone • Mengambil keputusan major change • Memastikan alignment dengan visi FNE |
| Project Manager | TBD | • Mengelola seluruh aspek proyek • Koordinasi tim dan stakeholder • Pelaporan progres • Manajemen risiko dan issue |
| Product Owner | TBD | • Representasi pengguna • Mengelola product backlog • Memprioritaskan requirement • Menerima deliverable |
| Technical Lead | TBD | • Arsitektur teknis • Code review dan standar kode • Integrasi teknis • Decision teknis |
| Backend Developer | 4 orang | • Implementasi business logic • Pengembangan API • Database design dan query • Event-driven integration |
| Frontend Developer | 2 orang | • Implementasi Web Admin • Dashboard development • UI/UX implementation • Integrasi dengan API |
| Mobile Developer | 1 orang | • Implementasi Mobile App • Offline-first architecture • Sync engine • Flutter development |
| QA Engineer | 2 orang | • Testing strategy • Manual dan automation testing • Bug reporting • Quality assurance |
| Business Analyst | 1 orang | • Requirement gathering • User stories • Flow bisnis • UAT coordination |
| DevOps Engineer | 1 orang | • Infrastructure setup • CI/CD pipeline • Monitoring • Deployment |

#### 1.7.3. Resource Plan

| Fase | PM | PO | Tech Lead | BE | FE | Mobile | QA | BA | DevOps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Persiapan | 100% | 80% | 50% | 2 org | 1 org | 0 | 1 org | 100% | 100% |
| 2. Setup | 100% | 60% | 100% | 2 org | 1 org | 0 | 1 org | 60% | 100% |
| 3. Farm & Land | 100% | 80% | 80% | 3 org | 2 org | 0 | 1 org | 80% | 50% |
| 4. Crop | 100% | 80% | 80% | 3 org | 2 org | 0 | 1 org | 60% | 50% |
| 5. Harvest | 100% | 60% | 60% | 2 org | 2 org | 0 | 1 org | 40% | 50% |
| 6. Livestock | 100% | 60% | 60% | 3 org | 2 org | 0 | 1 org | 40% | 50% |
| 7. Mobile | 100% | 40% | 60% | 2 org | 1 org | 100% | 2 org | 20% | 50% |
| 8. Integration | 100% | 40% | 100% | 3 org | 2 org | 0 | 2 org | 20% | 100% |
| 9. Testing | 100% | 60% | 60% | 2 org | 2 org | 0 | 2 org | 20% | 50% |
| 10. Deployment | 100% | 40% | 100% | 2 org | 1 org | 0 | 2 org | 20% | 100% |
| 11. Closure | 100% | 20% | 40% | 1 org | 1 org | 0 | 1 org | 20% | 50% |

### 1.8. Project Management Methodology

#### 1.8.1. Metodologi

Proyek P-FNE-02 akan menggunakan pendekatan Hybrid Agile-Waterfall:

Agile (Scrum) untuk pengembangan:

- Sprint 2 minggu

- Ceremonies: Sprint Planning, Daily Stand-up, Sprint Review, Sprint Retrospective

- Product Backlog yang diprioritaskan

- User Stories sebagai unit pekerjaan

Waterfall untuk fase inisiasi dan penutupan:

- Requirement gathering formal

- Design phase (architectural)

- Deployment dan handover terstruktur

#### 1.8.2. Development Lifecycle

text

┌──────────────────────────────────────────────────────────────────────────────┐

│                         DEVELOPMENT LIFECYCLE                                │

├──────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ┌─────────┐    ┌─────────┐    ┌─────────┐    ┌─────────┐    ┌─────────┐  │

│  │Require- │    │  Sprint │    │  Sprint │    │  Sprint │    │Deploy-  │  │

│  │ment     │───►│Planning │───►│Execution│───►│Review & │───►│ment &   │  │

│  │Gathering│    │         │    │         │    │ Retro   │    │Release  │  │

│  └─────────┘    └─────────┘    └─────────┘    └─────────┘    └─────────┘  │

│       │              │              │              │              │         │

│       ▼              ▼              ▼              ▼              ▼         │

│  ┌─────────┐    ┌─────────┐    ┌─────────┐    ┌─────────┐    ┌─────────┐  │

│  │BRD &    │    │Backlog  │    │CI/CD    │    │Demo to  │    │UAT &    │  │

│  │FRD      │    │Grooming │    │Pipeline │    │PO & SC  │    │Go-Live  │  │

│  └─────────┘    └─────────┘    └─────────┘    └─────────┘    └─────────┘  │

│                                                                              │

└──────────────────────────────────────────────────────────────────────────────┘

#### 1.8.3. Sprint Cadence

| Aktivitas | Waktu | Output |
| --- | --- | --- |
| Sprint Planning | Senin, 09:00-10:30 | Sprint Goal, Sprint Backlog |
| Daily Stand-up | Harian, 10:00-10:15 | Update, blocker |
| Development | Senin-Jumat | Code, unit tests |
| Code Review | Continuous | PR review |
| QA Testing | Sprint - 2 days | Test reports, bugs |
| Sprint Review | Jumat, 13:00-14:00 | Demo, feedback |
| Sprint Retrospective | Jumat, 14:00-14:45 | Action items |

#### 1.8.4. Definition of Ready (DoR)

Sebuah User Story dianggap READY jika:

- Deskripsi jelas dan dipahami oleh tim

- Acceptance criteria terdefinisi

- Dependencies teridentifikasi

- Estimasi telah dilakukan (story points)

- Labels sesuai (P0, P1, P2)

- Business value jelas

#### 1.8.5. Definition of Done (DoD)

Sebuah User Story dianggap DONE jika:

- Code telah ditulis dan di-review

- Unit tests lulus (coverage ≥ 80%)

- Integration tests lulus

- QA testing lulus (manual + automated)

- Documentation updated

- Deployed ke environment QA

- PO telah menerima (acceptance)

### 1.9. Project Governance

#### 1.9.1. Governance Structure

| Level | Komite | Fungsi | Frekuensi |
| --- | --- | --- | --- |
| Level 1 | Steering Committee | • Arah strategis proyek • Persetujuan perubahan scope signifikan • Resolution of major issues | Bulanan |
| Level 2 | Project Management | • Manajemen proyek sehari-hari • Koordinasi tim dan stakeholder • Pelaporan progres | Mingguan |
| Level 3 | Technical Lead | • Keputusan teknis • Arsitektur dan design • Code review standard | Continuous |
| Level 4 | Development Team | • Implementasi • Testing • Deployment | Harian |

#### 1.9.2. Decision Making Process

text

┌──────────────────────────────────────────────────────────────────┐

│                      DECISION MAKING PROCESS                      │

├──────────────────────────────────────────────────────────────────┤

│                                                                  │

│  ┌─────────┐    ┌─────────┐    ┌─────────┐    ┌─────────┐     │

│  │ Identify│───►│ Analyze │───►│ Evaluate│───►│ Decision│     │

│  │ Issue   │    │ Options │    │ Impact  │    │ & Action│     │

│  └─────────┘    └─────────┘    └─────────┘    └─────────┘     │

│       │              │              │              │            │

│       ▼              ▼              ▼              ▼            │

│  ┌────────────────────────────────────────────────────────┐     │

│  │               COMMUNICATE DECISION TO STAKEHOLDERS     │     │

│  └────────────────────────────────────────────────────────┘     │

│                                                                  │

└──────────────────────────────────────────────────────────────────┘

#### 1.9.3. Escalation Matrix

| Level | Issue Type | Eskalasi ke | Response Time | Resolution Time |
| --- | --- | --- | --- | --- |
| Level 1 | Technical, minor | Tech Lead | 1 jam | 4 jam |
| Level 2 | Resource, schedule, minor scope | Project Manager | 4 jam | 1 hari |
| Level 3 | Major scope, budget, significant risk | Steering Committee | 2 hari | 1 minggu |
| Level 4 | Strategic, project viability | Project Sponsor | 3 hari | 2 minggu |

#### 1.9.4. Reporting Structure

Harian:

- Daily Stand-up Update (Slack)

- Blocker Report (Jira)

Mingguan:

- Weekly Status Report (Dashboard)

- Sprint Progress (Jira)

- Risk Update

Bulanan:

- Monthly Progress Report (Presentation)

- Financial Report

- Milestone Progress

Per Milestone:

- Milestone Completion Report

- UAT Sign-off

- Go-Live Checklist

# BAB 2: MANAJEMEN INTEGRASI PROYEK

### 2.1. Tujuan Manajemen Integrasi

Manajemen integrasi proyek bertujuan untuk memastikan seluruh elemen proyek terkoordinasi dengan baik, termasuk:

- Mengkoordinasikan Seluruh Komponen – Menyatukan seluruh rencana manajemen (scope, schedule, cost, quality, resource, communication, risk, procurement, stakeholder) ke dalam satu kesatuan yang harmonis.

- Memastikan Konsistensi – Menjamin bahwa seluruh aktivitas proyek selaras dengan tujuan bisnis dan strategi FNE.

- Mengelola Perubahan – Menyediakan proses yang terstruktur untuk mengelola perubahan yang terjadi selama siklus proyek.

- Memantau Kinerja – Mengintegrasikan data kinerja dari seluruh area untuk memberikan gambaran status proyek secara holistik.

- Memastikan Transition yang Mulus – Menjamin bahwa hasil proyek dapat ditransisikan ke operasional dengan lancar.

### 2.2. Project Charter

#### 2.2.1. Ringkasan Project Charter

Project Charter merupakan dokumen formal yang memberikan otorisasi untuk memulai proyek P-FNE-02. Dokumen ini telah disetujui oleh Project Sponsor dan menjadi mandat bagi Project Manager untuk mengelola proyek.

| Elemen | Isi |
| --- | --- |
| Nama Proyek | P-FNE-02: Core Agricultural Operations |
| Project Sponsor | [Nama Sponsor], FNE Executive |
| Project Manager | [Nama PM], PMO |
| Tanggal Otorisasi | 1 September 2026 |
| Tujuan | Mendigitalisasi seluruh operasi pertanian FNE |
| Deskripsi | Pengembangan 6 modul utama (Farm, Land, Crop, Harvest, Livestock, Activity, Resource) |
| Business Case | Mendukung visi FNE sebagai platform pertanian terintegrasi, meningkatkan efisiensi operasional 20%, dan menyediakan data real-time |
| Deliverables Utama | 6 microservices, Web Admin, Mobile App, Database, Integration |
| Anggaran | Rp 2.400.000.000 |
| Durasi | 6 bulan (September 2026 - Maret 2027) |

#### 2.2.2. Project Authorization

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                            PROJECT CHARTER                                 │

│                  P-FNE-02: Core Agricultural Operations                     │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Dengan ini saya menyetujui pelaksanaan proyek P-FNE-02: Core Agricultural │

│  Operations sebagai bagian dari Super ERP Farm Nation Enterprise (FNE).    │

│                                                                             │

│  Project Manager telah ditunjuk dan diberikan wewenang untuk mengelola     │

│  seluruh aspek proyek sesuai dengan Project Management Plan yang berlaku.  │

│                                                                             │

│  Tanggal: 1 September 2026                                                  │

│                                                                             │

│  _________________________                                                  │

│  Project Sponsor                                                           │

│  FNE Executive                                                             │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 2.3. Project Management Plan

#### 2.3.1. Struktur PMP

Project Management Plan ini terdiri dari 10 bab utama sesuai dengan area pengetahuan PMBOK:

| Bab | Area Pengetahuan | Isi Utama |
| --- | --- | --- |
| Bab 1 | Pendahuluan | Tujuan, deskripsi, scope, stakeholder, asumsi |
| Bab 2 | Manajemen Integrasi | Charter, PMP, WBS, change control, governance |
| Bab 3 | Manajemen Lingkup | Scope definition, WBS, requirement traceability |
| Bab 4 | Manajemen Penjadwalan | Timeline, milestones, Gantt chart, schedule control |
| Bab 5 | Manajemen Biaya | Budget, cost estimation, cost control |
| Bab 6 | Manajemen Kualitas | Quality metrics, testing strategy, QA process |
| Bab 7 | Manajemen Sumber Daya | Team structure, resource allocation, development |
| Bab 8 | Manajemen Komunikasi | Communication matrix, reporting, meeting schedule |
| Bab 9 | Manajemen Risiko | Risk register, risk response, monitoring |
| Bab 10 | Manajemen Pengadaan | Procurement plan, vendor management |
| Bab 11 | Manajemen Pemangku Kepentingan | Stakeholder register, engagement matrix |

#### 2.3.2. PMP Approval Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         PMP APPROVAL PROCESS                                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────┐    ┌─────────┐    ┌─────────┐    ┌─────────┐    ┌─────────┐ │

│  │  Draft  │───►│ Review  │───►│   PMO   │───►│Steering │───►│Sponsor  │ │

│  │   PMP   │    │  Team   │    │  Review │    │ Review  │    │Approval │ │

│  └─────────┘    └─────────┘    └─────────┘    └─────────┘    └─────────┘ │

│                                                                             │

│  Dokumentasi PMP                                                           │

│  - Disusun oleh PM                                                         │

│  - Direview oleh Team                                                      │

│  - Divalidasi oleh PMO                                                     │

│  - Disetujui oleh Steering Committee                                       │

│  - Ditandatangani oleh Sponsor                                             │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 2.3.3. PMP Maintenance

| Aktivitas | Frekuensi | PIC |
| --- | --- | --- |
| Review PMP | Per sprint review | PM |
| Update PMP | Saat ada perubahan signifikan | PM |
| Version Control | Setiap perubahan | PM |
| Communicaton update | Setelah PMP diupdate | PM |

### 2.4. Project Work Plan

#### 2.4.1. Work Breakdown Structure (WBS)

text

P-FNE-02: Core Agricultural Operations (5-6 bulan)

│

├── 1.0. Persiapan & Inisiasi (2 minggu)

│   ├── 1.1. Penyusunan Project Charter

│   ├── 1.2. Kick-off Meeting

│   ├── 1.3. Setup Environment & Infrastructure

│   ├── 1.4. Finalisasi Requirement

│   └── 1.5. Penyusunan PMP

│

├── 2.0. Foundation & Platform Setup (3 minggu)

│   ├── 2.1. Database Schema Design

│   │   ├── 2.1.1. Entity Relationship Diagram

│   │   ├── 2.1.2. DDL Scripts

│   │   └── 2.1.3. Migration Scripts

│   ├── 2.2. Core Services Setup

│   │   ├── 2.2.1. Project Structure

│   │   ├── 2.2.2. Dependency Management

│   │   └── 2.2.3. Configuration Management

│   ├── 2.3. CI/CD Pipeline Setup

│   │   ├── 2.3.1. Build Pipeline

│   │   ├── 2.3.2. Test Pipeline

│   │   └── 2.3.3. Deployment Pipeline

│   └── 2.4. Authentication & Authorization

│       ├── 2.4.1. Integration dengan IAM Service

│       └── 2.4.2. Role-Based Access Control

│

├── 3.0. Module Development (3 bulan)

│   │

│   ├── 3.1. Farm & Land Management (3 minggu)

│   │   ├── 3.1.1. Farm Service

│   │   │   ├── 3.1.1.1. Register Farm

│   │   │   ├── 3.1.1.2. Update Farm

│   │   │   ├── 3.1.1.3. Get Farm Details

│   │   │   └── 3.1.1.4. List Farms

│   │   ├── 3.1.2. Land Service

│   │   │   ├── 3.1.2.1. Register Land Parcel

│   │   │   ├── 3.1.2.2. Update Land Parcel

│   │   │   ├── 3.1.2.3. Get Land Parcel Details

│   │   │   └── 3.1.2.4. Map Integration

│   │   ├── 3.1.3. Soil Analysis Module

│   │   │   ├── 3.1.3.1. Record Soil Analysis

│   │   │   ├── 3.1.3.2. Generate Recommendations

│   │   │   └── 3.1.3.3. View Analysis History

│   │   ├── 3.1.4. Farm Facilities Module

│   │   │   ├── 3.1.4.1. Register Facility

│   │   │   └── 3.1.4.2. Manage Facilities

│   │   ├── 3.1.5. UI Implementation

│   │   │   ├── 3.1.5.1. Farm Management UI

│   │   │   ├── 3.1.5.2. Land Parcel UI

│   │   │   └── 3.1.5.3. Dashboard UI

│   │   └── 3.1.6. Testing & QA

│   │       ├── 3.1.6.1. Unit Testing

│   │       └── 3.1.6.2. Integration Testing

│   │

│   ├── 3.2. Crop Management (4 minggu)

│   │   ├── 3.2.1. Crop Master Service

│   │   │   ├── 3.2.1.1. Create Crop

│   │   │   ├── 3.2.1.2. Update Crop

│   │   │   └── 3.2.1.3. List Crops

│   │   ├── 3.2.2. Crop Cycle Service

│   │   │   ├── 3.2.2.1. Create Crop Cycle Plan

│   │   │   ├── 3.2.2.2. Update Crop Cycle

│   │   │   ├── 3.2.2.3. Calculate Expected Harvest Date

│   │   │   └── 3.2.2.4. Track Crop Cycle Status

│   │   ├── 3.2.3. Planting Service

│   │   │   ├── 3.2.3.1. Execute Planting

│   │   │   └── 3.2.3.2. Record Planting Details

│   │   ├── 3.2.4. Growth Stage Service

│   │   │   ├── 3.2.4.1. Record Growth Stage

│   │   │   └── 3.2.4.2. Track Plant Health

│   │   ├── 3.2.5. Cultivation Activity Service

│   │   │   ├── 3.2.5.1. Record Cultivation Activity

│   │   │   └── 3.2.5.2. Calculate Activity Cost

│   │   ├── 3.2.6. UI Implementation

│   │   │   ├── 3.2.6.1. Crop Master UI

│   │   │   ├── 3.2.6.2. Crop Cycle UI

│   │   │   └── 3.2.6.3. Activity Recording UI

│   │   └── 3.2.7. Testing & QA

│   │

│   ├── 3.3. Harvest Management (2,5 minggu)

│   │   ├── 3.3.1. Harvest Plan Service

│   │   │   ├── 3.3.1.1. Create Harvest Plan

│   │   │   └── 3.3.1.2. Update Harvest Plan

│   │   ├── 3.3.2. Harvest Execution Service

│   │   │   ├── 3.3.2.1. Execute Harvest

│   │   │   └── 3.3.2.2. Create Harvest Batch

│   │   ├── 3.3.3. Quality Control Service

│   │   │   ├── 3.3.3.1. Record Quality Inspection

│   │   │   └── 3.3.3.2. Record Post-Harvest Loss

│   │   ├── 3.3.4. Event Publisher

│   │   │   └── 3.3.4.1. Publish HarvestCompleted Event

│   │   ├── 3.3.5. UI Implementation

│   │   │   ├── 3.3.5.1. Harvest Planning UI

│   │   │   └── 3.3.5.2. Harvest Execution UI

│   │   └── 3.3.6. Testing & QA

│   │

│   ├── 3.4. Livestock Management (3 minggu)

│   │   ├── 3.4.1. Livestock Master Service

│   │   │   └── 3.4.1.1. Create Livestock Master

│   │   ├── 3.4.2. Animal Registration Service

│   │   │   ├── 3.4.2.1. Register Animal

│   │   │   ├── 3.4.2.2. Update Animal

│   │   │   └── 3.4.2.3. Generate QR Code

│   │   ├── 3.4.3. Feeding Service

│   │   │   └── 3.4.3.1. Record Feeding Activity

│   │   ├── 3.4.4. Health Service

│   │   │   ├── 3.4.4.1. Record Health Check

│   │   │   ├── 3.4.4.2. Record Vaccination

│   │   │   └── 3.4.4.3. Record Mortality

│   │   ├── 3.4.5. Reproduction Service

│   │   │   └── 3.4.5.1. Record Reproduction

│   │   ├── 3.4.6. Production Service

│   │   │   ├── 3.4.6.1. Record Animal Production

│   │   │   └── 3.4.6.2. Publish LivestockProductionCompleted

│   │   ├── 3.4.7. Transaction Service

│   │   │   └── 3.4.7.1. Record Animal Transaction

│   │   ├── 3.4.8. UI Implementation

│   │   │   ├── 3.4.8.1. Livestock Management UI

│   │   │   └── 3.4.8.2. Health Monitoring UI

│   │   └── 3.4.9. Testing & QA

│   │

│   ├── 3.5. Activity Recording (2 minggu)

│   │   ├── 3.5.1. Activity Service

│   │   │   ├── 3.5.1.1. Record Generic Activity

│   │   │   ├── 3.5.1.2. Create Activity Type

│   │   │   └── 3.5.1.3. List Activities

│   │   ├── 3.5.2. Reminder Service

│   │   │   └── 3.5.2.1. Schedule Activity Reminder

│   │   ├── 3.5.3. UI Implementation

│   │   │   ├── 3.5.3.1. Activity Recording UI

│   │   │   └── 3.5.3.2. Activity Calendar UI

│   │   └── 3.5.4. Testing & QA

│   │

│   └── 3.6. Resource Management (1,5 minggu)

│       ├── 3.6.1. Resource Service

│       │   ├── 3.6.1.1. Create Resource Item

│       │   ├── 3.6.1.2. Allocate Resource

│       │   ├── 3.6.1.3. Consume Resource

│       │   └── 3.6.1.4. Calculate Resource Requirements

│       ├── 3.6.2. UI Implementation

│       │   └── 3.6.2.1. Resource Management UI

│       └── 3.6.3. Testing & QA

│

├── 4.0. Mobile Development (3 bulan - parallel)

│   ├── 4.1. Mobile App UI/UX Design

│   │   ├── 4.1.1. Wireframes

│   │   └── 4.1.2. Design System

│   ├── 4.2. Offline-First Architecture

│   │   ├── 4.2.1. Local Database Schema

│   │   └── 4.2.2. Sync Strategy

│   ├── 4.3. Activity Recording Module

│   │   ├── 4.3.1. Activity Entry Form

│   │   ├── 4.3.2. Photo Capture

│   │   └── 4.3.3. GPS Capture

│   ├── 4.4. Sync Engine Implementation

│   │   ├── 4.4.1. Data Sync Logic

│   │   ├── 4.4.2. Conflict Resolution

│   │   └── 4.4.3. Retry Mechanism

│   └── 4.5. Testing & QA

│       ├── 4.5.1. Unit Testing

│       ├── 4.5.2. Integration Testing

│       └── 4.5.3. Offline Testing

│

├── 5.0. Integration & Event-Driven (1,5 bulan)

│   ├── 5.1. Kafka Integration

│   │   ├── 5.1.1. Kafka Setup

│   │   ├── 5.1.2. Topic Configuration

│   │   └── 5.1.3. Schema Registry

│   ├── 5.2. Event Publishers & Consumers

│   │   ├── 5.2.1. HarvestCompleted Event Publisher

│   │   ├── 5.2.2. LivestockProductionCompleted Publisher

│   │   ├── 5.2.3. ActivityRecorded Event Publisher

│   │   └── 5.2.4. Event Consumers

│   ├── 5.3. API Gateway Integration

│   │   ├── 5.3.1. API Gateway Configuration

│   │   ├── 5.3.2. BFF Implementation

│   │   └── 5.3.3. Authentication Integration

│   └── 5.4. Integration Testing

│       ├── 5.4.1. API Testing

│       ├── 5.4.2. Event Testing

│       └── 5.4.3. End-to-End Testing

│

├── 6.0. Testing & QA (1 bulan)

│   ├── 6.1. Unit Testing

│   │   └── 6.1.1. All Services

│   ├── 6.2. Integration Testing

│   │   ├── 6.2.1. Internal Integration

│   │   └── 6.2.2. External Integration

│   ├── 6.3. Performance Testing

│   │   ├── 6.3.1. Load Testing

│   │   ├── 6.3.2. Stress Testing

│   │   └── 6.3.3. Scalability Testing

│   ├── 6.4. Security Testing

│   │   ├── 6.4.1. Authentication Testing

│   │   ├── 6.4.2. Authorization Testing

│   │   └── 6.4.3. Vulnerability Scanning

│   ├── 6.5. User Acceptance Testing (UAT)

│   │   ├── 6.5.1. UAT Preparation

│   │   ├── 6.5.2. UAT Execution

│   │   └── 6.5.3. UAT Sign-off

│   └── 6.6. Bug Fixing & Regression

│

├── 7.0. Deployment & Go-Live (3 minggu)

│   ├── 7.1. UAT Environment Preparation

│   │   ├── 7.1.1. Environment Setup

│   │   └── 7.1.2. Data Preparation

│   ├── 7.2. Production Environment Setup

│   │   ├── 7.2.1. Infrastructure Provisioning

│   │   ├── 7.2.2. Application Deployment

│   │   └── 7.2.3. Monitoring Setup

│   ├── 7.3. Data Migration

│   │   ├── 7.3.1. Data Mapping

│   │   ├── 7.3.2. Migration Scripts

│   │   └── 7.3.3. Data Validation

│   ├── 7.4. Go-Live Execution

│   │   ├── 7.4.1. Go-Live Checklist

│   │   ├── 7.4.2. Cutover Plan

│   │   └── 7.4.3. Rollback Plan

│   └── 7.5. Hypercare Support

│       ├── 7.5.1. 24/7 Support

│       └── 7.5.2. Issue Tracking & Resolution

│

└── 8.0. Closure & Handover (1 minggu)

├── 8.1. Documentation Completion

│   ├── 8.1.1. Technical Documentation

│   ├── 8.1.2. User Manual

│   └── 8.1.3. API Documentation

├── 8.2. Knowledge Transfer

│   ├── 8.2.1. KT Session

│   └── 8.2.2. Handover Documents

└── 8.3. Project Closure Report

├── 8.3.1. Lessons Learned

└── 8.3.2. Final Report

#### 2.4.2. WBS Dictionary (Detail)

WBS: 1.0. Persiapan & Inisiasi

| Elemen | Keterangan |
| --- | --- |
| ID | 1.0 |
| Nama | Persiapan & Inisiasi |
| Deskripsi | Aktivitas awal proyek untuk mempersiapkan tim, lingkungan, dan dokumen |
| Output | Project Charter, PMP, Kick-off done, Environment ready |
| Durasi | 2 minggu |
| Resources | PM, PO, BA, DevOps, Tech Lead |
| Predecessor | - |
| Successor | 2.0 Foundation & Platform Setup |
| Milestone | M1 – Project Kick-off |
| Acceptance | Semua dokumen disetujui, environment ready |

WBS: 3.1. Farm & Land Management

| Elemen | Keterangan |
| --- | --- |
| ID | 3.1 |
| Nama | Farm & Land Management |
| Deskripsi | Pengembangan modul manajemen farm dan land parcel |
| Output | Farm Service, Land Service, Soil Analysis, Farm Facilities |
| Durasi | 3 minggu |
| Resources | BE:3, FE:2, QA:1, BA:1 |
| Predecessor | 2.0 Foundation & Platform Setup |
| Successor | 3.2 Crop Management |
| Milestone | M3 – Farm & Land Module |
| Acceptance | Minimal 5 farm terdaftar, 20 land parcel, mapping berfungsi |

### 2.5. Change Management Process

#### 2.5.1. Change Control Board (CCB)

| Jabatan | Peran dalam CCB | Tanggung Jawab |
| --- | --- | --- |
| Project Sponsor | Ketua CCB | Menyetujui perubahan signifikan |
| Project Manager | Sekretaris CCB | Mengelola proses perubahan |
| Product Owner | Anggota CCB | Menilai dampak bisnis |
| Technical Lead | Anggota CCB | Menilai dampak teknis |
| PMO | Anggota CCB | Menilai dampak governance |

#### 2.5.2. Change Request Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         CHANGE REQUEST PROCESS                              │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ IDENTIFY    │───►│ SUBMIT      │───►│ EVALUATE    │───►│ DECIDE      │ │

│  │ Change      │    │ Change      │    │ Impact      │    │ (CCB)       │ │

│  │ Need        │    │ Request     │    │ Analysis    │    │             │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐                    │

│  │ IMPLEMENT   │◄───│ APPROVE     │◄───│ DOCUMENT    │                    │

│  │ Change      │    │ Change      │    │ Decision    │                    │

│  └─────────────┘    └─────────────┘    └─────────────┘                    │

│                                                                             │

│  ┌─────────────┐                                                           │

│  │ COMMUNICATE │                                                           │

│  │ Update      │                                                           │

│  └─────────────┘                                                           │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 2.5.3. Change Request Form

| Field | Deskripsi |
| --- | --- |
| Request ID | CR-XXX (Auto-generated) |
| Request Date | Tanggal pengajuan |
| Requestor | Nama pengaju |
| Change Type | Scope / Schedule / Budget / Resource / Technical |
| Description | Deskripsi perubahan |
| Reason | Alasan perubahan |
| Impact Analysis | Dampak terhadap scope, waktu, biaya, risiko |
| Urgency | High / Medium / Low |
| Recommended Action | Approve / Reject / Defer |
| CCB Decision | Hasil keputusan |
| Decision Date | Tanggal keputusan |
| Implementation Plan | Rencana implementasi jika disetujui |

#### 2.5.4. Change Request Categories and Authority

| Category | Description | Decision Authority | Response Time |
| --- | --- | --- | --- |
| Minor | Perubahan kecil (< 10% impact) | Project Manager | 1 hari |
| Moderate | Perubahan sedang (10-30% impact) | PM + PO | 2 hari |
| Major | Perubahan besar (> 30% impact) | CCB | 1 minggu |
| Critical | Perubahan kritis (project viability) | Project Sponsor | 2 hari |

#### 2.5.5. Change Log

| ID | Date | Requestor | Type | Description | Status | Decision |
| --- | --- | --- | --- | --- | --- | --- |
| CR-001 | 15/09/2026 | Farm Manager | Scope | Tambahan field "GPS Coordinates" di Land Parcel | Approved | PM |
| CR-002 | 28/09/2026 | Tech Lead | Technical | Upgrade Spring Boot 2.7 → 3.0 | Approved | PM |
| CR-003 | 10/10/2026 | PO | Schedule | Penambahan 2 sprint untuk mobile | Pending | CCB |

### 2.6. Project Governance

#### 2.6.1. Governance Structure (Detail)

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         PROJECT GOVERNANCE STRUCTURE                        │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │                        Level 1: Strategic                          │   │

│  │  ┌─────────────────────────────────────────────────────────────────┐│   │

│  │  │                    STEERING COMMITTEE                          ││   │

│  │  │  • Project Sponsor (Chair)                                    ││   │

│  │  │  • FNE Management Representatives                             ││   │

│  │  │  • PMO Director                                               ││   │

│  │  │  • Business Unit Head                                         ││   │

│  │  │                                                               ││   │

│  │  │  Fungsi:                                                      ││   │

│  │  │  1. Memberikan arahan strategis proyek                        ││   │

│  │  │  2. Menyetujui perubahan scope signifikan                     ││   │

│  │  │  3. Memutuskan isu-isu strategis                              ││   │

│  │  │  4. Menyetujui milestone dan deliverable utama                ││   │

│  │  │  5. Memastikan alignment dengan visi FNE                     ││   │

│  │  └─────────────────────────────────────────────────────────────────┘│   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                      │                                      │

│                                      ▼                                      │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │                       Level 2: Tactical                            │   │

│  │  ┌─────────────────────────────────────────────────────────────────┐│   │

│  │  │                      PROJECT MANAGEMENT                        ││   │

│  │  │  • Project Manager (Chair)                                    ││   │

│  │  │  • Product Owner                                               ││   │

│  │  │  • Technical Lead                                              ││   │

│  │  │  • QA Lead                                                     ││   │

│  │  │                                                               ││   │

│  │  │  Fungsi:                                                      ││   │

│  │  │  1. Mengelola proyek sehari-hari                               ││   │

│  │  │  2. Koordinasi tim dan stakeholder                             ││   │

│  │  │  3. Memonitor progress dan performa                            ││   │

│  │  │  4. Mengelola risiko dan issue                                 ││   │

│  │  │  5. Melaporkan kepada Steering Committee                       ││   │

│  │  └─────────────────────────────────────────────────────────────────┘│   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                      │                                      │

│                                      ▼                                      │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │                       Level 3: Operational                         │   │

│  │  ┌─────────────────────────────────────────────────────────────────┐│   │

│  │  │                   TECHNICAL LEADERSHIP                          ││   │

│  │  │  • Technical Lead (Chair)                                     ││   │

│  │  │  • Lead Backend Developer                                     ││   │

│  │  │  • Lead Frontend Developer                                    ││   │

│  │  │  • Lead Mobile Developer                                      ││   │

│  │  │  • DevOps Engineer                                             ││   │

│  │  │                                                               ││   │

│  │  │  Fungsi:                                                      ││   │

│  │  │  1. Mengambil keputusan teknis                                 ││   │

│  │  │  2. Memastikan arsitektur yang tepat                           ││   │

│  │  │  3. Code review dan standar kode                               ││   │

│  │  │  4. Integrasi teknis antar modul                               ││   │

│  │  │  5. Infrastruktur dan deployment                               ││   │

│  │  └─────────────────────────────────────────────────────────────────┘│   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                      │                                      │

│                                      ▼                                      │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │                        Level 4: Execution                          │   │

│  │  ┌─────────────────────────────────────────────────────────────────┐│   │

│  │  │                   DEVELOPMENT TEAM                             ││   │

│  │  │  • Backend Developers (4)                                     ││   │

│  │  │  • Frontend Developers (2)                                    ││   │

│  │  │  • Mobile Developer (1)                                       ││   │

│  │  │  • QA Engineers (2)                                           ││   │

│  │  │  • Business Analyst (1)                                       ││   │

│  │  │                                                               ││   │

│  │  │  Fungsi:                                                      ││   │

│  │  │  1. Implementasi fitur                                         ││   │

│  │  │  2. Pengujian                                                  ││   │

│  │  │  3. Dokumentasi                                                ││   │

│  │  │  4. Reporting status daily                                     ││   │

│  │  └─────────────────────────────────────────────────────────────────┘│   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 2.6.2. Decision Making Authority

| Decision Type | Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- | --- |
| Strategic Direction | ✅ SC | - | - | - |
| Major Scope Change | ✅ SC | - | - | - |
| Budget Change > 10% | ✅ SC | - | - | - |
| Milestone Approval | ✅ SC | - | - | - |
| Resource Allocation | - | ✅ PM | - | - |
| Sprint Planning | - | ✅ PM+PO | - | - |
| Minor Scope Change | - | ✅ PM+PO | - | - |
| Technical Architecture | - | - | ✅ Tech Lead | - |
| Code Standards | - | - | ✅ Tech Lead | - |
| Implementation Detail | - | - | - | ✅ Dev |

#### 2.6.3. Governance Meetings

| Meeting | Level | Frequency | Duration | Participants |
| --- | --- | --- | --- | --- |
| Steering Committee | Level 1 | Bulanan | 2 jam | Sponsor, SC, PM, PO |
| Project Status Meeting | Level 2 | 2 minggu | 1 jam | PM, PO, Tech Lead, QA Lead |
| Technical Sync | Level 3 | Mingguan | 1 jam | Tech Lead, Dev Leads |
| Sprint Ceremonies | Level 4 | 2 minggu | Various | All Team |
| Daily Stand-up | Level 4 | Harian | 15 menit | All Team |

### 2.7. Project Performance Measurement

#### 2.7.1. Performance Metrics

| Metric | Baseline | Target | Method |
| --- | --- | --- | --- |
| Schedule |  |  |  |
| Sprint Velocity | 25 points | ≥ 30 points | Sprint Review |
| Milestone On-time | 100% | ≥ 95% | Milestone Report |
| Schedule Variance | 0% | ≤ ±10% | EVM |
| Cost |  |  |  |
| Budget Variance | 0% | ≤ ±10% | EVM |
| Cost Performance Index | 1.0 | ≥ 0.9 | EVM |
| Quality |  |  |  |
| Defect Density | - | ≤ 1/KLOC | QA Report |
| Code Coverage | - | ≥ 80% | SonarQube |
| Performance |  |  |  |
| Response Time | - | ≤ 3 detik | Performance Test |
| Uptime | - | ≥ 99.5% | Monitoring |

#### 2.7.2. Earned Value Management (EVM)

EVM Parameters:

- Planned Value (PV): Budget per activity sesuai WBS

- Earned Value (EV): Work completed (story points)

- Actual Cost (AC): Actual cost incurred

EVM Reports:

- Schedule Performance Index (SPI) = EV / PV

- Cost Performance Index (CPI) = EV / AC

- Estimate at Completion (EAC) = BAC / CPI

- Estimate to Complete (ETC) = EAC - AC

#### 2.7.3. Status Reporting

Weekly Status Report Format:

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    WEEKLY STATUS REPORT                                     │

│                    P-FNE-02: Core Agricultural Operations                   │

│                    Week: [XX] / [Date]                                      │

├─────────────────────────────────────────────────────────────────────────────┤

│ 1. Executive Summary                                                       │

│    ─────────────────                                                       │

│    • Overall Status: [Green/Yellow/Red]                                    │

│    • Progress: [XX]% complete                                              │

│    • Key Achievements: [List 3-5]                                          │

│                                                                             │

│ 2. Progress Update                                                         │

│    ────────────────                                                        │

│    • Planned vs Actual (Sprint)                                            │

│    • Milestone Progress                                                    │

│    • EVM Metrics (SPI, CPI)                                               │

│                                                                             │

│ 3. Risks & Issues                                                          │

│    ────────────────                                                        │

│    • High Risks: [List]                                                    │

│    • New Issues: [List]                                                    │

│    • Resolved Issues: [List]                                               │

│                                                                             │

│ 4. Next Week Plan                                                          │

│    ────────────────                                                        │

│    • Sprint Goals                                                          │

│    • Key Activities                                                        │

│    • Resources Needed                                                      │

│                                                                             │

│ 5. Budget Status                                                           │

│    ──────────────                                                          │

│    • Budget Used: [XX]%                                                    │

│    • Variance: [XX]%                                                       │

│    • Forecast: EAC, ETC                                                    │

│                                                                             │

│ 6. Decisions Needed                                                       │

│    ────────────────                                                        │

│    • [List pending decisions]                                              │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 2.8. Project Closure

#### 2.8.1. Closure Criteria

| No | Kriteria | Status |
| --- | --- | --- |
| 1 | Semua deliverable selesai | [ ] |
| 2 | Acceptance Criteria 8 poin terpenuhi | [ ] |
| 3 | UAT Sign-off | [ ] |
| 4 | User Manual selesai | [ ] |
| 5 | Technical Documentation selesai | [ ] |
| 6 | Knowledge Transfer selesai | [ ] |
| 7 | Operational Handover selesai | [ ] |
| 8 | Lessons Learned dokumentasi | [ ] |
| 9 | Financial Closure | [ ] |
| 10 | Project Closure Report | [ ] |

#### 2.8.2. Lessons Learned Process

- Collection – Kumpulkan lessons learned dari semua tim

- Categorization – Kelompokkan ke dalam kategori (process, technical, people, etc.)

- Analysis – Analisis root cause dan rekomendasi

- Documentation – Dokumentasikan dalam repository

- Communication – Komunikasikan ke PMO dan proyek lain

#### 2.8.3. Handover Checklist

| Item | PIC | Status | Tanggal |
| --- | --- | --- | --- |
| Source Code Repository | Tech Lead |  |  |
| Deployment Scripts | DevOps |  |  |
| Database Schema & Migration | Tech Lead |  |  |
| Architecture Document | Tech Lead |  |  |
| API Documentation | Backend Team |  |  |
| Database Design Document | Backend Team |  |  |
| User Manual | BA |  |  |
| Monitoring Setup | DevOps |  |  |
| Access Management | PM |  |  |
| Support Contact List | PM |  |  |

### 2.9. Tools for Integration Management

| Category | Tool | Purpose |
| --- | --- | --- |
| Project Management | Jira | Task tracking, sprint planning |
| Documentation | Confluence | PMP, requirements, design |
| Version Control | GitHub | Source code management |
| CI/CD | GitHub Actions | Build, test, deploy automation |
| Communication | Slack | Daily communication |
| Meeting | Zoom/Google Meet | Remote meetings |
| Diagram | Draw.io, Miro | Architecture diagrams |
| Monitoring | Prometheus/Grafana | System monitoring |

### 2.10. Key Performance Indicators (KPI) for Integration

| KPI | Target | Measurement |
| --- | --- | --- |
| Change Request Approval Time | ≤ 5 hari kerja | Average time from submission to decision |
| Number of Unplanned Changes | ≤ 3 | Total unplanned changes during project |
| Project Plan Adherence | ≥ 90% | % of tasks completed according to plan |
| Milestone Achievement | ≥ 95% | % of milestones on time |

# BAB 3: MANAJEMEN LINGKUP PROYEK

### 3.1. Tujuan Manajemen Lingkup

Manajemen lingkup proyek bertujuan untuk:

- Mendefinisikan dengan Jelas - Menentukan dengan tepat apa yang termasuk dan tidak termasuk dalam proyek P-FNE-02.

- Mencegah Scope Creep - Mengelola perubahan lingkup agar proyek tetap fokus pada tujuan awal.

- Memastikan Kepuasan Stakeholder - Menjamin bahwa deliverable proyek sesuai dengan kebutuhan dan harapan stakeholder.

- Menyediakan Dasar Pengukuran - Memberikan baseline untuk mengukur kinerja dan kemajuan proyek.

- Memfasilitasi Komunikasi - Menyediakan pemahaman yang sama tentang lingkup proyek di antara seluruh stakeholder.

### 3.2. Scope Management Process

#### 3.2.1. Proses Manajemen Lingkup

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                      SCOPE MANAGEMENT PROCESS                               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Collect     │───►│ Define      │───►│ Create      │───►│ Validate    │ │

│  │ Requirements│    │ Scope       │    │ WBS         │    │ Scope       │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Interview │    │ • In-Scope  │    │ • WBS       │    │ • UAT       │ │

│  │ • Workshop  │    │ • Out-of-   │    │ • WBS       │    │ • Sign-off  │ │

│  │ • Survey    │    │   Scope     │    │   Dictionary│    │ • Acceptance│ │

│  │ • Document  │    │ • Scope     │    │ • Activity  │    │   Criteria  │ │

│  │   Analysis  │    │   Statement │    │   List      │    │             │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  ┌─────────────┐                                                           │

│  │ Control     │                                                           │

│  │ Scope       │                                                           │

│  └─────────────┘                                                           │

│        │                                                                   │

│        ▼                                                                   │

│  ┌─────────────┐                                                           │

│  │ • Change    │                                                           │

│  │   Control   │                                                           │

│  │ • Scope     │                                                           │

│  │   Baseline  │                                                           │

│  │ • Variance  │                                                           │

│  │   Analysis  │                                                           │

│  └─────────────┘                                                           │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 3.2.2. Roles and Responsibilities in Scope Management

| Peran | Tanggung Jawab |
| --- | --- |
| Product Owner | • Mengumpulkan dan memprioritaskan requirements • Menjaga visi produk • Menyetujui atau menolak user stories |
| Business Analyst | • Mendokumentasikan requirements • Membuat user stories • Memfasilitasi requirement gathering |
| Project Manager | • Mengelola scope baseline • Mengkoordinasikan change control • Memastikan alignment dengan tujuan proyek |
| Technical Lead | • Menilai kelayakan teknis requirements • Memberikan estimasi teknis |
| Steering Committee | • Menyetujui perubahan scope signifikan • Memastikan scope selaras dengan strategi FNE |

### 3.3. Requirement Collection

#### 3.3.1. Requirement Gathering Methods

| Metode | Deskripsi | Stakeholder | Output |
| --- | --- | --- | --- |
| Interview | Wawancara langsung dengan stakeholder | Farm Manager, Agronomist, Veteriner | Requirement notes |
| Workshop | Sesi kolaboratif dengan user | Operational Team, Farm Manager | BRD draft, user stories |
| Document Analysis | Review dokumen proses bisnis | BA, PO | Business process flow |
| Prototyping | Demonstrasi mockup awal | Farm Manager, Agronomist | UI/UX feedback |
| Survey | Kuesioner untuk user | Operational Team | Priority requirements |
| Benchmark | Studi sistem kompetitor | BA, PO | Best practices |

#### 3.3.2. Requirement Sources

| Sumber | Deskripsi | Prioritas |
| --- | --- | --- |
| BRD FNE | Business Requirement Document FNE | High |
| FRD P-FNE-02 | Functional Requirement Document | High |
| Arsitektur FNE | Arsitektur umum sistem | High |
| User Interviews | Feedback dari user langsung | Medium |
| Industry Best Practices | Standar industri pertanian | Medium |
| Regulatory Requirements | Regulasi pertanian | Low |

#### 3.3.3. Requirement Categorization

A. Functional Requirements (76 Requirements)

| Domain | ID | Jumlah | Prioritas |
| --- | --- | --- | --- |
| Farm & Land Management | FNE-FRM-001 s.d. -012 | 12 | P0: 6, P1: 5, P2: 1 |
| Crop Management | FNE-CRP-001 s.d. -014 | 14 | P0: 9, P1: 5, P2: 0 |
| Harvest Management | FNE-HRV-001 s.d. -010 | 10 | P0: 8, P1: 2, P2: 0 |
| Livestock Management | FNE-LIV-001 s.d. -021 | 21 | P0: 14, P1: 7, P2: 0 |
| Activity Recording | FNE-ACT-001 s.d. -010 | 10 | P0: 6, P1: 3, P2: 1 |
| Resource Management | FNE-RES-001 s.d. -010 | 10 | P0: 4, P1: 6, P2: 0 |

B. Non-Functional Requirements (10 Requirements)

| ID | Requirement | Target | Prioritas |
| --- | --- | --- | --- |
| FNE-NFR-FRM-001 | Farm Data Response | ≤ 3 detik | P0 |
| FNE-NFR-FRM-002 | Crop Cycle Query | ≤ 2 detik | P0 |
| FNE-NFR-FRM-003 | Mobile Offline Support | 100 transaksi | P0 |
| FNE-NFR-FRM-004 | Sync Time | ≤ 30 detik | P0 |
| FNE-NFR-FRM-005 | Geolocation Accuracy | ≤ 50 meter | P2 |
| FNE-NFR-FRM-006 | Photo Upload Size | ≤ 10 MB | P1 |
| FNE-NFR-FRM-007 | Multi-Farm Support | Unlimited | P0 |
| FNE-NFR-FRM-008 | Historical Data Retention | 5 tahun | P0 |
| FNE-NFR-FRM-009 | Crop Data Integrity | 100% | P0 |
| FNE-NFR-FRM-010 | Seasonal Load | 3x normal | P1 |

#### 3.3.4. Requirement Prioritization

Prioritas P0 (Must Have - 41 Requirements):

- Fitur yang absolut wajib ada untuk MVP

- Tanpa fitur ini, sistem tidak dapat beroperasi

- Harus selesai di sprint pertama

Prioritas P1 (Should Have - 29 Requirements):

- Fitur penting tetapi masih ada workaround

- Meningkatkan pengalaman pengguna

- Ditargetkan di sprint kedua

Prioritas P2 (Could Have - 5 Requirements):

- Fitur nice-to-have

- Dapat ditiadakan jika waktu/anggaran terbatas

- Dilakukan jika ada waktu

Prioritas P3 (Won't Have for Now):

- Ditunda untuk fase berikutnya

### 3.4. Scope Definition

#### 3.4.1. Scope Statement

Project Scope Statement

Nama Proyek: P-FNE-02: Core Agricultural Operations

Project Scope Description:
Membangun sistem manajemen operasi pertanian terintegrasi yang mencakup:

- Farm & Land Management - Manajemen farm, land parcel, analisis tanah, dan fasilitas farm

- Crop Management - Siklus tanam dari perencanaan hingga panen

- Harvest Management - Perencanaan panen, eksekusi, batch management, dan quality control

- Livestock Management - Manajemen ternak, pakan, kesehatan, reproduksi, dan produksi

- Activity Recording - Pencatatan aktivitas farm dengan dukungan mobile offline

- Resource Management - Manajemen resource pertanian, alokasi, dan konsumsi

Project Deliverables:

- 6 Backend Microservices (Spring Boot/NestJS)

- 1 Web Admin Portal (React/Next.js)

- 1 Mobile Field App (Flutter)

- 1 Executive Dashboard (React)

- Database: PostgreSQL (PostGIS) + TimescaleDB + Redis

- Event-Driven Integration (Apache Kafka)

- Complete Documentation

Acceptance Criteria:

- Farm registration dan land parcel registration berfungsi

- Minimal 5 farm dan 20 land parcel terdaftar

- Crop master (minimal 10 crop) tersedia

- Crop cycle planning, planting, dan growth stage recording berfungsi

- Harvest planning dan execution berfungsi

- Harvest batch dengan unique ID dapat dibuat

- Harvest to inventory integrasi berfungsi

- Livestock master (minimal 5 species) tersedia

- Animal registration dan group management berfungsi

- Mobile offline mode berfungsi

- Event HarvestCompleted dan LivestockProductionCompleted terpublikasi

- Dashboard farm load ≤ 3 detik

- Query crop cycle ≤ 2 detik

- Sinkronisasi offline ≤ 30 detik

#### 3.4.2. Detailed In-Scope

A. Farm & Land Management

| ID | Requirement | Deskripsi |
| --- | --- | --- |
| FNE-FRM-001 | Farm Registration | Register farm dengan atribut lengkap |
| FNE-FRM-002 | Farm Manager Assignment | Tetapkan farm manager |
| FNE-FRM-003 | Farm Status Management | Ubah status farm |
| FNE-FRM-004 | Land Parcel Registration | Register land parcel dengan atribut lengkap |
| FNE-FRM-005 | Land Parcel Mapping | Visualisasi peta sederhana |
| FNE-FRM-006 | Land Parcel Boundaries | Tentukan batas land parcel pada peta |
| FNE-FRM-007 | Land Use History | History penggunaan lahan |
| FNE-FRM-008 | Soil Analysis Record | Catat hasil analisis tanah |
| FNE-FRM-009 | Farm Facility Management | Registrasi fasilitas farm |
| FNE-FRM-010 | Farm Cost Center | Cost center untuk akuntansi |
| FNE-FRM-011 | Farm Performance Dashboard | KPI farm |
| FNE-FRM-012 | Farm Activity Calendar | Kalender aktivitas |

B. Crop Management

| ID | Requirement | Deskripsi |
| --- | --- | --- |
| FNE-CRP-001 | Crop Master Management | Kelola master tanaman |
| FNE-CRP-002 | Crop Cycle Planning | Buat crop cycle plan |
| FNE-CRP-003 | Crop Cycle Status | Status siklus tanam |
| FNE-CRP-004 | Crop Rotation Planning | Rekomendasi rotasi |
| FNE-CRP-005 | Planting Execution | Catat penanaman |
| FNE-CRP-006 | Growth Stage Recording | Catat fase pertumbuhan |
| FNE-CRP-007 | Cultivation Activity Recording | Catat aktivitas budidaya |
| FNE-CRP-008 | Fertilization Recording | Catat pemupukan |
| FNE-CRP-009 | Irrigation Recording | Catat irigasi |
| FNE-CRP-010 | Pest & Disease Monitoring | Monitoring hama & penyakit |
| FNE-CRP-011 | Crop Health Assessment | Penilaian kesehatan |
| FNE-CRP-012 | Expected Harvest Date | Hitung tanggal panen |
| FNE-CRP-013 | Crop Cycle Cost Tracking | Lacak biaya |
| FNE-CRP-014 | Crop Cycle Analytics | Analisis siklus |

C. Harvest Management

| ID | Requirement | Deskripsi |
| --- | --- | --- |
| FNE-HRV-001 | Harvest Planning | Buat rencana panen |
| FNE-HRV-002 | Harvest Execution | Catat aktivitas panen |
| FNE-HRV-003 | Harvest Batch | Buat batch panen |
| FNE-HRV-004 | Harvest Batch Quality | Inspeksi kualitas |
| FNE-HRV-005 | Multiple Harvest | Dukung multiple harvest |
| FNE-HRV-006 | Harvest Loss Recording | Catat post-harvest loss |
| FNE-HRV-007 | Harvest Resource Usage | Catat resource panen |
| FNE-HRV-008 | Harvest to Inventory | Trigger event ke inventory |
| FNE-HRV-009 | Harvest Report | Laporan panen |
| FNE-HRV-010 | Harvest Forecast | Prediksi hasil panen |

D. Livestock Management

| ID | Requirement | Deskripsi |
| --- | --- | --- |
| FNE-LIV-001 | Livestock Master | Kelola master ternak |
| FNE-LIV-002 | Animal Registration | Daftar hewan individu/group |
| FNE-LIV-003 | Animal Group Management | Manajemen group |
| FNE-LIV-004 | Animal Identification | QR Code/RFID |
| FNE-LIV-005 | Animal Location Tracking | Lokasi dan perpindahan |
| FNE-LIV-006 | Feeding Management | Pencatatan pakan |
| FNE-LIV-007 | Feeding Schedule | Jadwal pakan |
| FNE-LIV-008 | Animal Health Record | Catatan kesehatan |
| FNE-LIV-009 | Vaccination Record | Catatan vaksinasi |
| FNE-LIV-010 | Reproduction Management | Pencatatan reproduksi |
| FNE-LIV-011 | Pregnancy Tracking | Lacak kebuntingan |
| FNE-LIV-012 | Animal Production Recording | Produksi ternak |
| FNE-LIV-013 | Production Batch | Batch produksi |
| FNE-LIV-014 | Animal Mortality Recording | Catat kematian |
| FNE-LIV-015 | Animal Sale Recording | Catat penjualan |
| FNE-LIV-016 | Animal Purchase Recording | Catat pembelian |
| FNE-LIV-017 | Feed Inventory | Kelola stok pakan |
| FNE-LIV-018 | Feed Consumption Analysis | Analisis konsumsi pakan |
| FNE-LIV-019 | Livestock Cost Tracking | Lacak biaya ternak |
| FNE-LIV-020 | Livestock Dashboard | KPI ternak |
| FNE-LIV-021 | Livestock to Production | Trigger event ke produksi |

E. Activity Recording

| ID | Requirement | Deskripsi |
| --- | --- | --- |
| FNE-ACT-001 | Generic Activity Recording | Catat aktivitas umum |
| FNE-ACT-002 | Activity Type Master | Kelola tipe aktivitas |
| FNE-ACT-003 | Activity Photo Attachment | Upload foto |
| FNE-ACT-004 | Activity Geo-Tagging | Catat GPS |
| FNE-ACT-005 | Activity Reminder | Reminder aktivitas |
| FNE-ACT-006 | Activity History | History aktivitas |
| FNE-ACT-007 | Activity Approval | Approval workflow |
| FNE-ACT-008 | Weather Integration | Integrasi cuaca |
| FNE-ACT-009 | Mobile Activity Recording | Dukungan offline |
| FNE-ACT-010 | Activity Report | Laporan aktivitas |

F. Resource Management

| ID | Requirement | Deskripsi |
| --- | --- | --- |
| FNE-RES-001 | Agricultural Resource Master | Daftar resource |
| FNE-RES-002 | Resource Requirement Planning | Hitung kebutuhan |
| FNE-RES-003 | Resource Allocation | Alokasi resource |
| FNE-RES-004 | Resource Usage Tracking | Tracking penggunaan |
| FNE-RES-005 | Resource Availability Check | Cek ketersediaan |
| FNE-RES-006 | Resource Procurement Request | Request procurement |
| FNE-RES-007 | Equipment Management | Manajemen peralatan |
| FNE-RES-008 | Equipment Usage Schedule | Jadwal penggunaan |
| FNE-RES-009 | Labor Management | Manajemen tenaga kerja |
| FNE-RES-010 | Resource Cost Analysis | Analisis biaya resource |

#### 3.4.3. Detailed Out-of-Scope

| Domain | Spesifikasi | Alasan |
| --- | --- | --- |
| Keuangan (P-FNE-06) | • General Ledger • Account Payable/Receivable • Payroll • CAPEX Management | Ditangani oleh proyek tersendiri sesuai arsitektur FNE |
| Supply Chain (P-FNE-03) | • Procurement • Inventory Management • Warehouse Management • Supplier Management | Modul terpisah yang terintegrasi via event |
| Production (P-FNE-04) | • Production Planning • BOM Management • Execution Service • Maintenance Service | Modul terpisah yang menerima input dari P-FNE-02 |
| Commerce (P-FNE-05) | • Sales Order • CRM • Marketplace • Logistics | Modul terpisah yang menggunakan data produk |
| Intelligence (P-FNE-07) | • BI Service • AI/ML Service • Knowledge Graph | Modul terpisah yang mengonsumsi data |
| Advanced (P-FNE-08) | • IoT Service • Digital Twin • Simulation | Modul terpisah dengan teknologi berbeda |
| Hardware | • IoT Sensors • RFID Readers • GPS Devices | Diluar tanggung jawab software |
| Integrasi Enterprise | • ERP lain • Sistem legacy | Tidak termasuk dalam scope FNE |

### 3.5. Work Breakdown Structure (WBS)

#### 3.5.1. WBS Hierarchical Structure

text

1.0. Persiapan & Inisiasi (2 minggu)

1.1. Penyusunan Project Charter

1.2. Kick-off Meeting

1.3. Setup Environment & Infrastructure

1.4. Finalisasi Requirement

1.5. Penyusunan PMP

2.0. Foundation & Platform Setup (3 minggu)

2.1. Database Schema Design

2.1.1. Entity Relationship Diagram

2.1.2. DDL Scripts

2.1.3. Migration Scripts

2.2. Core Services Setup

2.2.1. Project Structure

2.2.2. Dependency Management

2.2.3. Configuration Management

2.3. CI/CD Pipeline Setup

2.3.1. Build Pipeline

2.3.2. Test Pipeline

2.3.3. Deployment Pipeline

2.4. Authentication & Authorization

2.4.1. Integration dengan IAM Service

2.4.2. Role-Based Access Control

3.0. Module Development (3 bulan)

3.1. Farm & Land Management (3 minggu)

3.1.1. Farm Service

3.1.1.1. Register Farm

3.1.1.2. Update Farm

3.1.1.3. Get Farm Details

3.1.1.4. List Farms

3.1.2. Land Service

3.1.2.1. Register Land Parcel

3.1.2.2. Update Land Parcel

3.1.2.3. Get Land Parcel Details

3.1.2.4. Map Integration

3.1.3. Soil Analysis Module

3.1.3.1. Record Soil Analysis

3.1.3.2. Generate Recommendations

3.1.3.3. View Analysis History

3.1.4. Farm Facilities Module

3.1.4.1. Register Facility

3.1.4.2. Manage Facilities

3.1.5. UI Implementation

3.1.5.1. Farm Management UI

3.1.5.2. Land Parcel UI

3.1.5.3. Dashboard UI

3.1.6. Testing & QA

3.1.6.1. Unit Testing

3.1.6.2. Integration Testing

3.2. Crop Management (4 minggu)

3.2.1. Crop Master Service

3.2.1.1. Create Crop

3.2.1.2. Update Crop

3.2.1.3. List Crops

3.2.2. Crop Cycle Service

3.2.2.1. Create Crop Cycle Plan

3.2.2.2. Update Crop Cycle

3.2.2.3. Calculate Expected Harvest Date

3.2.2.4. Track Crop Cycle Status

3.2.3. Planting Service

3.2.3.1. Execute Planting

3.2.3.2. Record Planting Details

3.2.4. Growth Stage Service

3.2.4.1. Record Growth Stage

3.2.4.2. Track Plant Health

3.2.5. Cultivation Activity Service

3.2.5.1. Record Cultivation Activity

3.2.5.2. Calculate Activity Cost

3.2.6. UI Implementation

3.2.6.1. Crop Master UI

3.2.6.2. Crop Cycle UI

3.2.6.3. Activity Recording UI

3.2.7. Testing & QA

3.3. Harvest Management (2.5 minggu)

3.3.1. Harvest Plan Service

3.3.1.1. Create Harvest Plan

3.3.1.2. Update Harvest Plan

3.3.2. Harvest Execution Service

3.3.2.1. Execute Harvest

3.3.2.2. Create Harvest Batch

3.3.3. Quality Control Service

3.3.3.1. Record Quality Inspection

3.3.3.2. Record Post-Harvest Loss

3.3.4. Event Publisher

3.3.4.1. Publish HarvestCompleted Event

3.3.5. UI Implementation

3.3.5.1. Harvest Planning UI

3.3.5.2. Harvest Execution UI

3.3.6. Testing & QA

3.4. Livestock Management (3 minggu)

3.4.1. Livestock Master Service

3.4.1.1. Create Livestock Master

3.4.2. Animal Registration Service

3.4.2.1. Register Animal

3.4.2.2. Update Animal

3.4.2.3. Generate QR Code

3.4.3. Feeding Service

3.4.3.1. Record Feeding Activity

3.4.4. Health Service

3.4.4.1. Record Health Check

3.4.4.2. Record Vaccination

3.4.4.3. Record Mortality

3.4.5. Reproduction Service

3.4.5.1. Record Reproduction

3.4.6. Production Service

3.4.6.1. Record Animal Production

3.4.6.2. Publish LivestockProductionCompleted

3.4.7. Transaction Service

3.4.7.1. Record Animal Transaction

3.4.8. UI Implementation

3.4.8.1. Livestock Management UI

3.4.8.2. Health Monitoring UI

3.4.9. Testing & QA

3.5. Activity Recording (2 minggu)

3.5.1. Activity Service

3.5.1.1. Record Generic Activity

3.5.1.2. Create Activity Type

3.5.1.3. List Activities

3.5.2. Reminder Service

3.5.2.1. Schedule Activity Reminder

3.5.3. UI Implementation

3.5.3.1. Activity Recording UI

3.5.3.2. Activity Calendar UI

3.5.4. Testing & QA

3.6. Resource Management (1.5 minggu)

3.6.1. Resource Service

3.6.1.1. Create Resource Item

3.6.1.2. Allocate Resource

3.6.1.3. Consume Resource

3.6.1.4. Calculate Resource Requirements

3.6.2. UI Implementation

3.6.2.1. Resource Management UI

3.6.3. Testing & QA

4.0. Mobile Development (3 bulan - parallel)

4.1. Mobile App UI/UX Design

4.1.1. Wireframes

4.1.2. Design System

4.2. Offline-First Architecture

4.2.1. Local Database Schema

4.2.2. Sync Strategy

4.3. Activity Recording Module

4.3.1. Activity Entry Form

4.3.2. Photo Capture

4.3.3. GPS Capture

4.4. Sync Engine Implementation

4.4.1. Data Sync Logic

4.4.2. Conflict Resolution

4.4.3. Retry Mechanism

4.5. Testing & QA

4.5.1. Unit Testing

4.5.2. Integration Testing

4.5.3. Offline Testing

5.0. Integration & Event-Driven (1.5 bulan)

5.1. Kafka Integration

5.1.1. Kafka Setup

5.1.2. Topic Configuration

5.1.3. Schema Registry

5.2. Event Publishers & Consumers

5.2.1. HarvestCompleted Event Publisher

5.2.2. LivestockProductionCompleted Publisher

5.2.3. ActivityRecorded Event Publisher

5.2.4. Event Consumers

5.3. API Gateway Integration

5.3.1. API Gateway Configuration

5.3.2. BFF Implementation

5.3.3. Authentication Integration

5.4. Integration Testing

5.4.1. API Testing

5.4.2. Event Testing

5.4.3. End-to-End Testing

6.0. Testing & QA (1 bulan)

6.1. Unit Testing

6.1.1. All Services

6.2. Integration Testing

6.2.1. Internal Integration

6.2.2. External Integration

6.3. Performance Testing

6.3.1. Load Testing

6.3.2. Stress Testing

6.3.3. Scalability Testing

6.4. Security Testing

6.4.1. Authentication Testing

6.4.2. Authorization Testing

6.4.3. Vulnerability Scanning

6.5. User Acceptance Testing (UAT)

6.5.1. UAT Preparation

6.5.2. UAT Execution

6.5.3. UAT Sign-off

6.6. Bug Fixing & Regression

7.0. Deployment & Go-Live (3 minggu)

7.1. UAT Environment Preparation

7.1.1. Environment Setup

7.1.2. Data Preparation

7.2. Production Environment Setup

7.2.1. Infrastructure Provisioning

7.2.2. Application Deployment

7.2.3. Monitoring Setup

7.3. Data Migration

7.3.1. Data Mapping

7.3.2. Migration Scripts

7.3.3. Data Validation

7.4. Go-Live Execution

7.4.1. Go-Live Checklist

7.4.2. Cutover Plan

7.4.3. Rollback Plan

7.5. Hypercare Support

7.5.1. 24/7 Support

7.5.2. Issue Tracking & Resolution

8.0. Closure & Handover (1 minggu)

8.1. Documentation Completion

8.1.1. Technical Documentation

8.1.2. User Manual

8.1.3. API Documentation

8.2. Knowledge Transfer

8.2.1. KT Session

8.2.2. Handover Documents

8.3. Project Closure Report

8.3.1. Lessons Learned

8.3.2. Final Report

#### 3.5.2. WBS Dictionary

WBS Dictionary Format:

| Elemen | Deskripsi |
| --- | --- |
| WBS ID | 3.1.1.1 |
| Nama | Register Farm |
| Deskripsi | Endpoint untuk mendaftarkan farm baru ke sistem |
| Output | Farm data saved, FarmResponseDTO returned |
| Durasi | 2 hari |
| Predecessor | 2.4 (Authentication & Authorization) |
| Successor | 3.1.1.2 (Update Farm) |
| Resources | BE:2, QA:0.5 |
| Kriteria Penerimaan | Farm tersimpan dengan semua field, farm manager ter-validasi |
| Acceptance Test | TC-FRM-001: Register Farm with valid data → success |
| Risk | Integrasi dengan IAM Service |

#### 3.5.3. WBS Dictionary - Sample Entries

WBS: 3.1.1.1 - Register Farm

| Elemen | Keterangan |
| --- | --- |
| WBS ID | 3.1.1.1 |
| Nama | Register Farm |
| Deskripsi | Endpoint untuk mendaftarkan farm baru ke dalam sistem. Mencakup validasi data, pengecekan duplikasi kode farm, inisialisasi cost center, dan pencatatan audit trail |
| Deliverable | REST API POST /api/v1/farms |
| Duration | 2 hari |
| Resources | 2 Backend Developer, 0.5 QA |
| Predecessor | 2.4.1 (Integrasi dengan IAM Service) |
| Successor | 3.1.1.2 (Update Farm) |
| Acceptance Criteria | 1. Farm tersimpan dengan semua field yang valid 2. Farm manager ter-validasi dari IAM 3. Cost center otomatis terbuat 4. Audit trail tercatat |
| Test Cases | TC-FRM-001: Register farm dengan data lengkap dan valid → success TC-FRM-002: Register farm dengan kode duplikat → error TC-FRM-003: Register farm dengan farm manager invalid → error |
| Dependencies | P-FNE-01 IAM Service harus ready |
| Risks | IAM Service belum siap → gunakan mock service |

### 3.6. Requirement Traceability Matrix (RTM)

#### 3.6.1. RTM Format

| Requirement ID | Requirement | Priority | WBS | Design Spec | Test Case ID | Status |
| --- | --- | --- | --- | --- | --- | --- |
| FNE-FRM-001 | Farm Registration | P0 | 3.1.1.1 | Farm Service API | TC-FRM-001 - TC-FRM-003 | Pending |
| FNE-FRM-002 | Farm Manager Assignment | P0 | 3.1.1.1 | Farm Service API | TC-FRM-004 | Pending |
| FNE-FRM-003 | Farm Status Management | P0 | 3.1.1.2 | Farm Service API | TC-FRM-005 - TC-FRM-006 | Pending |

#### 3.6.2. Complete RTM

| Requirement ID | Requirement | Priority | WBS | Test Case ID | Status |
| --- | --- | --- | --- | --- | --- |
| Farm & Land Management |  |  |  |  |  |
| FNE-FRM-001 | Farm Registration | P0 | 3.1.1.1 | TC-FRM-001, TC-FRM-002, TC-FRM-003 | Pending |
| FNE-FRM-002 | Farm Manager Assignment | P0 | 3.1.1.1 | TC-FRM-004 | Pending |
| FNE-FRM-003 | Farm Status Management | P0 | 3.1.1.2 | TC-FRM-005, TC-FRM-006 | Pending |
| FNE-FRM-004 | Land Parcel Registration | P0 | 3.1.2.1 | TC-FRM-007, TC-FRM-008 | Pending |
| FNE-FRM-005 | Land Parcel Mapping | P1 | 3.1.2.4 | TC-FRM-009 | Pending |
| FNE-FRM-006 | Land Parcel Boundaries | P2 | 3.1.2.4 | TC-FRM-010 | Pending |
| FNE-FRM-007 | Land Use History | P1 | 3.1.2.3 | TC-FRM-011 | Pending |
| FNE-FRM-008 | Soil Analysis Record | P1 | 3.1.3.1 | TC-FRM-012 | Pending |
| FNE-FRM-009 | Farm Facility Management | P1 | 3.1.4.1 | TC-FRM-013 | Pending |
| FNE-FRM-010 | Farm Cost Center | P0 | 3.1.1.1 | TC-FRM-014 | Pending |
| FNE-FRM-011 | Farm Performance Dashboard | P0 | 3.1.5.3 | TC-FRM-015 | Pending |
| FNE-FRM-012 | Farm Activity Calendar | P1 | 3.5.3.2 | TC-FRM-016 | Pending |
| Crop Management |  |  |  |  |  |
| FNE-CRP-001 | Crop Master Management | P0 | 3.2.1.1 | TC-CRP-001 - TC-CRP-003 | Pending |
| FNE-CRP-002 | Crop Cycle Planning | P0 | 3.2.2.1 | TC-CRP-004 - TC-CRP-006 | Pending |
| FNE-CRP-003 | Crop Cycle Status | P0 | 3.2.2.4 | TC-CRP-007 | Pending |
| FNE-CRP-004 | Crop Rotation Planning | P1 | 3.2.2.1 | TC-CRP-008 | Pending |
| FNE-CRP-005 | Planting Execution | P0 | 3.2.3.1 | TC-CRP-009 | Pending |
| FNE-CRP-006 | Growth Stage Recording | P1 | 3.2.4.1 | TC-CRP-010 | Pending |
| FNE-CRP-007 | Cultivation Activity Recording | P0 | 3.2.5.1 | TC-CRP-011 | Pending |
| FNE-CRP-008 | Fertilization Recording | P0 | 3.2.5.1 | TC-CRP-012 | Pending |
| FNE-CRP-009 | Irrigation Recording | P0 | 3.2.5.1 | TC-CRP-013 | Pending |
| FNE-CRP-010 | Pest & Disease Monitoring | P0 | 3.2.5.1 | TC-CRP-014 | Pending |
| FNE-CRP-011 | Crop Health Assessment | P1 | 3.2.4.1 | TC-CRP-015 | Pending |
| FNE-CRP-012 | Expected Harvest Date | P0 | 3.2.2.3 | TC-CRP-016 | Pending |
| FNE-CRP-013 | Crop Cycle Cost Tracking | P0 | 3.2.5.2 | TC-CRP-017 | Pending |
| FNE-CRP-014 | Crop Cycle Analytics | P1 | 3.2.6.3 | TC-CRP-018 | Pending |
| Harvest Management |  |  |  |  |  |
| FNE-HRV-001 | Harvest Planning | P0 | 3.3.1.1 | TC-HRV-001 - TC-HRV-003 | Pending |
| FNE-HRV-002 | Harvest Execution | P0 | 3.3.2.1 | TC-HRV-004 - TC-HRV-006 | Pending |
| FNE-HRV-003 | Harvest Batch | P0 | 3.3.2.2 | TC-HRV-007, TC-HRV-008 | Pending |
| FNE-HRV-004 | Harvest Batch Quality | P0 | 3.3.3.1 | TC-HRV-009 | Pending |
| FNE-HRV-005 | Multiple Harvest | P0 | 3.3.2.1 | TC-HRV-010 | Pending |
| FNE-HRV-006 | Harvest Loss Recording | P1 | 3.3.3.2 | TC-HRV-011 | Pending |
| FNE-HRV-007 | Harvest Resource Usage | P1 | 3.3.2.1 | TC-HRV-012 | Pending |
| FNE-HRV-008 | Harvest to Inventory | P0 | 3.3.4.1 | TC-HRV-013 | Pending |
| FNE-HRV-009 | Harvest Report | P0 | 3.3.5.2 | TC-HRV-014 | Pending |
| FNE-HRV-010 | Harvest Forecast | P1 | 3.3.4.1 | TC-HRV-015 | Pending |

### 3.7. Scope Verification

#### 3.7.1. Scope Verification Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                     SCOPE VERIFICATION PROCESS                              │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Deliverable │───►│ Inspect &   │───►│ Compare to  │───►│ Accept or   │ │

│  │ Complete    │    │ Test        │    │ Requirements│    │ Reject      │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  Verification Methods:                                                      │

│  • UAT (User Acceptance Testing)                                          │

│  • Inspection / Walkthrough                                                │

│  • Testing (Functional & Non-Functional)                                   │

│  • Demo to stakeholders                                                    │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 3.7.2. Acceptance Criteria Checklist

| No | Kriteria | Status | Tanggal |
| --- | --- | --- | --- |
| 1 | Farm registration dan land parcel registration berfungsi | [ ] |  |
| 2 | Minimal 5 farm dan 20 land parcel terdaftar dalam sistem | [ ] |  |
| 3 | Land parcel mapping (peta) berfungsi | [ ] |  |
| 4 | Crop master (minimal 10 crop) telah tersedia | [ ] |  |
| 5 | Crop cycle planning, planting, dan growth stage recording berfungsi | [ ] |  |
| 6 | Aktivitas budidaya (fertilization, irrigation, pest control) dapat dicatat | [ ] |  |
| 7 | Expected harvest date dihitung secara otomatis | [ ] |  |
| 8 | Harvest planning dan execution berfungsi | [ ] |  |
| 9 | Harvest batch dapat dibuat dengan unique ID | [ ] |  |
| 10 | Harvest to inventory integrasi berfungsi (trigger event) | [ ] |  |
| 11 | Livestock master (minimal 5 species) telah tersedia | [ ] |  |
| 12 | Animal registration dan group management berfungsi | [ ] |  |
| 13 | Feeding, health, reproduction, dan production recording berfungsi | [ ] |  |
| 14 | Livestock production to inventory integrasi berfungsi | [ ] |  |
| 15 | Pekerja lapangan dapat mencatat aktivitas melalui mobile app | [ ] |  |
| 16 | Offline mode berfungsi | [ ] |  |
| 17 | Sinkronisasi berhasil | [ ] |  |
| 18 | Event HarvestCompleted terpublikasi dan diterima oleh sistem lain | [ ] |  |
| 19 | Event LivestockProductionCompleted terpublikasi dan diterima oleh sistem lain | [ ] |  |
| 20 | Dashboard farm load dalam ≤ 3 detik | [ ] |  |
| 21 | Query crop cycle dalam ≤ 2 detik | [ ] |  |
| 22 | Sinkronisasi offline selesai dalam ≤ 30 detik | [ ] |  |
| 23 | User hanya dapat mengakses farm yang menjadi tanggung jawabnya | [ ] |  |
| 24 | Audit trail untuk semua aktivitas farm tersedia | [ ] |  |

#### 3.7.3. UAT Sign-off Form

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                           UAT SIGN-OFF FORM                                 │

│                    P-FNE-02: Core Agricultural Operations                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Project: P-FNE-02: Core Agricultural Operations                           │

│  Date: ___________________                                                  │

│  UAT Period: ___________________                                            │

│                                                                             │

│  UAT Participants:                                                          │

│  ──────────────────                                                         │

│  Name: ___________________      Role: Farm Manager                         │

│  Name: ___________________      Role: Agronomist                           │

│  Name: ___________________      Role: Operational Team                     │

│                                                                             │

│  Test Summary:                                                              │

│  ─────────────                                                              │

│  Total Test Cases: ________                                                │

│  Passed: ________                                                           │

│  Failed: ________                                                           │

│  Acceptance Rate: ________%                                                │

│                                                                             │

│  UAT Result:                                                               │

│  ────────────                                                              │

│  [ ] Accepted                                                              │

│  [ ] Accepted with Conditions                                              │

│  [ ] Rejected                                                              │

│                                                                             │

│  Conditions / Notes:                                                       │

│  ────────────────────                                                      │

│  ______________________________________________________________________    │

│  ______________________________________________________________________    │

│                                                                             │

│  _________________________                                                  │

│  Product Owner                                                             │

│                                                                             │

│  _________________________                                                  │

│  Project Manager                                                           │

│                                                                             │

│  _________________________                                                  │

│  Farm Manager / User Representative                                        │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 3.8. Scope Control

#### 3.8.1. Scope Change Process

| Tahap | Aktivitas | PIC |
| --- | --- | --- |
| 1. Identifikasi | Stakeholder mengidentifikasi kebutuhan perubahan | Stakeholder |
| 2. Pengajuan | Mengisi Change Request Form | Requestor |
| 3. Analisis | Analisis dampak terhadap scope, waktu, biaya, risiko | PM + Tech Lead |
| 4. Evaluasi | Evaluasi oleh CCB | CCB |
| 5. Keputusan | Approve / Reject / Defer | CCB |
| 6. Implementasi | Jika approve, implementasikan perubahan | PM |
| 7. Komunikasi | Informasikan ke semua stakeholder | PM |

#### 3.8.2. Scope Baseline

Scope baseline terdiri dari:

- Scope Statement - Dokumen yang mendefinisikan in-scope dan out-of-scope

- WBS - Work Breakdown Structure

- WBS Dictionary - Detail setiap elemen WBS

- Requirement Traceability Matrix - Link requirement ke WBS dan testing

#### 3.8.3. Scope Performance Measurement

| Metric | Target | Measurement |
| --- | --- | --- |
| Scope Change Rate | ≤ 5% | Number of CRs / Total scope |
| Scope Variance | ≤ 10% | Delivered scope / Planned scope |
| Scope Creep | 0% | Unapproved changes / Total scope |
| Requirement Completion | 100% P0 | P0 requirements completed |

### 3.9. Scope Management Plan Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    SCOPE MANAGEMENT PLAN APPROVAL                           │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│                                                                             │

│  Saya menyetujui Scope Management Plan ini dan akan menjadi baseline      │

│  untuk manajemen scope proyek.                                             │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Product Owner                                                              │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  Technical Lead                                                             │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 4: MANAJEMEN PENJADWALAN PROYEK

### 4.1. Tujuan Manajemen Penjadwalan

Manajemen penjadwalan proyek bertujuan untuk:

- Memastikan Ketepatan Waktu – Menjamin proyek diselesaikan sesuai dengan timeline yang telah disetujui (5-6 bulan).

- Mengidentifikasi Jalur Kritis – Menentukan aktivitas-aktivitas yang paling kritis terhadap keberhasilan proyek.

- Mengalokasikan Sumber Daya Secara Optimal – Memastikan sumber daya tersedia pada waktu yang tepat untuk setiap aktivitas.

- Memantau Kemajuan – Menyediakan mekanisme untuk melacak kemajuan proyek secara real-time.

- Mengantisipasi Keterlambatan – Menyediakan buffer dan mitigasi untuk mengatasi potensi keterlambatan.

### 4.2. Schedule Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                     SCHEDULE MANAGEMENT PROCESS                             │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Define      │───►│ Sequence    │───►│ Estimate    │───►│ Develop     │ │

│  │ Activities  │    │ Activities  │    │ Duration    │    │ Schedule    │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Activity  │    │ • PDM       │    │ • Analogous │    │ • Gantt     │ │

│  │   List      │    │ • Dependencies│   │ • Parametric│    │ • Milestone │ │

│  │ • Milestone │    │ • Leads &   │    │ • Three-    │    │ • Critical  │ │

│  │   List      │    │   Lags      │    │   Point     │    │   Path      │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  ┌─────────────┐                                                           │

│  │ Control     │                                                           │

│  │ Schedule    │                                                           │

│  └─────────────┘                                                           │

│        │                                                                   │

│        ▼                                                                   │

│  ┌─────────────┐                                                           │

│  │ • EVM       │                                                           │

│  │ • Trend     │                                                           │

│  │   Analysis  │                                                           │

│  │ • Schedule  │                                                           │

│  │   Variance  │                                                           │

│  │   Analysis  │                                                           │

│  └─────────────┘                                                           │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 4.3. Activity Definition

#### 4.3.1. Activity List

Fase 1: Persiapan & Inisiasi (2 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 1.1.1 | Penyusunan Project Charter | 2 | - | PM, PO, BA |
| 1.1.2 | Kick-off Meeting | 1 | 1.1.1 | All Team |
| 1.1.3 | Setup Environment & Infrastructure | 5 | 1.1.2 | DevOps |
| 1.1.4 | Finalisasi Requirement | 3 | 1.1.2 | BA, PO |
| 1.1.5 | Penyusunan PMP | 5 | 1.1.4 | PM |

Fase 2: Foundation & Platform Setup (3 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 2.1.1 | Database Schema Design - ERD | 3 | 1.1.5 | BE Lead |
| 2.1.2 | Database Schema Design - DDL | 2 | 2.1.1 | BE Lead |
| 2.1.3 | Migration Scripts | 2 | 2.1.2 | BE Lead |
| 2.2.1 | Project Structure Setup | 2 | 1.1.5 | BE, FE Lead |
| 2.2.2 | Dependency Management | 1 | 2.2.1 | BE Lead |
| 2.2.3 | Configuration Management | 2 | 2.2.2 | BE, DevOps |
| 2.3.1 | CI/CD - Build Pipeline | 3 | 2.2.3 | DevOps |
| 2.3.2 | CI/CD - Test Pipeline | 2 | 2.3.1 | DevOps, QA |
| 2.3.3 | CI/CD - Deployment Pipeline | 2 | 2.3.2 | DevOps |
| 2.4.1 | Integration dengan IAM Service | 3 | 2.3.3 | BE Lead |
| 2.4.2 | Role-Based Access Control | 2 | 2.4.1 | BE Lead |

Fase 3: Module Development (3 bulan)

3.1. Farm & Land Management (3 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 3.1.1.1 | Register Farm | 2 | 2.4.2 | BE:2 |
| 3.1.1.2 | Update Farm | 1 | 3.1.1.1 | BE:2 |
| 3.1.1.3 | Get Farm Details | 1 | 3.1.1.2 | BE:2 |
| 3.1.1.4 | List Farms | 1 | 3.1.1.3 | BE:2 |
| 3.1.2.1 | Register Land Parcel | 3 | 3.1.1.4 | BE:2 |
| 3.1.2.2 | Update Land Parcel | 1 | 3.1.2.1 | BE:2 |
| 3.1.2.3 | Get Land Parcel Details | 1 | 3.1.2.2 | BE:2 |
| 3.1.2.4 | Map Integration | 3 | 3.1.2.3 | BE:1, FE:1 |
| 3.1.3.1 | Record Soil Analysis | 2 | 3.1.2.4 | BE:1 |
| 3.1.3.2 | Generate Recommendations | 1 | 3.1.3.1 | BE:1 |
| 3.1.3.3 | View Analysis History | 1 | 3.1.3.2 | BE:1, FE:1 |
| 3.1.4.1 | Register Facility | 1 | 3.1.2.4 | BE:1 |
| 3.1.4.2 | Manage Facilities | 1 | 3.1.4.1 | BE:1, FE:1 |
| 3.1.5.1 | Farm Management UI | 3 | 3.1.1.4 | FE:2 |
| 3.1.5.2 | Land Parcel UI | 3 | 3.1.2.4 | FE:2 |
| 3.1.5.3 | Dashboard UI | 2 | 3.1.5.2 | FE:2 |
| 3.1.6.1 | Unit Testing | 2 | 3.1.5.3 | QA:1 |
| 3.1.6.2 | Integration Testing | 2 | 3.1.6.1 | QA:1 |

3.2. Crop Management (4 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 3.2.1.1 | Create Crop | 2 | 3.1.6.2 | BE:2 |
| 3.2.1.2 | Update Crop | 1 | 3.2.1.1 | BE:2 |
| 3.2.1.3 | List Crops | 1 | 3.2.1.2 | BE:2 |
| 3.2.2.1 | Create Crop Cycle Plan | 3 | 3.2.1.3 | BE:2 |
| 3.2.2.2 | Update Crop Cycle | 1 | 3.2.2.1 | BE:2 |
| 3.2.2.3 | Calculate Expected Harvest Date | 1 | 3.2.2.2 | BE:2 |
| 3.2.2.4 | Track Crop Cycle Status | 2 | 3.2.2.3 | BE:2 |
| 3.2.3.1 | Execute Planting | 3 | 3.2.2.4 | BE:2 |
| 3.2.3.2 | Record Planting Details | 1 | 3.2.3.1 | BE:2 |
| 3.2.4.1 | Record Growth Stage | 2 | 3.2.3.2 | BE:2 |
| 3.2.4.2 | Track Plant Health | 1 | 3.2.4.1 | BE:2 |
| 3.2.5.1 | Record Cultivation Activity | 3 | 3.2.4.2 | BE:2 |
| 3.2.5.2 | Calculate Activity Cost | 1 | 3.2.5.1 | BE:2 |
| 3.2.6.1 | Crop Master UI | 2 | 3.2.1.3 | FE:2 |
| 3.2.6.2 | Crop Cycle UI | 4 | 3.2.2.4 | FE:2 |
| 3.2.6.3 | Activity Recording UI | 3 | 3.2.5.2 | FE:2 |
| 3.2.7.1 | Unit Testing | 3 | 3.2.6.3 | QA:1 |
| 3.2.7.2 | Integration Testing | 2 | 3.2.7.1 | QA:1 |

3.3. Harvest Management (2.5 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 3.3.1.1 | Create Harvest Plan | 2 | 3.2.7.2 | BE:2 |
| 3.3.1.2 | Update Harvest Plan | 1 | 3.3.1.1 | BE:2 |
| 3.3.2.1 | Execute Harvest | 3 | 3.3.1.2 | BE:2 |
| 3.3.2.2 | Create Harvest Batch | 2 | 3.3.2.1 | BE:2 |
| 3.3.3.1 | Record Quality Inspection | 2 | 3.3.2.2 | BE:2 |
| 3.3.3.2 | Record Post-Harvest Loss | 1 | 3.3.3.1 | BE:1 |
| 3.3.4.1 | Publish HarvestCompleted Event | 2 | 3.3.2.2 | BE:2 |
| 3.3.5.1 | Harvest Planning UI | 2 | 3.3.1.2 | FE:2 |
| 3.3.5.2 | Harvest Execution UI | 2 | 3.3.2.2 | FE:2 |
| 3.3.6.1 | Unit Testing | 2 | 3.3.5.2 | QA:1 |
| 3.3.6.2 | Integration Testing | 1 | 3.3.6.1 | QA:1 |

3.4. Livestock Management (3 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 3.4.1.1 | Create Livestock Master | 1 | 3.3.6.2 | BE:2 |
| 3.4.2.1 | Register Animal | 2 | 3.4.1.1 | BE:2 |
| 3.4.2.2 | Update Animal | 1 | 3.4.2.1 | BE:2 |
| 3.4.2.3 | Generate QR Code | 1 | 3.4.2.2 | BE:1 |
| 3.4.3.1 | Record Feeding Activity | 2 | 3.4.2.3 | BE:2 |
| 3.4.4.1 | Record Health Check | 2 | 3.4.3.1 | BE:2 |
| 3.4.4.2 | Record Vaccination | 1 | 3.4.4.1 | BE:2 |
| 3.4.4.3 | Record Mortality | 1 | 3.4.4.2 | BE:1 |
| 3.4.5.1 | Record Reproduction | 2 | 3.4.4.3 | BE:2 |
| 3.4.6.1 | Record Animal Production | 2 | 3.4.5.1 | BE:2 |
| 3.4.6.2 | Publish LivestockProductionCompleted | 1 | 3.4.6.1 | BE:1 |
| 3.4.7.1 | Record Animal Transaction | 1 | 3.4.6.2 | BE:1 |
| 3.4.8.1 | Livestock Management UI | 3 | 3.4.2.3 | FE:2 |
| 3.4.8.2 | Health Monitoring UI | 2 | 3.4.4.3 | FE:2 |
| 3.4.9.1 | Unit Testing | 2 | 3.4.8.2 | QA:1 |
| 3.4.9.2 | Integration Testing | 1 | 3.4.9.1 | QA:1 |

3.5. Activity Recording (2 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 3.5.1.1 | Record Generic Activity | 2 | 3.4.9.2 | BE:2 |
| 3.5.1.2 | Create Activity Type | 1 | 3.5.1.1 | BE:1 |
| 3.5.1.3 | List Activities | 1 | 3.5.1.2 | BE:1, FE:1 |
| 3.5.2.1 | Schedule Activity Reminder | 2 | 3.5.1.3 | BE:1 |
| 3.5.3.1 | Activity Recording UI | 2 | 3.5.1.3 | FE:2 |
| 3.5.3.2 | Activity Calendar UI | 2 | 3.5.2.1 | FE:2 |
| 3.5.4.1 | Unit Testing | 1 | 3.5.3.2 | QA:1 |
| 3.5.4.2 | Integration Testing | 1 | 3.5.4.1 | QA:1 |

3.6. Resource Management (1.5 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 3.6.1.1 | Create Resource Item | 1 | 3.5.4.2 | BE:1 |
| 3.6.1.2 | Allocate Resource | 2 | 3.6.1.1 | BE:1 |
| 3.6.1.3 | Consume Resource | 2 | 3.6.1.2 | BE:1 |
| 3.6.1.4 | Calculate Resource Requirements | 1 | 3.6.1.3 | BE:1 |
| 3.6.2.1 | Resource Management UI | 2 | 3.6.1.4 | FE:1 |
| 3.6.3.1 | Unit Testing | 1 | 3.6.2.1 | QA:1 |
| 3.6.3.2 | Integration Testing | 1 | 3.6.3.1 | QA:1 |

Fase 4: Mobile Development (3 bulan - parallel)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 4.1.1 | Wireframes | 3 | 1.1.5 | Mobile:1 |
| 4.1.2 | Design System | 3 | 4.1.1 | Mobile:1 |
| 4.2.1 | Local Database Schema | 3 | 4.1.2 | Mobile:1 |
| 4.2.2 | Sync Strategy | 3 | 4.2.1 | Mobile:1 |
| 4.3.1 | Activity Entry Form | 5 | 4.2.2 | Mobile:1 |
| 4.3.2 | Photo Capture | 3 | 4.3.1 | Mobile:1 |
| 4.3.3 | GPS Capture | 2 | 4.3.2 | Mobile:1 |
| 4.4.1 | Data Sync Logic | 5 | 4.3.3 | Mobile:1 |
| 4.4.2 | Conflict Resolution | 3 | 4.4.1 | Mobile:1 |
| 4.4.3 | Retry Mechanism | 2 | 4.4.2 | Mobile:1 |
| 4.5.1 | Unit Testing | 3 | 4.4.3 | Mobile:1, QA:1 |
| 4.5.2 | Integration Testing | 2 | 4.5.1 | Mobile:1, QA:1 |
| 4.5.3 | Offline Testing | 2 | 4.5.2 | QA:1 |

Fase 5: Integration & Event-Driven (1.5 bulan)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 5.1.1 | Kafka Setup | 2 | 3.6.3.2 | DevOps |
| 5.1.2 | Topic Configuration | 1 | 5.1.1 | DevOps |
| 5.1.3 | Schema Registry | 2 | 5.1.2 | BE Lead |
| 5.2.1 | HarvestCompleted Event Publisher | 2 | 5.1.3 | BE:2 |
| 5.2.2 | LivestockProductionCompleted Publisher | 2 | 5.2.1 | BE:2 |
| 5.2.3 | ActivityRecorded Event Publisher | 1 | 5.2.2 | BE:2 |
| 5.2.4 | Event Consumers | 3 | 5.2.3 | BE:2 |
| 5.3.1 | API Gateway Configuration | 2 | 5.2.4 | DevOps |
| 5.3.2 | BFF Implementation | 4 | 5.3.1 | BE:3, FE:2 |
| 5.3.3 | Authentication Integration | 2 | 5.3.2 | BE:2 |
| 5.4.1 | API Testing | 2 | 5.3.3 | QA:2 |
| 5.4.2 | Event Testing | 2 | 5.4.1 | QA:2 |
| 5.4.3 | End-to-End Testing | 3 | 5.4.2 | QA:2 |

Fase 6: Testing & QA (1 bulan)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 6.1.1 | All Services Unit Testing | 5 | 5.4.3 | QA:2, Dev |
| 6.2.1 | Internal Integration Testing | 3 | 6.1.1 | QA:2 |
| 6.2.2 | External Integration Testing | 2 | 6.2.1 | QA:2 |
| 6.3.1 | Load Testing | 3 | 6.2.2 | QA:2 |
| 6.3.2 | Stress Testing | 2 | 6.3.1 | QA:2 |
| 6.3.3 | Scalability Testing | 2 | 6.3.2 | QA:2 |
| 6.4.1 | Authentication Testing | 1 | 6.3.3 | QA:1 |
| 6.4.2 | Authorization Testing | 1 | 6.4.1 | QA:1 |
| 6.4.3 | Vulnerability Scanning | 2 | 6.4.2 | QA:1 |
| 6.5.1 | UAT Preparation | 2 | 6.4.3 | BA, PO |
| 6.5.2 | UAT Execution | 5 | 6.5.1 | BA, PO, QA |
| 6.5.3 | UAT Sign-off | 1 | 6.5.2 | PO, Farm Mgr |
| 6.6.1 | Bug Fixing & Regression | 5 | 6.5.3 | Dev, QA |

Fase 7: Deployment & Go-Live (3 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 7.1.1 | UAT Environment Setup | 2 | 6.6.1 | DevOps |
| 7.1.2 | UAT Data Preparation | 2 | 7.1.1 | DevOps |
| 7.2.1 | Infrastructure Provisioning | 3 | 7.1.2 | DevOps |
| 7.2.2 | Application Deployment | 2 | 7.2.1 | DevOps, BE |
| 7.2.3 | Monitoring Setup | 2 | 7.2.2 | DevOps |
| 7.3.1 | Data Mapping | 2 | 7.2.3 | BE Lead |
| 7.3.2 | Migration Scripts | 2 | 7.3.1 | BE Lead |
| 7.3.3 | Data Validation | 2 | 7.3.2 | QA:1, BA |
| 7.4.1 | Go-Live Checklist | 1 | 7.3.3 | PM |
| 7.4.2 | Cutover Plan | 1 | 7.4.1 | PM |
| 7.4.3 | Rollback Plan | 1 | 7.4.2 | PM |
| 7.5.1 | 24/7 Support | 5 | 7.4.3 | All Team |
| 7.5.2 | Issue Tracking & Resolution | 5 | 7.5.1 | All Team |

Fase 8: Closure & Handover (1 minggu)

| ID | Aktivitas | Durasi (Hari) | Predecessor | Resource |
| --- | --- | --- | --- | --- |
| 8.1.1 | Technical Documentation | 2 | 7.5.2 | Tech Lead |
| 8.1.2 | User Manual | 2 | 8.1.1 | BA |
| 8.1.3 | API Documentation | 1 | 8.1.2 | BE Lead |
| 8.2.1 | KT Session | 2 | 8.1.3 | All Team |
| 8.2.2 | Handover Documents | 1 | 8.2.1 | PM, Tech Lead |
| 8.3.1 | Lessons Learned | 1 | 8.2.2 | All Team |
| 8.3.2 | Final Report | 1 | 8.3.1 | PM |

### 4.4. Milestone Schedule

#### 4.4.1. Milestone List

| Milestone ID | Nama Milestone | Target Tanggal | Deliverable | Kriteria Penerimaan |
| --- | --- | --- | --- | --- |
| M1 | Project Kick-off | Minggu 1 (2 Sep 2026) | Project Charter, Team Setup | Tim terbentuk, charter disetujui |
| M2 | Database & Foundation | Minggu 5 (30 Sep 2026) | Database Schema, Core Services | ERD disetujui, CI/CD running |
| M3 | Farm & Land Module | Minggu 8 (21 Okt 2026) | Farm & Land Management | 5 farm, 20 land parcel, mapping |
| M4 | Crop Management Module | Minggu 12 (18 Nov 2026) | Crop & Harvest Management | 10 crop master, crop cycle |
| M5 | Livestock Management Module | Minggu 15 (9 Des 2026) | Livestock Management | 5 species, animal registration |
| M6 | Mobile & Resource Module | Minggu 18 (30 Des 2026) | Mobile App, Resource Management | Offline mode, resource management |
| M7 | Integration Complete | Minggu 20 (13 Jan 2027) | Event-Driven Integration | Events terpublish & terima |
| M8 | UAT Complete | Minggu 22 (27 Jan 2027) | UAT Sign-off | 95% acceptance rate |
| M9 | Go-Live | Minggu 23 (3 Feb 2027) | Production Deployment | System live in production |
| M10 | Project Closure | Minggu 24 (10 Feb 2027) | Closure Report | Handover complete |

#### 4.4.2. Milestone Timeline

text

Minggu:  1  2  3  4  5  6  7  8  9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24

│  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │  │

M1       ████████████████████████████████████████████████████████████████████████

(Kick-off)

M2                        ████████████████████████████████████████████████████████

(Foundation)

M3                                          ██████████████████████████████████████

(Farm & Land)

M4                                                                  ██████████████

(Crop)

M5                                                                           ██████

(Livestock)

M6                                                                                ██

(Mobile)

M7                                                                                 ██

(Integration)

M8                                                                                   ██

(UAT)

M9                                                                                     ██

(Go-Live)

M10                                                                                      ██

(Closure)

### 4.5. Dependencies

#### 4.5.1. Internal Dependencies

| ID | Predecessor Activity | Successor Activity | Type | Lag |
| --- | --- | --- | --- | --- |
| D1 | 1.1.5 (PMP Final) | 2.1.1 (Database Design) | Finish-to-Start | 0 |
| D2 | 2.3.3 (CI/CD Done) | 2.4.1 (IAM Integration) | Finish-to-Start | 0 |
| D3 | 2.4.2 (RBAC Done) | 3.1.1.1 (Farm Register) | Finish-to-Start | 0 |
| D4 | 3.1.6.2 (Farm Testing) | 3.2.1.1 (Create Crop) | Finish-to-Start | 0 |
| D5 | 3.2.7.2 (Crop Testing) | 3.3.1.1 (Harvest Plan) | Finish-to-Start | 0 |
| D6 | 3.3.6.2 (Harvest Testing) | 3.4.1.1 (Livestock Master) | Finish-to-Start | 0 |
| D7 | 3.4.9.2 (Livestock Testing) | 3.5.1.1 (Activity Record) | Finish-to-Start | 0 |
| D8 | 3.5.4.2 (Activity Testing) | 3.6.1.1 (Resource Item) | Finish-to-Start | 0 |
| D9 | 3.6.3.2 (Resource Testing) | 5.1.1 (Kafka Setup) | Finish-to-Start | 0 |

#### 4.5.2. External Dependencies

| ID | Dependency | Project | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| E1 | IAM Service Ready | P-FNE-01 | Authentication & Authorization | Mock service, parallel engineering |
| E2 | Master Data Service | P-FNE-01 | Data master | Data seeding script |
| E3 | Inventory Service API | P-FNE-03 | Harvest to Inventory | Mock API, integration later |
| E4 | Finance Service API | P-FNE-06 | Cost tracking | Manual entry fallback |
| E5 | API Gateway Configuration | FNE Platform | Routing | Local gateway for testing |

### 4.6. Critical Path Analysis

#### 4.6.1. Critical Path Identification

text

Critical Path: 1.1.1 → 1.1.2 → 1.1.4 → 1.1.5 → 2.1.1 → 2.1.2 → 2.1.3 → 2.2.1 → 2.2.2 → 2.2.3 → 2.3.1 → 2.3.2 → 2.3.3 → 2.4.1 → 2.4.2 → 3.1.1.1 → 3.1.1.2 → 3.1.1.3 → 3.1.1.4 → 3.1.2.1 → 3.1.2.2 → 3.1.2.3 → 3.1.2.4 → 3.1.5.2 → 3.1.6.1 → 3.1.6.2 → 3.2.1.1 → 3.2.1.2 → 3.2.1.3 → 3.2.2.1 → 3.2.2.2 → 3.2.2.3 → 3.2.2.4 → 3.2.3.1 → 3.2.3.2 → 3.2.4.1 → 3.2.4.2 → 3.2.5.1 → 3.2.5.2 → 3.2.6.2 → 3.2.7.1 → 3.2.7.2 → 3.3.1.1 → 3.3.1.2 → 3.3.2.1 → 3.3.2.2 → 3.3.4.1 → 3.3.5.2 → 3.3.6.1 → 3.3.6.2 → 3.4.1.1 → 3.4.2.1 → 3.4.2.2 → 3.4.2.3 → 3.4.3.1 → 3.4.4.1 → 3.4.4.2 → 3.4.4.3 → 3.4.5.1 → 3.4.6.1 → 3.4.6.2 → 3.4.8.1 → 3.4.9.1 → 3.4.9.2 → 3.5.1.1 → 3.5.1.2 → 3.5.1.3 → 3.5.2.1 → 3.5.3.2 → 3.5.4.1 → 3.5.4.2 → 3.6.1.1 → 3.6.1.2 → 3.6.1.3 → 3.6.1.4 → 3.6.2.1 → 3.6.3.1 → 3.6.3.2 → 5.1.1 → 5.1.2 → 5.1.3 → 5.2.1 → 5.2.2 → 5.2.3 → 5.2.4 → 5.3.1 → 5.3.2 → 5.3.3 → 5.4.1 → 5.4.2 → 5.4.3 → 6.1.1 → 6.2.1 → 6.2.2 → 6.3.1 → 6.3.2 → 6.3.3 → 6.4.1 → 6.4.2 → 6.4.3 → 6.5.1 → 6.5.2 → 6.5.3 → 6.6.1 → 7.1.1 → 7.1.2 → 7.2.1 → 7.2.2 → 7.2.3 → 7.3.1 → 7.3.2 → 7.3.3 → 7.4.1 → 7.4.2 → 7.4.3 → 7.5.1 → 7.5.2 → 8.1.1 → 8.1.2 → 8.1.3 → 8.2.1 → 8.2.2 → 8.3.1 → 8.3.2

#### 4.6.2. Critical Path Duration

| Fase | Total Durasi (Hari) |
| --- | --- |
| 1. Persiapan & Inisiasi | 10 |
| 2. Foundation & Platform Setup | 15 |
| 3. Module Development | 65 |
| 4. Mobile Development (Parallel) | 10 |
| 5. Integration & Event-Driven | 25 |
| 6. Testing & QA | 20 |
| 7. Deployment & Go-Live | 15 |
| 8. Closure & Handover | 5 |
| Total | 155 Hari |

#### 4.6.3. Critical Path Buffer

| Buffer Type | Durasi | Lokasi |
| --- | --- | --- |
| Project Buffer | 10 hari | Akhir proyek |
| Feeding Buffer | 3 hari | Sebelum M2 |
| Feeding Buffer | 3 hari | Sebelum M5 |
| Feeding Buffer | 4 hari | Sebelum M7 |

### 4.7. Schedule Performance Measurement

#### 4.7.1. Earned Value Management (EVM) Parameters

| Parameter | Definisi | Measurement |
| --- | --- | --- |
| Planned Value (PV) | Budget per activity sesuai WBS | Per Sprint / Per Milestone |
| Earned Value (EV) | Work completed (story points) | Sprint Review |
| Actual Cost (AC) | Actual cost incurred | Per Sprint |

#### 4.7.2. EVM Metrics

| Metric | Formula | Target |
| --- | --- | --- |
| Schedule Performance Index (SPI) | EV / PV | ≥ 0.9 |
| Cost Performance Index (CPI) | EV / AC | ≥ 0.9 |
| Estimate at Completion (EAC) | BAC / CPI | ≤ BAC |
| Estimate to Complete (ETC) | EAC - AC | As planned |

#### 4.7.3. Schedule Variance Analysis

| Variance | Tolerance | Action |
| --- | --- | --- |
| 0-10% | Green | Monitor only |
| 10-20% | Yellow | Investigation, corrective action |
| >20% | Red | Escalation, recovery plan |

#### 4.7.4. Status Reporting Schedule

| Report Type | Frequency | Audience |
| --- | --- | --- |
| Daily Stand-up | Harian | Development Team |
| Sprint Burndown | 2 minggu | PM, PO, Tech Lead |
| Weekly Status | Mingguan | PMO, Sponsor |
| Milestone Report | Per Milestone | Steering Committee |
| EVM Report | Bulanan | PMO, Sponsor |

### 4.8. Schedule Control

#### 4.8.1. Schedule Change Process

| Step | Activity | PIC | Timeline |
| --- | --- | --- | --- |
| 1 | Identify delay/change | PM/Dev | Continuous |
| 2 | Assess impact | PM + Tech Lead | 1 hari |
| 3 | Develop options | PM | 2 hari |
| 4 | Get approval | CCB | 2 hari |
| 5 | Implement changes | PM + Dev | Varies |
| 6 | Update schedule | PM | 1 hari |
| 7 | Communicate | PM | 1 hari |

#### 4.8.2. Schedule Recovery Strategies

| Strategy | Description | When to Apply |
| --- | --- | --- |
| Crashing | Menambah resource | Jika di awal proyek |
| Fast Tracking | Aktivitas parallel | Jika ada dependency non-kritis |
| Scope Reduction | Mengurangi fitur | Jika di tengah proyek |
| Overtime | Perpanjang jam kerja | Jika mendekati deadline |
| Resource Reallocation | Pindahkan resource | Jika ada idle resource |

#### 4.8.3. Schedule Recovery Plan Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        SCHEDULE RECOVERY PLAN                               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Date: __________________                                                   │

│  Current Schedule Variance: __________________%                            │

│  Root Cause: __________________                                             │

│                                                                             │

│  Recovery Strategy:                                                         │

│  ────────────────────                                                      │

│  [ ] Crashing - Add resources                                              │

│  [ ] Fast Tracking - Parallel activities                                   │

│  [ ] Scope Reduction                                                       │

│  [ ] Overtime                                                              │

│  [ ] Resource Reallocation                                                 │

│                                                                             │

│  Recovery Actions:                                                          │

│  1. __________________                                                     │

│  2. __________________                                                     │

│  3. __________________                                                     │

│                                                                             │

│  New Target Date: __________________                                        │

│  Additional Cost: __________________                                        │

│  Risk of Recovery: __________________                                       │

│                                                                             │

│  Approved by: __________________                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 4.9. Resource Calendar

#### 4.9.1. Team Availability

| Peran | Hari Kerja/Minggu | Jam/Hari | Hari Libur |
| --- | --- | --- | --- |
| PM, PO, BA | Senin - Jumat | 8 jam | Nasional, Company |
| Dev (BE, FE, Mobile) | Senin - Jumat | 8 jam | Nasional, Company |
| QA | Senin - Jumat | 8 jam | Nasional, Company |
| DevOps | Senin - Jumat | 8 jam | Nasional, Company |

#### 4.9.2. Public Holidays (2026-2027)

| Tanggal | Hari Libur | Dampak |
| --- | --- | --- |
| 16 September 2026 | Maulid Nabi | -1 hari kerja |
| 25 Desember 2026 | Natal | -1 hari kerja |
| 1 Januari 2027 | Tahun Baru | -1 hari kerja |

### 4.10. Project Schedule Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        SCHEDULE APPROVAL FORM                              │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│  Durasi: 155 Hari (22 Minggu)                                              │

│  Target Go-Live: 3 Februari 2027                                           │

│                                                                             │

│  Saya menyetujui Project Schedule ini dan akan menjadi baseline untuk      │

│  manajemen penjadwalan proyek.                                             │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  Product Owner                                                              │

│                                                                             │

│  ___________________________                                                │

│  Project Sponsor                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 5: MANAJEMEN BIAYA PROYEK

### 5.1. Tujuan Manajemen Biaya

Manajemen biaya proyek bertujuan untuk:

- Memastikan Anggaran Terkendali – Menjamin proyek diselesaikan sesuai dengan anggaran yang telah disetujui.

- Menyediakan Estimasi Akurat – Memberikan estimasi biaya yang realistis berdasarkan Activity Based Costing (ABC).

- Memonitor Pengeluaran – Melacak pengeluaran aktual terhadap anggaran baseline.

- Mengoptimalkan Biaya – Mengidentifikasi area penghematan tanpa mengurangi kualitas.

- Memberikan Transparansi – Menyediakan informasi biaya yang jelas kepada stakeholder.

### 5.2. Cost Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         COST MANAGEMENT PROCESS                             │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Plan Cost   │───►│ Estimate    │───►│ Determine   │───►│ Control     │ │

│  │ Management  │    │ Costs       │    │ Budget      │    │ Costs       │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Cost      │    │ • Activity  │    │ • Cost      │    │ • EVM       │ │

│  │   Baseline  │    │   Based     │    │   Baseline  │    │ • Variance  │ │

│  │ • Cost      │    │   Costing   │    │ • Budget    │    │   Analysis  │ │

│  │   Mgmt Plan │    │ • Personnel │    │   Allocation│    │ • Forecast  │ │

│  │             │    │   Rates     │    │ • Reserve   │    │ • Change    │ │

│  │             │    │             │    │   Analysis  │    │   Control  │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 5.3. Activity Based Costing (ABC) Methodology

#### 5.3.1. Metode Estimasi Biaya

Proyek ini menggunakan Activity Based Costing (ABC) dengan pendekatan bottom-up, di mana setiap aktivitas dalam WBS diestimasi biayanya berdasarkan:

- Sumber Daya Manusia – Tarif personil berdasarkan standar INKINDO 2026

- Waktu Pengerjaan – Durasi aktivitas yang telah ditetapkan

- Biaya Langsung – Software, infrastruktur, dan operasional

- Biaya Tidak Langsung – Overhead dan kontingensi

#### 5.3.2. Personil Rate (Tarif INKINDO 2026)

Berdasarkan standar IKATAN KONSULTAN INDONESIA (INKINDO) 2026, berikut adalah tarif personil yang digunakan:

| Level / Peran | Golongan | Tarif per Jam (Rp) | Tarif per Hari (8 Jam) | Tarif per Bulan (22 Hari) |
| --- | --- | --- | --- | --- |
| Project Manager | Senior | 350.000 | 2.800.000 | 61.600.000 |
| Senior Consultant | Senior | 325.000 | 2.600.000 | 57.200.000 |
| Technical Lead | Senior | 325.000 | 2.600.000 | 57.200.000 |
| Product Owner | Senior | 325.000 | 2.600.000 | 57.200.000 |
| Senior Backend Developer | Middle | 275.000 | 2.200.000 | 48.400.000 |
| Backend Developer | Middle | 225.000 | 1.800.000 | 39.600.000 |
| Senior Frontend Developer | Middle | 250.000 | 2.000.000 | 44.000.000 |
| Frontend Developer | Middle | 200.000 | 1.600.000 | 35.200.000 |
| Senior Mobile Developer | Middle | 250.000 | 2.000.000 | 44.000.000 |
| Mobile Developer | Middle | 200.000 | 1.600.000 | 35.200.000 |
| Senior QA Engineer | Middle | 225.000 | 1.800.000 | 39.600.000 |
| QA Engineer | Middle | 175.000 | 1.400.000 | 30.800.000 |
| Business Analyst | Middle | 200.000 | 1.600.000 | 35.200.000 |
| DevOps Engineer | Middle | 225.000 | 1.800.000 | 39.600.000 |
| Senior UX/UI Designer | Middle | 250.000 | 2.000.000 | 44.000.000 |
| UX/UI Designer | Junior | 150.000 | 1.200.000 | 26.400.000 |

#### 5.3.3. Activity Based Costing Formula

text

Biaya Aktivitas = (Durasi Aktivitas × Jumlah Personil × Tarif Personil) + Biaya Langsung + Alokasi Biaya Tidak Langsung

Dimana:

- Durasi Aktivitas = Hari kerja × 8 jam

- Jumlah Personil = Sesuai resource plan

- Tarif Personil = Sesuai tarif INKINDO 2026

- Biaya Langsung = Software license, infrastructure, travel, training

- Biaya Tidak Langsung = Overhead (15% dari total biaya personil)

- Kontingensi = 10% dari total biaya

### 5.4. Cost Estimation by Phase

#### 5.4.1. Fase 1: Persiapan & Inisiasi (2 minggu / 10 hari kerja)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 | Penyusunan Project Charter | 2 | PM:1, BA:1 | PM: 2.800.000, BA: 1.600.000 | 8.800.000 |
| 1.1.2 | Kick-off Meeting | 1 | All Team:14 | Rata-rata 1.500.000 | 21.000.000 |
| 1.1.3 | Setup Environment & Infrastructure | 5 | DevOps:1 | 1.800.000 | 9.000.000 |
| 1.1.4 | Finalisasi Requirement | 3 | BA:1, PO:1 | BA: 1.600.000, PO: 2.600.000 | 12.600.000 |
| 1.1.5 | Penyusunan PMP | 5 | PM:1, BA:0.5 | PM: 2.800.000, BA: 1.600.000 | 18.000.000 |

Total Fase 1: 69.400.000

#### 5.4.2. Fase 2: Foundation & Platform Setup (3 minggu / 15 hari kerja)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 2.1.1 | Database Schema Design - ERD | 3 | BE Lead:1 | 2.600.000 | 7.800.000 |
| 2.1.2 | Database Schema Design - DDL | 2 | BE Lead:1 | 2.600.000 | 5.200.000 |
| 2.1.3 | Migration Scripts | 2 | BE Lead:1 | 2.600.000 | 5.200.000 |
| 2.2.1 | Project Structure Setup | 2 | BE Lead:1, FE Lead:1 | BE:2.600.000, FE:2.600.000 | 10.400.000 |
| 2.2.2 | Dependency Management | 1 | BE Lead:1 | 2.600.000 | 2.600.000 |
| 2.2.3 | Configuration Management | 2 | BE:1, DevOps:1 | BE:1.800.000, DevOps:1.800.000 | 7.200.000 |
| 2.3.1 | CI/CD - Build Pipeline | 3 | DevOps:1 | 1.800.000 | 5.400.000 |
| 2.3.2 | CI/CD - Test Pipeline | 2 | DevOps:1, QA Lead:0.5 | DevOps:1.800.000, QA:1.800.000 | 5.400.000 |
| 2.3.3 | CI/CD - Deployment Pipeline | 2 | DevOps:1 | 1.800.000 | 3.600.000 |
| 2.4.1 | Integration dengan IAM Service | 3 | BE Lead:1, BE:1 | BE Lead:2.600.000, BE:1.800.000 | 13.200.000 |
| 2.4.2 | Role-Based Access Control | 2 | BE Lead:1, BE:1 | BE Lead:2.600.000, BE:1.800.000 | 8.800.000 |

Total Fase 2: 74.800.000

#### 5.4.3. Fase 3: Module Development (3 bulan / 66 hari kerja)

##### 3.1. Farm & Land Management (3 minggu / 15 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 3.1.1.1 | Register Farm | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.1.1.2 | Update Farm | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.1.1.3 | Get Farm Details | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.1.1.4 | List Farms | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.1.2.1 | Register Land Parcel | 3 | BE:2 | 1.800.000 × 2 | 10.800.000 |
| 3.1.2.2 | Update Land Parcel | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.1.2.3 | Get Land Parcel Details | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.1.2.4 | Map Integration | 3 | BE:1, FE:1 | BE:1.800.000, FE:1.600.000 | 10.200.000 |
| 3.1.3.1 | Record Soil Analysis | 2 | BE:1 | 1.800.000 | 3.600.000 |
| 3.1.3.2 | Generate Recommendations | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.1.3.3 | View Analysis History | 1 | BE:1, FE:1 | BE:1.800.000, FE:1.600.000 | 3.400.000 |
| 3.1.4.1 | Register Facility | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.1.4.2 | Manage Facilities | 1 | BE:1, FE:1 | BE:1.800.000, FE:1.600.000 | 3.400.000 |
| 3.1.5.1 | Farm Management UI | 3 | FE:2 | 1.600.000 × 2 | 9.600.000 |
| 3.1.5.2 | Land Parcel UI | 3 | FE:2 | 1.600.000 × 2 | 9.600.000 |
| 3.1.5.3 | Dashboard UI | 2 | FE:2 | 1.600.000 × 2 | 6.400.000 |
| 3.1.6.1 | Unit Testing | 2 | QA:1 | 1.400.000 | 2.800.000 |
| 3.1.6.2 | Integration Testing | 2 | QA:1 | 1.400.000 | 2.800.000 |

Subtotal 3.1: 91.400.000

##### 3.2. Crop Management (4 minggu / 20 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 3.2.1.1 | Create Crop | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.2.1.2 | Update Crop | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.2.1.3 | List Crops | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.2.2.1 | Create Crop Cycle Plan | 3 | BE:2 | 1.800.000 × 2 | 10.800.000 |
| 3.2.2.2 | Update Crop Cycle | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.2.2.3 | Calculate Expected Harvest Date | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.2.2.4 | Track Crop Cycle Status | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.2.3.1 | Execute Planting | 3 | BE:2 | 1.800.000 × 2 | 10.800.000 |
| 3.2.3.2 | Record Planting Details | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.2.4.1 | Record Growth Stage | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.2.4.2 | Track Plant Health | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.2.5.1 | Record Cultivation Activity | 3 | BE:2 | 1.800.000 × 2 | 10.800.000 |
| 3.2.5.2 | Calculate Activity Cost | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.2.6.1 | Crop Master UI | 2 | FE:2 | 1.600.000 × 2 | 6.400.000 |
| 3.2.6.2 | Crop Cycle UI | 4 | FE:2 | 1.600.000 × 2 | 12.800.000 |
| 3.2.6.3 | Activity Recording UI | 3 | FE:2 | 1.600.000 × 2 | 9.600.000 |
| 3.2.7.1 | Unit Testing | 3 | QA:1 | 1.400.000 | 4.200.000 |
| 3.2.7.2 | Integration Testing | 2 | QA:1 | 1.400.000 | 2.800.000 |

Subtotal 3.2: 114.600.000

##### 3.3. Harvest Management (2.5 minggu / 13 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 3.3.1.1 | Create Harvest Plan | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.3.1.2 | Update Harvest Plan | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.3.2.1 | Execute Harvest | 3 | BE:2 | 1.800.000 × 2 | 10.800.000 |
| 3.3.2.2 | Create Harvest Batch | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.3.3.1 | Record Quality Inspection | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.3.3.2 | Record Post-Harvest Loss | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.3.4.1 | Publish HarvestCompleted Event | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.3.5.1 | Harvest Planning UI | 2 | FE:2 | 1.600.000 × 2 | 6.400.000 |
| 3.3.5.2 | Harvest Execution UI | 2 | FE:2 | 1.600.000 × 2 | 6.400.000 |
| 3.3.6.1 | Unit Testing | 2 | QA:1 | 1.400.000 | 2.800.000 |
| 3.3.6.2 | Integration Testing | 1 | QA:1 | 1.400.000 | 1.400.000 |

Subtotal 3.3: 62.000.000

##### 3.4. Livestock Management (3 minggu / 15 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 3.4.1.1 | Create Livestock Master | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.4.2.1 | Register Animal | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.4.2.2 | Update Animal | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.4.2.3 | Generate QR Code | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.4.3.1 | Record Feeding Activity | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.4.4.1 | Record Health Check | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.4.4.2 | Record Vaccination | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 3.4.4.3 | Record Mortality | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.4.5.1 | Record Reproduction | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.4.6.1 | Record Animal Production | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.4.6.2 | Publish LivestockProductionCompleted | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.4.7.1 | Record Animal Transaction | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.4.8.1 | Livestock Management UI | 3 | FE:2 | 1.600.000 × 2 | 9.600.000 |
| 3.4.8.2 | Health Monitoring UI | 2 | FE:2 | 1.600.000 × 2 | 6.400.000 |
| 3.4.9.1 | Unit Testing | 2 | QA:1 | 1.400.000 | 2.800.000 |
| 3.4.9.2 | Integration Testing | 1 | QA:1 | 1.400.000 | 1.400.000 |

Subtotal 3.4: 73.400.000

##### 3.5. Activity Recording (2 minggu / 10 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 3.5.1.1 | Record Generic Activity | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 3.5.1.2 | Create Activity Type | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.5.1.3 | List Activities | 1 | BE:1, FE:1 | BE:1.800.000, FE:1.600.000 | 3.400.000 |
| 3.5.2.1 | Schedule Activity Reminder | 2 | BE:1 | 1.800.000 | 3.600.000 |
| 3.5.3.1 | Activity Recording UI | 2 | FE:2 | 1.600.000 × 2 | 6.400.000 |
| 3.5.3.2 | Activity Calendar UI | 2 | FE:2 | 1.600.000 × 2 | 6.400.000 |
| 3.5.4.1 | Unit Testing | 1 | QA:1 | 1.400.000 | 1.400.000 |
| 3.5.4.2 | Integration Testing | 1 | QA:1 | 1.400.000 | 1.400.000 |

Subtotal 3.5: 31.600.000

##### 3.6. Resource Management (1.5 minggu / 8 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 3.6.1.1 | Create Resource Item | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.6.1.2 | Allocate Resource | 2 | BE:1 | 1.800.000 | 3.600.000 |
| 3.6.1.3 | Consume Resource | 2 | BE:1 | 1.800.000 | 3.600.000 |
| 3.6.1.4 | Calculate Resource Requirements | 1 | BE:1 | 1.800.000 | 1.800.000 |
| 3.6.2.1 | Resource Management UI | 2 | FE:1 | 1.600.000 | 3.200.000 |
| 3.6.3.1 | Unit Testing | 1 | QA:1 | 1.400.000 | 1.400.000 |
| 3.6.3.2 | Integration Testing | 1 | QA:1 | 1.400.000 | 1.400.000 |

Subtotal 3.6: 16.800.000

Total Fase 3: 389.800.000

#### 5.4.4. Fase 4: Mobile Development (3 bulan - parallel / 66 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 4.1.1 | Wireframes | 3 | Mobile:1, UX/UI:0.5 | Mobile:1.600.000, UX:2.000.000 | 7.800.000 |
| 4.1.2 | Design System | 3 | Mobile:1, UX/UI:0.5 | Mobile:1.600.000, UX:2.000.000 | 7.800.000 |
| 4.2.1 | Local Database Schema | 3 | Mobile:1 | 1.600.000 | 4.800.000 |
| 4.2.2 | Sync Strategy | 3 | Mobile:1, BE:0.5 | Mobile:1.600.000, BE:1.800.000 | 7.500.000 |
| 4.3.1 | Activity Entry Form | 5 | Mobile:1, FE:0.5 | Mobile:1.600.000, FE:1.600.000 | 12.000.000 |
| 4.3.2 | Photo Capture | 3 | Mobile:1 | 1.600.000 | 4.800.000 |
| 4.3.3 | GPS Capture | 2 | Mobile:1 | 1.600.000 | 3.200.000 |
| 4.4.1 | Data Sync Logic | 5 | Mobile:1, BE:0.5 | Mobile:1.600.000, BE:1.800.000 | 12.500.000 |
| 4.4.2 | Conflict Resolution | 3 | Mobile:1, BE:0.5 | Mobile:1.600.000, BE:1.800.000 | 7.500.000 |
| 4.4.3 | Retry Mechanism | 2 | Mobile:1, BE:0.5 | Mobile:1.600.000, BE:1.800.000 | 5.000.000 |
| 4.5.1 | Unit Testing | 3 | Mobile:1, QA:1 | Mobile:1.600.000, QA:1.400.000 | 9.000.000 |
| 4.5.2 | Integration Testing | 2 | Mobile:1, QA:1 | Mobile:1.600.000, QA:1.400.000 | 6.000.000 |
| 4.5.3 | Offline Testing | 2 | QA:1 | 1.400.000 | 2.800.000 |

Total Fase 4: 90.700.000

#### 5.4.5. Fase 5: Integration & Event-Driven (1.5 bulan / 33 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 5.1.1 | Kafka Setup | 2 | DevOps:1 | 1.800.000 | 3.600.000 |
| 5.1.2 | Topic Configuration | 1 | DevOps:1 | 1.800.000 | 1.800.000 |
| 5.1.3 | Schema Registry | 2 | BE Lead:1 | 2.600.000 | 5.200.000 |
| 5.2.1 | HarvestCompleted Event Publisher | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 5.2.2 | LivestockProductionCompleted Publisher | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 5.2.3 | ActivityRecorded Event Publisher | 1 | BE:2 | 1.800.000 × 2 | 3.600.000 |
| 5.2.4 | Event Consumers | 3 | BE:2 | 1.800.000 × 2 | 10.800.000 |
| 5.3.1 | API Gateway Configuration | 2 | DevOps:1 | 1.800.000 | 3.600.000 |
| 5.3.2 | BFF Implementation | 4 | BE:3, FE:2 | BE:1.800.000×3, FE:1.600.000×2 | 34.400.000 |
| 5.3.3 | Authentication Integration | 2 | BE:2 | 1.800.000 × 2 | 7.200.000 |
| 5.4.1 | API Testing | 2 | QA:2 | 1.400.000 × 2 | 5.600.000 |
| 5.4.2 | Event Testing | 2 | QA:2 | 1.400.000 × 2 | 5.600.000 |
| 5.4.3 | End-to-End Testing | 3 | QA:2 | 1.400.000 × 2 | 8.400.000 |

Total Fase 5: 104.200.000

#### 5.4.6. Fase 6: Testing & QA (1 bulan / 22 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 6.1.1 | All Services Unit Testing | 5 | QA:2, Dev Support | QA:1.400.000×2, Dev:1.800.000×2 | 16.000.000 |
| 6.2.1 | Internal Integration Testing | 3 | QA:2 | 1.400.000 × 2 | 8.400.000 |
| 6.2.2 | External Integration Testing | 2 | QA:2 | 1.400.000 × 2 | 5.600.000 |
| 6.3.1 | Load Testing | 3 | QA:2 | 1.400.000 × 2 | 8.400.000 |
| 6.3.2 | Stress Testing | 2 | QA:2 | 1.400.000 × 2 | 5.600.000 |
| 6.3.3 | Scalability Testing | 2 | QA:2 | 1.400.000 × 2 | 5.600.000 |
| 6.4.1 | Authentication Testing | 1 | QA:1 | 1.400.000 | 1.400.000 |
| 6.4.2 | Authorization Testing | 1 | QA:1 | 1.400.000 | 1.400.000 |
| 6.4.3 | Vulnerability Scanning | 2 | QA:1 | 1.400.000 | 2.800.000 |
| 6.5.1 | UAT Preparation | 2 | BA:1, PO:0.5 | BA:1.600.000, PO:2.600.000 | 7.000.000 |
| 6.5.2 | UAT Execution | 5 | BA:1, PO:0.5, QA:1 | BA:1.600.000, PO:2.600.000, QA:1.400.000 | 32.000.000 |
| 6.5.3 | UAT Sign-off | 1 | PO:0.5, FM:0.5 | PO:2.600.000, FM:0 | 1.300.000 |
| 6.6.1 | Bug Fixing & Regression | 5 | Dev:2, QA:1 | Dev:1.800.000×2, QA:1.400.000 | 25.000.000 |

Total Fase 6: 120.500.000

#### 5.4.7. Fase 7: Deployment & Go-Live (3 minggu / 15 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 7.1.1 | UAT Environment Setup | 2 | DevOps:1 | 1.800.000 | 3.600.000 |
| 7.1.2 | UAT Data Preparation | 2 | DevOps:1, BA:0.5 | DevOps:1.800.000, BA:1.600.000 | 5.600.000 |
| 7.2.1 | Infrastructure Provisioning | 3 | DevOps:1 | 1.800.000 | 5.400.000 |
| 7.2.2 | Application Deployment | 2 | DevOps:1, BE Lead:0.5 | DevOps:1.800.000, BE Lead:2.600.000 | 7.000.000 |
| 7.2.3 | Monitoring Setup | 2 | DevOps:1 | 1.800.000 | 3.600.000 |
| 7.3.1 | Data Mapping | 2 | BE Lead:1 | 2.600.000 | 5.200.000 |
| 7.3.2 | Migration Scripts | 2 | BE Lead:1 | 2.600.000 | 5.200.000 |
| 7.3.3 | Data Validation | 2 | QA:1, BA:0.5 | QA:1.400.000, BA:1.600.000 | 6.000.000 |
| 7.4.1 | Go-Live Checklist | 1 | PM:1 | 2.800.000 | 2.800.000 |
| 7.4.2 | Cutover Plan | 1 | PM:1 | 2.800.000 | 2.800.000 |
| 7.4.3 | Rollback Plan | 1 | PM:1 | 2.800.000 | 2.800.000 |
| 7.5.1 | 24/7 Support | 5 | Dev:2, QA:1, DevOps:1 | Dev:1.800.000×2, QA:1.400.000, DevOps:1.800.000 | 35.000.000 |
| 7.5.2 | Issue Tracking & Resolution | 5 | Dev:2, QA:1, DevOps:1 | Dev:1.800.000×2, QA:1.400.000, DevOps:1.800.000 | 35.000.000 |

Total Fase 7: 120.000.000

#### 5.4.8. Fase 8: Closure & Handover (1 minggu / 5 hari)

| ID | Aktivitas | Durasi (Hari) | Personil | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- | --- |
| 8.1.1 | Technical Documentation | 2 | Tech Lead:1 | 2.600.000 | 5.200.000 |
| 8.1.2 | User Manual | 2 | BA:1 | 1.600.000 | 3.200.000 |
| 8.1.3 | API Documentation | 1 | BE Lead:1 | 2.600.000 | 2.600.000 |
| 8.2.1 | KT Session | 2 | All Team | - | 0 |
| 8.2.2 | Handover Documents | 1 | PM:1, Tech Lead:0.5 | PM:2.800.000, Tech Lead:2.600.000 | 4.100.000 |
| 8.3.1 | Lessons Learned | 1 | All Team | - | 0 |
| 8.3.2 | Final Report | 1 | PM:1 | 2.800.000 | 2.800.000 |

Total Fase 8: 17.900.000

### 5.5. Cost Summary

#### 5.5.1. Total Cost by Phase

| Fase | Durasi | Biaya Personil (Rp) | Persentase |
| --- | --- | --- | --- |
| Fase 1: Persiapan & Inisiasi | 2 minggu | 69.400.000 | 3.2% |
| Fase 2: Foundation & Platform Setup | 3 minggu | 74.800.000 | 3.4% |
| Fase 3: Module Development | 3 bulan | 389.800.000 | 17.9% |
| Fase 4: Mobile Development | 3 bulan | 90.700.000 | 4.2% |
| Fase 5: Integration & Event-Driven | 1.5 bulan | 104.200.000 | 4.8% |
| Fase 6: Testing & QA | 1 bulan | 120.500.000 | 5.5% |
| Fase 7: Deployment & Go-Live | 3 minggu | 120.000.000 | 5.5% |
| Fase 8: Closure & Handover | 1 minggu | 17.900.000 | 0.8% |
| Subtotal Personil |  | 987.300.000 | 45.3% |

#### 5.5.2. Biaya Langsung (Direct Costs)

| Kategori | Item | Biaya (Rp) | Keterangan |
| --- | --- | --- | --- |
| Infrastruktur | Cloud Infrastructure (AWS/GCP) | 120.000.000 | 6 bulan × Rp 20.000.000/bulan |
|  | Database Services | 30.000.000 | RDS / Cloud SQL |
|  | CDN & Storage | 15.000.000 | 6 bulan × Rp 2.500.000/bulan |
| Software License | IDE (IntelliJ, VS Code) | 15.000.000 | 14 personil × 6 bulan |
|  | Jira & Confluence | 12.000.000 | 14 personil × 6 bulan |
|  | Monitoring Tools | 8.000.000 | Prometheus, Grafana, ELK |
|  | Testing Tools | 5.000.000 | k6, OWASP ZAP, SonarQube |
|  | Design Tools (Figma) | 6.000.000 | 2 personil × 6 bulan |
| Operasional | Travel & Akomodasi | 30.000.000 | UAT, Workshop, Sprints |
|  | Pelatihan & Workshop | 20.000.000 | Training tim dan user |
|  | Communication Tools | 6.000.000 | Slack/Zoom premium |
|  | Hardware Support | 15.000.000 | Laptop/device support |
| Subtotal Biaya Langsung |  | 282.000.000 | 12.9% |

#### 5.5.3. Biaya Tidak Langsung (Indirect Costs / Overhead)

| Kategori | Item | Biaya (Rp) | Keterangan |
| --- | --- | --- | --- |
| Overhead 15% | Manajemen, HR, Fasilitas | 148.095.000 | 15% dari biaya personil |
| Subtotal Biaya Tidak Langsung |  | 148.095.000 | 6.8% |

#### 5.5.4. Kontingensi (10%)

| Kategori | Item | Biaya (Rp) | Keterangan |
| --- | --- | --- | --- |
| Kontingensi | Risiko, perubahan, delay | 141.739.500 | 10% dari total biaya |
| Subtotal Kontingensi |  | 141.739.500 | 6.5% |

#### 5.5.5. Total Budget

| Kategori | Biaya (Rp) | Persentase |
| --- | --- | --- |
| Personil | 987.300.000 | 45.3% |
| Biaya Langsung | 282.000.000 | 12.9% |
| Biaya Tidak Langsung (Overhead 15%) | 148.095.000 | 6.8% |
| Kontingensi (10%) | 141.739.500 | 6.5% |
| Total | 1.559.134.500 | 71.5% |

#### 5.5.6. Budget Allocation Pie Chart

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         BUDGET ALLOCATION                                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ■ Personil (45.3%)     ■ Direct Costs (12.9%)                             │

│  ■ Overhead (6.8%)      ■ Kontingensi (6.5%)                              │

│  ■ Subtotal (28.5%)                                                        │

│                                                                             │

│  ┌──────────────────────────────────────────────────────────────────┐      │

│  │                                                                  │      │

│  │              ■■■■■■■■■■■■■■■■■■■■■■■■■■ (45.3%)                  │      │

│  │              ■■■■■■■■■■ (12.9%)                                   │      │

│  │              ■■■■■ (6.8%)                                         │      │

│  │              ■■■■■ (6.5%)                                         │      │

│  │              ■■■■■■■■■■■■■■■■■■■■ (28.5%)                         │      │

│  │                                                                  │      │

│  └──────────────────────────────────────────────────────────────────┘      │

│                                                                             │

│  Total Budget: Rp 2.180.000.000                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 5.6. Cost Baseline

#### 5.6.1. Time-Phased Budget

| Bulan | Fase | Biaya Personil | Biaya Langsung | Overhead | Total |
| --- | --- | --- | --- | --- | --- |
| Bulan 1 (Sep 2026) | Fase 1 & 2 | 144.200.000 | 40.000.000 | 21.630.000 | 205.830.000 |
| Bulan 2 (Okt 2026) | Fase 3.1 & 3.2 | 140.000.000 | 35.000.000 | 21.000.000 | 196.000.000 |
| Bulan 3 (Nov 2026) | Fase 3.3 & 3.4 | 130.000.000 | 35.000.000 | 19.500.000 | 184.500.000 |
| Bulan 4 (Des 2026) | Fase 3.5, 3.6 & 4 | 120.000.000 | 40.000.000 | 18.000.000 | 178.000.000 |
| Bulan 5 (Jan 2027) | Fase 4, 5 & 6 | 200.000.000 | 45.000.000 | 30.000.000 | 275.000.000 |
| Bulan 6 (Feb 2027) | Fase 6, 7 & 8 | 253.100.000 | 87.000.000 | 37.965.000 | 378.065.000 |
| Total |  | 987.300.000 | 282.000.000 | 148.095.000 | 1.417.395.000 |

#### 5.6.2. Biaya Personil by Role (Estimasi Akhir)

| Peran | Jumlah | Total Man-Days | Tarif/Hari (Rp) | Total (Rp) |
| --- | --- | --- | --- | --- |
| Project Manager | 1 | 120 | 2.800.000 | 336.000.000 |
| Product Owner | 1 | 80 | 2.600.000 | 208.000.000 |
| Technical Lead | 1 | 100 | 2.600.000 | 260.000.000 |
| Business Analyst | 1 | 70 | 1.600.000 | 112.000.000 |
| Backend Developer | 4 | 400 | 1.800.000 | 720.000.000 |
| Frontend Developer | 2 | 180 | 1.600.000 | 288.000.000 |
| Mobile Developer | 1 | 66 | 1.600.000 | 105.600.000 |
| QA Engineer | 2 | 150 | 1.400.000 | 210.000.000 |
| DevOps Engineer | 1 | 80 | 1.800.000 | 144.000.000 |
| UX/UI Designer | 0.5 (shared) | 20 | 2.000.000 | 40.000.000 |
| Total | 14 | 1.266 |  | 2.423.600.000 |

### 5.7. Cost Control

#### 5.7.1. Earned Value Management (EVM)

| Parameter | Nilai |
| --- | --- |
| Budget at Completion (BAC) | 2.180.000.000 |
| Planned Value (PV) | Per sprint / phase |
| Earned Value (EV) | Berdasarkan story points completed |
| Actual Cost (AC) | Biaya aktual yang dikeluarkan |
| Schedule Performance Index (SPI) | EV / PV (target ≥ 0.9) |
| Cost Performance Index (CPI) | EV / AC (target ≥ 0.9) |
| Estimate at Completion (EAC) | BAC / CPI |
| Estimate to Complete (ETC) | EAC - AC |

#### 5.7.2. Biaya Personil by Rate (Per Bulan)

| Peran | Per Bulan (Rp) | Bulan 1 | Bulan 2 | Bulan 3 | Bulan 4 | Bulan 5 | Bulan 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager | 61.600.000 | 1 | 1 | 1 | 1 | 1 | 1 |
| Product Owner | 57.200.000 | 0.5 | 0.8 | 0.8 | 0.8 | 0.6 | 0.4 |
| Technical Lead | 57.200.000 | 0.5 | 1 | 1 | 1 | 0.8 | 0.6 |
| Business Analyst | 35.200.000 | 1 | 0.8 | 0.6 | 0.6 | 0.4 | 0.2 |
| Backend Developer | 39.600.000 | 2 | 3 | 3 | 3 | 2 | 2 |
| Frontend Developer | 35.200.000 | 1 | 2 | 2 | 2 | 1 | 1 |
| Mobile Developer | 35.200.000 | 0 | 0 | 0.5 | 1 | 1 | 0.5 |
| QA Engineer | 30.800.000 | 1 | 1 | 1 | 1 | 2 | 2 |
| DevOps Engineer | 39.600.000 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 |

#### 5.7.3. Monthly Cost Forecast

| Bulan | Planned Cost | Actual Cost | Variance | CPI |
| --- | --- | --- | --- | --- |
| Bulan 1 | 205.830.000 |  |  |  |
| Bulan 2 | 196.000.000 |  |  |  |
| Bulan 3 | 184.500.000 |  |  |  |
| Bulan 4 | 178.000.000 |  |  |  |
| Bulan 5 | 275.000.000 |  |  |  |
| Bulan 6 | 378.065.000 |  |  |  |

#### 5.7.4. Biaya Kontingensi

| Kategori | Alokasi (Rp) | Digunakan | Sisa |
| --- | --- | --- | --- |
| Risiko Teknis | 50.000.000 |  |  |
| Perubahan Scope | 40.000.000 |  |  |
| Keterlambatan | 30.000.000 |  |  |
| Lainnya | 21.739.500 |  |  |
| Total | 141.739.500 |  |  |

#### 5.7.5. Cost Control Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         COST CONTROL PROCESS                                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Track Cost  │───►│ Compare to  │───►│ Analyze     │───►│ Take Action │ │

│  │ Actual      │    │ Baseline    │    │ Variance    │    │             │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Timesheet │    │ • EVM       │    │ • Root Cause│    │ • Re-budget │ │

│  │ • Invoice   │    │ • Variance  │    │   Analysis  │    │ • Recovery  │ │

│  │ • Expense   │    │   Report    │    │ • Forecast  │    │   Plan      │ │

│  │   Report    │    │ • Trend     │    │             │    │ • Change    │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 5.7.6. Variance Threshold

| Variance | Tolerance | Action |
| --- | --- | --- |
| 0-5% | Green | Monitor only |
| 5-10% | Yellow | Investigation, corrective action |
| >10% | Red | Escalation, recovery plan, CCB approval |

### 5.8. Biaya Operasional (Year 1)

| Kategori | Item | Biaya (Rp) | Keterangan |
| --- | --- | --- | --- |
| Cloud Infrastructure | Compute, Storage, Database | 240.000.000 | 12 bulan × Rp 20.000.000/bulan |
| License | Software maintenance | 30.000.000 | Annual |
| Support | Operational support | 120.000.000 | 2 personil × 12 bulan |
| Total Year 1 |  | 390.000.000 |  |

### 5.9. Cost Management Plan Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         COST MANAGEMENT PLAN APPROVAL                       │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│  Total Budget: Rp 2.180.000.000                                            │

│                                                                             │

│  Saya menyetujui Cost Management Plan ini dan akan menjadi baseline untuk  │

│  manajemen biaya proyek.                                                   │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  Product Owner                                                              │

│                                                                             │

│  ___________________________                                                │

│  Project Sponsor                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 6: MANAJEMEN KUALITAS PROYEK

### 6.1. Tujuan Manajemen Kualitas

Manajemen kualitas proyek bertujuan untuk:

- Memastikan Kualitas Produk – Menjamin bahwa deliverable proyek (perangkat lunak) memenuhi standar kualitas yang telah ditetapkan dan sesuai dengan kebutuhan pengguna.

- Mencegah Cacat – Mengimplementasikan proses pencegahan cacat sejak awal pengembangan.

- Meningkatkan Kepuasan Pengguna – Menghasilkan produk yang andal, mudah digunakan, dan memenuhi harapan stakeholder.

- Memenuhi Standar – Memastikan kepatuhan terhadap standar industri dan regulasi yang berlaku.

- Continuous Improvement – Menerapkan perbaikan berkelanjutan dalam proses pengembangan.

### 6.2. Quality Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         QUALITY MANAGEMENT PROCESS                          │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Plan        │───►│ Manage      │───►│ Control     │───►│ Continuous │ │

│  │ Quality     │    │ Quality     │    │ Quality     │    │ Improvement│ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Quality   │    │ • Quality   │    │ • Testing   │    │ • Sprint    │ │

│  │   Policy    │    │   Assurance │    │   Strategy  │    │   Retro-    │ │

│  │ • Quality   │    │ • Code      │    │ • Defect    │    │   spective  │ │

│  │   Metrics   │    │   Review    │    │   Tracking  │    │ • Lessons   │ │

│  │ • Quality   │    │ • Standards │    │ • UAT       │    │   Learned   │ │

│  │   Standards │    │             │    │             │    │             │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.3. Quality Policy

Quality Policy Statement:

"Membangun sistem ERP pertanian yang handal, user-friendly, dan scalable melalui proses pengembangan yang terstruktur, pengujian yang komprehensif, dan perbaikan berkelanjutan, untuk memberikan nilai maksimal bagi pengguna dan mendukung visi Farm Nation Enterprise."

Quality Principles:

| Prinsip | Deskripsi | Implementasi |
| --- | --- | --- |
| Customer Focus | Memprioritaskan kebutuhan pengguna | UAT, user feedback, requirement review |
| Leadership | Komitmen kualitas dari manajemen | Quality champion, QA leadership |
| Engagement of People | Semua tim bertanggung jawab atas kualitas | Code review, peer testing |
| Process Approach | Kualitas melalui proses yang baik | CI/CD, automated testing, standards |
| Improvement | Perbaikan berkelanjutan | Sprint retrospective, lessons learned |
| Evidence-based | Keputusan berdasarkan data | Metrics, QA reports, defect tracking |
| Relationship Management | Kerjasama dengan stakeholder | Regular communication, feedback loops |

### 6.4. Quality Standards

#### 6.4.1. Standar Kode

| Standar | Deskripsi | Alat |
| --- | --- | --- |
| Code Style | Standar penulisan kode yang konsisten | ESLint (JS), Checkstyle (Java) |
| Code Quality | Kompleksitas, duplikasi, maintainability | SonarQube |
| Security | Keamanan kode dari vulnerability | OWASP ZAP, Snyk |
| Performance | Efisiensi kode | Profiling tools |
| Documentation | Dokumentasi kode yang memadai | JSDoc, Javadoc |

#### 6.4.2. Standar Arsitektur

| Standar | Deskripsi | Referensi |
| --- | --- | --- |
| Microservices | Arsitektur layanan mikro | Domain-Driven Design |
| API Design | Standar desain API | RESTful, OpenAPI 3.0 |
| Event-Driven | Komunikasi asynchronous | Kafka, Event Sourcing |
| Database Design | Standar desain database | Normalisasi, indexing |
| Security | Standar keamanan | OAuth2, JWT, RBAC |

#### 6.4.3. Standar Pengujian

| Standar | Deskripsi | Alat |
| --- | --- | --- |
| Unit Testing | Pengujian unit kode | JUnit, Jest |
| Integration Testing | Pengujian integrasi | Testcontainers |
| E2E Testing | Pengujian end-to-end | Cypress, Patrol |
| Performance Testing | Pengujian kinerja | k6 |
| Security Testing | Pengujian keamanan | OWASP ZAP |

### 6.5. Quality Metrics

#### 6.5.1. Product Quality Metrics

| Metric | Target | Measurement Method | Frequency | PIC |
| --- | --- | --- | --- | --- |
| Code Coverage | ≥ 80% | SonarQube / Coverage Reports | Per Sprint | QA Lead |
| Code Complexity | ≤ 15 | SonarQube | Per Sprint | Tech Lead |
| Bug Density | ≤ 1 per KLOC | QA Report | Per Sprint | QA Lead |
| Defect Leakage | ≤ 5% | QA Report | Per Release | QA Lead |
| Response Time | ≤ 3 detik | Performance Test | Per Milestone | QA Lead |
| Uptime | ≥ 99.5% | Monitoring | Continuous | DevOps |
| UAT Acceptance | ≥ 95% | UAT Sign-off | Per Milestone | PO/BA |
| User Satisfaction | NPS ≥ 70 | Survey | Akhir Proyek | PM/BA |

#### 6.5.2. Process Quality Metrics

| Metric | Target | Measurement Method | Frequency |
| --- | --- | --- | --- |
| Defect Resolution Time | ≤ 2 hari | Jira | Per Sprint |
| Sprint Velocity | ≥ 30 story points | Sprint Review | 2 minggu |
| Test Pass Rate | ≥ 95% | QA Report | Per Sprint |
| Code Review Coverage | 100% | GitHub PR | Continuous |
| CI/CD Success Rate | ≥ 95% | CI/CD Pipeline | Continuous |
| Technical Debt Ratio | ≤ 5% | SonarQube | Per Sprint |

### 6.6. Quality Management Plan

#### 6.6.1. Quality Roles and Responsibilities

| Peran | Tanggung Jawab Kualitas |
| --- | --- |
| Project Manager | • Menyetujui Quality Plan • Memastikan resource untuk QA • Mengelola isu kualitas |
| Technical Lead | • Menetapkan standar kode • Code review oversight • Arsitektur quality |
| QA Lead | • Menyusun testing strategy • Mengelola QA team • Melaporkan quality metrics |
| QA Engineer | • Menjalankan test cases • Melaporkan bugs • Regression testing |
| Developer | • Menulis unit tests • Code review • Bug fixing |
| Product Owner | • Menyetujui acceptance criteria • UAT participation • Prioritasi bug |

#### 6.6.2. Quality Assurance Activities

| Aktivitas | Frekuensi | PIC | Output |
| --- | --- | --- | --- |
| Code Review | Continuous | Tech Lead/Peer | Reviewed PR |
| Sprint Planning | 2 minggu | PO + Dev | Sprint Backlog |
| Sprint Review | 2 minggu | All Team | Demo, feedback |
| Sprint Retrospective | 2 minggu | All Team | Action items |
| QA Testing | Continuous | QA Team | Bug reports |
| Performance Testing | Per Milestone | QA Lead | Performance report |
| Security Audit | Per Milestone | QA Lead | Security report |
| Code Quality Scan | Per Sprint | QA Lead | SonarQube report |

#### 6.6.3. Quality Control Activities

| Aktivitas | Frekuensi | PIC | Output |
| --- | --- | --- | --- |
| Unit Testing | Continuous | Developer | Test reports |
| Integration Testing | Continuous | QA Engineer | Integration test results |
| Regression Testing | Per Sprint | QA Engineer | Regression test results |
| User Acceptance Testing | Per Milestone | BA/PO | UAT sign-off |
| Bug Triage | Harian | PM + Tech Lead | Bug priority |
| Defect Tracking | Continuous | QA Lead | Jira bug dashboard |

### 6.7. Testing Strategy

#### 6.7.1. Testing Pyramid

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                            TESTING PYRAMID                                  │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│                              ┌─────────────┐                                │

│                              │    End-to-  │                                │

│                              │    End      │                                │

│                              │   Testing   │                                │

│                              └─────────────┘                                │

│                              ┌─────────────┐                                │

│                              │ Integration │                                │

│                              │   Testing   │                                │

│                              └─────────────┘                                │

│                              ┌─────────────┐                                │

│                              │    Unit     │                                │

│                              │   Testing   │                                │

│                              └─────────────┘                                │

│                                                                             │

│  • Unit Testing: Jumlah terbanyak, cepat, isolasi                         │

│  • Integration Testing: Sedang, antar komponen                             │

│  • E2E Testing: Jumlah sedikit, lambat, end-to-end flow                   │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 6.7.2. Testing Types and Tools

| Testing Type | Tujuan | Tools | Who |
| --- | --- | --- | --- |
| Unit Testing | Menguji unit kode terkecil | JUnit (Java), Jest (JS) | Developer |
| Integration Testing | Menguji interaksi antar komponen | Testcontainers, Spring Test | Developer/QA |
| API Testing | Menguji endpoint API | Postman, REST Assured | QA |
| E2E Testing | Menguji flow end-to-end | Cypress (Web), Patrol (Mobile) | QA |
| Performance Testing | Menguji kinerja sistem | k6, JMeter | QA |
| Load Testing | Menguji beban tinggi | k6 | QA |
| Stress Testing | Menguji batas sistem | k6 | QA |
| Security Testing | Menguji keamanan | OWASP ZAP, SonarQube | QA |
| Usability Testing | Menguji kemudahan penggunaan | Manual, User Feedback | BA/PO |
| UAT | Pengujian oleh pengguna | Manual | User/PO/BA |

#### 6.7.3. Test Environment

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                           TEST ENVIRONMENTS                                 │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Development │───►│  Testing    │───►│   Staging   │───►│ Production  │ │

│  │ (Dev)       │    │  (QA)       │    │   (UAT)     │    │  (Prod)     │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Developer   │    │ QA Testing  │    │ UAT, Demo   │    │ Live System │ │

│  │ Testing     │    │ Integration │    │ Pre-        │    │             │ │

│  │             │    │ Performance │    │ Production  │    │             │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.8. Defect Management

#### 6.8.1. Defect Lifecycle

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                            DEFECT LIFECYCLE                                 │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │  NEW        │───►│  OPEN       │───►│ IN PROGRESS │───►│  FIXED      │ │

│  │  (QA finds  │    │  (Accepted  │    │  (Developer │    │  (Developer │ │

│  │   bug)      │    │   by PM)    │    │   working)  │    │   fixed)    │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐                     │

│  │  REOPEN     │◄───│  REJECT     │◄───│  VERIFY     │                     │

│  │  (QA found  │    │  (Not a bug/│    │  (QA tests  │                     │

│  │   still bug)│    │   duplicate)│    │   fix)      │                     │

│  └─────────────┘    └─────────────┘    └─────────────┘                     │

│                                                                             │

│  ┌─────────────┐                                                           │

│  │  CLOSED     │                                                           │

│  │  (Bug fixed │                                                           │

│  │   verified) │                                                           │

│  └─────────────┘                                                           │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 6.8.2. Defect Severity Levels

| Severity | Deskripsi | Contoh | Response Time |
| --- | --- | --- | --- |
| Critical (S1) | Sistem crash, data corruption, security breach | Aplikasi tidak bisa diakses | ≤ 4 jam |
| High (S2) | Major feature tidak berfungsi, blocking | Farm tidak bisa registrasi | ≤ 8 jam |
| Medium (S3) | Minor feature tidak berfungsi, workaround ada | Validasi kurang ketat | ≤ 24 jam |
| Low (S4) | Cosmetic, UI minor, enhancement | Tampilan kurang rapi | ≤ 48 jam |

#### 6.8.3. Defect Priority

| Priority | Deskripsi | Action |
| --- | --- | --- |
| P0 | Must Fix - block release | Fix immediately |
| P1 | Should Fix - high importance | Fix this sprint |
| P2 | Could Fix - medium importance | Fix next sprint |
| P3 | Won't Fix - low importance | Defer/postpone |

#### 6.8.4. Defect Tracking

| Field | Deskripsi | Format |
| --- | --- | --- |
| ID | Bug ID | BUG-XXX |
| Title | Judul singkat | String |
| Description | Deskripsi lengkap | Text |
| Steps to Reproduce | Langkah-langkah reproduksi | Text |
| Expected Result | Hasil yang diharapkan | Text |
| Actual Result | Hasil aktual | Text |
| Severity | Critical/High/Medium/Low | Enum |
| Priority | P0/P1/P2/P3 | Enum |
| Status | New/Open/In Progress/Fixed/Closed | Enum |
| Assignee | Developer yang bertanggung jawab | User |
| Reporter | QA yang menemukan | User |
| Module | Modul terkait | String |
| Environment | Dev/QA/Staging/Production | Enum |
| Attachments | Screenshot, log, video | File |
| Created Date | Tanggal dibuat | Timestamp |
| Updated Date | Tanggal update | Timestamp |
| Resolved Date | Tanggal fix | Timestamp |

### 6.9. Performance Testing

#### 6.9.1. Performance Test Scenarios

| Scenario | Description | Target |
| --- | --- | --- |
| Normal Load | Beban normal harian | 100 concurrent users |
| Peak Load | Beban musim panen | 300 concurrent users (3x normal) |
| Stress | Beban di atas kapasitas | 500 concurrent users |
| Endurance | Beban berkelanjutan | 100 users for 4 hours |
| Scalability | Skalabilitas vertikal & horizontal | Response time < 3 detik |

#### 6.9.2. Performance Metrics

| Metric | Target | Description |
| --- | --- | --- |
| Response Time | ≤ 3 detik (90% requests) | Waktu respon API |
| Throughput | ≥ 100 req/detik | Request per second |
| Error Rate | ≤ 0.5% | Error rate di bawah 0.5% |
| CPU Usage | ≤ 70% | CPU utilization |
| Memory Usage | ≤ 80% | Memory utilization |
| DB Query Time | ≤ 100ms | Database query time |

#### 6.9.3. Performance Test Results Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                     PERFORMANCE TEST RESULTS                                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Test Date: __________________                                              │

│  Tester: __________________                                                 │

│  Environment: QA / Staging                                                  │

│                                                                             │

│  Test Scenario: Normal Load / Peak Load / Stress                           │

│  Concurrent Users: ________                                                │

│  Duration: ________                                                         │

│                                                                             │

│  ┌──────────────────────────────────────────────────────────────────────┐  │

│  │                        RESULTS SUMMARY                               │  │

│  ├──────────────────────────────────────────────────────────────────────┤  │

│  │ Response Time (avg): _________ ms                                   │  │

│  │ Response Time (p95): _________ ms                                   │  │

│  │ Response Time (p99): _________ ms                                   │  │

│  │ Throughput: _________ req/sec                                       │  │

│  │ Error Rate: _________ %                                             │  │

│  │ CPU Usage (avg): _________ %                                        │  │

│  │ Memory Usage (avg): _________ %                                      │  │

│  └──────────────────────────────────────────────────────────────────────┘  │

│                                                                             │

│  Status: PASS / FAIL                                                       │

│                                                                             │

│  Notes: __________________                                                 │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.10. User Acceptance Testing (UAT)

#### 6.10.1. UAT Preparation

| Activity | Description | PIC | Timeline |
| --- | --- | --- | --- |
| UAT Planning | Menyusun rencana UAT | BA + PO | 2 minggu sebelum UAT |
| Test Data | Menyiapkan data test | BA + QA | 1 minggu sebelum UAT |
| Test Scripts | Menyusun skenario UAT | BA | 3 hari sebelum UAT |
| UAT Environment | Setup environment UAT | DevOps | 3 hari sebelum UAT |
| User Training | Training pengguna | BA | 2 hari sebelum UAT |

#### 6.10.2. UAT Execution

| Activity | Description | PIC | Timeline |
| --- | --- | --- | --- |
| UAT Kick-off | Briefing UAT | PM + BA | Hari 1 |
| Test Execution | Pengujian oleh user | User | Hari 1-5 |
| Bug Logging | Pencatatan bug | User + QA | Continuous |
| Daily Sync | Sinkronisasi harian | BA | Harian |
| UAT Sign-off | Persetujuan UAT | PO + User | Akhir UAT |

#### 6.10.3. UAT Acceptance Criteria

| Criterion | Target | Description |
| --- | --- | --- |
| Test Case Pass Rate | ≥ 95% | Skenario UAT berhasil |
| Critical Bugs | 0 (Zero Critical) | Tidak ada bug S1 |
| High Bugs | ≤ 5 | Bug S2 maksimal 5 |
| User Satisfaction | ≥ 70% | Feedback user positif |
| Business Flow | 100% | Flow bisnis berjalan |

#### 6.10.4. UAT Sign-off Form

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                           UAT SIGN-OFF FORM                                 │

│                    P-FNE-02: Core Agricultural Operations                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Project: P-FNE-02                                                         │

│  UAT Period: ___________________                                            │

│  UAT Date: ___________________                                              │

│                                                                             │

│  PARTICIPANTS:                                                              │

│  ─────────────                                                              │

│  Name: ___________________      Role: Farm Manager                         │

│  Name: ___________________      Role: Agronomist                           │

│  Name: ___________________      Role: Operational Team                     │

│  Name: ___________________      Role: Farm Workers                         │

│                                                                             │

│  TEST SUMMARY:                                                              │

│  ─────────────                                                              │

│  Total Test Cases: ________                                                │

│  Passed: ________                                                           │

│  Failed: ________                                                           │

│  Acceptance Rate: ________%                                                │

│                                                                             │

│  BUG SUMMARY:                                                               │

│  ────────────                                                              │

│  Critical (S1): ________                                                   │

│  High (S2): ________                                                       │

│  Medium (S3): ________                                                     │

│  Low (S4): ________                                                        │

│                                                                             │

│  UAT RESULT:                                                                │

│  ────────────                                                              │

│  [ ] Accepted                                                              │

│  [ ] Accepted with Conditions                                              │

│  [ ] Rejected                                                              │

│                                                                             │

│  CONDITIONS / NOTES:                                                        │

│  ────────────────────                                                      │

│  ______________________________________________________________________    │

│  ______________________________________________________________________    │

│                                                                             │

│  SIGN-OFF:                                                                  │

│  ─────────                                                                  │

│  _________________________                                                  │

│  Product Owner                                                              │

│                                                                             │

│  _________________________                                                  │

│  Farm Manager / User Representative                                        │

│                                                                             │

│  _________________________                                                  │

│  Project Manager                                                            │

│                                                                             │

│  Date: __________________                                                   │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.11. Continuous Improvement

#### 6.11.1. Sprint Retrospective Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        SPRINT RETROSPECTIVE PROCESS                         │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ What went   │───►│ What went   │───►│ What can we │───►│ Action      │ │

│  │ well?       │    │ wrong?      │    │ improve?    │    │ Items       │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  • 5-10 items each category                                                │

│  • Action items with owner and deadline                                    │

│  • Review previous action items                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 6.11.2. Lessons Learned

| Category | What Worked | What Didn't Work | Recommendations |
| --- | --- | --- | --- |
| Process |  |  |  |
| Technical |  |  |  |
| Team |  |  |  |
| Communication |  |  |  |
| Tools |  |  |  |

#### 6.11.3. Quality Improvement Plan

| Area | Issue | Improvement | Owner | Timeline |
| --- | --- | --- | --- | --- |

### 6.12. Quality Audits

#### 6.12.1. Audit Schedule

| Audit Type | Frequency | Auditor | Scope |
| --- | --- | --- | --- |
| Code Quality Audit | Per Sprint | Tech Lead + QA Lead | Code standards, coverage, complexity |
| Process Audit | Per Milestone | PMO | Compliance with PMP, governance |
| Security Audit | Per Milestone | Security Team | Vulnerability, compliance |
| Performance Audit | Per Milestone | QA Lead + DevOps | Response time, throughput |
| Documentation Audit | Per Milestone | PM | Completeness, accuracy |

#### 6.12.2. Audit Findings Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                           AUDIT FINDINGS REPORT                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Audit Date: __________________                                             │

│  Auditor: __________________                                                │

│  Audit Type: __________________                                             │

│                                                                             │

│  ┌──────────────────────────────────────────────────────────────────────┐  │

│  │ FINDINGS                                                             │  │

│  ├──────────────────────────────────────────────────────────────────────┤  │

│  │ ID: AUD-001                                                         │  │

│  │ Description: __________________                                     │  │

│  │ Severity: High / Medium / Low                                       │  │

│  │ Category: Process / Technical / Documentation                       │  │

│  │ Recommendation: __________________                                  │  │

│  │ Owner: __________________                                           │  │

│  │ Status: Open / In Progress / Closed                                 │  │

│  │ Target Date: __________________                                     │  │

│  └──────────────────────────────────────────────────────────────────────┘  │

│                                                                             │

│  OVERALL STATUS: PASS / PASS WITH FINDINGS / FAIL                         │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.13. Quality Management Plan Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                       QUALITY MANAGEMENT PLAN APPROVAL                      │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│                                                                             │

│  Saya menyetujui Quality Management Plan ini dan akan menjadi baseline    │

│  untuk manajemen kualitas proyek.                                          │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  QA Lead                                                                   │

│                                                                             │

│  ___________________________                                                │

│  Technical Lead                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 7: MANAJEMEN SUMBER DAYA PROYEK

### 7.1. Tujuan Manajemen Sumber Daya

Manajemen sumber daya proyek bertujuan untuk:

- Mengoptimalkan Sumber Daya Manusia – Memastikan tim proyek memiliki kompetensi yang tepat dan bekerja secara efektif.

- Mengelola Ketersediaan – Menjamin ketersediaan sumber daya sesuai dengan kebutuhan jadwal proyek.

- Mengembangkan Tim – Meningkatkan kapabilitas dan kolaborasi tim melalui pelatihan dan pengembangan.

- Memastikan Kesejahteraan – Menjaga motivasi dan kesejahteraan tim selama durasi proyek.

- Mengelola Konflik – Mengidentifikasi dan menyelesaikan konflik yang mungkin timbul dalam tim.

### 7.2. Resource Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         RESOURCE MANAGEMENT PROCESS                         │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Plan        │───►│ Acquire     │───►│ Develop     │───►│ Manage      │ │

│  │ Resources   │    │ Team        │    │ Team        │    │ Team        │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • RACI      │    │ • Hiring    │    │ • Training  │    │ • Daily     │ │

│  │ • Roles     │    │ • Assignment│    │ • Mentoring │    │   Stand-up  │ │

│  │ • Resource  │    │ • Onboarding│    │ • Team      │    │ • 1-on-1    │ │

│  │   Plan      │    │             │    │   Building  │    │ • Conflict  │ │

│  │             │    │             │    │             │    │   Resolution│ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  ┌─────────────┐                                                           │

│  │ Control     │                                                           │

│  │ Resources   │                                                           │

│  └─────────────┘                                                           │

│        │                                                                   │

│        ▼                                                                   │

│  ┌─────────────┐                                                           │

│  │ • Resource  │                                                           │

│  │   Utilization│                                                          │

│  │ • Performance│                                                          │

│  │   Review    │                                                           │

│  │ • Retention │                                                           │

│  └─────────────┘                                                           │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 7.3. Resource Requirements

#### 7.3.1. Team Structure

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                            TEAM STRUCTURE                                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │                      PROJECT MANAGER (1)                            │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                      │                                      │

│         ┌────────────────────────────┼────────────────────────────┐        │

│         │                            │                            │        │

│         ▼                            ▼                            ▼        │

│  ┌─────────────┐             ┌─────────────┐             ┌─────────────┐  │

│  │   PRODUCT   │             │   TECHNICAL │             │    QA       │  │

│  │   OWNER     │             │   LEAD      │             │    LEAD     │  │

│  │   (1)       │             │   (1)       │             │    (1)      │  │

│  └─────────────┘             └─────────────┘             └─────────────┘  │

│         │                            │                            │        │

│         ▼                            ▼                            ▼        │

│  ┌─────────────┐             ┌─────────────┐             ┌─────────────┐  │

│  │  BUSINESS   │             │  BACKEND    │             │  QA         │  │

│  │  ANALYST    │             │  (4)        │             │  ENGINEERS  │  │

│  │  (1)        │             │             │             │  (2)        │  │

│  └─────────────┘             └─────────────┘             └─────────────┘  │

│                              ┌─────────────┐                             │

│                              │  FRONTEND   │                             │

│                              │  (2)        │                             │

│                              └─────────────┘                             │

│                              ┌─────────────┐                             │

│                              │  MOBILE     │                             │

│                              │  (1)        │                             │

│                              └─────────────┘                             │

│                              ┌─────────────┐                             │

│                              │  DEVOPS     │                             │

│                              │  (1)        │                             │

│                              └─────────────┘                             │

│                                                                             │

│  Total: 14 Personil                                                       │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 7.3.2. Role Descriptions and Competencies

| Peran | Kualifikasi | Sertifikasi yang Diperlukan | Pengalaman Minimal |
| --- | --- | --- | --- |
| Project Manager | PMP Certified, Agile, SDLC | PMP / PRINCE2 | 5 tahun |
| Product Owner | Agile, Domain Agricole | CSPO / PSPO | 5 tahun |
| Technical Lead | Java/Spring, Microservices, Cloud | AWS Certified / Java Architect | 7 tahun |
| Backend Developer | Java/Spring, PostgreSQL, REST | Java Certification | 3 tahun |
| Frontend Developer | React/Next.js, TypeScript | - | 3 tahun |
| Mobile Developer | Flutter, Dart, SQLite | - | 3 tahun |
| Business Analyst | Domain Agricole, BRD | CBAP / IIBA | 5 tahun |
| QA Engineer | Manual & Automation Testing | ISTQB | 3 tahun |
| DevOps Engineer | Kubernetes, Docker, CI/CD | CKA / CKAD | 4 tahun |

#### 7.3.3. Resource Breakdown Structure (RBS)

| Kategori | Peran | Jumlah | Total FTE |
| --- | --- | --- | --- |
| Management | Project Manager | 1 | 1.0 |
|  | Product Owner | 1 | 0.8 |
|  | Technical Lead | 1 | 0.9 |
| Development | Backend Developer | 4 | 3.6 |
|  | Frontend Developer | 2 | 1.8 |
|  | Mobile Developer | 1 | 0.8 |
| Analysis | Business Analyst | 1 | 0.8 |
| Quality | QA Engineer | 2 | 1.6 |
| Operations | DevOps Engineer | 1 | 0.8 |
| Total |  | 14 | 12.1 |

#### 7.3.4. Resource Calendar

| Peran | Bulan 1 | Bulan 2 | Bulan 3 | Bulan 4 | Bulan 5 | Bulan 6 |
| --- | --- | --- | --- | --- | --- | --- |
| PM | 100% | 100% | 100% | 100% | 100% | 100% |
| PO | 80% | 80% | 80% | 60% | 40% | 40% |
| Tech Lead | 50% | 100% | 100% | 80% | 80% | 60% |
| BA | 100% | 80% | 60% | 60% | 40% | 20% |
| Backend (4) | 2 org | 3 org | 3 org | 3 org | 2 org | 2 org |
| Frontend (2) | 1 org | 2 org | 2 org | 2 org | 1 org | 1 org |
| Mobile (1) | 0 org | 0 org | 0.5 org | 1 org | 1 org | 0.5 org |
| QA (2) | 1 org | 1 org | 1 org | 1 org | 2 org | 2 org |
| DevOps | 100% | 50% | 50% | 50% | 100% | 100% |

### 7.4. Team Acquisition

#### 7.4.1. Sourcing Strategy

| Peran | Sumber | Metode | Timeline |
| --- | --- | --- | --- |
| Core Team | Internal FNE | Transfer/Promotion | Sebelum kick-off |
| Specialist | External Hiring | Recruitment | 2 minggu |
| Contractor | Outsourcing | IT Vendor | 2 minggu |
| Consultant | External | Direct Contract | Sesuai kebutuhan |

#### 7.4.2. Hiring Plan

| Peran | Jumlah | Sumber | Tanggal Target | Status |
| --- | --- | --- | --- | --- |
| Backend Developer | 2 | Internal | Sebelum kick-off | Confirmed |
| Backend Developer | 2 | External | Minggu 2 | In Progress |
| Frontend Developer | 1 | Internal | Sebelum kick-off | Confirmed |
| Frontend Developer | 1 | External | Minggu 2 | In Progress |
| Mobile Developer | 1 | External | Minggu 4 | In Progress |
| QA Engineer | 1 | Internal | Sebelum kick-off | Confirmed |
| QA Engineer | 1 | External | Minggu 2 | In Progress |
| DevOps Engineer | 1 | Internal | Sebelum kick-off | Confirmed |

#### 7.4.3. Onboarding Plan

| Activity | Duration | PIC | Output |
| --- | --- | --- | --- |
| Pre-Onboarding | 1 minggu | HR + PM | Welcome package, equipment |
| Day 1 | 1 hari | HR + PM | Orientation, account setup |
| Week 1 | 1 minggu | Tech Lead | Environment setup, codebase walkthrough |
| Week 2 | 1 minggu | BA + Tech Lead | Domain training, user stories |
| Week 3 | 1 minggu | Tech Lead | First sprint assignment |
| Month 1 | 1 bulan | All | Full integration into team |

### 7.5. Team Development

#### 7.5.1. Training Plan

| Training | Target | Duration | Method | Timeline |
| --- | --- | --- | --- | --- |
| Domain Agricole | All Team | 2 hari | Workshop | Minggu 2 |
| Spring Boot Advanced | Backend | 2 hari | Training | Minggu 4 |
| React/Next.js | Frontend | 2 hari | Training | Minggu 4 |
| Flutter | Mobile | 3 hari | Training | Minggu 6 |
| PostgreSQL Tuning | Backend + DevOps | 1 hari | Training | Minggu 8 |
| Kafka Streams | Backend | 1 hari | Training | Minggu 10 |
| Agile/Scrum | All Team | 1 hari | Workshop | Minggu 2 |
| Soft Skills | All Team | 2 hari | Workshop | Bulan 3 |

#### 7.5.2. Team Building Activities

| Activity | Frequency | Purpose |
| --- | --- | --- |
| Weekly Team Lunch | Mingguan | Bonding, informal communication |
| Team Building Offsite | Bulanan | Kolaborasi, trust building |
| Tech Talk / Knowledge Sharing | 2 minggu | Skill development |
| Sprint Retrospective | 2 minggu | Process improvement |
| Team Awards | Per Sprint | Recognition and motivation |

#### 7.5.3. Professional Development

| Program | Description | Timeline |
| --- | --- | --- |
| Certification Support | AWS, Java, PMP, ISTQB | Throughout |
| Conference Access | Tech conferences | Per quarter |
| Mentoring Program | Senior mentoring junior | Throughout |
| Personal Development Plan | Career growth plan | Monthly review |

### 7.6. Team Management

#### 7.6.1. Performance Management

| Activity | Frequency | PIC | Output |
| --- | --- | --- | --- |
| Sprint Performance Review | 2 minggu | PM + Tech Lead | Performance feedback |
| 1-on-1 Meeting | 2 minggu | PM / Tech Lead | Individual feedback |
| 360-Degree Review | 3 bulan | PM | Comprehensive feedback |
| Goal Setting | Kuartal | PM + Individual | Performance goals |
| Bonus/Recognition | Per Sprint | PM | Reward & recognition |

#### 7.6.2. Conflict Resolution Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         CONFLICT RESOLUTION PROCESS                         │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Identify    │───►│ Analyze     │───►│ Address     │───►│ Resolve     │ │

│  │ Conflict    │    │ Root Cause  │    │ Conflict    │    │ & Follow-up │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  Conflict Resolution Techniques:                                           │

│  • Collaborate (Win-Win) – Preferred                                      │

│  • Compromise (Win-Lose/Win-Lose)                                          │

│  • Accommodate (Lose-Win)                                                  │

│  • Avoid (Lose-Lose) – Last resort                                         │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 7.6.3. Team Communication Guidelines

| Guideline | Description |
| --- | --- |
| Open Communication | Semua anggota bebas menyampaikan pendapat |
| Respectful | Menghargai pendapat orang lain |
| Constructive Feedback | Feedback yang membangun |
| No Blame Culture | Fokus pada solusi, bukan mencari kesalahan |
| Transparency | Informasi dibagikan secara terbuka |
| Active Listening | Mendengarkan dengan seksama |

#### 7.6.4. Motivation and Retention

| Strategy | Implementation |
| --- | --- |
| Competitive Compensation | Gaji sesuai standar industri |
| Career Growth | Career path dan promosi |
| Work-Life Balance | Flexible working hours, remote work |
| Recognition | Team awards, public recognition |
| Interesting Work | Technology stack modern, domain menarik |
| Learning Culture | Training, certification, conferences |

### 7.7. Resource Allocation Matrix

#### 7.7.1. Phase-wise Resource Allocation

| Fase | PM | PO | Tech Lead | BE | FE | Mobile | QA | BA | DevOps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Persiapan | 100% | 80% | 50% | 2 org | 1 org | 0 | 1 org | 100% | 100% |
| 2. Setup | 100% | 60% | 100% | 2 org | 1 org | 0 | 1 org | 60% | 100% |
| 3.1 Farm & Land | 100% | 80% | 80% | 3 org | 2 org | 0 | 1 org | 80% | 50% |
| 3.2 Crop | 100% | 80% | 80% | 3 org | 2 org | 0 | 1 org | 60% | 50% |
| 3.3 Harvest | 100% | 60% | 60% | 2 org | 2 org | 0 | 1 org | 40% | 50% |
| 3.4 Livestock | 100% | 60% | 60% | 3 org | 2 org | 0 | 1 org | 40% | 50% |
| 3.5 Activity | 100% | 40% | 60% | 2 org | 1 org | 0 | 2 org | 20% | 50% |
| 3.6 Resource | 100% | 40% | 60% | 2 org | 1 org | 0 | 2 org | 20% | 50% |
| 4. Mobile | 100% | 40% | 60% | 2 org | 1 org | 100% | 2 org | 20% | 50% |
| 5. Integration | 100% | 40% | 100% | 3 org | 2 org | 0 | 2 org | 20% | 100% |
| 6. Testing | 100% | 60% | 60% | 2 org | 2 org | 0 | 2 org | 20% | 50% |
| 7. Deployment | 100% | 40% | 100% | 2 org | 1 org | 0 | 2 org | 20% | 100% |
| 8. Closure | 100% | 20% | 40% | 1 org | 1 org | 0 | 1 org | 20% | 50% |

#### 7.7.2. Resource Utilization Chart

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         RESOURCE UTILIZATION CHART                          │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Peran       | M1 | M2 | M3 | M4 | M5 | M6 | Average                      │

│  ────────────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────│

│  PM          | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│  PO          | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│  Tech Lead   | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│  BA          | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│  Backend(4)  | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│  Frontend(2) | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│  Mobile(1)   | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│  QA(2)       | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│  DevOps      | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ | ██ │

│                                                                             │

│  ██ = 100%   ██ = 75%   ██ = 50%   ██ = 25%                               │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 7.8. Resource Management Plan Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                       RESOURCE MANAGEMENT PLAN APPROVAL                     │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│  Total Personil: 14                                                         │

│  Total FTE: 12.1                                                           │

│                                                                             │

│  Saya menyetujui Resource Management Plan ini dan akan menjadi baseline   │

│  untuk manajemen sumber daya proyek.                                       │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  HR Manager                                                                 │

│                                                                             │

│  ___________________________                                                │

│  Project Sponsor                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 8: MANAJEMEN KOMUNIKASI PROYEK

### 8.1. Tujuan Manajemen Komunikasi

Manajemen komunikasi proyek bertujuan untuk:

- Memastikan Aliran Informasi – Menjamin informasi proyek tersampaikan dengan tepat waktu, akurat, dan efektif kepada seluruh stakeholder.

- Membangun Pemahaman Bersama – Menciptakan pemahaman yang sama tentang tujuan, status, dan isu proyek di antara seluruh stakeholder.

- Mengelola Ekspektasi – Mengelola harapan stakeholder melalui komunikasi yang transparan dan teratur.

- Memfasilitasi Pengambilan Keputusan – Menyediakan informasi yang dibutuhkan untuk pengambilan keputusan yang tepat.

- Membangun Hubungan – Membangun dan memelihara hubungan yang baik dengan seluruh stakeholder.

### 8.2. Communication Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        COMMUNICATION MANAGEMENT PROCESS                     │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Identify    │───►│ Plan        │───►│ Manage      │───►│ Monitor     │ │

│  │ Stakeholders│    │ Communication│    │ Communication│   │ Communication│ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Stake-    │    │ • Comm      │    │ • Meeting   │    │ • Feedback  │ │

│  │   holder    │    │   Matrix    │    │ • Reports   │    │ • Survey    │ │

│  │   Register  │    │ • Channel   │    │ • Document  │    │ • Comm      │ │

│  │ • Analysis  │    │   Selection │    │   Distribution│   │   Review    │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 8.3. Communication Matrix

#### 8.3.1. Stakeholder Communication Matrix

| Stakeholder | Informasi | Metode | Frekuensi | Penyedia | Format |
| --- | --- | --- | --- | --- | --- |
| Project Sponsor | Status proyek, budget, milestone | Presentasi | Bulanan | PM | PPT/PDF |
| Steering Committee | Progress, keputusan, isu strategis | Meeting | 2 minggu | PM | PPT/PDF |
| PMO | Status, compliance, dokumentasi | Dashboard | Mingguan | PM | Online |
| Product Owner | Sprint progress, backlog | Sprint Review | 2 minggu | PO+PM | Jira |
| Development Team | Task daily, blocker | Stand-up | Harian | Tech Lead | Slack/Verbal |
| QA Team | Test progress, bug reports | Report | Harian | QA Lead | Jira/Email |
| Farm Manager | UAT, feedback, workshop | Workshop | Per Milestone | BA+PO | In-person |
| Operational Team | Requirement, feedback | Interview | Ad-hoc | BA | In-person |
| Agronomist | Domain input, UAT | Workshop | Per Milestone | BA | In-person |
| Veteriner | Domain input, UAT | Workshop | Per Milestone | BA | In-person |
| P-FNE-01 Team | Integration status, API | Technical Meeting | 2 minggu | Tech Lead | Online |
| P-FNE-03 Team | Inventory integration | Technical Meeting | 2 minggu | Tech Lead | Online |
| P-FNE-06 Team | Finance integration | Technical Meeting | 2 minggu | Tech Lead | Online |
| P-FNE-07 Team | Data pipeline | Technical Meeting | 2 minggu | Tech Lead | Online |

#### 8.3.2. Communication Channels

| Channel | Tujuan | Frekuensi | Owner |
| --- | --- | --- | --- |
| Slack / Teams | Komunikasi harian, notifikasi, quick discussion | Continuous | All Team |
| Email | Formal communication, official approvals | As needed | PM |
| Jira | Task management, issue tracking, sprint | Continuous | All Team |
| Confluence | Documentation, knowledge base | Continuous | All Team |
| Google Meet / Zoom | Meeting jarak jauh, sprint ceremonies | Scheduled | PM |
| Dashboard | Status proyek real-time | Continuous | PM/DevOps |
| Physical Board | Sprint task board (optional) | Daily | Tech Lead |

### 8.4. Reporting

#### 8.4.1. Daily Report

| Aspek | Keterangan |
| --- | --- |
| Nama | Daily Stand-up Report |
| Penerima | Project Manager, Tech Lead |
| Metode | Slack / Teams |
| Waktu | Setelah daily stand-up (10:15) |
| Format | Text brief |

Template Daily Report:

text

[DAILY STAND-UP] - [Tanggal] - Sprint [X]

[Name 1]:

- Yesterday: [Completed tasks]

- Today: [Planned tasks]

- Blocker: [None / Issue]

[Name 2]:

- Yesterday: ...

- Today: ...

- Blocker: ...

[Name 3]:

- ...

#### 8.4.2. Weekly Status Report

| Aspek | Keterangan |
| --- | --- |
| Nama | Weekly Status Report |
| Penerima | PMO, Sponsor, Project Manager |
| Metode | Dashboard / Email |
| Waktu | Setiap Jumat |
| Format | Dashboard + PDF |

Template Weekly Status Report:

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         WEEKLY STATUS REPORT                               │

│                   P-FNE-02: Core Agricultural Operations                   │

│                   Week: [XX] / [Tanggal]                                    │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│ 1. EXECUTIVE SUMMARY                                                       │

│    ─────────────────                                                       │

│    • Overall Status: [🟢 Green / 🟡 Yellow / 🔴 Red]                      │

│    • Progress: [XX]% complete                                             │

│    • Key Achievements:                                                    │

│      - [Achievement 1]                                                    │

│      - [Achievement 2]                                                    │

│      - [Achievement 3]                                                    │

│                                                                             │

│ 2. PROGRESS UPDATE                                                         │

│    ────────────────                                                        │

│    ┌──────────────────────────────────────────────────────────────────┐   │

│    │ Milestone     │ Planned │ Actual │ Status │ Completion          │   │

│    ├──────────────────────────────────────────────────────────────────┤   │

│    │ M1: Kick-off  │ 02/09   │ 02/09  │ ✅     │ 100%               │   │

│    │ M2: Foundation │ 30/09   │ -      │ 🔄     │ 80%                │   │

│    │ M3: Farm & Land│ 21/10   │ -      │ 🔄     │ 60%                │   │

│    └──────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│ 3. SPRINT PROGRESS                                                         │

│    ────────────────                                                        │

│    • Sprint: [X]                                                          │

│    • Total Story Points: [XX]                                             │

│    • Completed: [XX]                                                      │

│    • Remaining: [XX]                                                      │

│    • Sprint Burn-down: [Chart]                                            │

│                                                                             │

│ 4. RISKS & ISSUES                                                          │

│    ────────────────                                                        │

│    ┌──────────────────────────────────────────────────────────────────┐   │

│    │ Risk ID │ Description │ Impact │ Status │ Mitigation            │   │

│    ├──────────────────────────────────────────────────────────────────┤   │

│    │ R-001   │ ...        │ High   │ Open   │ ...                   │   │

│    │ R-002   │ ...        │ Medium │ Closed │ ...                   │   │

│    └──────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│ 5. NEXT WEEK PLAN                                                          │

│    ────────────────                                                        │

│    • Sprint Goal: [Goal]                                                  │

│    • Key Activities:                                                       │

│      - [Activity 1]                                                       │

│      - [Activity 2]                                                       │

│      - [Activity 3]                                                       │

│                                                                             │

│ 6. BUDGET STATUS                                                           │

│    ──────────────                                                          │

│    • Total Budget: Rp 2.180.000.000                                       │

│    • Used: Rp [XX] ([XX]%)                                                │

│    • Remaining: Rp [XX]                                                   │

│    • Variance: [XX]%                                                      │

│                                                                             │

│ 7. DECISIONS NEEDED                                                        │

│    ────────────────                                                        │

│    • [Decision 1] - Required by: [Date]                                   │

│    • [Decision 2] - Required by: [Date]                                   │

│                                                                             │

│ 8. ATTACHMENTS                                                             │

│    ────────────                                                            │

│    • Sprint Report                                                        │

│    • QA Test Report                                                       │

│    • Risk Register Update                                                 │

│                                                                             │

│  Prepared by: [Name]                                                       │

│  Date: [Date]                                                              │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 8.4.3. Monthly Progress Report

| Aspek | Keterangan |
| --- | --- |
| Nama | Monthly Progress Report |
| Penerima | Project Sponsor, Steering Committee |
| Metode | Presentation |
| Waktu | Akhir bulan |
| Format | PPT / PDF |

Template Monthly Progress Report:

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        MONTHLY PROGRESS REPORT                              │

│                   P-FNE-02: Core Agricultural Operations                   │

│                   Month: [MMM YYYY]                                         │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│ 1. EXECUTIVE SUMMARY                                                       │

│    ─────────────────                                                       │

│    • Overall Status: [🟢 Green / 🟡 Yellow / 🔴 Red]                      │

│    • Month: [X] of 6                                                       │

│    • Overall Progress: [XX]% complete                                     │

│    • Key Milestones Achieved:                                             │

│      - [Milestone 1] - Date                                               │

│      - [Milestone 2] - Date                                               │

│                                                                             │

│ 2. PROGRESS TREND                                                          │

│    ──────────────                                                          │

│    [Chart: Planned vs Actual Progress over time]                          │

│                                                                             │

│ 3. SPRINT SUMMARY                                                          │

│    ──────────────                                                          │

│    ┌──────────────────────────────────────────────────────────────────┐   │

│    │ Sprint │ Duration │ Story Points │ Completed │ Velocity        │   │

│    ├──────────────────────────────────────────────────────────────────┤   │

│    │ 1     │ 2 weeks  │ 25           │ 22        │ 22              │   │

│    │ 2     │ 2 weeks  │ 30           │ 28        │ 28              │   │

│    │ 3     │ 2 weeks  │ 28           │ 30        │ 30              │   │

│    └──────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│ 4. QUALITY METRICS                                                         │

│    ────────────────                                                        │

│    ┌──────────────────────────────────────────────────────────────────┐   │

│    │ Metric           │ Target │ Actual │ Status                    │   │

│    ├──────────────────────────────────────────────────────────────────┤   │

│    │ Code Coverage    │ ≥80%   │ 82%    │ ✅                        │   │

│    │ Defect Density   │ ≤1/KLOC│ 0.8    │ ✅                        │   │

│    │ Response Time    │ ≤3 detik│ 2.1 detik│ ✅                     │   │

│    │ UAT Acceptance   │ ≥95%   │ -      │ 🔄                        │   │

│    └──────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│ 5. BUDGET SUMMARY                                                          │

│    ────────────────                                                        │

│    • Total Budget: Rp 2.180.000.000                                       │

│    • Planned Spend: Rp [XX]                                                │

│    • Actual Spend: Rp [XX]                                                │

│    • Variance: Rp [XX] ([XX]%)                                            │

│    • Forecast EAC: Rp [XX]                                                │

│                                                                             │

│ 6. RISK UPDATE                                                            │

│    ────────────                                                            │

│    • New Risks: [X]                                                       │

│    • Closed Risks: [X]                                                    │

│    • Open High Risks: [X]                                                 │

│    • Risk Trend: [Improving / Stable / Deteriorating]                    │

│                                                                             │

│ 7. KEY DECISIONS MADE                                                     │

│    ────────────────────                                                    │

│    • Decision 1: [Description] - Date                                     │

│    • Decision 2: [Description] - Date                                     │

│                                                                             │

│ 8. PLAN FOR NEXT MONTH                                                    │

│    ────────────────────                                                    │

│    • Focus Area: [Area]                                                   │

│    • Key Deliverables:                                                    │

│      - [Deliverable 1]                                                    │

│      - [Deliverable 2]                                                    │

│      - [Deliverable 3]                                                    │

│                                                                             │

│ 9. RECOMMENDATIONS / REQUESTS                                             │

│    ──────────────────────────                                              │

│    • [Recommendation 1]                                                    │

│    • [Recommendation 2]                                                    │

│                                                                             │

│  Prepared by: [Name]                                                       │

│  Date: [Date]                                                              │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 8.4.4. Milestone Report

| Aspek | Keterangan |
| --- | --- |
| Nama | Milestone Completion Report |
| Penerima | Steering Committee, Sponsor |
| Metode | Presentation + Document |
| Waktu | Saat milestone tercapai |
| Format | PPT / PDF |

Template Milestone Report:

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        MILESTONE COMPLETION REPORT                          │

│                   P-FNE-02: Core Agricultural Operations                   │

│                   Milestone: [M3 - Farm & Land Module]                     │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│ 1. MILESTONE OVERVIEW                                                      │

│    ──────────────────                                                      │

│    • Milestone ID: [M3]                                                    │

│    • Milestone Name: Farm & Land Module                                    │

│    • Planned Date: 21 October 2026                                         │

│    • Actual Date: 25 October 2026                                          │

│    • Variance: +4 Days                                                     │

│    • Status: [✅ Completed / ⚠️ Completed with Issues / 🔴 Not Completed]  │

│                                                                             │

│ 2. DELIVERABLES                                                            │

│    ────────────                                                            │

│    ┌──────────────────────────────────────────────────────────────────┐   │

│    │ Deliverable          │ Status │ Quality │ Notes                │   │

│    ├──────────────────────────────────────────────────────────────────┤   │

│    │ Farm Service         │ ✅     │ PASS    │ All APIs implemented │   │

│    │ Land Service         │ ✅     │ PASS    │ With PostGIS support │   │

│    │ Soil Analysis Module │ ✅     │ PASS    │ 5 soil records       │   │

│    │ Farm Facilities      │ ✅     │ PASS    │ Complete             │   │

│    │ Farm UI              │ ✅     │ PASS    │ Dashboard included   │   │

│    │ Land Parcel UI       │ ✅     │ PASS    │ Map integration      │   │

│    └──────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│ 3. ACCEPTANCE CRITERIA ACHIEVEMENT                                         │

│    ───────────────────────────                                             │

│    ┌──────────────────────────────────────────────────────────────────┐   │

│    │ Criterion                     │ Status │ Evidence              │   │

│    ├──────────────────────────────────────────────────────────────────┤   │

│    │ 5 farm terdaftar               │ ✅     │ Database records     │   │

│    │ 20 land parcel terdaftar       │ ✅     │ Database records     │   │

│    │ Land parcel mapping berfungsi  │ ✅     │ Screenshot           │   │

│    │ Farm dashboard load ≤3 detik   │ ✅     │ Performance test     │   │

│    └──────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│ 4. LESSONS LEARNED                                                         │

│    ────────────────                                                        │

│    • What Went Well:                                                       │

│      - [Lesson 1]                                                         │

│      - [Lesson 2]                                                         │

│    • What Could Be Improved:                                               │

│      - [Improvement 1]                                                    │

│      - [Improvement 2]                                                    │

│                                                                             │

│ 5. NEXT STEPS                                                             │

│    ────────────                                                            │

│    • Next Milestone: [M4 - Crop Management]                               │

│    • Planned Date: 18 November 2026                                       │

│    • Key Focus: Crop Cycle, Planting, Growth Stage                        │

│                                                                             │

│ 6. APPROVAL                                                               │

│    ─────────                                                               │

│    _________________________                                               │

│    Steering Committee                                                      │

│                                                                             │

│    _________________________                                               │

│    Project Sponsor                                                         │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 8.5. Meeting Schedule

#### 8.5.1. Recurring Meetings

| Meeting | Agenda | Waktu | Hari | Peserta | Platform |
| --- | --- | --- | --- | --- | --- |
| Sprint Planning | Planning sprint backlog | 2 jam | Senin (Sprint 1) | PO, PM, Dev, QA | Zoom |
| Daily Stand-up | Status, blocker | 15 menit | Hari kerja | All Team | Zoom/Slack |
| Sprint Review | Demo deliverable | 1 jam | Jumat (Sprint akhir) | All Team | Zoom |
| Sprint Retrospective | Process improvement | 45 menit | Jumat (Sprint akhir) | All Team | Zoom |
| Technical Sync | Arsitektur, technical issues | 1 jam | Rabu | Tech Lead, Dev | Zoom |
| QA Sync | Test progress, bugs | 30 menit | Kamis | QA, Dev Lead | Zoom |
| Steering Committee | Progress, decisions | 1,5 jam | 2 minggu | Sponsor, SC, PM, PO | Zoom/In-person |
| Integration Sync | Integration status | 1 jam | 2 minggu | Tech Lead, P-FNE teams | Zoom |
| UAT Workshop | User feedback, UAT | 2 jam | Per Milestone | BA, PO, Users | In-person |

#### 8.5.2. Meeting Ground Rules

| Rule | Description |
| --- | --- |
| Punctuality | Datang tepat waktu |
| Agenda | Agenda disampaikan 24 jam sebelumnya |
| Timebox | Meeting sesuai durasi yang dijadwalkan |
| Participation | Semua peserta aktif berkontribusi |
| No Distraction | Fokus pada meeting, tidak multitasking |
| Action Items | Action items dicatat dengan jelas |
| Minutes | Notulen meeting disimpan |

#### 8.5.3. Meeting Minutes Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                            MEETING MINUTES                                  │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Meeting: [Sprint Planning / Review / Retrospective / etc]                │

│  Date: [Date]                                                              │

│  Time: [Start - End]                                                       │

│  Location: [Online / In-person]                                            │

│  Facilitator: [Name]                                                       │

│  Minute Taker: [Name]                                                      │

│                                                                             │

│  ATTENDEES:                                                                 │

│  ──────────                                                                 │

│  - [Name 1] - [Role]                                                       │

│  - [Name 2] - [Role]                                                       │

│  - [Name 3] - [Role]                                                       │

│                                                                             │

│  AGENDA:                                                                    │

│  ──────                                                                     │

│  1. [Agenda Item 1]                                                        │

│  2. [Agenda Item 2]                                                        │

│  3. [Agenda Item 3]                                                        │

│                                                                             │

│  DISCUSSION SUMMARY:                                                        │

│  ──────────────────                                                       │

│  1. [Agenda Item 1]                                                        │

│     - [Discussion points]                                                  │

│     - [Decision made]                                                      │

│                                                                             │

│  2. [Agenda Item 2]                                                        │

│     - [Discussion points]                                                  │

│     - [Decision made]                                                      │

│                                                                             │

│  ACTION ITEMS:                                                              │

│  ─────────────                                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐  │

│  │ No │ Action Item       │ Owner   │ Deadline │ Status              │  │

│  ├─────────────────────────────────────────────────────────────────────┤  │

│  │ 1  │ ...               │ ...     │ ...     │ Pending             │  │

│  │ 2  │ ...               │ ...     │ ...     │ Pending             │  │

│  └─────────────────────────────────────────────────────────────────────┘  │

│                                                                             │

│  NEXT MEETING:                                                              │

│  ─────────────                                                              │

│  • Date: [Date]                                                            │

│  • Time: [Time]                                                            │

│  • Topic: [Topic]                                                          │

│                                                                             │

│  Minutes Prepared by: [Name]                                               │

│  Date: [Date]                                                              │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 8.6. Document Management

#### 8.6.1. Document Repository

| Category | Documents | Repository | Access |
| --- | --- | --- | --- |
| Project Management | PMP, Charter, Reports | Confluence | All Team |
| Requirements | BRD, FRD, User Stories | Confluence/Jira | All Team |
| Design | Architecture, API Spec, DB Design | Confluence | All Team |
| Development | Code, PR, Comments | GitHub | Dev Team |
| Testing | Test Cases, Bug Reports | Jira | QA Team |
| User | User Manual, Training Materials | Confluence | All Team |
| Operational | Deployment, Monitoring | Confluence | DevOps |

#### 8.6.2. Document Naming Convention

| Type | Format | Example |
| --- | --- | --- |
| Project Document | [Project Code]-[Doc Type]-[Version].docx | P-FNE-02-PMP-V1.0.docx |
| Requirement | [Project Code]-REQ-[Module]-[Version].docx | P-FNE-02-REQ-FRM-V1.0.docx |
| Design | [Project Code]-[Design Type]-[Version].docx | P-FNE-02-ARCH-V1.0.docx |
| Report | [Project Code]-[Report Type]-[Date].docx | P-FNE-02-Status-20261015.docx |
| User Manual | [Project Code]-UM-[Module]-[Version].docx | P-FNE-02-UM-FRM-V1.0.docx |

#### 8.6.3. Version Control

| Version | Change | Author | Date | Reviewer |
| --- | --- | --- | --- | --- |
| 0.1 | Draft | [Name] | [Date] | - |
| 0.5 | Review | [Name] | [Date] | [Name] |
| 1.0 | Final | [Name] | [Date] | [Name] |
| 1.1 | Minor update | [Name] | [Date] | [Name] |

### 8.7. Communication Plan Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         COMMUNICATION PLAN APPROVAL                         │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│                                                                             │

│  Saya menyetujui Communication Management Plan ini dan akan menjadi       │

│  baseline untuk manajemen komunikasi proyek.                              │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  Project Sponsor                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 9: MANAJEMEN RISIKO PROYEK

### 9.1. Tujuan Manajemen Risiko

Manajemen risiko proyek bertujuan untuk:

- Mengidentifikasi Risiko – Menemukan potensi risiko yang dapat mempengaruhi keberhasilan proyek secara proaktif.

- Menganalisis Risiko – Mengevaluasi dampak dan probabilitas setiap risiko yang teridentifikasi.

- Merencanakan Respons – Mengembangkan strategi mitigasi untuk risiko-risiko prioritas tinggi.

- Memantau Risiko – Melacak status risiko dan efektivitas respons secara berkelanjutan.

- Mengurangi Ketidakpastian – Meminimalkan dampak negatif dan memaksimalkan peluang yang muncul.

### 9.2. Risk Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                          RISK MANAGEMENT PROCESS                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Plan Risk   │───►│ Identify    │───►│ Analyze     │───►│ Plan        │ │

│  │ Management  │    │ Risks       │    │ Risks       │    │ Response    │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Risk      │    │ • Brain-    │    │ • Risk      │    │ • Mitigation│ │

│  │   Policy    │    │   storming  │    │   Matrix    │    │ • Avoidance │ │

│  │ • Risk      │    │ • Checklist │    │ • Impact &  │    │ • Transfer  │ │

│  │   Tolerance │    │ • Interview │    │   Probability│   │ • Acceptance│ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

│  ┌─────────────┐                                                           │

│  │ Monitor     │                                                           │

│  │ Risks       │                                                           │

│  └─────────────┘                                                           │

│        │                                                                   │

│        ▼                                                                   │

│  ┌─────────────┐                                                           │

│  │ • Risk      │                                                           │

│  │   Register  │                                                           │

│  │ • Risk      │                                                           │

│  │   Review    │                                                           │

│  │ • Risk      │                                                           │

│  │   Reporting │                                                           │

│  └─────────────┘                                                           │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 9.3. Risk Identification

#### 9.3.1. Risk Identification Methods

| Metode | Deskripsi | Kapan Digunakan | PIC |
| --- | --- | --- | --- |
| Brainstorming | Sesi curah pendapat dengan tim | Kick-off, setiap milestone | PM |
| Checklist | Menggunakan checklist risiko standar | Awal proyek | PM + Tech Lead |
| Interview | Wawancara dengan stakeholder ahli | Awal proyek | BA + PM |
| WBS Review | Review setiap elemen WBS | Per phase | Tech Lead |
| Expert Judgment | Konsultasi dengan ahli domain | Awal proyek | PM |
| Assumption Analysis | Analisis asumsi yang diambil | Awal proyek | PM + Tech Lead |

#### 9.3.2. Risk Categories

| Kategori | Deskripsi | Contoh |
| --- | --- | --- |
| Teknis | Risiko terkait teknologi dan arsitektur | Stack mismatch, performance issue |
| Manajemen | Risiko terkait manajemen proyek | Schedule delay, resource shortage |
| Organisasi | Risiko terkait organisasi dan stakeholder | Stakeholder resistance, communication |
| Eksternal | Risiko dari luar proyek | Market change, regulatory change |
| Domain | Risiko terkait domain pertanian | Data complexity, user adoption |

### 9.4. Risk Analysis

#### 9.4.1. Risk Probability and Impact Scale

Probability Scale:

| Level | Nilai | Deskripsi | Kriteria |
| --- | --- | --- | --- |
| Sangat Rendah | 1 | < 5% | Hampir tidak mungkin terjadi |
| Rendah | 2 | 5% - 20% | Kemungkinan kecil terjadi |
| Sedang | 3 | 20% - 50% | Kemungkinan terjadi cukup besar |
| Tinggi | 4 | 50% - 80% | Kemungkinan besar terjadi |
| Sangat Tinggi | 5 | > 80% | Hampir pasti terjadi |

Impact Scale:

| Level | Nilai | Deskripsi | Kriteria |
| --- | --- | --- | --- |
| Sangat Rendah | 1 | < Rp 50 Juta | Dampak minimal, mudah diatasi |
| Rendah | 2 | Rp 50-100 Juta | Dampak kecil, masih bisa diatasi |
| Sedang | 3 | Rp 100-250 Juta | Dampak signifikan, perlu perhatian |
| Tinggi | 4 | Rp 250-500 Juta | Dampak besar, perlu mitigasi serius |
| Sangat Tinggi | 5 | > Rp 500 Juta | Dampak kritis, bisa mengancam proyek |

#### 9.4.2. Risk Matrix

|  | Probability |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Impact | 1 (SR) | 2 (R) | 3 (S) | 4 (T) | 5 (ST) |
| 5 (ST) | 5 | 10 | 15 | 20 | 25 |
| 4 (T) | 4 | 8 | 12 | 16 | 20 |
| 3 (S) | 3 | 6 | 9 | 12 | 15 |
| 2 (R) | 2 | 4 | 6 | 8 | 10 |
| 1 (SR) | 1 | 2 | 3 | 4 | 5 |

Keterangan:

- Merah (≥ 15): Risiko Kritis - Perlu mitigasi segera

- Kuning (6-14): Risiko Signifikan - Perlu rencana mitigasi

- Hijau (≤ 5): Risiko Rendah - Monitor saja

### 9.5. Risk Register

#### 9.5.1. Risk Register Format

| ID | Kategori | Risiko | Penyebab | Dampak | Prob | Impact | Score | Strategi | Respons | PIC | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Manajemen | Keterlambatan P-FNE-01 | P-FNE-01 belum siap | Blocking development | 4 | 5 | 20 | Mitigasi | Sinkronisasi intensif, parallel dev | PM | Active |
| R-002 | Manajemen | Perubahan requirement signifikan | Stakeholder request | Rework dan delay | 3 | 4 | 12 | Mitigasi | Change control strict | PO | Active |
| ... | ... | ... | ... | ... | ... | ... | ... | ... | ... | ... | ... |

#### 9.5.2. Detailed Risk Register

Risiko Internal

| ID | R-001 |
| --- | --- |
| Kategori | Manajemen |
| Nama Risiko | Keterlambatan pada P-FNE-01 (Foundation) |
| Deskripsi | Proyek P-FNE-01 yang menyediakan IAM Service dan Master Data Service belum selesai tepat waktu, sehingga P-FNE-02 tidak bisa memulai integrasi dan testing |
| Penyebab | • P-FNE-01 mengalami delay • Resource P-FNE-01 terbatas • Dependency management kurang baik |
| Dampak | • Blocking development P-FNE-02 (2-4 minggu) • Integrasi tertunda • Risk terhadap milestone |
| Probabilitas | 4 (Tinggi) |
| Impact | 5 (Sangat Tinggi) |
| Risk Score | 20 (Kritis) |
| Strategi | Mitigasi |
| Rencana Respons | • Sinkronisasi mingguan dengan P-FNE-01 team • Parallel engineering menggunakan mock service • Early integration testing • Sprint buffer 20% untuk integrasi |
| PIC | Project Manager |
| Status | Active |

| ID | R-002 |
| --- | --- |
| Kategori | Manajemen |
| Nama Risiko | Perubahan requirement signifikan |
| Deskripsi | Stakeholder (Farm Manager, Agronomist) meminta penambahan atau perubahan fitur yang signifikan di tengah pengembangan |
| Penyebab | • Requirement tidak clear di awal • User feedback selama UAT • Perubahan bisnis |
| Dampak** | • Rework (2-4 minggu) • Impact terhadap jadwal • Potensi scope creep |
| Probabilitas | 3 (Sedang) |
| Impact | 4 (Tinggi) |
| Risk Score | 12 (Signifikan) |
| Strategi | Mitigasi |
| Rencana Respons | • Change control process yang strict • Sprint buffer 20% • Requirement finalisasi yang matang • UAT dilakukan early dengan prototyping |
| PIC | Product Owner |
| Status | Active |

| ID | R-003 |
| --- | --- |
| Kategori | Organisasi |
| Nama Risiko | Turnover tim kunci |
| Deskripsi | Anggota tim kunci (Tech Lead, Senior Developer) keluar dari proyek di tengah pengembangan |
| Penyebab | • Kesempatan karir lain • Kompensasi kurang kompetitif • Workload berlebihan |
| Dampak | • Knowledge loss (2-3 minggu) • Delay pengembangan • Kualitas kode menurun |
| Probabilitas | 2 (Rendah) |
| Impact | 4 (Tinggi) |
| Risk Score | 8 (Signifikan) |
| Strategi | Mitigasi |
| Rencana Respons | • Cross-training antar developer • Dokumentasi kode yang baik • Knowledge sharing session bulanan • 2-week notice period • Succession planning |
| PIC | HR + PM |
| Status | Active |

| ID | R-004 |
| --- | --- |
| Kategori | Teknis |
| Nama Risiko | Integrasi event-driven gagal |
| Deskripsi | Implementasi Kafka dan event-driven architecture tidak berjalan dengan baik, menyebabkan kegagalan komunikasi antar service |
| Penyebab | • Kafka configuration salah • Event schema tidak kompatibel • Network issue • Kafka cluster unstable |
| Dampak | • Integrasi gagal (1-2 minggu) • Data tidak sinkron • System tidak reliable |
| Probabilitas | 2 (Rendah) |
| Impact | 5 (Sangat Tinggi) |
| Risk Score | 10 (Signifikan) |
| Strategi | Mitigasi |
| Rencana Respons | • Kafka POC di awal proyek • Schema Registry dengan versioning • Fallback mechanism (sync API) • Monitoring dan alerting untuk Kafka |
| PIC | Technical Lead |
| Status | Completed (POC done) |

| ID | R-005 |
| --- | --- |
| Kategori | Teknis |
| Nama Risiko | Database performance issue |
| Deskripsi | Query database lambat di bawah beban tinggi, terutama saat query data geospasial (PostGIS) |
| Penyebab | • Indexing tidak optimal • Query kompleks • Data volume besar • PostGIS configuration |
| Dampak | • Response time > 3 detik • User experience buruk • Scalability issue |
| Probabilitas | 3 (Sedang) |
| Impact | 4 (Tinggi) |
| Risk Score | 12 (Signifikan) |
| Strategi | Mitigasi |
| Rencana Respons | • Database architecture review • Indexing strategy • Query optimization • Caching (Redis) • Performance testing early |
| PIC | Technical Lead |
| Status | Active |

Risiko Eksternal

| ID | R-006 |
| --- | --- |
| Kategori | Eksternal |
| Nama Risiko | Tidak tersedia user untuk UAT |
| Deskripsi | Farm Manager atau user yang dibutuhkan untuk UAT tidak tersedia karena kesibukan operasional |
| Penyebab | • Musim panen bersamaan dengan UAT • User tidak diberi prioritas • Kurangnya koordinasi |
| Dampak | • UAT tertunda (1-2 minggu) • Quality kurang terjamin • Feedback terlambat |
| Probabilitas | 3 (Sedang) |
| Impact | 3 (Sedang) |
| Risk Score | 9 (Signifikan) |
| Strategi | Mitigasi |
| Rencana Respons | • Jadwalkan UAT 2 minggu sebelum deadline • Koordinasi dengan farm management • Backup user dari farm lain • UAT dilakukan dalam batch |
| PIC | BA + PM |
| Status | Active |

| ID | R-007 |
| --- | --- |
| Kategori | Eksternal |
| Nama Risiko | Cloud infrastructure issue |
| Deskripsi | Gangguan pada cloud provider (AWS/GCP) menyebabkan downtime atau performance issue |
| Penyebab | • Cloud provider outage • Network issue • Resource limit reached |
| Dampak | • Downtime (1-24 jam) • Progres terhambat • User trust menurun |
| Probabilitas | 2 (Rendah) |
| Impact | 4 (Tinggi) |
| Risk Score | 8 (Signifikan) |
| Strategi | Mitigasi |
| Rencana Respons | • Multi-region backup • Monitoring dan alerting (24/7) • Auto-scaling configuration • Disaster recovery plan • Regular backup |
| PIC | DevOps |
| Status | Active |

| ID | R-008 |
| --- | --- |
| Kategori | Eksternal |
| Nama Risiko | Perubahan regulasi pertanian |
| Deskripsi | Ada perubahan regulasi dari pemerintah terkait pencatatan data pertanian |
| Penyebab | • Perubahan kebijakan • Regulasi baru • Persyaratan pelaporan baru |
| Dampak | • Perubahan requirement (1-2 minggu) • Data mapping tambahan • Compliance issue |
| Probabilitas | 2 (Rendah) |
| Impact | 3 (Sedang) |
| Risk Score | 6 (Signifikan) |
| Strategi | Acceptance |
| Rencana Respons | • Monitor regulasi terbaru • Koordinasi dengan legal & compliance • Desain sistem yang fleksibel • Sprint buffer untuk regulatory changes |
| PIC | BA + PM |
| Status | Active |

| ID | R-009 |
| --- | --- |
| Kategori | Domain |
| Nama Risiko | Kompleksitas data pertanian |
| Deskripsi | Data pertanian memiliki kompleksitas tinggi (musim, varietas, kondisi tanah, dll) yang sulit dimodelkan |
| Penyebab | • Domain knowledge kurang • Variasi data tinggi • Ekspektasi user tinggi |
| Dampak | • Rework (1-2 minggu) • Akurasi data rendah • User dissatisfaction |
| Probabilitas | 3 (Sedang) |
| Impact | 3 (Sedang) |
| Risk Score | 9 (Signifikan) |
| Strategi | Mitigasi |
| Rencana Respons | • Libatkan domain expert (Agronomist) • Frequent user validation • Iterative development • Prototyping sebelum UAT |
| PIC | BA + PO |
| Status | Active |

| ID | R-010 |
| --- | --- |
| Kategori | Teknis |
| Nama Risiko | Mobile offline sync failure |
| Deskripsi | Mekanisme sinkronisasi data offline di mobile app tidak bekerja dengan baik, menyebabkan data hilang atau conflict |
| Penyebab | • Conflict resolution strategy • Network instability • Data size besar • Background sync issue |
| Dampak | • Data tidak sinkron (1-2 minggu) • User frustration • Loss of offline capability |
| Probabilitas | 3 (Sedang) |
| Impact | 3 (Sedang) |
| Risk Score | 9 (Signifikan) |
| Strategi | Mitigasi |
| Rencana Respons | • Comprehensive testing offline • Conflict resolution strategy (LWW) • Retry mechanism • Data compression • Background sync optimization |
| PIC | Mobile Lead |
| Status | Active |

### 9.6. Risk Response Plan

#### 9.6.1. Response Strategies

| Strategi | Deskripsi | Contoh |
| --- | --- | --- |
| Mitigasi | Mengurangi probabilitas atau dampak risiko | Melakukan POC, training, early testing |
| Avoidance | Menghilangkan risiko dengan mengubah pendekatan | Menggunakan mock service untuk dependency |
| Transfer | Memindahkan risiko ke pihak ketiga | Menggunakan cloud provider yang reliable |
| Acceptance | Menerima risiko dan menyiapkan contingency | Menyediakan buffer untuk regulatory changes |

#### 9.6.2. Risk Response Matrix

| ID | Risiko | Strategi | Respons | PIC | Tanggal Target |
| --- | --- | --- | --- | --- | --- |
| R-001 | Keterlambatan P-FNE-01 | Mitigasi | Sinkronisasi intensif, parallel dev | PM | Continuous |
| R-002 | Perubahan requirement | Mitigasi | Change control strict | PO | Continuous |
| R-003 | Turnover tim kunci | Mitigasi | Cross-training, dokumentasi | PM + HR | Continuous |
| R-004 | Integrasi event-driven gagal | Mitigasi | Kafka POC, fallback mechanism | Tech Lead | Minggu 8 |
| R-005 | Database performance issue | Mitigasi | Indexing, caching, optimization | Tech Lead | Minggu 6 |
| R-006 | User tidak tersedia UAT | Mitigasi | Schedule UAT early | BA | Minggu 16 |
| R-007 | Cloud infrastructure issue | Mitigasi | Multi-region, monitoring | DevOps | Continuous |
| R-008 | Perubahan regulasi | Acceptance | Monitor regulasi, buffer | BA + PM | Continuous |
| R-009 | Kompleksitas data pertanian | Mitigasi | Domain expert involvement | BA + PO | Continuous |
| R-010 | Mobile offline sync failure | Mitigasi | Comprehensive testing | Mobile Lead | Minggu 14 |

### 9.7. Risk Monitoring and Control

#### 9.7.1. Risk Monitoring Plan

| Aktivitas | Frekuensi | PIC | Output |
| --- | --- | --- | --- |
| Risk Review | Sprint Review (2 minggu) | PM | Updated risk register |
| Risk Audit | Per Milestone | PMO | Risk audit report |
| Risk Reporting | Weekly | PM | Risk status in weekly report |
| Risk Escalation | Continuous | PM | Escalation to SC/Sponsor |

#### 9.7.2. Risk Review Template

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                            RISK REVIEW REPORT                              │

│                            P-FNE-02: Core Agricultural Operations          │

│                            Date: [Date]                                    │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  SUMMARY:                                                                   │

│  ─────────                                                                  │

│  • Total Risks Identified: [XX]                                            │

│  • Active Risks: [XX]                                                      │

│  • Closed Risks: [XX]                                                      │

│  • Risk Trend: [Improving / Stable / Deteriorating]                       │

│                                                                             │

│  HIGH RISKS (Score ≥ 15):                                                  │

│  ────────────────────                                                      │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ ID │ Risk              │ Score │ Status │ Action / Progress        │   │

│  ├─────────────────────────────────────────────────────────────────────┤   │

│  │ R-001│ Keterlambatan P-│ 20    │ Open  │ Sync weekly, mock ready  │   │

│  │     │ FNE-01           │       │       │                          │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  SIGNIFICANT RISKS (Score 6-14):                                           │

│  ─────────────────────────────                                             │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │ ID │ Risk              │ Score │ Status │ Action / Progress        │   │

│  ├─────────────────────────────────────────────────────────────────────┤   │

│  │ R-002│ Perubahan req   │ 12    │ Open  │ Change control active    │   │

│  │ R-005│ DB performance  │ 12    │ Open  │ Indexing in progress     │   │

│  │ R-006│ User UAT        │ 9     │ Open  │ Schedule confirmed       │   │

│  │ R-009│ Data complexity │ 9     │ Open  │ Domain expert onboard    │   │

│  │ R-010│ Mobile sync     │ 9     │ Open  │ Testing in progress      │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                                                                             │

│  NEW RISKS IDENTIFIED:                                                     │

│  ──────────────────────                                                    │

│  • [Risk 1] - [Impact] - [Response]                                       │

│  • [Risk 2] - [Impact] - [Response]                                       │

│                                                                             │

│  RISKS CLOSED:                                                             │

│  ─────────────                                                             │

│  • R-004: Integrasi event-driven gagal - Closed (POC successful)          │

│                                                                             │

│  RECOMMENDATIONS:                                                          │

│  ────────────────                                                          │

│  • [Recommendation 1]                                                      │

│  • [Recommendation 2]                                                      │

│                                                                             │

│  Prepared by: [Name]                                                       │

│  Date: [Date]                                                              │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 9.7.3. Risk Escalation Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                          RISK ESCALATION PROCESS                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Level 1: Developer → Tech Lead                                            │

│    ├── Teknis: Bug, performance issue, integration issue                   │

│    └── Respon: 4 jam                                                       │

│                                                                             │

│  Level 2: Tech Lead → Project Manager                                      │

│    ├── Manajemen: Resource, schedule, dependency                            │

│    └── Respon: 1 hari                                                      │

│                                                                             │

│  Level 3: Project Manager → Steering Committee                             │

│    ├── Strategis: Scope, budget, major risk                                 │

│    └── Respon: 1 minggu                                                    │

│                                                                             │

│  Level 4: Steering Committee → Project Sponsor                             │

│    ├── Kritis: Project viability, funding                                   │

│    └── Respon: 2 minggu                                                    │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 9.8. Risk Management Plan Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         RISK MANAGEMENT PLAN APPROVAL                       │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│  Total Risiko Teridentifikasi: 10                                           │

│  Risiko Kritis: 1                                                           │

│  Risiko Signifikan: 7                                                       │

│  Risiko Rendah: 2                                                           │

│                                                                             │

│  Saya menyetujui Risk Management Plan ini dan akan menjadi baseline        │

│  untuk manajemen risiko proyek.                                            │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  Project Sponsor                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 10: MANAJEMEN PENGADAAN PROYEK

### 10.1. Tujuan Manajemen Pengadaan

Manajemen pengadaan proyek bertujuan untuk:

- Memastikan Ketersediaan – Menjamin barang dan jasa yang dibutuhkan proyek tersedia tepat waktu dan sesuai spesifikasi.

- Mengoptimalkan Biaya – Mendapatkan nilai terbaik dari setiap pengeluaran melalui proses seleksi yang kompetitif.

- Mengelola Vendor – Memastikan vendor memenuhi komitmen dan memberikan kualitas yang diharapkan.

- Meminimalkan Risiko – Mengurangi risiko terkait ketergantungan pada pihak eksternal.

- Mematuhi Regulasi – Memastikan proses pengadaan sesuai dengan kebijakan dan regulasi yang berlaku.

### 10.2. Procurement Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        PROCUREMENT MANAGEMENT PROCESS                       │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Plan        │───►│ Conduct     │───►│ Control     │───►│ Close       │ │

│  │ Procurement │    │ Procurement │    │ Procurement │    │ Procurement │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Needs     │    │ • RFx       │    │ • Contract  │    │ • Contract  │ │

│  │   Analysis  │    │ • Vendor    │    │   Mgmt     │    │   Closure   │ │

│  │ • Make-or-  │    │   Selection │    │ • Payment   │    │ • Lessons   │ │

│  │   Buy       │    │ • Contract  │    │ • Dispute   │    │   Learned   │ │

│  │ • Sourcing  │    │   Award     │    │   Resolution│    │             │ │

│  │   Strategy  │    │             │    │             │    │             │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 10.3. Procurement Needs Analysis

#### 10.3.1. Make-or-Buy Analysis

| Item | Make (Internal) | Buy (External) | Keputusan | Alasan |
| --- | --- | --- | --- | --- |
| Software Development | ✅ | - | Make | Core kompetensi, intellectual property |
| Cloud Infrastructure | - | ✅ | Buy | Capital expenditure vs operational expenditure |
| Software License | - | ✅ | Buy | Tidak efisien membangun sendiri |
| Consulting Services | - | ✅ | Buy | Membutuhkan keahlian spesifik |
| Testing Tools | - | ✅ | Buy | Open source + licensed tools |
| Training | - | ✅ | Buy | Membutuhkan trainer profesional |
| Hardware | - | ✅ | Buy | Tidak memiliki kapasitas produksi |

#### 10.3.2. Procurement Categories

| Kategori | Item | Metode | Kriteria | Estimasi Biaya (Rp) |
| --- | --- | --- | --- | --- |
| Infrastruktur | Cloud Services (AWS/GCP) | Tender | Technical capability, cost | 120.000.000 |
| Software | Jira/Confluence License | Direct | - | 12.000.000 |
| Software | IDE Licenses | Direct | - | 15.000.000 |
| Software | Monitoring Tools | Direct | - | 8.000.000 |
| Software | Testing Tools | Direct | - | 5.000.000 |
| Software | Design Tools (Figma) | Direct | - | 6.000.000 |
| Consulting | Domain Agricole Expert | RFQ | Experience, references | 15.000.000 |
| Training | Team Training | RFQ | Curriculum, trainer | 20.000.000 |
| Hardware | Mobile Devices for Testing | Direct | - | 10.000.000 |
| Other | Communication Tools | Direct | - | 6.000.000 |
| Total |  |  |  | 217.000.000 |

### 10.4. Procurement Plan

#### 10.4.1. Detailed Procurement Plan

| No | Item | Quantity | Specification | Vendor | Method | Timeline | Budget (Rp) | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Infrastruktur |  |  |  |  |  |  |  |  |
| 1 | Cloud Services | 6 months | AWS/GCP, Production + Dev | AWS/GCP | Tender | M1 | 120.000.000 | Planned |
| Software |  |  |  |  |  |  |  |  |
| 2 | Jira/Confluence | 14 users | Cloud, Enterprise | Atlassian | Direct | M1 | 12.000.000 | Planned |
| 3 | IDE Licenses | 14 users | IntelliJ, VS Code | JetBrains/Microsoft | Direct | M1 | 15.000.000 | Planned |
| 4 | Monitoring Tools | 1 year | Prometheus, Grafana, ELK | Open Source + Custom | Direct | M1 | 8.000.000 | Planned |
| 5 | Testing Tools | 1 year | k6, OWASP ZAP, SonarQube | Various | Direct | M1 | 5.000.000 | Planned |
| 6 | Design Tools | 2 users | Figma Team | Figma | Direct | M1 | 6.000.000 | Planned |
| Services |  |  |  |  |  |  |  |  |
| 7 | Domain Expert | 40 hours | Agricole Domain | Consultant | RFQ | M2 | 15.000.000 | Planned |
| 8 | Team Training | 2 sessions | Agile + Technical | Training Provider | RFQ | M2 | 20.000.000 | Planned |
| Hardware |  |  |  |  |  |  |  |  |
| 9 | Mobile Devices | 3 units | Android + iOS | Various | Direct | M4 | 10.000.000 | Planned |
| Other |  |  |  |  |  |  |  |  |
| 10 | Communication Tools | 1 year | Slack/Zoom | Various | Direct | M1 | 6.000.000 | Planned |
| Total |  |  |  |  |  |  | 217.000.000 |  |

#### 10.4.2. Procurement Schedule

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         PROCUREMENT SCHEDULE                                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Item               | M1 | M2 | M3 | M4 | M5 | M6                         │

│  ───────────────────┼────┼────┼────┼────┼────┼────                        │

│  Cloud Services     | ████| ████| ████| ████| ████| ████                  │

│  Jira/Confluence    | ████| ████| ████| ████| ████| ████                  │

│  IDE Licenses       | ████| ████| ████| ████| ████| ████                  │

│  Monitoring Tools   | ████| ████| ████| ████| ████| ████                  │

│  Testing Tools      | ████| ████| ████| ████| ████| ████                  │

│  Design Tools       | ████| ████| ████| ████| ████| ████                  │

│  Domain Expert      |     | ████| ████|     |     |                       │

│  Team Training      |     | ████| ████|     |     |                       │

│  Mobile Devices     |     |     |     | ████|     |                       │

│  Communication Tools| ████| ████| ████| ████| ████| ████                  │

│                                                                             │

│  ████ = Active / Ongoing                                                   │

│  ████ = One-time Activity                                                   │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 10.5. Vendor Management

#### 10.5.1. Vendor Selection Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                         VENDOR SELECTION PROCESS                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Define      │───►│ Request for │───►│ Evaluate    │───►│ Select &    │ │

│  │ Requirements│    │ Proposal    │    │ Proposals   │    │ Award       │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Spec      │    │ • RFI/RFP   │    │ • Technical │    │ • Contract  │ │

│  │ • SOW       │    │ • RFQ       │    │ • Commercial│    │ • Signing   │ │

│  │ • Criteria  │    │             │    │ • References│    │ • PO        │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 10.5.2. Evaluation Criteria

| Kriteria | Bobot | Deskripsi |
| --- | --- | --- |
| Technical Capability | 30% | Keahlian teknis vendor, portofolio, pengalaman |
| Price | 25% | Total biaya pengadaan |
| Delivery Timeline | 15% | Kemampuan memenuhi jadwal proyek |
| Support & Maintenance | 10% | Kualitas support, SLA |
| References | 10% | Testimoni dari klien sebelumnya |
| Compliance | 10% | Kepatuhan terhadap regulasi dan standar |

#### 10.5.3. Vendor Scorecard

| Vendor | Technical (30%) | Price (25%) | Timeline (15%) | Support (10%) | References (10%) | Compliance (10%) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AWS | 28 | 22 | 14 | 9 | 9 | 10 | 92 |
| GCP | 26 | 20 | 13 | 8 | 8 | 10 | 85 |
| Azure | 24 | 18 | 12 | 8 | 7 | 9 | 78 |

#### 10.5.4. Contract Management

| Contract | Vendor | Term | Value | Renewal Date | Status |
| --- | --- | --- | --- | --- | --- |
| Cloud Services | AWS | 1 Year | Rp 120 Jt | Aktif | Active |
| Jira License | Atlassian | 1 Year | Rp 30 Jt | Aktif | Active |
| IDE Licenses | JetBrains | 1 Year | Rp 15 Jt | Aktif | Active |
| Domain Expert | Consultant | 40 hours | Rp 15 Jt | - | Planned |

### 10.6. Procurement Control

#### 10.6.1. Procurement Tracking

| Item | Planned Date | Actual Date | Status | Variance | Notes |
| --- | --- | --- | --- | --- | --- |
| Cloud Services | 01/09/2026 | 01/09/2026 | ✅ Delivered | 0 | - |
| Jira/Confluence | 01/09/2026 | 01/09/2026 | ✅ Delivered | 0 | - |
| IDE Licenses | 01/09/2026 | 01/09/2026 | ✅ Delivered | 0 | - |
| Monitoring Tools | 01/09/2026 | 05/09/2026 | ✅ Delivered | +4 | Minor delay |
| Testing Tools | 01/09/2026 | 01/09/2026 | ✅ Delivered | 0 | - |
| Design Tools | 01/09/2026 | 01/09/2026 | ✅ Delivered | 0 | - |
| Domain Expert | 15/09/2026 | - | 🔄 In Progress | - | RFQ ongoing |
| Team Training | 15/09/2026 | - | 🔄 In Progress | - | RFQ ongoing |
| Mobile Devices | 15/11/2026 | - | ⏳ Planned | - | - |
| Communication Tools | 01/09/2026 | 01/09/2026 | ✅ Delivered | 0 | - |

#### 10.6.2. Vendor Performance Review

| Vendor | Service | Performance | SLA | Issues | Action |
| --- | --- | --- | --- | --- | --- |
| AWS | Cloud Services | 🟢 Excellent | 99.9% | None | Renew |
| Atlassian | Jira/Confluence | 🟢 Good | 99.5% | None | Renew |
| JetBrains | IDE | 🟢 Excellent | - | None | Renew |

#### 10.6.3. Invoice and Payment Schedule

| No | Vendor | Item | Invoice Date | Due Date | Amount (Rp) | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | AWS | Cloud (Month 1) | 01/09/2026 | 15/09/2026 | 20.000.000 | Paid |
| 2 | AWS | Cloud (Month 2) | 01/10/2026 | 15/10/2026 | 20.000.000 | Pending |
| 3 | Atlassian | Jira License | 01/09/2026 | 15/09/2026 | 12.000.000 | Paid |
| ... | ... | ... | ... | ... | ... | ... |

### 10.7. Procurement Risk Management

| Risk | Probability | Impact | Score | Mitigation |
| --- | --- | --- | --- | --- |
| Vendor not delivering on time | Medium | High | 12 | Select vendor with proven track record, include penalty clause, early ordering |
| Budget overrun | Medium | High | 12 | Multiple quotes, negotiate, contingency budget |
| Vendor quality issue | Low | High | 8 | Technical evaluation, reference check, quality clause |
| Vendor dependency | High | Medium | 12 | Diversify vendors, include exit clause |
| License compliance | Low | Medium | 6 | Legal review, compliance check |

### 10.8. Procurement Closure

#### 10.8.1. Contract Closure Checklist

| No | Item | Status |
| --- | --- | --- |
| 1 | All deliverables received | [ ] |
| 2 | All invoices paid | [ ] |
| 3 | Vendor performance reviewed | [ ] |
| 4 | Contract closed | [ ] |
| 5 | Lessons learned documented | [ ] |
| 6 | Future procurement recommendation | [ ] |

#### 10.8.2. Lessons Learned - Procurement

| Category | What Worked | What Could Be Improved |
| --- | --- | --- |
| Vendor Selection | - | - |
| Contract Management | - | - |
| Payment Process | - | - |
| Vendor Communication | - | - |

### 10.9. Procurement Management Plan Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                      PROCUREMENT MANAGEMENT PLAN APPROVAL                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│  Total Anggaran Pengadaan: Rp 217.000.000                                 │

│  Jumlah Vendor: 6                                                          │

│                                                                             │

│  Saya menyetujui Procurement Management Plan ini dan akan menjadi         │

│  baseline untuk manajemen pengadaan proyek.                               │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  Procurement Manager                                                        │

│                                                                             │

│  ___________________________                                                │

│  Project Sponsor                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 11: MANAJEMEN PEMANGKU KEPENTINGAN

### 11.1. Tujuan Manajemen Pemangku Kepentingan

Manajemen pemangku kepentingan bertujuan untuk:

- Mengidentifikasi Pemangku Kepentingan – Menemukan semua pihak yang memiliki kepentingan atau pengaruh terhadap proyek.

- Memahami Kebutuhan dan Harapan – Menganalisis apa yang diinginkan dan dibutuhkan oleh setiap pemangku kepentingan.

- Mengelola Keterlibatan – Memastikan pemangku kepentingan terlibat secara tepat sesuai dengan tingkat kepentingan dan pengaruhnya.

- Membangun Hubungan Positif – Menjaga komunikasi yang baik dan membangun kepercayaan dengan seluruh pemangku kepentingan.

- Mengelola Konflik Kepentingan – Mengidentifikasi dan menyelesaikan potensi konflik antar pemangku kepentingan.

### 11.2. Stakeholder Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                     STAKEHOLDER MANAGEMENT PROCESS                          │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ Identify    │───►│ Plan        │───►│ Manage      │───►│ Monitor     │ │

│  │ Stakeholders│    │ Engagement  │    │ Engagement  │    │ Engagement  │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│        │                  │                  │                  │          │

│        ▼                  ▼                  ▼                  ▼          │

│  ┌─────────────┐    ┌─────────────┐    ┌─────────────┐    ┌─────────────┐ │

│  │ • Stake-    │    │ • Stake-    │    │ • Commu-    │    │ • Feedback  │ │

│  │   holder    │    │   holder    │    │   nication  │    │   Loop      │ │

│  │   Register  │    │   Matrix    │    │ • Meeting   │    │ • Satis-    │ │

│  │ • Analysis  │    │ • Engage-   │    │ • Workshop  │    │   faction   │ │

│  │   Matrix    │    │   ment Plan │    │ • Reporting │    │   Survey    │ │

│  └─────────────┘    └─────────────┘    └─────────────┘    └─────────────┘ │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 11.3. Stakeholder Identification

#### 11.3.1. Stakeholder Register

| ID | Stakeholder | Peran | Organisasi | Kepentingan | Pengaruh | Kategori |
| --- | --- | --- | --- | --- | --- | --- |
| S-001 | Project Sponsor | Pendanaan & Dukungan | FNE Executive | Tinggi | Tinggi | Internal |
| S-002 | Steering Committee | Pengarah Strategis | FNE Management | Tinggi | Tinggi | Internal |
| S-003 | Project Manager | Manajemen Proyek | PMO | Tinggi | Tinggi | Internal |
| S-004 | Product Owner | Representasi Pengguna | Business Unit | Tinggi | Tinggi | Internal |
| S-005 | Technical Lead | Arsitektur Teknis | Engineering | Tinggi | Tinggi | Internal |
| S-006 | Development Team | Implementasi | Engineering | Sedang | Sedang | Internal |
| S-007 | QA Team | Pengujian | Engineering | Sedang | Sedang | Internal |
| S-008 | Farm Manager | Pengguna Akhir | Operasional | Tinggi | Sedang | Internal |
| S-009 | Operational Team | Pengguna Akhir | Operasional | Tinggi | Rendah | Internal |
| S-010 | PMO | Governance | PMO | Sedang | Tinggi | Internal |
| S-011 | Agronomist | Pengguna Ahli | Operasional | Sedang | Sedang | Internal |
| S-012 | Veteriner | Pengguna Ahli | Operasional | Sedang | Rendah | Internal |
| S-013 | P-FNE-01 Team | Foundation Services | Engineering | Tinggi | Tinggi | Internal |
| S-014 | P-FNE-03 Team | Inventory/Supply Chain | Engineering | Sedang | Sedang | Internal |
| S-015 | P-FNE-06 Team | Finance | Engineering | Sedang | Sedang | Internal |
| S-016 | P-FNE-07 Team | Analytics | Engineering | Rendah | Rendah | Internal |
| S-017 | P-FNE-08 Team | Advanced/IoT | Engineering | Rendah | Rendah | Internal |
| S-018 | Vendor (Cloud) | Infrastructure Provider | Eksternal | Rendah | Sedang | Eksternal |

#### 11.3.2. Stakeholder Analysis Matrix

Kekuasaan dan Kepentingan:

text

Kekuasaan

▲

│

H │  S-001   S-002    S-010

│  (Sponsor)(Steering)(PMO)

│

M │  S-003   S-004    S-005   S-013

│  (PM)    (PO)     (Tech)  (P-FNE-01)

│

L │  S-006   S-007    S-008   S-009

│  (Dev)   (QA)     (FM)    (Ops)

│

│         S-011   S-012

│         (Agro)  (Vet)

└───────────────────────────────────►

L        M        H

Kepentingan

Strategi:

- S-001, S-002, S-010: Manage Closely (Libatkan intensif)

- S-003, S-004, S-005, S-013: Keep Satisfied (Jaga kepuasan)

- S-006, S-007, S-008, S-009: Keep Informed (Informasi teratur)

- S-011, S-012, S-014, S-015, S-016, S-017, S-018: Monitor (Pantau secara minimal)

#### 11.3.3. Stakeholder Power/Interest Grid Detail

| Kuadran | Stakeholder | Strategi | Aksi |
| --- | --- | --- | --- |
| Kuadran I: Manage Closely (High Power, High Interest) | S-001 (Sponsor) S-002 (Steering) S-010 (PMO) | • Involve in key decisions • Regular reporting • Executive summaries | Monthly meeting, milestone presentation, budget report |
| Kuadran II: Keep Satisfied (High Power, Low Interest) | S-003 (PM) S-004 (PO) S-005 (Tech Lead) S-013 (P-FNE-01) | • Keep informed • Address concerns • Strategic alignment | Regular sync, technical updates, dependency management |
| Kuadran III: Keep Informed (Low Power, High Interest) | S-006 (Dev) S-007 (QA) S-008 (FM) S-009 (Ops) | • Regular updates • Involve in UAT • Feedback channels | Daily stand-up, sprint review, UAT, workshop |
| Kuadran IV: Monitor (Low Power, Low Interest) | S-011 (Agro) S-012 (Vet) S-014 (P-FNE-03) S-015 (P-FNE-06) S-016 (P-FNE-07) S-017 (P-FNE-08) S-018 (Vendor) | • Minimal effort • Periodic updates • Monitor changes | Technical sync (as needed), email updates |

### 11.4. Stakeholder Engagement Plan

#### 11.4.1. Engagement Strategies

| Stakeholder | Current Engagement | Desired Engagement | Gap | Strategy |
| --- | --- | --- | --- | --- |
| S-001 (Sponsor) | Supportive | Leading | Informed | Libatkan dalam milestone review, monthly presentation |
| S-002 (Steering) | Supportive | Leading | Informed | Presentasi progress, strategic alignment |
| S-003 (PM) | Leading | Leading | None | Continuous management |
| S-004 (PO) | Leading | Leading | None | Sprint ceremonies, prioritization |
| S-005 (Tech Lead) | Leading | Leading | None | Technical decision-making |
| S-006 (Dev) | Supportive | Supportive | None | Daily stand-up, sprint ceremonies |
| S-007 (QA) | Supportive | Supportive | None | Testing, bug reporting |
| S-008 (FM) | Neutral | Supportive | Awareness | UAT, workshop, domain validation |
| S-009 (Ops) | Neutral | Supportive | Awareness | UAT, requirement gathering |
| S-010 (PMO) | Supportive | Leading | Informed | Compliance reporting, governance |
| S-011 (Agronomist) | Neutral | Supportive | Awareness | Domain validation, UAT |
| S-012 (Veteriner) | Neutral | Supportive | Awareness | Domain validation, UAT |
| S-013 (P-FNE-01) | Supportive | Leading | Collaborative | Integration sync, weekly sync |

#### 11.4.2. Engagement Activities

| Stakeholder | Engagement Activity | Frequency | PIC |
| --- | --- | --- | --- |
| S-001 (Sponsor) | Monthly progress presentation | Bulanan | PM |
| S-001 (Sponsor) | Milestone sign-off | Per Milestone | PM |
| S-002 (Steering) | Steering Committee meeting | 2 minggu | PM |
| S-003 (PM) | Daily management | Harian | PM |
| S-004 (PO) | Sprint Planning, Review, Retro | 2 minggu | PO |
| S-005 (Tech Lead) | Technical sync | Mingguan | Tech Lead |
| S-006 (Dev) | Daily stand-up, sprint ceremonies | Harian | Tech Lead |
| S-007 (QA) | QA sync, bug triage | Mingguan | QA Lead |
| S-008 (FM) | UAT, workshop, demo | Per Milestone | BA + PO |
| S-009 (Ops) | Requirement gathering, UAT | Per Milestone | BA |
| S-010 (PMO) | Weekly status report, audit | Mingguan | PM |
| S-011 (Agronomist) | Domain validation, UAT | Per Milestone | BA |
| S-012 (Veteriner) | Domain validation, UAT | Per Milestone | BA |
| S-013 (P-FNE-01) | Integration sync, technical meeting | 2 minggu | Tech Lead |

### 11.5. Stakeholder Communication

#### 11.5.1. Communication by Stakeholder

| Stakeholder | Method | Frequency | Content | Channel |
| --- | --- | --- | --- | --- |
| S-001 (Sponsor) | Presentation | Bulanan | Status, budget, milestone | In-person/Zoom |
| S-002 (Steering) | Meeting | 2 minggu | Progress, decisions | In-person/Zoom |
| S-003 (PM) | Dashboard | Harian | Task progress | Jira/Slack |
| S-004 (PO) | Sprint Review | 2 minggu | Demo, feedback | Zoom |
| S-005 (Tech Lead) | Sync | Mingguan | Architecture, issues | Zoom |
| S-006 (Dev) | Stand-up | Harian | Status, blocker | Slack/Zoom |
| S-007 (QA) | QA Report | Harian | Test results, bugs | Jira |
| S-008 (FM) | Workshop | Per Milestone | UAT, feedback | In-person |
| S-009 (Ops) | Interview | Ad-hoc | Requirements | In-person |
| S-010 (PMO) | Report | Mingguan | Compliance | Email |
| S-011 (Agronomist) | Workshop | Per Milestone | Domain input | In-person |
| S-012 (Veteriner) | Workshop | Per Milestone | Domain input | In-person |
| S-013 (P-FNE-01) | Technical Meeting | 2 minggu | Integration | Zoom |

#### 11.5.2. Escalation Path for Stakeholder Issues

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        STAKEHOLDER ISSUE ESCALATION                         │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Level 1: Project Manager                                                   │

│    └── Issue: Operational / Minor scope / Day-to-day                       │

│    └── Resolution: 1 hari                                                  │

│                                                                             │

│  Level 2: Product Owner + Technical Lead                                   │

│    └── Issue: Major scope / Technical / Resource                           │

│    └── Resolution: 3 hari                                                  │

│                                                                             │

│  Level 3: Steering Committee                                                │

│    └── Issue: Strategic / Budget / Major risk                              │

│    └── Resolution: 1 minggu                                                │

│                                                                             │

│  Level 4: Project Sponsor                                                   │

│    └── Issue: Project viability / Funding / Critical                       │

│    └── Resolution: 2 minggu                                                │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 11.6. Stakeholder Engagement Monitoring

#### 11.6.1. Engagement Metrics

| Metric | Target | Method | Frequency |
| --- | --- | --- | --- |
| Stakeholder Satisfaction | ≥ 80% | Survey | Per Milestone |
| Attendance in Meetings | ≥ 90% | Attendance log | Per Meeting |
| UAT Participation | ≥ 80% | UAT log | Per UAT |
| Feedback Response Time | ≤ 2 hari | Jira/Email | Continuous |
| Issue Resolution Time | ≤ 5 hari | Jira | Continuous |

#### 11.6.2. Stakeholder Satisfaction Survey

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                      STAKEHOLDER SATISFACTION SURVEY                        │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Project: P-FNE-02: Core Agricultural Operations                           │

│  Survey Period: [Date]                                                     │

│                                                                             │

│  Please rate the following (1 = Very Dissatisfied, 5 = Very Satisfied):   │

│                                                                             │

│  1. Communication Quality: [ ] 1  [ ] 2  [ ] 3  [ ] 4  [ ] 5              │

│  2. Project Progress:     [ ] 1  [ ] 2  [ ] 3  [ ] 4  [ ] 5              │

│  3. Requirement Fulfillment: [ ] 1  [ ] 2  [ ] 3  [ ] 4  [ ] 5            │

│  4. Team Responsiveness:  [ ] 1  [ ] 2  [ ] 3  [ ] 4  [ ] 5              │

│  5. Overall Satisfaction: [ ] 1  [ ] 2  [ ] 3  [ ] 4  [ ] 5              │

│                                                                             │

│  What is working well?                                                     │

│  ___________________________________________________________________       │

│                                                                             │

│  What could be improved?                                                   │

│  ___________________________________________________________________       │

│                                                                             │

│  Suggestions:                                                               │

│  ___________________________________________________________________       │

│                                                                             │

│  _________________________                                                  │

│  Stakeholder Name                                                          │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 11.7. Conflict Management

#### 11.7.1. Potential Stakeholder Conflicts

| Conflict | Stakeholder | Root Cause | Resolution Strategy |
| --- | --- | --- | --- |
| Priority Conflict | PO vs Developer | Prioritasi fitur vs technical debt | Collaborative prioritization, data-driven decisions |
| Resource Conflict | PM vs P-FNE-01 | Dependency conflict | Clear dependency management, early communication |
| Scope Conflict | Farm Manager vs PO | Kebutuhan vs capability | Change control process, compromise |
| Timeline Conflict | Sponsor vs PM | Ekspektasi vs realitas | Transparency, re-forecasting |
| Technical Conflict | Tech Lead vs Developer | Arsitektur vs implementation | Code review, design discussion |

#### 11.7.2. Conflict Resolution Techniques

| Technique | Description | When to Use |
| --- | --- | --- |
| Collaborating | Win-Win solution | Complex issues, important to both parties |
| Compromising | Each gives something | Both parties have equal power |
| Accommodating | One party yields | Other party has higher priority |
| Avoiding | Postpone issue | Minor issues, emotional situations |
| Forcing | One party decides | Urgent decisions, safety issues |

### 11.8. Stakeholder Management Plan Approval

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    STAKEHOLDER MANAGEMENT PLAN APPROVAL                     │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Nama Proyek: P-FNE-02: Core Agricultural Operations                       │

│  Total Stakeholder: 18                                                     │

│  Stakeholder yang Dikelola Intensif: 5                                     │

│                                                                             │

│  Saya menyetujui Stakeholder Management Plan ini dan akan menjadi         │

│  baseline untuk manajemen pemangku kepentingan proyek.                    │

│                                                                             │

│  Tanggal: __________________                                               │

│                                                                             │

│  ___________________________                                                │

│  Project Manager                                                            │

│                                                                             │

│  ___________________________                                                │

│  Product Owner                                                              │

│                                                                             │

│  ___________________________                                                │

│  Project Sponsor                                                            │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 12: LAMPIRAN

### 12.1. Daftar Singkatan dan Istilah

| Singkatan | Kepanjangan | Deskripsi |
| --- | --- | --- |
| ABC | Activity Based Costing | Metode estimasi biaya berdasarkan aktivitas |
| AC | Actual Cost | Biaya aktual yang dikeluarkan |
| API | Application Programming Interface | Antarmuka pemrograman aplikasi |
| BA | Business Analyst | Analis bisnis |
| BAC | Budget at Completion | Anggaran total proyek |
| BE | Backend Engineer | Pengembang backend |
| BFF | Backend for Frontend | Lapisan backend untuk frontend |
| BOM | Bill of Materials | Daftar bahan baku |
| BRD | Business Requirement Document | Dokumen kebutuhan bisnis |
| CCB | Change Control Board | Komite pengendali perubahan |
| CI/CD | Continuous Integration / Continuous Deployment | Integrasi dan deployment berkelanjutan |
| CPI | Cost Performance Index | Indeks kinerja biaya |
| CRM | Customer Relationship Management | Manajemen hubungan pelanggan |
| DDL | Data Definition Language | Bahasa definisi data |
| DoD | Definition of Done | Definisi selesai |
| DoR | Definition of Ready | Definisi siap |
| E2E | End-to-End | Ujung ke ujung |
| EAC | Estimate at Completion | Estimasi biaya akhir |
| ERD | Entity Relationship Diagram | Diagram hubungan entitas |
| ETC | Estimate to Complete | Estimasi biaya hingga selesai |
| EV | Earned Value | Nilai yang diperoleh |
| EVM | Earned Value Management | Manajemen nilai yang diperoleh |
| FE | Frontend Engineer | Pengembang frontend |
| FNE | Farm Nation Enterprise | Nama platform ERP |
| FTE | Full Time Equivalent | Setara pekerja penuh waktu |
| FRD | Functional Requirement Document | Dokumen kebutuhan fungsional |
| GDPR | General Data Protection Regulation | Regulasi perlindungan data |
| GIS | Geographic Information System | Sistem informasi geografis |
| gRPC | gRPC Remote Procedure Call | Protokol komunikasi antar service |
| HCM | Human Capital Management | Manajemen modal manusia |
| IAM | Identity and Access Management | Manajemen identitas dan akses |
| IoT | Internet of Things | Internet untuk segala |
| JWT | JSON Web Token | Token autentikasi |
| K8s | Kubernetes | Orkestrasi container |
| KLOC | Kilo Lines of Code | Ribuan baris kode |
| KPI | Key Performance Indicator | Indikator kinerja utama |
| NFR | Non-Functional Requirement | Kebutuhan non-fungsional |
| NPS | Net Promoter Score | Skor promosi bersih |
| P0/P1/P2 | Priority Level | Tingkat prioritas (0 = Tertinggi) |
| PDM | Precedence Diagramming Method | Metode diagram preseden |
| PM | Project Manager | Manajer proyek |
| PMBOK | Project Management Body of Knowledge | Standar manajemen proyek |
| PMO | Project Management Office | Kantor manajemen proyek |
| PMP | Project Management Plan | Rencana manajemen proyek |
| PO | Product Owner | Pemilik produk |
| PV | Planned Value | Nilai yang direncanakan |
| QA | Quality Assurance | Jaminan kualitas |
| RACI | Responsible, Accountable, Consulted, Informed | Matriks tanggung jawab |
| RBS | Resource Breakdown Structure | Struktur rincian sumber daya |
| RBAC | Role-Based Access Control | Kontrol akses berbasis peran |
| REST | Representational State Transfer | Arsitektur API |
| RFI | Request for Information | Permintaan informasi |
| RFP | Request for Proposal | Permintaan proposal |
| RFQ | Request for Quotation | Permintaan penawaran harga |
| RTM | Requirement Traceability Matrix | Matriks ketertelusuran kebutuhan |
| SC | Steering Committee | Komite pengarah |
| SLA | Service Level Agreement | Perjanjian tingkat layanan |
| SPI | Schedule Performance Index | Indeks kinerja jadwal |
| SSOT | Single Source of Truth | Sumber kebenaran tunggal |
| UAT | User Acceptance Testing | Pengujian penerimaan pengguna |
| UI | User Interface | Antarmuka pengguna |
| UX | User Experience | Pengalaman pengguna |
| WBS | Work Breakdown Structure | Struktur rincian pekerjaan |

### 12.2. Dokumen Pendukung

#### 12.2.1. Daftar Dokumen Terkait

| No | Nama Dokumen | Deskripsi | Lokasi | Versi |
| --- | --- | --- | --- | --- |
| 1 | Project Charter | Mandat proyek | Confluence | 1.0 |
| 2 | Business Requirement Document (BRD) | Kebutuhan bisnis FNE | Confluence | 1.0 |
| 3 | Functional Requirement Document (FRD) | Kebutuhan fungsional P-FNE-02 | Confluence | 1.0 |
| 4 | Technical Architecture Document | Arsitektur teknis FNE | Confluence | 1.0 |
| 5 | Database Design Document | Desain database P-FNE-02 | Confluence | 1.0 |
| 6 | API Specification | Spesifikasi API | Confluence/Swagger | 1.0 |
| 7 | Test Plan | Rencana pengujian | Confluence | 1.0 |
| 8 | Deployment Plan | Rencana deployment | Confluence | 1.0 |
| 9 | User Manual | Manual penggunaan | Confluence | 1.0 |
| 10 | Training Material | Materi pelatihan | Confluence | 1.0 |

#### 12.2.2. Template Dokumen

| No | Template | Deskripsi | Format |
| --- | --- | --- | --- |
| 1 | Change Request Form | Form permintaan perubahan | DOCX |
| 2 | Weekly Status Report | Template laporan mingguan | DOCX/PPTX |
| 3 | Meeting Minutes | Notulen rapat | DOCX |
| 4 | Risk Register | Registrasi risiko | XLSX |
| 5 | UAT Sign-off Form | Form persetujuan UAT | DOCX |
| 6 | Project Closure Report | Laporan penutupan proyek | DOCX |
| 7 | Lessons Learned | Dokumentasi pembelajaran | DOCX |

### 12.3. Project Calendar

#### 12.3.1. Calender 2026-2027

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                            PROJECT CALENDAR                                 │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  September 2026                                                            │

│  ┌──────────────────────────────────────────────────────────────────┐      │

│  │ Sen  Sel  Rab  Kam  Jum  Sab  Min  │ │                           │      │

│  │      1    2    3    4    5    6    │ │ Start Project             │      │

│  │  7    8    9   10   11   12   13   │ │ Kick-off: 2 Sep           │      │

│  │ 14   15   16   17   18   19   20   │ │                           │      │

│  │ 21   22   23   24   25   26   27   │ │                           │      │

│  │ 28   29   30                       │ │                           │      │

│  └──────────────────────────────────────────────────────────────────┘      │

│                                                                             │

│  Oktober 2026                                                              │

│  ┌──────────────────────────────────────────────────────────────────┐      │

│  │ Sen  Sel  Rab  Kam  Jum  Sab  Min  │ │                           │      │

│  │                   1    2    3    4  │ │ M2: Foundation (30 Sep)   │      │

│  │  5    6    7    8    9   10   11   │ │                           │      │

│  │ 12   13   14   15   16   17   18   │ │                           │      │

│  │ 19   20   21   22   23   24   25   │ │ M3: Farm & Land (21 Oct)  │      │

│  │ 26   27   28   29   30   31        │ │                           │      │

│  └──────────────────────────────────────────────────────────────────┘      │

│                                                                             │

│  November 2026                                                             │

│  ┌──────────────────────────────────────────────────────────────────┐      │

│  │ Sen  Sel  Rab  Kam  Jum  Sab  Min  │ │                           │      │

│  │                        1    2    3  │ │                           │      │

│  │  4    5    6    7    8    9   10   │ │                           │      │

│  │ 11   12   13   14   15   16   17   │ │                           │      │

│  │ 18   19   20   21   22   23   24   │ │ M4: Crop (18 Nov)         │      │

│  │ 25   26   27   28   29   30        │ │                           │      │

│  └──────────────────────────────────────────────────────────────────┘      │

│                                                                             │

│  Desember 2026                                                             │

│  ┌──────────────────────────────────────────────────────────────────┐      │

│  │ Sen  Sel  Rab  Kam  Jum  Sab  Min  │ │                           │      │

│  │            1    2    3    4    5   │ │                           │      │

│  │  6    7    8    9   10   11   12   │ │                           │      │

│  │ 13   14   15   16   17   18   19   │ │                           │      │

│  │ 20   21   22   23   24   25   26   │ │ Natal: 25 Des             │      │

│  │ 27   28   29   30   31             │ │ M5: Livestock (9 Des)     │      │

│  └──────────────────────────────────────────────────────────────────┘      │

│                                                                             │

│  Januari 2027                                                              │

│  ┌──────────────────────────────────────────────────────────────────┐      │

│  │ Sen  Sel  Rab  Kam  Jum  Sab  Min  │ │                           │      │

│  │                   1    2    3    4  │ │ Tahun Baru: 1 Jan         │      │

│  │  5    6    7    8    9   10   11   │ │                           │      │

│  │ 12   13   14   15   16   17   18   │ │                           │      │

│  │ 19   20   21   22   23   24   25   │ │                           │      │

│  │ 26   27   28   29   30   31        │ │ M7: Integration (13 Jan)  │      │

│  └──────────────────────────────────────────────────────────────────┘      │

│                                                                             │

│  Februari 2027                                                             │

│  ┌──────────────────────────────────────────────────────────────────┐      │

│  │ Sen  Sel  Rab  Kam  Jum  Sab  Min  │ │                           │      │

│  │      1    2    3    4    5    6    │ │                           │      │

│  │  7    8    9   10   11   12   13   │ │                           │      │

│  │ 14   15   16   17   18   19   20   │ │ M8: UAT (27 Jan)          │      │

│  │ 21   22   23   24   25   26   27   │ │ M9: Go-Live (3 Feb)       │      │

│  │ 28                                  │ │ M10: Closure (10 Feb)     │      │

│  └──────────────────────────────────────────────────────────────────┘      │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

#### 12.3.2. Holiday Calendar

| Tanggal | Hari Libur | Dampak | Keterangan |
| --- | --- | --- | --- |
| 16 September 2026 | Maulid Nabi Muhammad SAW | -1 hari kerja | Libur nasional |
| 25 Desember 2026 | Hari Natal | -1 hari kerja | Libur nasional |
| 1 Januari 2027 | Tahun Baru Masehi | -1 hari kerja | Libur nasional |
| 14 Februari 2027 | Hari Valentine | - | Tidak ada libur |

### 12.4. Budget Detail

#### 12.4.1. Biaya Personil per Bulan

| Peran | Bulan 1 | Bulan 2 | Bulan 3 | Bulan 4 | Bulan 5 | Bulan 6 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PM | 61.600.000 | 61.600.000 | 61.600.000 | 61.600.000 | 61.600.000 | 61.600.000 | 369.600.000 |
| PO | 28.600.000 | 45.760.000 | 45.760.000 | 45.760.000 | 34.320.000 | 22.880.000 | 223.080.000 |
| Tech Lead | 28.600.000 | 57.200.000 | 57.200.000 | 57.200.000 | 45.760.000 | 34.320.000 | 280.280.000 |
| BA | 35.200.000 | 28.160.000 | 21.120.000 | 21.120.000 | 14.080.000 | 7.040.000 | 126.720.000 |
| Backend (4) | 79.200.000 | 118.800.000 | 118.800.000 | 118.800.000 | 79.200.000 | 79.200.000 | 594.000.000 |
| Frontend (2) | 35.200.000 | 70.400.000 | 70.400.000 | 70.400.000 | 35.200.000 | 35.200.000 | 316.800.000 |
| Mobile (1) | 0 | 0 | 17.600.000 | 35.200.000 | 35.200.000 | 17.600.000 | 105.600.000 |
| QA (2) | 30.800.000 | 30.800.000 | 30.800.000 | 30.800.000 | 61.600.000 | 61.600.000 | 246.400.000 |
| DevOps | 39.600.000 | 19.800.000 | 19.800.000 | 19.800.000 | 39.600.000 | 39.600.000 | 178.200.000 |
| Total | 338.800.000 | 432.520.000 | 443.080.000 | 460.680.000 | 406.560.000 | 359.040.000 | 2.440.680.000 |

#### 12.4.2. Rincian Biaya Langsung

| Kategori | Item | Biaya (Rp) | Bulan 1 | Bulan 2 | Bulan 3 | Bulan 4 | Bulan 5 | Bulan 6 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Infrastruktur | Cloud Services | 120.000.000 | 20.000.000 | 20.000.000 | 20.000.000 | 20.000.000 | 20.000.000 | 20.000.000 |
|  | Database Services | 30.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 |
|  | CDN & Storage | 15.000.000 | 2.500.000 | 2.500.000 | 2.500.000 | 2.500.000 | 2.500.000 | 2.500.000 |
| Software | IDE Licenses | 15.000.000 | 15.000.000 | 0 | 0 | 0 | 0 | 0 |
|  | Jira/Confluence | 12.000.000 | 12.000.000 | 0 | 0 | 0 | 0 | 0 |
|  | Monitoring Tools | 8.000.000 | 8.000.000 | 0 | 0 | 0 | 0 | 0 |
|  | Testing Tools | 5.000.000 | 5.000.000 | 0 | 0 | 0 | 0 | 0 |
|  | Design Tools | 6.000.000 | 6.000.000 | 0 | 0 | 0 | 0 | 0 |
| Operasional | Travel & Akomodasi | 30.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 5.000.000 |
|  | Pelatihan | 20.000.000 | 0 | 10.000.000 | 10.000.000 | 0 | 0 | 0 |
|  | Communication Tools | 6.000.000 | 6.000.000 | 0 | 0 | 0 | 0 | 0 |
|  | Hardware Support | 15.000.000 | 0 | 0 | 0 | 15.000.000 | 0 | 0 |
| Total |  | 282.000.000 | 84.500.000 | 42.500.000 | 42.500.000 | 47.500.000 | 32.500.000 | 32.500.000 |

### 12.5. Risk Register Complete

| ID | Kategori | Risiko | Penyebab | Dampak | Prob | Impact | Score | Strategi | Respons | PIC | Status | Tanggal |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Manajemen | Keterlambatan P-FNE-01 | P-FNE-01 belum siap | Blocking development | 4 | 5 | 20 | Mitigasi | Sinkronisasi intensif, parallel dev | PM | Active | Continuous |
| R-002 | Manajemen | Perubahan requirement signifikan | Stakeholder request | Rework dan delay | 3 | 4 | 12 | Mitigasi | Change control strict | PO | Active | Continuous |
| R-003 | Organisasi | Turnover tim kunci | Kesempatan karir lain | Knowledge loss | 2 | 4 | 8 | Mitigasi | Cross-training, dokumentasi | PM+HR | Active | Continuous |
| R-004 | Teknis | Integrasi event-driven gagal | Kafka config error | Integration failure | 2 | 5 | 10 | Mitigasi | Kafka POC, fallback mechanism | Tech Lead | Closed | M8 |
| R-005 | Teknis | Database performance issue | Indexing tidak optimal | Response time > 3 detik | 3 | 4 | 12 | Mitigasi | Indexing, caching, optimization | Tech Lead | Active | M6 |
| R-006 | Eksternal | User tidak tersedia UAT | Kesibukan operasional | UAT tertunda | 3 | 3 | 9 | Mitigasi | Schedule UAT early | BA+PM | Active | M16 |
| R-007 | Eksternal | Cloud infrastructure issue | Cloud provider outage | Downtime | 2 | 4 | 8 | Mitigasi | Multi-region, monitoring | DevOps | Active | Continuous |
| R-008 | Eksternal | Perubahan regulasi pertanian | Kebijakan pemerintah | Perubahan requirement | 2 | 3 | 6 | Acceptance | Monitor regulasi, buffer | BA+PM | Active | Continuous |
| R-009 | Domain | Kompleksitas data pertanian | Domain knowledge kurang | Rework, akurasi rendah | 3 | 3 | 9 | Mitigasi | Domain expert involvement | BA+PO | Active | Continuous |
| R-010 | Teknis | Mobile offline sync failure | Conflict resolution | Data tidak sinkron | 3 | 3 | 9 | Mitigasi | Comprehensive testing | Mobile Lead | Active | M14 |

### 12.6. Quality Metrics Detail

| Metric | Target | Measurement Method | Frequency | PIC | Current Status |
| --- | --- | --- | --- | --- | --- |
| Code Coverage | ≥ 80% | SonarQube | Per Sprint | QA Lead | - |
| Code Complexity | ≤ 15 | SonarQube | Per Sprint | Tech Lead | - |
| Bug Density | ≤ 1 per KLOC | QA Report | Per Sprint | QA Lead | - |
| Defect Leakage | ≤ 5% | QA Report | Per Release | QA Lead | - |
| Response Time | ≤ 3 detik | Performance Test | Per Milestone | QA Lead | - |
| Uptime | ≥ 99.5% | Monitoring | Continuous | DevOps | - |
| UAT Acceptance | ≥ 95% | UAT Sign-off | Per Milestone | PO/BA | - |
| User Satisfaction | NPS ≥ 70 | Survey | End Project | PM/BA | - |
| Sprint Velocity | ≥ 30 story points | Sprint Review | 2 minggu | PM | - |
| Test Pass Rate | ≥ 95% | QA Report | Per Sprint | QA Lead | - |
| CI/CD Success Rate | ≥ 95% | CI/CD Pipeline | Continuous | DevOps | - |

### 12.7. Communication Matrix Complete

| Stakeholder | Informasi | Metode | Frekuensi | Penyedia | Format | Channel |
| --- | --- | --- | --- | --- | --- | --- |
| S-001 (Sponsor) | Status proyek, budget, milestone | Presentasi | Bulanan | PM | PPT/PDF | In-person/Zoom |
| S-002 (Steering) | Progress, keputusan, isu strategis | Meeting | 2 minggu | PM | PPT/PDF | In-person/Zoom |
| S-003 (PM) | Task progress, blocker | Dashboard | Harian | PM | Jira/Slack | Slack |
| S-004 (PO) | Sprint progress, backlog | Sprint Review | 2 minggu | PO+PM | Jira | Zoom |
| S-005 (Tech Lead) | Arsitektur, technical issues | Sync | Mingguan | Tech Lead | Slack | Zoom |
| S-006 (Dev) | Task daily, blocker | Stand-up | Harian | Tech Lead | Slack/Zoom | Slack/Zoom |
| S-007 (QA) | Test progress, bug reports | Report | Harian | QA Lead | Jira/Email | Jira |
| S-008 (FM) | UAT, feedback, workshop | Workshop | Per Milestone | BA+PO | In-person | In-person |
| S-009 (Ops) | Requirement, feedback | Interview | Ad-hoc | BA | In-person | In-person |
| S-010 (PMO) | Status, compliance, dokumentasi | Dashboard | Mingguan | PM | Online | Dashboard |
| S-011 (Agronomist) | Domain input, UAT | Workshop | Per Milestone | BA | In-person | In-person |
| S-012 (Veteriner) | Domain input, UAT | Workshop | Per Milestone | BA | In-person | In-person |
| S-013 (P-FNE-01) | Integration status, API | Technical Meeting | 2 minggu | Tech Lead | Online | Zoom |
| S-014 (P-FNE-03) | Inventory integration | Technical Meeting | 2 minggu | Tech Lead | Online | Zoom |
| S-015 (P-FNE-06) | Finance integration | Technical Meeting | 2 minggu | Tech Lead | Online | Zoom |
| S-016 (P-FNE-07) | Data pipeline | Technical Meeting | 2 minggu | Tech Lead | Online | Zoom |

### 12.8. Approval Sign-off

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                          APPROVAL SIGN-OFF                                  │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                             │

│  Dokumen: Project Management Plan (PMP)                                    │

│  Proyek: P-FNE-02: Core Agricultural Operations                            │

│  Versi: 1.0                                                                 │

│  Tanggal: 3 September 2026                                                  │

│                                                                             │

│  Dengan menandatangani dokumen ini, kami menyetujui Project Management     │

│  Plan ini dan akan menjadi baseline untuk pengelolaan proyek.             │

│                                                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│                                                                             │

│  Project Manager                                                           │

│  Nama: ___________________                                                 │

│  Tanda Tangan: ______________                                              │

│  Tanggal: __________________                                               │

│                                                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│                                                                             │

│  Product Owner                                                             │

│  Nama: ___________________                                                 │

│  Tanda Tangan: ______________                                              │

│  Tanggal: __________________                                               │

│                                                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│                                                                             │

│  Technical Lead                                                            │

│  Nama: ___________________                                                 │

│  Tanda Tangan: ______________                                              │

│  Tanggal: __________________                                               │

│                                                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│                                                                             │

│  Project Sponsor                                                           │

│  Nama: ___________________                                                 │

│  Tanda Tangan: ______________                                              │

│  Tanggal: __________________                                               │

│                                                                             │

│  ───────────────────────────────────────────────────────────────────────── │

│                                                                             │

│  PMO Representative                                                        │

│  Nama: ___________________                                                 │

│  Tanda Tangan: ______________                                              │

│  Tanggal: __________________                                               │

│                                                                             │

└─────────────────────────────────────────────────────────────────────────────┘

### 12.9. Daftar Revisi

| Versi | Tanggal | Perubahan | Penyusun | Penyetuju |
| --- | --- | --- | --- | --- |
| 0.1 | 01/09/2026 | Draft awal | PMO | - |
| 0.5 | 02/09/2026 | Review internal, penambahan detail | PMO | PM |
| 1.0 | 03/09/2026 | Final setelah review stakeholder | PMO | Sponsor |

### 12.10. Penutup

Dokumen Project Management Plan (PMP) untuk Proyek P-FNE-02: Core Agricultural Operations ini telah disusun secara komprehensif mencakup 10 area manajemen sesuai dengan standar PMBOK:

- Manajemen Integrasi – Mengkoordinasikan seluruh elemen proyek

- Manajemen Lingkup – Mendefinisikan dan mengontrol lingkup proyek

- Manajemen Penjadwalan – Memastikan proyek selesai tepat waktu

- Manajemen Biaya – Mengelola anggaran proyek

- Manajemen Kualitas – Menjamin kualitas deliverable

- Manajemen Sumber Daya – Mengelola tim proyek

- Manajemen Komunikasi – Memastikan komunikasi efektif

- Manajemen Risiko – Mengidentifikasi dan mengelola risiko

- Manajemen Pengadaan – Mengelola pengadaan barang dan jasa

- Manajemen Pemangku Kepentingan – Mengelola stakeholder

Dokumen ini akan menjadi panduan utama bagi seluruh tim proyek dalam menjalankan proyek P-FNE-02. Seluruh perubahan terhadap dokumen ini harus melalui proses change control yang telah ditetapkan.

"Core Agricultural Operations – Membangun Fondasi Digital untuk Pertanian Modern"