# PROJECT MANAGEMENT PLAN (PMP) - DETAIL PER BAB

## Proyek Foundation & Core Platform (P-FNE-01)

### Super ERP Farm Nation Enterprise (FNE)

# BAB 1: PENDAHULUAN (INTRODUCTION)

## 1.1 TUJUAN DOKUMEN

Dokumen Project Management Plan (PMP) ini bertujuan untuk:

- Menyediakan panduan komprehensif bagi seluruh tim proyek dalam melaksanakan, memantau, dan mengendalikan Proyek Foundation & Core Platform (P-FNE-01).

- Mendefinisikan secara jelas ruang lingkup, jadwal, biaya, kualitas, sumber daya, komunikasi, risiko, pengadaan, dan keterlibatan stakeholder.

- Menjadi acuan resmi bagi seluruh pihak yang terlibat dalam proyek, termasuk tim internal, vendor, dan stakeholder.

- Memastikan keselarasan antara pelaksanaan proyek dengan tujuan strategis organisasi.

- Memberikan mekanisme pengendalian dan pengambilan keputusan yang terstruktur.

- Memenuhi standar manajemen proyek sesuai dengan PMBOK (Project Management Body of Knowledge) dan best practices industri.

Dokumen ini bersifat living document yang akan diperbarui secara berkala sesuai dengan perkembangan proyek, dengan tetap melalui proses perubahan yang telah ditetapkan.

## 1.2 GAMBARAN PROYEK

### 1.2.1 Latar Belakang

Super ERP Farm Nation Enterprise (FNE) adalah ekosistem digital terintegrasi yang terdiri dari 8 (delapan) proyek turunan yang saling terkait:

| Kode Proyek | Nama Proyek |
| --- | --- |
| P-FNE-01 | Foundation & Core Platform |
| P-FNE-02 | Core Agricultural Operations |
| P-FNE-03 | Supply Chain & Procurement |
| P-FNE-04 | Production & Manufacturing |
| P-FNE-05 | Commerce, Sales & Logistics |
| P-FNE-06 | Enterprise Finance & HCM |
| P-FNE-07 | Intelligence & Decision Platform |
| P-FNE-08 | Advanced & Autonomous Enterprise |

Proyek P-FNE-01: Foundation & Core Platform merupakan fondasi dari seluruh ekosistem. Tanpa proyek ini, proyek-proyek lain tidak dapat beroperasi karena tidak memiliki platform yang aman, terintegrasi, dan memiliki sumber data yang konsisten.

### 1.2.2 Deskripsi Singkat Proyek

Proyek P-FNE-01 bertujuan membangun infrastruktur teknologi, keamanan, dan data master yang akan menjadi tulang punggung bagi semua proyek berikutnya. Proyek ini mencakup:

| Komponen | Deskripsi |
| --- | --- |
| Infrastructure & DevOps | Environment provisioning, container orchestration (Kubernetes), CI/CD pipeline, monitoring, logging, backup & DR, secrets management |
| Identity & Access Management (IAM) | User registration, authentication (SSO/MFA), authorization (RBAC), role & permission management, session management |
| Master Data Management (MDM) | 24 entitas master data (Company, Product, Supplier, Customer, Farm, Crop, dll.) dengan CRUD, import/export, versioning, duplicate detection |
| Audit & Logging | Audit trail untuk semua transaksi, akses, dan perubahan master data, query & export, retention management |
| API Gateway & Integration | API Gateway sebagai entry point tunggal, routing, rate limiting, authentication, versioning, documentation |
| Event Bus & Messaging | Kafka untuk komunikasi asynchronous, event publisher & subscriber, dead letter queue, event monitoring |
| Workflow Engine | Definisi workflow, execution, approval matrix, task management, escalation, monitoring |
| Notification Service | Multi-channel notification (email, SMS, push, in-app), template management, user preferences, history |

### 1.2.3 Data Proyek

| Atribut | Detail |
| --- | --- |
| Nama Proyek | Foundation & Core Platform (P-FNE-01) |
| Project ID | P-FNE-01 |
| Program | Super ERP Farm Nation Enterprise (FNE) |
| Tipe Proyek | Pengembangan Sistem Baru (Greenfield) |
| Metodologi | Agile (Scrum) dengan pendekatan incremental |
| Tim Pengerjaan | 10-15 orang (DevOps, Backend, Frontend, Security, QA) |
| Durasi Estimasi | 5 bulan (20 minggu) |
| Anggaran Estimasi | Rp 4.600.000.000,- (IDR) |
| Tanggal Mulai | Oktober 2026 |
| Tanggal Selesai | Maret 2027 |
| Project Sponsor | VP of Technology |
| Project Manager | [Nama PM] |

## 1.3 VISI DAN MISI PROYEK

### 1.3.1 Visi Proyek

"Membangun fondasi digital yang aman, terintegrasi, dan skalabel untuk mendukung ekosistem Super ERP Farm Nation Enterprise sebagai sistem operasi perusahaan pertanian terkemuka di Indonesia."

### 1.3.2 Misi Proyek

- Menyediakan platform infrastruktur yang reliable, scalable, dan cost-effective untuk mendukung seluruh aplikasi dalam ekosistem FNE.

- Membangun sistem identitas dan manajemen akses terpusat yang menjamin keamanan data dan kepatuhan terhadap regulasi.

- Menyediakan Single Source of Truth (SSOT) untuk seluruh data master enterprise dengan kualitas data yang tinggi.

- Menyediakan mekanisme audit dan logging yang komprehensif untuk memenuhi kebutuhan kepatuhan dan investigasi.

- Membangun fondasi integrasi yang memungkinkan komunikasi antar layanan berjalan dengan aman dan efisien.

- Menyediakan workflow engine yang fleksibel untuk mengotomatisasi proses bisnis.

- Menyediakan sistem notifikasi multi-channel untuk memastikan informasi tersampaikan dengan cepat dan tepat.

### 1.3.3 Tujuan Proyek (SMART)

| No | Tujuan | Target | Metrik | Timeline |
| --- | --- | --- | --- | --- |
| 1 | Membangun infrastruktur cloud-native | 100% environment tersedia | Environment count: 4 (Dev, Test, Staging, Prod) | M1-M2 |
| 2 | Implementasi IAM | 100% fitur IAM berfungsi | User dapat login, MFA, RBAC | M1-M6 |
| 3 | Implementasi MDM | 24 entitas master data | All entities can CRUD | M1-M10 |
| 4 | Implementasi Audit | 100% transaksi tercatat | Audit log capture all actions | M1-M12 |
| 5 | Implementasi Workflow | Minimal 3 workflow | 3 workflows running | M1-M14 |
| 6 | Integrasi penuh | 100% integration complete | All services communicate | M1-M16 |
| 7 | Quality & Security | Zero critical vulnerability | Security scan passed | M1-M18 |
| 8 | Go-Live | 100% production ready | System live, DR tested | M1-M20 |

## 1.4 ALIGNMENT DENGAN STRATEGI PERUSAHAAN

### 1.4.1 Keterkaitan dengan Visi Perusahaan

Proyek P-FNE-01 mendukung visi perusahaan untuk menjadi perusahaan agrikultur terintegrasi berbasis teknologi melalui:

| Pilar Strategis | Kontribusi Proyek |
| --- | --- |
| Digitalisasi Operasional | Menyediakan fondasi digital yang memungkinkan otomatisasi proses bisnis di seluruh lini |
| Data-Driven Decision Making | Menyediakan SSOT dan audit trail untuk mendukung analisis data dan pengambilan keputusan |
| Keamanan & Kepatuhan | Memastikan seluruh data enterprise terlindungi dan sesuai dengan regulasi |
| Efisiensi & Skalabilitas | Menyediakan infrastruktur yang scalable untuk mendukung pertumbuhan bisnis |
| Inovasi | Mendukung implementasi AI, IoT, dan Digital Twin di proyek-proyek selanjutnya |

### 1.4.2 Keterkaitan dengan Roadmap Transformasi Digital

Proyek P-FNE-01 merupakan fase pertama dari roadmap transformasi digital Super ERP FNE:

text

┌─────────────────────────────────────────────────────────────────────────┐

│                ROADMAP TRANSFORMASI DIGITAL FNE                        │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  FASE 1: FONDASI (P-FNE-01)                     [OKTOBER 2026 - MARET 2027] │

│  ┌─────────────────────────────────────────────┐                        │

│  │ • Infrastructure & DevOps                   │                        │

│  │ • Identity & Access Management (IAM)       │                        │

│  │ • Master Data Management (MDM)             │                        │

│  │ • Audit & Logging                          │                        │

│  │ • API Gateway & Integration               │                        │

│  │ • Event Bus & Messaging                   │                        │

│  │ • Workflow Engine                         │                        │

│  │ • Notification Service                    │                        │

│  └─────────────────────────────────────────────┘                        │

│                              │                                          │

│                              ▼                                          │

│  FASE 2: OPERASIONAL CORE (P-FNE-02, 03, 04)  [APRIL - AGUSTUS 2027]   │

│  ┌─────────────────────────────────────────────┐                        │

│  │ • Agricultural Operations                  │                        │

│  │ • Supply Chain & Procurement               │                        │

│  │ • Production & Manufacturing               │                        │

│  └─────────────────────────────────────────────┘                        │

│                              │                                          │

│                              ▼                                          │

│  FASE 3: COMMERCE & FINANCE (P-FNE-05, 06)     [SEPTEMBER - DESEMBER 2027] │

│  ┌─────────────────────────────────────────────┐                        │

│  │ • Commerce, Sales & Logistics              │                        │

│  │ • Enterprise Finance & HCM                 │                        │

│  └─────────────────────────────────────────────┘                        │

│                              │                                          │

│                              ▼                                          │

│  FASE 4: INTELLIGENCE & ADVANCED (P-FNE-07, 08) [JANUARI - APRIL 2028] │

│  ┌─────────────────────────────────────────────┐                        │

│  │ • Intelligence & Decision Platform         │                        │

│  │ • Advanced & Autonomous Enterprise         │                        │

│  └─────────────────────────────────────────────┘                        │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 1.4.3 Business Case

| Aspek | Kuantifikasi |
| --- | --- |
| Efisiensi Operasional | Mengurangi biaya operasional IT hingga 30% melalui standardisasi dan otomatisasi |
| Keamanan Data | Mengurangi risiko kehilangan data dan kebocoran data hingga 80% |
| Kecepatan Pengembangan | Mempercepat pengembangan proyek turunan hingga 40% dengan fondasi yang sudah tersedia |
| Kepatuhan | Memastikan kepatuhan terhadap regulasi (ISO 27001, GDPR, dll.) |
| ROI | Diperkirakan mencapai 150% dalam 3 tahun |
| Time-to-Market | Mempercepat time-to-market fitur baru hingga 50% |

## 1.5 ASUMSI DAN KENDALA

### 1.5.1 Asumsi Proyek

| No | Asumsi | Dampak jika Tidak Terpenuhi |
| --- | --- | --- |
| A-01 | Tim proyek tersedia sesuai dengan yang direncanakan | Keterlambatan jadwal, penurunan kualitas |
| A-02 | Anggaran proyek disetujui dan tersedia sesuai rencana | Pengurangan ruang lingkup atau kualitas |
| A-03 | Spesifikasi requirement stabil selama fase pengembangan | Scope creep, keterlambatan, biaya tambahan |
| A-04 | Infrastruktur cloud tersedia dan dapat diakses | Gangguan pengembangan dan testing |
| A-05 | Integrasi dengan sistem legacy dapat dilakukan dengan API yang tersedia | Pengembangan connector tambahan, keterlambatan |
| A-06 | Vendor third-party (SMTP, SMS, dll.) menyediakan service yang reliable | Gangguan layanan notifikasi |
| A-07 | Security assessment dapat dilakukan tepat waktu | Keterlambatan Go-Live |
| A-08 | User acceptance testing (UAT) dapat dilakukan sesuai jadwal | Keterlambatan Go-Live |
| A-09 | Data master yang dibutuhkan tersedia dan dapat dimigrasi | Keterlambatan MDM |
| A-10 | Semua stakeholder memberikan dukungan penuh | Resistensi, keterlambatan pengambilan keputusan |

### 1.5.2 Kendala Proyek

| No | Kendala | Dampak | Mitigasi |
| --- | --- | --- | --- |
| K-01 | Durasi proyek maksimal 5 bulan | Tekanan pada tim, potensi burnout | Agile delivery, prioritisasi fitur |
| K-02 | Anggaran terbatas | Tidak bisa menambah sumber daya | Efisiensi, penggunaan open source |
| K-03 | Ketersediaan sumber daya terbatas | Tidak bisa hire semua sekaligus | Rekrutmen bertahap, kontraktor |
| K-04 | Integrasi dengan 7 proyek lain | Kompleksitas tinggi | API-first design, contract testing |
| K-05 | Regulasi keamanan yang ketat | Biaya dan waktu compliance | Security by design, early involvement |
| K-06 | Infrastruktur cloud dengan spesifikasi tertentu | Terbatas pada provider tertentu | Cloud-agnostic design |
| K-07 | Tim tersebar di beberapa lokasi | Komunikasi yang tidak efektif | Daily stand-up, collaboration tools |

### 1.5.3 Ketergantungan (Dependencies)

| No | Ketergantungan | Deskripsi | Mitigasi |
| --- | --- | --- | --- |
| D-01 | Layanan Cloud | Perlu subscription cloud aktif | Proses procurement dimulai sejak awal |
| D-02 | Hardware/Device | Perlu perangkat untuk tim | Pengadaan dilakukan parallel |
| D-03 | Data Master | Perlu data master dari user | Data preparation dimulai H-1 |
| D-04 | API Legacy | Perlu API dari sistem legacy | Early engagement dengan tim legacy |
| D-05 | Security Approval | Perlu approval dari security team | Security review dijadwalkan sejak awal |

## 1.6 REFERENSI DOKUMEN

Dokumen PMP ini mengacu pada dokumen-dokumen berikut:

| No | Kode Dokumen | Nama Dokumen | Versi | Tanggal |
| --- | --- | --- | --- | --- |
| 1 | ARC-001 | Arsitektur Super ERP Farm Nation Enterprise (FNE) | 1.0 | September 2026 |
| 2 | ARC-001-DTL | Arsitektur Software Detil P-FNE-01 | 1.0 | September 2026 |
| 3 | SRS-001 | Software Requirement Specification P-FNE-01 | 1.0 | September 2026 |
| 4 | DB-001 | Database Design & ERD P-FNE-01 | 1.0 | September 2026 |
| 5 | UI-001 | User Interface Specification P-FNE-01 | 1.0 | September 2026 |
| 6 | API-001 | API Specification (OpenAPI) P-FNE-01 | 1.0 | September 2026 |
| 7 | SEC-001 | Security & Compliance Checklist P-FNE-01 | 1.0 | September 2026 |
| 8 | TST-001 | Testing Strategy & Test Cases P-FNE-01 | 1.0 | September 2026 |
| 9 | OPS-001 | Deployment & Operations Guide P-FNE-01 | 1.0 | September 2026 |
| 10 | PMP-001 | Project Management Plan P-FNE-01 | 1.0 | September 2026 |
| 11 | CHR-001 | Project Charter P-FNE-01 | 1.0 | September 2026 |

### 1.6.1 Standar dan Regulasi yang Digunakan

| No | Standar/Regulasi | Deskripsi |
| --- | --- | --- |
| 1 | PMBOK 7th Edition | Standar manajemen proyek |
| 2 | ISO 27001 | Standar keamanan informasi |
| 3 | OWASP Top 10 | Standar keamanan aplikasi web |
| 4 | GDPR | Regulasi perlindungan data (jika berlaku) |
| 5 | UU No. 27 Tahun 2022 | Perlindungan Data Pribadi (PDP) Indonesia |
| 6 | IEEE 829 | Standar dokumentasi testing |
| 7 | JSON Schema | Standar validasi data |
| 8 | OpenAPI 3.0 | Standar dokumentasi API |

## 1.7 STRUKTUR DOKUMEN PMP

Dokumen PMP ini disusun dengan struktur sebagai berikut:

| Bab | Judul | Deskripsi |
| --- | --- | --- |
| 1 | Pendahuluan | Tujuan, gambaran, visi, misi, asumsi, kendala |
| 2 | Manajemen Integrasi | Project charter, execution, monitoring, change control, closure |
| 3 | Manajemen Ruang Lingkup | Scope statement, WBS, verification, control |
| 4 | Manajemen Jadwal | Schedule approach, milestones, Gantt chart, control |
| 5 | Manajemen Biaya | Cost estimation, budgeting, control, EVM |
| 6 | Manajemen Kualitas | Quality metrics, QA/QC, testing strategy |
| 7 | Manajemen Sumber Daya | Organization structure, RACI, staffing, training |
| 8 | Manajemen Komunikasi | Stakeholder analysis, communication matrix, escalation |
| 9 | Manajemen Risiko | Risk identification, analysis, response, monitoring |
| 10 | Manajemen Pengadaan | Procurement plan, make-or-buy, vendor management |
| 11 | Manajemen Stakeholder | Stakeholder engagement, issue management |
| 12 | Lampiran | Dokumen pendukung, template, glossary |
| 13 | Perubahan & Persetujuan | Change control, approval process |
| 14 | Penutupan | Closure criteria, handover, final report |

# BAB 2: MANAJEMEN INTEGRASI PROYEK

## (PROJECT INTEGRATION MANAGEMENT)

## 2.1 PROJECT CHARTER

### 2.1.1 Ringkasan Project Charter

Project Charter merupakan dokumen otorisasi formal yang memberikan wewenang kepada Project Manager untuk mengalokasikan sumber daya dan mengarahkan aktivitas proyek. Project Charter P-FNE-01 telah disetujui pada tanggal [Tanggal Persetujuan] oleh Project Sponsor.

Elemen Kunci Project Charter:

| Elemen | Detail |
| --- | --- |
| Nama Proyek | Foundation & Core Platform (P-FNE-01) |
| Project Sponsor | VP of Technology |
| Project Manager | [Nama PM] |
| Business Need | Dibutuhkannya fondasi digital yang aman, terintegrasi, dan skalabel untuk mendukung 7 proyek turunan Super ERP FNE |
| Project Objectives | 1. Membangun infrastruktur cloud-native 2. Implementasi IAM, MDM, Audit, Workflow, Notification 3. Menyediakan API Gateway & Event Bus 4. Memastikan keamanan dan kepatuhan |
| High-Level Requirements | Sesuai dengan SRS-001 (36 functional requirements, 17 non-functional requirements) |
| High-Level Risks | 1. Kompleksitas integrasi microservices 2. Performa audit log volume tinggi 3. Keamanan credential 4. Ketersediaan sumber daya |
| Summary Milestones | Lihat Bab 4 (Manajemen Jadwal) |
| Budget | Rp 4.600.000.000,- (IDR) |
| Approval Authority | Project Sponsor dan Steering Committee |
| Project Exit Criteria | Semua acceptance criteria terpenuhi (lihat Bab 6) |

### 2.1.2 Project Charter Approval

| Peran | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Sponsor | VP of Technology |  |  |
| Head of PMO |  |  |  |
| Business Owner |  |  |  |

## 2.2 PROJECT MANAGEMENT PLAN

### 2.2.1 Proses Pengembangan PMP

PMP dikembangkan melalui proses kolaboratif yang melibatkan seluruh stakeholder kunci:

text

┌──────────────────────────────────────────────────────────────────────┐

│             PROSES PENGEMBANGAN PMP P-FNE-01                       │

├──────────────────────────────────────────────────────────────────────┤

│                                                                      │

│  STEP 1: INISIASI                                                    │

│  ┌─────────────────────────────────────────────────────────────┐    │

│  │ • Review Project Charter                                    │    │

│  │ • Identifikasi stakeholder awal                            │    │

│  │ • Penyusunan draft outline PMP                             │    │

│  └─────────────────────────────────────────────────────────────┘    │

│                              │                                       │

│                              ▼                                       │

│  STEP 2: PERENCANAAN                                                │

│  ┌─────────────────────────────────────────────────────────────┐    │

│  │ • Workshop perencanaan (Scope, Schedule, Cost, Quality)    │    │

│  │ • Identifikasi risiko awal                                 │    │

│  │ • Penyusunan draft PMP per bab                             │    │

│  └─────────────────────────────────────────────────────────────┘    │

│                              │                                       │

│                              ▼                                       │

│  STEP 3: REVIEW & VALIDASI                                          │

│  ┌─────────────────────────────────────────────────────────────┐    │

│  │ • Review oleh Project Sponsor                              │    │

│  │ • Review oleh Steering Committee                           │    │

│  │ • Review oleh PMO                                          │    │

│  │ • Review oleh Tim Proyek                                   │    │

│  └─────────────────────────────────────────────────────────────┘    │

│                              │                                       │

│                              ▼                                       │

│  STEP 4: PERSETUJUAN                                                │

│  ┌─────────────────────────────────────────────────────────────┐    │

│  │ • Approval oleh Project Sponsor                            │    │

│  │ • Approval oleh Steering Committee                         │    │

│  │ • Sosialisasi ke seluruh stakeholder                       │    │

│  └─────────────────────────────────────────────────────────────┘    │

│                              │                                       │

│                              ▼                                       │

│  STEP 5: PEMELIHARAAN                                               │

│  ┌─────────────────────────────────────────────────────────────┐    │

│  │ • Pembaruan berkala (setiap Sprint Planning)               │    │

│  │ • Perubahan melalui Integrated Change Control              │    │

│  │ • Versi dokumen dikelola                                   │    │

│  └─────────────────────────────────────────────────────────────┘    │

│                                                                      │

└──────────────────────────────────────────────────────────────────────┘

### 2.2.2 Komponen PMP

PMP P-FNE-01 terdiri dari 10 area manajemen yang terintegrasi:

| No | Area Manajemen | Dokumen Pendukung |
| --- | --- | --- |
| 1 | Integration Management | Project Charter, PMP, Change Control Log |
| 2 | Scope Management | Scope Statement, WBS, Requirements Traceability Matrix |
| 3 | Schedule Management | Gantt Chart, Milestone Schedule, Resource Calendar |
| 4 | Cost Management | Cost Estimation, Budget Baseline, Cash Flow |
| 5 | Quality Management | Quality Metrics, Test Plan, Acceptance Criteria |
| 6 | Resource Management | RACI Matrix, Staffing Plan, Training Plan |
| 7 | Communication Management | Communication Matrix, Stakeholder Register |
| 8 | Risk Management | Risk Register, Risk Response Plan |
| 9 | Procurement Management | Procurement Plan, Vendor Contracts |
| 10 | Stakeholder Management | Stakeholder Engagement Plan, Issue Log |

### 2.2.3 Pemeliharaan PMP

| Aspek | Mekanisme |
| --- | --- |
| Frekuensi Update | Setiap Sprint Planning (2 minggu) dan saat ada perubahan signifikan |
| Pemilik | Project Manager |
| Proses Perubahan | Melalui Integrated Change Control (lihat Bab 2.5) |
| Versi | Menggunakan format vX.Y (X = major, Y = minor) |
| Distribusi | Seluruh stakeholder via Confluence/SharePoint |
| Arsip | Disimpan di repository proyek minimal 5 tahun |

## 2.3 PROJECT EXECUTION

### 2.3.1 Pendekatan Eksekusi

Proyek P-FNE-01 akan dieksekusi menggunakan pendekatan Agile (Scrum) dengan elemen Waterfall untuk fase-fase tertentu (infrastruktur, keamanan, compliance).

Model Eksekusi Hibrida:

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                MODEL EKSEKUSI HIBRIDA P-FNE-01                              │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  FASE 1: INFRASTRUKTUR (WATERFALL)           [MINGGU 1-4]                   │

│  ┌─────────────────────────────────────────────────────────────────┐        │

│  │ • Environment provisioning (IaC)                               │        │

│  │ • Kubernetes cluster setup                                     │        │

│  │ • CI/CD pipeline                                               │        │

│  │ • Monitoring & logging                                         │        │

│  │ • Backup & DR                                                  │        │

│  └─────────────────────────────────────────────────────────────────┘        │

│                                                                              │

│  FASE 2: PENGEMBANGAN INTI (SCRUM)            [MINGGU 5-18]                  │

│  ┌─────────────────────────────────────────────────────────────────┐        │

│  │  SPRINT 1 (W5-6)   │  SPRINT 2 (W7-8)   │  SPRINT 3 (W9-10)  │        │

│  │  IAM Service       │  MDM (Part 1)      │  MDM (Part 2)      │        │

│  │  - Auth & MFA      │  - Core Entities   │  - Advanced Entities│        │

│  │  - RBAC            │  - CRUD            │  - Import/Export    │        │

│  └────────────────────┼────────────────────┼─────────────────────┘        │

│                       │                    │                                │

│  ┌────────────────────┼────────────────────┼─────────────────────┐        │

│  │  SPRINT 4 (W11-12) │  SPRINT 5 (W13-14) │  SPRINT 6 (W15-16)  │        │

│  │  Audit & Logging   │  Workflow Engine   │  Integration        │        │

│  │  - Audit Trail     │  - Definition      │  - API Gateway      │        │

│  │  - Query/Export    │  - Execution       │  - Event Bus        │        │

│  │  - Retention       │  - Monitoring      │  - Notification     │        │

│  └────────────────────┼────────────────────┼─────────────────────┘        │

│                       │                    │                                │

│  ┌─────────────────────────────────────────────────────────────────┐        │

│  │  SPRINT 7 (W17-18)                                             │        │

│  │  - Integration Testing                                         │        │

│  │  - Performance Testing                                         │        │

│  │  - Security Testing                                            │        │

│  └─────────────────────────────────────────────────────────────────┘        │

│                                                                              │

│  FASE 3: GO-LIVE (WATERFALL)                 [MINGGU 19-20]                  │

│  ┌─────────────────────────────────────────────────────────────────┐        │

│  │ • UAT (User Acceptance Testing)                               │        │

│  │ • Production deployment                                       │        │

│  │ • DR Drill                                                    │        │

│  │ • Handover                                                    │        │

│  └─────────────────────────────────────────────────────────────────┘        │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 2.3.2 Sprint Structure

Setiap sprint dalam fase pengembangan inti memiliki struktur sebagai berikut:

| Sprint Element | Durasi | Deskripsi |
| --- | --- | --- |
| Sprint Planning | 2 jam | Menentukan sprint backlog berdasarkan prioritas |
| Daily Stand-up | 15 menit | Sinkronisasi harian tim |
| Development | 9 hari | Implementasi fitur, unit testing, code review |
| Sprint Review | 1 jam | Demo hasil sprint ke stakeholder |
| Sprint Retrospective | 1 jam | Evaluasi dan perbaikan proses |
| Total Sprint | 10 hari kerja (2 minggu) |  |

### 2.3.3 Daily Execution Activities

| Aktivitas | Waktu | Owner | Deskripsi |
| --- | --- | --- | --- |
| Daily Stand-up | 09:00-09:15 | Scrum Master | Sinkronisasi progress, blockers, plan hari ini |
| Development Work | 09:15-17:00 | Developer | Coding, testing, code review |
| Code Review | Continuous | Developer | Peer review setiap pull request |
| Deployment (Dev) | Continuous | DevOps | Auto-deploy ke dev environment |
| Defect Triage | 15:00-15:30 | Tech Leads | Review dan prioritisasi bug |

### 2.3.4 Definisi Done (DoD)

Sebuah user story atau task dinyatakan SELESAI (DONE) apabila memenuhi seluruh kriteria berikut:

| No | Kriteria | Deskripsi |
| --- | --- | --- |
| 1 | Code Complete | Kode telah ditulis dan di-commit ke repository |
| 2 | Unit Testing | Unit test telah dibuat dan lulus (coverage ≥ 80%) |
| 3 | Integration Testing | Integration test lulus (jika ada ketergantungan) |
| 4 | Code Review | Code review telah dilakukan dan disetujui |
| 5 | Documentation | Dokumentasi kode dan API telah diperbarui |
| 6 | Deployed to Dev | Kode telah dideploy ke environment development |
| 7 | Functional Testing | Manual testing oleh QA telah dilakukan |
| 8 | Acceptance Criteria | Semua acceptance criteria terpenuhi |
| 9 | Security Review | Security scan tidak menemukan critical vulnerability |
| 10 | Peer Validation | Product Owner telah memvalidasi fitur |

## 2.4 PROJECT MONITORING & CONTROL

### 2.4.1 Monitoring Framework

Proyek akan dipantau menggunakan framework yang komprehensif:

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                      MONITORING FRAMEWORK P-FNE-01                          │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │                    MONITORING LEVELS                                 │    │

│  │                                                                      │    │

│  │  LEVEL 1: DAILY                                                     │    │

│  │  ┌─────────────────────────────────────────────────────────────┐    │    │

│  │  │ • Daily Stand-up                                            │    │    │

│  │  │ • Burndown Chart                                            │    │    │

│  │  │ • Build Status (CI/CD)                                      │    │    │

│  │  │ • Infrastructure Health                                     │    │    │

│  │  └─────────────────────────────────────────────────────────────┘    │    │

│  │                                                                      │    │

│  │  LEVEL 2: WEEKLY                                                    │    │

│  │  ┌─────────────────────────────────────────────────────────────┐    │    │

│  │  │ • Sprint Progress Review                                    │    │    │

│  │  │ • Velocity Tracking                                         │    │    │

│  │  │ • Risk Review                                               │    │    │

│  │  │ • Budget Burn Rate                                          │    │    │

│  │  └─────────────────────────────────────────────────────────────┘    │    │

│  │                                                                      │    │

│  │  LEVEL 3: MONTHLY                                                   │    │

│  │  ┌─────────────────────────────────────────────────────────────┐    │    │

│  │  │ • Steering Committee Meeting                                │    │    │

│  │  │ • Milestone Progress                                        │    │    │

│  │  │ • Quality Metrics                                           │    │    │

│  │  │ • Stakeholder Satisfaction                                  │    │    │

│  │  └─────────────────────────────────────────────────────────────┘    │    │

│  │                                                                      │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │                    MONITORING TOOLS                                  │    │

│  │                                                                      │    │

│  │  TOOL              │  PURPOSE                                        │    │

│  │  ──────────────────┼──────────────────────────────────────────────── │    │

│  │  Jira              │  Sprint backlog, issue tracking                │    │

│  │  Confluence        │  Dokumentasi, meeting notes                    │    │

│  │  GitHub/GitLab     │  Code repository, CI/CD                        │    │

│  │  Prometheus/Grafana│  Infrastructure metrics                        │    │

│  │  ELK/Loki          │  Log aggregation                               │    │

│  │  SonarQube         │  Code quality                                  │    │

│  │  OWASP ZAP         │  Security scanning                            │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 2.4.2 Performance Metrics & KPIs

| No | KPI | Target | Metode Pengukuran | Frekuensi |
| --- | --- | --- | --- | --- |
| 1 | Sprint Velocity | Stabil (baseline +10%) | Story points per sprint | Setiap Sprint |
| 2 | Sprint Burndown | On track | Actual vs planned burn | Setiap Sprint |
| 3 | Defect Density | < 1 per 1000 LOC | SonarQube | Weekly |
| 4 | Code Coverage | ≥ 80% | SonarQube | Weekly |
| 5 | API Response Time | ≤ 500ms (median) | Performance testing | Monthly |
| 6 | System Availability | ≥ 99.9% | Monitoring | Daily |
| 7 | CI/CD Success Rate | ≥ 95% | Build pipeline | Daily |
| 8 | Risk Response Effectiveness | ≥ 80% | Risk Register | Monthly |
| 9 | Stakeholder Satisfaction | ≥ 4.0/5.0 | Survey | Monthly |

### 2.4.3 Control Mechanisms

| No | Mekanisme Kontrol | Deskripsi | Frekuensi |
| --- | --- | --- | --- |
| 1 | Sprint Review | Review hasil sprint dengan stakeholder | Setiap Sprint (2 minggu) |
| 2 | Steering Committee | Laporan progress ke komite pengarah | Bulanan |
| 3 | Change Control | Evaluasi dan approval permintaan perubahan | As needed |
| 4 | Risk Review | Review dan update risk register | Mingguan |
| 5 | Quality Gate | Verifikasi kualitas sebelum deployment | Per deployment |
| 6 | Security Check | Security scanning sebelum release | Per sprint |
| 7 | Performance Test | Load dan stress testing | Per milestone |
| 8 | Budget Review | Review actual vs budget | Bulanan |

### 2.4.4 Reporting Cadence

| Jenis Laporan | Penerima | Frekuensi | Format | Isi |
| --- | --- | --- | --- | --- |
| Daily Status | Tim Proyek | Harian | Chat/Email | Progress, blockers, plan hari ini |
| Sprint Report | Stakeholder | Setiap Sprint | Slide/PDF | Sprint backlog, velocity, demo |
| Weekly Status | PMO, Sponsor | Mingguan | Dashboard | Progress, risks, issues, changes |
| Monthly Report | Steering Committee | Bulanan | Presentasi | Milestone, budget, quality, risks |
| Risk Report | PMO, Sponsor | Bulanan | Tabel | Risk status, new risks, mitigasi |
| Quality Report | QA Lead, PM | Mingguan | Dashboard | Code quality, test coverage, defects |
| Financial Report | Sponsor, Finance | Bulanan | Spreadsheet | Actual vs budget, forecast |
| Milestone Report | All Stakeholders | Per Milestone | Presentasi | Completion status, deliverables |

## 2.5 INTEGRATED CHANGE CONTROL

### 2.5.1 Change Control Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    CHANGE CONTROL PROCESS P-FNE-01                          │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  STEP 1: IDENTIFIKASI PERUBAHAN                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Setiap stakeholder dapat mengajukan perubahan                     │    │

│  │ • Menggunakan Change Request Form (CRF)                            │    │

│  │ • Mengklasifikasi: Urgency, Impact, Priority                       │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 2: EVALUASI & ANALISIS                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Project Manager melakukan evaluasi awal                          │    │

│  │ • Analisis dampak: Scope, Schedule, Cost, Quality, Risk           │    │

│  │ • Konsultasi dengan Tech Leads (jika perubahan teknis)             │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 3: REKOMENDASI                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • PM memberikan rekomendasi: Approve, Reject, atau Defer           │    │

│  │ • Menyertakan justifikasi dan alternatif                           │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 4: KEPUTUSAN                                                          │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Perubahan kecil (≤ 5% impact) → PM approve                       │    │

│  │ • Perubahan sedang (≤ 20% impact) → Sponsor approve                │    │

│  │ • Perubahan besar (> 20% impact) → Steering Committee approve      │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 5: IMPLEMENTASI                                                       │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Update dokumen PMP dan terkait                                  │    │

│  │ • Komunikasi ke seluruh stakeholder                              │    │

│  │ • Update schedule, budget, dan baseline lainnya                  │    │

│  │ • Implementasi perubahan                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 6: CLOSE & ARCHIVE                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Verifikasi implementasi sukses                                  │    │

│  │ • Dokumentasi perubahan di Change Log                             │    │

│  │ • Lessons learned (jika signifikan)                               │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 2.5.2 Change Request Form (CRF)

CHANGE REQUEST FORM - P-FNE-01

| Field | Deskripsi |
| --- | --- |
| CRF Number | CRF-XXX (auto-generated) |
| Date Submitted | [DD/MM/YYYY] |
| Submitted By | [Nama, Role] |
| Change Category | [ ] Scope [ ] Schedule [ ] Budget [ ] Resources [ ] Quality [ ] Risk [ ] Technical |
| Change Description | [Deskripsi perubahan yang diusulkan] |
| Reason / Justification | [Alasan perubahan diperlukan] |
| Impact Analysis |  |
| - Scope Impact | [Bertambah/berkurang ruang lingkup] |
| - Schedule Impact | [+ X hari/minggu] |
| - Cost Impact | [+ Rp X] |
| - Quality Impact | [Dampak terhadap kualitas] |
| - Risk Impact | [Risiko baru atau perubahan risiko] |
| Proposed Solution | [Cara implementasi perubahan] |
| Alternatives | [Opsi alternatif (jika ada)] |
| Priority | [ ] Low [ ] Medium [ ] High [ ] Critical |
| Recommendation | [ ] Approve [ ] Reject [ ] Defer |
| Approved By | [Nama, Role, Signature, Date] |
| Implementation Date | [DD/MM/YYYY] |
| Actual Impact | [Realisasi dampak setelah implementasi] |
| Closed By | [Nama, Role, Date] |

### 2.5.3 Change Control Board (CCB)

| Peran | Anggota | Wewenang |
| --- | --- | --- |
| Chairperson | Project Sponsor | Memimpin keputusan, veto untuk perubahan kritis |
| PMO Representative | Head of PMO | Memastikan alignment dengan standar PMO |
| Project Manager | PM P-FNE-01 | Menyajikan analisis dan rekomendasi |
| Tech Lead | Lead Developer | Analisis dampak teknis |
| Business Representative | Business Owner | Analisis dampak bisnis |
| Quality Lead | QA Lead | Analisis dampak kualitas |
| Security Lead | Security Engineer | Analisis dampak keamanan |

Kriteria Keputusan:

| Kategori | Approver | Waktu Respons |
| --- | --- | --- |
| Perubahan dengan impact ≤ 5% dari baseline | Project Manager | 1 hari kerja |
| Perubahan dengan impact 5-20% dari baseline | Project Sponsor | 2 hari kerja |
| Perubahan dengan impact > 20% dari baseline | Steering Committee | 5 hari kerja |
| Perubahan kritis (security, compliance) | Steering Committee + Sponsor | 1 hari kerja |

### 2.5.4 Change Log

| CRF # | Tanggal | Deskripsi | Kategori | Status | Approved By | Tanggal Implementasi | Actual Impact |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CRF-001 | [Date] | [Description] | [Category] | [Status] | [Name] | [Date] | [Impact] |
| ... | ... | ... | ... | ... | ... | ... | ... |

### 2.5.5 Change Communication

Setiap perubahan yang disetujui akan dikomunikasikan melalui:

- Email Notification ke seluruh stakeholder dalam 24 jam

- Update PMP di repository proyek

- Sprint Planning untuk pekerjaan yang terkait

- Steering Committee untuk perubahan signifikan

## 2.6 PROJECT CLOSURE

### 2.6.1 Project Closure Criteria

Proyek P-FNE-01 dinyatakan SELESAI dan DITUTUP apabila seluruh kondisi berikut terpenuhi:

| No | Kriteria | Status | Verifikasi |
| --- | --- | --- | --- |
| 1 | Semua acceptance criteria di Bab 6 terpenuhi | [ ] | PM + QA |
| 2 | Semua deliverable telah diserahkan dan diterima | [ ] | PM + Sponsor |
| 3 | Semua NFR target terpenuhi berdasarkan performance testing | [ ] | QA + DevOps |
| 4 | Security assessment tidak menemukan critical vulnerability | [ ] | Security Lead |
| 5 | User Acceptance Testing (UAT) sukses (≥ 90% satisfaction) | [ ] | Business Owner |
| 6 | Production deployment sukses | [ ] | DevOps Lead |
| 7 | Disaster Recovery drill sukses (RPO ≤ 15m, RTO ≤ 2h) | [ ] | DevOps Lead |
| 8 | Semua dokumen proyek selesai dan diarsipkan | [ ] | PM |
| 9 | Lessons learned telah didokumentasikan | [ ] | PM |
| 10 | Handover ke tim operasional telah dilakukan | [ ] | PM + Operations |

### 2.6.2 Handover Plan

| Tahap | Aktivitas | Owner | Timeline |
| --- | --- | --- | --- |
| Preparation | Persiapan dokumen handover, training materials | PM, Tech Lead | M-2 |
| Training | Training untuk tim operasional | Tech Lead, DevOps | M-1 |
| Documentation | Finalisasi dokumentasi teknis dan operasional | All Leads | M-1 |
| Transition | Serah terima ke tim operasional | PM, Operations Lead | M |
| Support Period | Periode support (2 bulan) setelah handover | Development Team | M+1 - M+2 |
| Closure | Formal project closure | PM, Sponsor | M+2 |

Dokumen Handover:

- Architecture Documentation (final)

- API Documentation (OpenAPI)

- Database Schema & ERD

- Deployment & Operations Guide

- Monitoring & Alerting Guide

- Security & Compliance Checklist

- Disaster Recovery Procedure

- User Manuals

- Training Materials

- Knowledge Base Articles

### 2.6.3 Project Review & Lessons Learned

Lessons Learned Session:

| Aspek | Detail |
| --- | --- |
| Timing | Dilaksanakan dalam 2 minggu setelah Go-Live |
| Durasi | 1 hari (4 jam session) |
| Peserta | Seluruh tim proyek, stakeholder utama |
| Fasilitator | PMO atau external facilitator |
| Output | Lessons Learned Report, Action Items |

Topik yang Dikaji:

- What Went Well - Faktor keberhasilan yang perlu dipertahankan

- What Could Be Improved - Area perbaikan untuk proyek mendatang

- What Went Wrong - Masalah yang terjadi dan solusinya

- Lessons Learned - Pembelajaran kunci yang didokumentasikan

- Recommendations - Rekomendasi untuk proyek P-FNE-02 s.d. P-FNE-08

### 2.6.4 Final Report

Final Report Content:

| Bab | Isi |
| --- | --- |
| 1 | Executive Summary |
| 2 | Project Objectives & Achievements |
| 3 | Scope & Deliverables (actual) |
| 4 | Schedule (planned vs actual) |
| 5 | Budget (planned vs actual) |
| 6 | Quality (metrics achievement) |
| 7 | Risk Management (actual risks) |
| 8 | Lessons Learned |
| 9 | Benefits Realization |
| 10 | Recommendations for Future Projects |

### 2.6.5 Document Archiving

| Jenis Dokumen | Retention Period | Storage Location |
| --- | --- | --- |
| PMP & Project Documents | 5 tahun | Corporate Repository |
| Code Repository | Indefinite | GitHub/GitLab |
| Database Backup | 5 tahun | Cloud Archive |
| Audit Logs | 5 tahun (sesuai regulasi) | Audit Storage |
| Contract & Procurement | 7 tahun | Legal Repository |
| Training Materials | 3 tahun | Knowledge Base |
| Final Report & Lessons Learned | Indefinite | PMO Repository |

## 2.7 DELIVERABLE ACCEPTANCE CRITERIA

### 2.7.1 Acceptance Criteria per Deliverable

| No | Deliverable | Acceptance Criteria | Verification Method |
| --- | --- | --- | --- |
| 1 | Infrastructure & DevOps | • 4 environment berfungsi • CI/CD pipeline otomatis • Monitoring & logging aktif • Backup & restore teruji | Manual review + Testing |
| 2 | IAM Service | • User registration & auth • MFA berfungsi • RBAC dengan 10 role dasar • SoD diterapkan | Functional testing |
| 3 | Master Data Management | • 24 entity CRUD • Import/export berfungsi • Duplicate detection • Versioning | Functional testing + UAT |
| 4 | Audit & Logging | • Semua transaksi tercatat • Audit log immutable • Query & export | Functional testing |
| 5 | API Gateway | • Routing berfungsi • Rate limiting • Auth at gateway • Documentation | Integration testing |
| 6 | Event Bus | • Publish/subscribe • DLQ & retry • Correlation ID | Integration testing |
| 7 | Workflow Engine | • 3 workflow basic • Approval matrix • Notifikasi | Functional testing |
| 8 | Notification Service | • 4 channel • Template management • History | Functional testing |

### 2.7.2 NFR Acceptance Criteria

| No | NFR | Target | Verification |
| --- | --- | --- | --- |
| 1 | Availability | ≥ 99.9% | Monitoring over 30 days |
| 2 | API Response Time | ≤ 500ms (median) | Performance testing |
| 3 | Concurrent Users | 1.000 users | Load testing |
| 4 | RPO | ≤ 15 minutes | DR drill |
| 5 | RTO | ≤ 2 hours | DR drill |
| 6 | Security | No critical vulnerability | Security scan |
| 7 | Data Encryption | TLS 1.2+ & AES-256 | Security audit |
| 8 | Audit Retention | 5 years | Policy review |

## 2.8 GOVERNANCE STRUCTURE

### 2.8.1 Governance Framework

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    GOVERNANCE STRUCTURE P-FNE-01                            │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ┌─────────────────────────────────────────────────────────────────────────┐│

│  │                    STEERING COMMITTEE                                   ││

│  │                    (Decision Making & Strategic Direction)              ││

│  │  • Project Sponsor (Chair)                                              ││

│  │  • Head of PMO                                                          ││

│  │  • Business Owner                                                       ││

│  │  • Head of IT Operations                                                ││

│  │  • Head of Security                                                     ││

│  └──────────────────────────────┬──────────────────────────────────────────┘│

│                                 │                                           │

│  ┌──────────────────────────────▼──────────────────────────────────────────┐│

│  │                    PROJECT MANAGEMENT OFFICE (PMO)                     ││

│  │                    (Support & Oversight)                                ││

│  │  • Methodology guidance                                                ││

│  │  • Quality assurance                                                   ││

│  │  • Reporting & metrics                                                 ││

│  └──────────────────────────────┬──────────────────────────────────────────┘│

│                                 │                                           │

│  ┌──────────────────────────────▼──────────────────────────────────────────┐│

│  │                    PROJECT MANAGER                                      ││

│  │                    (Execution & Delivery)                               ││

│  │  • Day-to-day management                                               ││

│  │  • Team coordination                                                   ││

│  │  • Stakeholder engagement                                               ││

│  └──────────────────────────────┬──────────────────────────────────────────┘│

│                                 │                                           │

│     ┌───────────────────────────┼───────────────────────────┐              │

│     │                           │                           │              │

│  ┌──▼─────────────┐     ┌───────▼─────────┐     ┌──────────▼────────┐     │

│  │  DevOps Lead   │     │  Tech Lead      │     │  Security Lead    │     │

│  │  (3 org)       │     │  (5 org)        │     │  (2 org)          │     │

│  └────────────────┘     └─────────────────┘     └───────────────────┘     │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 2.8.2 Roles & Responsibilities Summary

| Role | Tanggung Jawab Utama |
| --- | --- |
| Project Sponsor | • Menyetujui charter dan PMP • Mengambil keputusan strategis • Menyediakan resources • Menyetujui perubahan signifikan |
| Steering Committee | • Memberikan arahan strategis • Menyetujui milestone • Mengelola risiko tingkat tinggi • Menyetujui anggaran |
| Project Manager | • Mengelola seluruh aspek proyek • Melaporkan progress • Mengelola tim • Mengelola stakeholder |
| DevOps Lead | • Infrastruktur dan CI/CD • Monitoring dan logging • Backup dan DR • Security infrastructure |
| Tech Lead | • Arsitektur teknis • Code quality • Integration • Technical decision making |
| Security Lead | • Security architecture • IAM implementation • Security testing • Compliance |
| QA Lead | • Testing strategy • Quality metrics • Defect management • UAT coordination |

# BAB 3: MANAJEMEN RUANG LINGKUP PROYEK

## (PROJECT SCOPE MANAGEMENT)

## 3.1 SCOPE MANAGEMENT APPROACH

### 3.1.1 Pendekatan Umum

Manajemen ruang lingkup proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Metodologi | Hybrid (Agile untuk pengembangan fitur, Waterfall untuk infrastruktur) |
| Dekomposisi | Work Breakdown Structure (WBS) hingga level 3 |
| Verifikasi | Sprint Review dan UAT (User Acceptance Testing) |
| Kontrol | Change Control Process dengan Change Control Board |
| Dokumentasi | Scope Statement, WBS Dictionary, RTM |

### 3.1.2 Proses Manajemen Ruang Lingkup

text

┌─────────────────────────────────────────────────────────────────────────────┐

│              PROSES MANAJEMEN RUANG LINGKUP P-FNE-01                        │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1. PERENCANAAN RUANG LINGKUP                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penyusunan Scope Statement                                        │    │

│  │ • Pembuatan WBS                                                    │    │

│  │ • Penyusunan WBS Dictionary                                        │    │

│  │ • Definisi Acceptance Criteria                                     │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  2. DEFINISI RUANG LINGKUP                                                  │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • In-Scope & Out-of-Scope                                          │    │

│  │ • Requirement Breakdown                                            │    │

│  │ • Prioritization (MoSCoW)                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  3. VERIFIKASI RUANG LINGKUP                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Sprint Review setiap 2 minggu                                    │    │

│  │ • UAT sebelum Go-Live                                             │    │

│  │ • Sign-off dari stakeholder                                       │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  4. KONTROL RUANG LINGKUP                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Requirements Traceability Matrix                                │    │

│  │ • Change Control Process                                          │    │

│  │ • Scope Creep Prevention                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 3.2 PROJECT SCOPE STATEMENT

### 3.2.1 Project Scope Description

Proyek P-FNE-01 bertujuan membangun Foundation & Core Platform yang menjadi fondasi bagi seluruh ekosistem Super ERP Farm Nation Enterprise. Platform ini mencakup:

1. Infrastructure & DevOps Management

- Environment provisioning melalui Infrastructure as Code (IaC)

- Container orchestration dengan Kubernetes

- CI/CD pipeline otomatis (build, test, security scan, deploy)

- Monitoring (Prometheus/Grafana) dan logging (ELK/Loki)

- Backup automation dan Disaster Recovery

- Secrets management (HashiCorp Vault)

2. Identity & Access Management (IAM)

- User registration dan management

- Authentication (username/password dengan secure hashing)

- Multi-Factor Authentication (MFA)

- Single Sign-On (SSO) dengan OAuth 2.0 / OpenID Connect

- Role-Based Access Control (RBAC)

- Permission management

- Segregation of Duties (SoD)

- Session management

- Password policy dan account lockout

3. Master Data Management (MDM)

- 24 entitas master data:

  - Company, Business Unit, Location, Organization Structure

  - Product, Material, Supplier, Customer, Employee

  - Asset, Farm, Land Parcel, Crop, Livestock

  - Warehouse, UOM, Chart of Accounts, Price List

  - Tax Configuration, dan lainnya

- CRUD operations untuk setiap entitas

- Import/Export (Excel/CSV)

- Duplicate detection

- Versioning dan approval workflow

- Master data validation

4. Audit & Logging

- Audit trail untuk semua transaksi bisnis

- Audit trail untuk akses (login, logout, failed attempts)

- Audit trail untuk perubahan master data

- Audit trail untuk perubahan konfigurasi

- Immutable audit log

- Audit log query dan export

- Audit log retention (5 tahun)

- Centralized logging

5. API Gateway & Integration

- API Gateway sebagai entry point tunggal

- Request routing ke service yang tepat

- Rate limiting

- Authentication di gateway

- API versioning

- API documentation (OpenAPI/Swagger)

- API monitoring (latency, error rate, throughput)

- Circuit breaker, retry, timeout

6. Event Bus & Messaging

- Message broker (Apache Kafka)

- Event publisher dan subscriber

- Event schema (JSON schema)

- Event versioning

- Dead Letter Queue (DLQ)

- Retry mechanism

- Event monitoring

- Correlation ID untuk tracing

7. Workflow Engine

- Workflow definition

- Workflow execution

- Approval matrix berdasarkan amount, department, position

- Task assignment

- Task notification

- Approval/rejection

- Workflow monitoring dashboard

- Workflow escalation

- Workflow versioning

- Workflow audit

8. Notification Service

- Multi-channel notification (In-App, Email, SMS, Push)

- Notification template management

- User notification preferences

- Notification history

- Batch notification

### 3.2.2 Project Boundaries

Batas Organisasi:

- Proyek dilaksanakan oleh tim internal FNE dengan dukungan vendor untuk komponen tertentu

- Keputusan final berada di tangan Steering Committee

Batas Teknis:

- Platform dibangun di atas cloud infrastructure (AWS/GCP)

- Menggunakan teknologi stack yang telah ditentukan

- API-first design untuk semua layanan

- Event-driven architecture menggunakan Kafka

Batas Waktu:

- Durasi proyek: 5 bulan (20 minggu)

- Go-Live: Maret 2027

Batas Anggaran:

- Total anggaran: Rp 4.600.000.000,-

- Tidak boleh melebihi anggaran tanpa persetujuan Steering Committee

## 3.3 IN-SCOPE (FITUR & DELIVERABLES)

### 3.3.1 Deliverables by Category

| Kategori | Deliverable | Deskripsi | WBS |
| --- | --- | --- | --- |
| Infrastructure | Environment (4 env) | Dev, Test, Staging, Production | 1.1.1 |
|  | Kubernetes Cluster | Container orchestration | 1.1.2 |
|  | CI/CD Pipeline | Build, test, deploy automation | 1.1.3 |
|  | Monitoring & Logging | Prometheus, Grafana, ELK/Loki | 1.1.4 |
|  | Backup & DR | Automated backup, DR plan | 1.1.5 |
|  | Secrets Management | HashiCorp Vault | 1.1.6 |
| IAM | User Registration | Register user dengan validasi | 1.2.1 |
|  | Authentication | Login dengan username/password | 1.2.1 |
|  | MFA | Multi-Factor Authentication | 1.2.2 |
|  | RBAC | Role-Based Access Control | 1.2.3 |
|  | Permission Management | Manage permissions per role | 1.2.4 |
|  | SSO | Single Sign-On (OAuth2/OIDC) | 1.2.5 |
|  | Session Management | Session dengan timeout | 1.2.6 |
| MDM | Entity Schema | 24 entity master data | 1.3.1 |
|  | CRUD Operations | Create, Read, Update, Delete | 1.3.2 |
|  | Import/Export | Excel/CSV bulk operations | 1.3.3 |
|  | Duplicate Detection | Fuzzy matching detection | 1.3.4 |
|  | Versioning | Data version tracking | 1.3.5 |
| Audit | Audit Trail | Log semua aktivitas | 1.4.1 |
|  | Query & Export | Search dan export audit log | 1.4.2 |
|  | Security Logging | Failed auth, auth failure | 1.4.3 |
|  | Retention | 5 tahun retention | 1.4.4 |
| API Gateway | Gateway Setup | Kong/Traefik setup | 1.5.1 |
|  | Routing & Rate Limit | Route requests, rate limit | 1.5.2 |
|  | Auth at Gateway | Authentication before routing | 1.5.3 |
|  | API Documentation | OpenAPI/Swagger | 1.5.4 |
|  | Circuit Breaker | Resilience patterns | 1.5.5 |
| Event Bus | Kafka Setup | Kafka cluster | 1.6.1 |
|  | Publisher/Subscriber | Event pub/sub | 1.6.2 |
|  | DLQ | Dead Letter Queue | 1.6.3 |
|  | Event Monitoring | Monitor event volume | 1.6.4 |
| Workflow | Definition | Create workflow definitions | 1.7.1 |
|  | Execution | Run workflow instances | 1.7.2 |
|  | Approval Matrix | Conditional approval | 1.7.3 |
|  | Task Management | Assign, approve, reject | 1.7.4 |
| Notification | Multi-Channel | Email, SMS, Push, In-App | 1.8.1 |
|  | Template | Manage notification templates | 1.8.2 |
|  | Preferences | User notification settings | 1.8.3 |
|  | History | Notification delivery history | 1.8.4 |

### 3.3.2 Features by Priority (MoSCoW)

| Kategori | Must Have | Should Have | Could Have | Won't Have |
| --- | --- | --- | --- | --- |
| Infrastructure | Environment, K8s, CI/CD, Monitoring, Backup | Auto-scaling, Service Mesh | Distributed Tracing | None |
| IAM | Auth, RBAC, MFA, Password Policy, Session | SSO, SoD, Account Lockout | LDAP Integration | None |
| MDM | 24 Entity CRUD, Import/Export | Duplicate Detection, Versioning | Approval Workflow | None |
| Audit | Audit Trail, Query, Immutable | Export, Retention 5 years | Archival | None |
| API Gateway | Routing, Rate Limit, Auth, Documentation | Circuit Breaker, Retry, Versioning | Response Transformation | None |
| Event Bus | Pub/Sub, DLQ, Retry, Monitoring | Event Versioning, Persistence | None | None |
| Workflow | Definition, Execution, Task Assignment, Notif | Escalation, Monitoring | Versioning | None |
| Notification | Email, In-App, Push, Template | SMS, Batch, Preferences | None | None |

## 3.4 OUT-OF-SCOPE

### 3.4.1 Fitur yang Tidak Termasuk dalam P-FNE-01

| No | Fitur/Aktivitas | Keterangan | Akan Ditangani di |
| --- | --- | --- | --- |
| 1 | Core Agricultural Operations | Manajemen farm, crop, livestock, harvest | P-FNE-02 |
| 2 | Supply Chain & Procurement | Procurement, inventory, warehouse, quality | P-FNE-03 |
| 3 | Production & Manufacturing | Planning, BOM, execution, maintenance | P-FNE-04 |
| 4 | Commerce, Sales & Logistics | Sales, CRM, marketplace, logistics | P-FNE-05 |
| 5 | Enterprise Finance & HCM | Accounting, costing, HCM, project | P-FNE-06 |
| 6 | Intelligence & Decision Platform | BI, AI/ML, knowledge graph | P-FNE-07 |
| 7 | Advanced & Autonomous Enterprise | IoT, Digital Twin, Simulation | P-FNE-08 |
| 8 | Mobile App (Field Worker) | Aplikasi mobile untuk pekerja lapangan | P-FNE-02/05 |
| 9 | Executive Dashboard | Dashboard khusus direksi | P-FNE-07 |
| 10 | Customer Portal | Portal untuk pelanggan | P-FNE-05 |
| 11 | Supplier Portal | Portal untuk pemasok | P-FNE-03 |
| 12 | Data Migration dari Legacy | Migrasi data dari sistem lama | Proyek terpisah |
| 13 | Integration dengan External Systems | Payment gateway, banking, dll. | P-FNE-05/06 |
| 14 | AI/ML Models | Predictive analytics, forecasting | P-FNE-07 |
| 15 | IoT Gateway & Device Management | Manajemen perangkat IoT | P-FNE-08 |
| 16 | Digital Twin | Representasi digital aset fisik | P-FNE-08 |
| 17 | Mobile App (Executive) | Aplikasi mobile untuk eksekutif | P-FNE-07 |
| 18 | Data Warehouse/Lakehouse | Penyimpanan data historis untuk BI | P-FNE-07 |
| 19 | ETL/ELT Pipeline | Data pipeline ke data warehouse | P-FNE-07 |
| 20 | Advanced Reporting | Laporan bisnis kompleks | P-FNE-07 |

### 3.4.2 Batasan Implementasi

| No | Batasan | Deskripsi |
| --- | --- | --- |
| 1 | UI/UX | Hanya menyediakan admin portal dan basic UI; UI proyek turunan dikembangkan di proyek masing-masing |
| 2 | Multi-Tenancy | Belum mendukung multi-tenancy penuh; fokus pada single company terlebih dahulu |
| 3 | Mobile | Tidak ada pengembangan mobile app di P-FNE-01 |
| 4 | Localization | Belum mendukung multi-language; menggunakan Bahasa Indonesia dan Inggris |
| 5 | Customization | Belum menyediakan fitur customization untuk end-user |
| 6 | Scalability | Dirancang untuk 1.000 concurrent users; scaling di atas itu di proyek selanjutnya |
| 7 | Integration | Hanya menyediakan API; integrasi dengan sistem eksternal di proyek turunan |

## 3.5 WORK BREAKDOWN STRUCTURE (WBS)

### 3.5.1 WBS Level 1-3

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    1.0 FOUNDATION & CORE PLATFORM                           │

│                                                                              │

├── 1.1 Infrastructure & DevOps                                               │

│   ├── 1.1.1 Environment Provisioning (IaC)                                 │

│   ├── 1.1.2 Container Orchestration (Kubernetes)                           │

│   ├── 1.1.3 CI/CD Pipeline                                                 │

│   ├── 1.1.4 Monitoring & Logging                                           │

│   ├── 1.1.5 Backup & DR                                                    │

│   └── 1.1.6 Secrets Management                                             │

│                                                                              │

├── 1.2 Identity & Access Management (IAM)                                   │

│   ├── 1.2.1 User Registration & Authentication                             │

│   ├── 1.2.2 Multi-Factor Authentication (MFA)                              │

│   ├── 1.2.3 Role-Based Access Control (RBAC)                              │

│   ├── 1.2.4 Permission Management                                          │

│   ├── 1.2.5 Single Sign-On (SSO)                                           │

│   └── 1.2.6 Session & Token Management                                     │

│                                                                              │

├── 1.3 Master Data Management (MDM)                                         │

│   ├── 1.3.1 Entity Schema Definition (24 entity)                           │

│   ├── 1.3.2 CRUD Operations                                                │

│   ├── 1.3.3 Import/Export Functionality                                    │

│   ├── 1.3.4 Duplicate Detection                                            │

│   └── 1.3.5 Versioning & Audit History                                     │

│                                                                              │

├── 1.4 Audit & Logging                                                      │

│   ├── 1.4.1 Audit Trail Implementation                                     │

│   ├── 1.4.2 Audit Log Query & Export                                       │

│   ├── 1.4.3 Security Event Logging                                         │

│   └── 1.4.4 Data Retention & Archival                                      │

│                                                                              │

├── 1.5 API Gateway & Integration                                            │

│   ├── 1.5.1 API Gateway Setup (Kong/Traefik)                               │

│   ├── 1.5.2 Routing & Rate Limiting                                        │

│   ├── 1.5.3 Authentication at Gateway                                      │

│   ├── 1.5.4 API Documentation (OpenAPI)                                    │

│   └── 1.5.5 Circuit Breaker & Retry                                        │

│                                                                              │

├── 1.6 Event Bus & Messaging                                                │

│   ├── 1.6.1 Kafka Cluster Setup                                            │

│   ├── 1.6.2 Event Publisher & Subscriber                                   │

│   ├── 1.6.3 Dead Letter Queue                                              │

│   └── 1.6.4 Event Monitoring                                               │

│                                                                              │

├── 1.7 Workflow Engine                                                      │

│   ├── 1.7.1 Workflow Definition                                            │

│   ├── 1.7.2 Workflow Execution                                             │

│   ├── 1.7.3 Approval Matrix                                                │

│   └── 1.7.4 Task Management & Escalation                                   │

│                                                                              │

├── 1.8 Notification Service                                                 │

│   ├── 1.8.1 Multi-Channel Notification (Email, SMS, Push, In-App)          │

│   ├── 1.8.2 Template Management                                            │

│   ├── 1.8.3 User Preferences                                               │

│   └── 1.8.4 Notification History                                           │

│                                                                              │

└── 1.9 Project Management & Governance                                      │

├── 1.9.1 PMP & Project Documentation                                    │

├── 1.9.2 Quality Assurance                                              │

├── 1.9.3 Communication & Reporting                                      │

└── 1.9.4 Training & Handover                                            │

### 3.5.2 WBS Level 4 Sample (Master Data Management)

text

1.3 Master Data Management (MDM)

├── 1.3.1 Entity Schema Definition (24 entity)

│   ├── 1.3.1.1 Schema Design untuk Company

│   ├── 1.3.1.2 Schema Design untuk Product

│   ├── 1.3.1.3 Schema Design untuk Supplier

│   ├── 1.3.1.4 Schema Design untuk Customer

│   ├── 1.3.1.5 Schema Design untuk Farm

│   ├── 1.3.1.6 Schema Design untuk Crop

│   └── ... (18 entity lainnya)

├── 1.3.2 CRUD Operations

│   ├── 1.3.2.1 Create API untuk semua entity

│   ├── 1.3.2.2 Read API untuk semua entity

│   ├── 1.3.2.3 Update API untuk semua entity

│   ├── 1.3.2.4 Delete API untuk semua entity

│   └── 1.3.2.5 Search API untuk semua entity

├── 1.3.3 Import/Export Functionality

│   ├── 1.3.3.1 Import from Excel/CSV

│   ├── 1.3.3.2 Export to Excel/CSV

│   ├── 1.3.3.3 Validation Engine

│   └── 1.3.3.4 Error Reporting

├── 1.3.4 Duplicate Detection

│   ├── 1.3.4.1 Fuzzy Matching Algorithm

│   ├── 1.3.4.2 Duplicate Group Identification

│   ├── 1.3.4.3 Merge Functionality

│   └── 1.3.4.4 Duplicate Resolution Workflow

└── 1.3.5 Versioning & Audit History

├── 1.3.5.1 Version Tracking

├── 1.3.5.2 Historical Data Access

└── 1.3.5.3 Change Log

## 3.6 SCOPE VERIFICATION & CONTROL

### 3.6.1 Scope Verification Process

| Tahap | Aktivitas | Pelaku | Output |
| --- | --- | --- | --- |
| 1. Sprint Review | Demo hasil sprint ke stakeholder | Tim Proyek | Feedback, Approval |
| 2. UAT | User Acceptance Testing | Business Owner | UAT Sign-off |
| 3. Milestone Review | Review pencapaian milestone | PM + Sponsor | Milestone Approval |
| 4. Final Acceptance | Verifikasi seluruh deliverable | Sponsor + Steering | Project Acceptance |

### 3.6.2 Scope Control Mechanisms

| No | Mekanisme | Deskripsi |
| --- | --- | --- |
| 1 | Change Control Process | Setiap perubahan scope harus melalui CCB |
| 2 | Requirements Traceability | Setiap requirement dilacak ke deliverable |
| 3 | MoSCoW Prioritization | Perubahan hanya untuk Must Have dan Should Have |
| 4 | Scope Baseline | Baseline yang disetujui sebagai referensi |
| 5 | Variance Analysis | Analisis deviasi dari baseline |
| 6 | Daily Stand-up | Deteksi scope creep sejak dini |

### 3.6.3 Scope Creep Prevention

| No | Strategi Pencegahan | Implementasi |
| --- | --- | --- |
| 1 | Clear Scope Statement | Dokumen scope yang jelas dan disetujui |
| 2 | WBS and WBS Dictionary | Detail pekerjaan yang jelas per WBS |
| 3 | Change Request Required | Setiap tambahan harus melalui CRF |
| 4 | Stakeholder Alignment | Komunikasi rutin dengan stakeholder |
| 5 | Sprint Boundaries | Tidak ada perubahan di tengah sprint |
| 6 | Backlog Refinement | Review dan prioritisasi backlog setiap sprint |

## 3.7 REQUIREMENTS TRACEABILITY MATRIX (RTM)

### 3.7.1 RTM Format

| Req ID | Requirement | WBS | Design Component | Test Case | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-IAM-001 | User Registration | 1.2.1 | UserRegistrationForm | TC-IAM-001 | Not Started |
| FNE-IAM-002 | Authentication | 1.2.1 | LoginForm, AuthService | TC-IAM-002 | Not Started |
| FNE-IAM-003 | MFA | 1.2.2 | MfaService, OTP | TC-IAM-003 | Not Started |
| FNE-INF-001 | Environment Provisioning | 1.1.1 | Terraform Scripts | TC-INF-001 | Not Started |
| FNE-INF-002 | Container Orchestration | 1.1.2 | Kubernetes Config | TC-INF-002 | Not Started |
| FNE-MDM-001 | Company Master | 1.3.1, 1.3.2 | CompanyService | TC-MDM-001 | Not Started |
| ... | ... | ... | ... | ... | ... |

### 3.7.2 RTM Complete Matrix (Referensi)

A. Infrastructure & DevOps (FNE-INF-001 s.d. FNE-INF-015)

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-INF-001 | Environment Provisioning | 1.1.1 | TC-INF-001 | P0 | Pending |
| FNE-INF-002 | Container Orchestration | 1.1.2 | TC-INF-002 | P0 | Pending |
| FNE-INF-003 | CI/CD Pipeline | 1.1.3 | TC-INF-003 | P0 | Pending |
| FNE-INF-004 | Service Discovery | 1.1.2 | TC-INF-004 | P1 | Pending |
| FNE-INF-005 | Load Balancing | 1.5.2 | TC-INF-005 | P0 | Pending |
| FNE-INF-006 | Auto-Scaling | 1.1.2 | TC-INF-006 | P1 | Pending |
| FNE-INF-007 | Resource Monitoring | 1.1.4 | TC-INF-007 | P0 | Pending |
| FNE-INF-008 | Log Aggregation | 1.1.4 | TC-INF-008 | P0 | Pending |
| FNE-INF-009 | Distributed Tracing | 1.1.4 | TC-INF-009 | P1 | Pending |
| FNE-INF-010 | Backup Automation | 1.1.5 | TC-INF-010 | P0 | Pending |
| FNE-INF-011 | Disaster Recovery | 1.1.5 | TC-INF-011 | P0 | Pending |
| FNE-INF-012 | Secrets Management | 1.1.6 | TC-INF-012 | P0 | Pending |
| FNE-INF-013 | Environment Configuration | 1.1.1 | TC-INF-013 | P0 | Pending |
| FNE-INF-014 | Health Check | 1.1.4 | TC-INF-014 | P0 | Pending |
| FNE-INF-015 | Graceful Shutdown | 1.1.2 | TC-INF-015 | P1 | Pending |

B. IAM (FNE-IAM-001 s.d. FNE-IAM-015)

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-IAM-001 | User Registration | 1.2.1 | TC-IAM-001 | P0 | Pending |
| FNE-IAM-002 | User Authentication | 1.2.1 | TC-IAM-002 | P0 | Pending |
| FNE-IAM-003 | MFA | 1.2.2 | TC-IAM-003 | P0 | Pending |
| FNE-IAM-004 | SSO | 1.2.5 | TC-IAM-004 | P1 | Pending |
| FNE-IAM-005 | RBAC | 1.2.3 | TC-IAM-005 | P0 | Pending |
| FNE-IAM-006 | Permission Management | 1.2.4 | TC-IAM-006 | P0 | Pending |
| FNE-IAM-007 | SoD | 1.2.3 | TC-IAM-007 | P0 | Pending |
| FNE-IAM-008 | Session Management | 1.2.6 | TC-IAM-008 | P0 | Pending |
| FNE-IAM-009 | Password Policy | 1.2.1 | TC-IAM-009 | P0 | Pending |
| FNE-IAM-010 | Account Lockout | 1.2.1 | TC-IAM-010 | P0 | Pending |
| FNE-IAM-011 | User Deactivation | 1.2.1 | TC-IAM-011 | P0 | Pending |
| FNE-IAM-012 | Access Review | 1.2.3 | TC-IAM-012 | P1 | Pending |
| FNE-IAM-013 | Privileged Access | 1.2.3 | TC-IAM-013 | P0 | Pending |
| FNE-IAM-014 | Service Account | 1.2.1 | TC-IAM-014 | P0 | Pending |
| FNE-IAM-015 | LDAP Integration | 1.2.5 | TC-IAM-015 | P2 | Pending |

C. MDM (FNE-MDM-001 s.d. FNE-MDM-024)

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-MDM-001 | Company Master | 1.3.1, 1.3.2 | TC-MDM-001 | P0 | Pending |
| FNE-MDM-002 | Business Unit | 1.3.1, 1.3.2 | TC-MDM-002 | P0 | Pending |
| FNE-MDM-003 | Location Master | 1.3.1, 1.3.2 | TC-MDM-003 | P0 | Pending |
| FNE-MDM-004 | Organization Structure | 1.3.1, 1.3.2 | TC-MDM-004 | P0 | Pending |
| FNE-MDM-005 | Product Master | 1.3.1, 1.3.2 | TC-MDM-005 | P0 | Pending |
| ... | ... | ... | ... | ... | ... |

### 3.7.3 RTM Maintenance

| Aktivitas | Frekuensi | Owner |
| --- | --- | --- |
| Update status requirement | Setiap Sprint | Tech Lead |
| Verifikasi traceability | Setiap Milestone | PM + Tech Lead |
| Review dengan stakeholder | Setiap Sprint Review | PM |
| Update jika ada perubahan | Saat Change Request approved | PM |

# BAB 4: MANAJEMEN JADWAL PROYEK

## (PROJECT SCHEDULE MANAGEMENT)

## 4.1 SCHEDULE MANAGEMENT APPROACH

### 4.1.1 Pendekatan Umum

Manajemen jadwal proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Metodologi | Agile (Scrum) dengan sprint 2 minggu untuk pengembangan, Waterfall untuk infrastruktur |
| Estimasi | Story Points untuk pengembangan, bottom-up untuk infrastruktur |
| Alat | Jira untuk sprint management, MS Project/Gantt Chart untuk milestone tracking |
| Pengendalian | Burndown chart, velocity tracking, milestone review |
| Pelaporan | Sprint report, weekly status, milestone report |

### 4.1.2 Proses Manajemen Jadwal

text

┌─────────────────────────────────────────────────────────────────────────────┐

│              PROSES MANAJEMEN JADWAL P-FNE-01                               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1. PERENCANAAN JADWAL                                                       │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Definisi aktivitas                                              │    │

│  │ • Estimasi durasi (bottom-up / story points)                      │    │

│  │ • Penentuan dependensi dan urutan                                 │    │

│  │ • Penyusunan Gantt Chart                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  2. PENYUSUNAN JADWAL                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Milestone Schedule                                               │    │

│  │ • Sprint Schedule                                                  │    │

│  │ • Resource Loading & Leveling                                      │    │

│  │ • Critical Path Analysis                                           │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  3. PENGENDALIAN JADWAL                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Sprint Burndown Tracking                                         │    │

│  │ • Velocity Tracking                                                │    │

│  │ • Earned Value Management (EVM)                                    │    │

│  │ • Change Control untuk perubahan jadwal                           │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  4. PELAPORAN JADWAL                                                         │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Sprint Report (setiap 2 minggu)                                  │    │

│  │ • Weekly Status Report                                             │    │

│  │ • Milestone Report (per milestone)                                 │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 4.2 ACTIVITY DEFINITION & SEQUENCING

### 4.2.1 High-Level Activities by Phase

| Fase | Aktivitas | Durasi (Minggu) | Dependensi |
| --- | --- | --- | --- |
| Fase 1: Infrastruktur | Environment Provisioning (IaC) | 2 | - |
|  | Kubernetes Cluster Setup | 1 | Environment |
|  | CI/CD Pipeline | 1 | Kubernetes |
|  | Monitoring & Logging | 1 | Kubernetes |
|  | Backup & DR | 1 | Monitoring |
| Fase 2: IAM | User Registration & Auth | 2 | Infrastructure |
|  | MFA Implementation | 1 | Auth |
|  | RBAC & Permission | 2 | Auth |
|  | SSO Implementation | 2 | RBAC |
|  | Session Management | 1 | Auth |
| Fase 3: MDM | Schema Design (24 entities) | 2 | IAM |
|  | CRUD Operations | 3 | Schema |
|  | Import/Export | 1 | CRUD |
|  | Duplicate Detection | 1 | CRUD |
|  | Versioning | 1 | CRUD |
| Fase 4: Audit & Logging | Audit Trail Implementation | 2 | IAM |
|  | Query & Export | 1 | Audit Trail |
|  | Security Logging | 1 | Audit Trail |
|  | Retention | 1 | Audit Trail |
| Fase 5: API Gateway | Gateway Setup | 1 | IAM, MDM |
|  | Routing & Rate Limit | 1 | Gateway |
|  | Auth at Gateway | 1 | Gateway, IAM |
|  | Documentation | 1 | All Services |
| Fase 6: Event Bus | Kafka Setup | 1 | Infrastructure |
|  | Publisher/Subscriber | 1 | Kafka |
|  | DLQ & Monitoring | 1 | Publisher |
| Fase 7: Workflow | Workflow Definition | 1 | IAM, MDM |
|  | Workflow Execution | 1 | Definition |
|  | Approval Matrix | 1 | Execution |
|  | Task Management | 1 | Execution |
| Fase 8: Notification | Multi-Channel Setup | 1 | IAM |
|  | Template Management | 1 | Notification |
|  | Preferences & History | 1 | Notification |
| Fase 9: Integration | Integration Testing | 1 | All Services |
|  | Performance Testing | 1 | Integration |
|  | Security Testing | 1 | Integration |
| Fase 10: Go-Live | UAT | 1 | Testing |
|  | Production Deployment | 0.5 | UAT |
|  | DR Drill | 0.5 | Deployment |
|  | Handover | 1 | DR Drill |

### 4.2.2 Dependencies Map

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    DEPENDENCIES MAP P-FNE-01                                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ┌─────────────┐                                                            │

│  │ INFRASTRUKTUR│                                                            │

│  │ (Minggu 1-4) │                                                            │

│  └──────┬──────┘                                                            │

│         │                                                                   │

│    ┌────┼────┬──────┬──────────┐                                           │

│    │    │    │      │          │                                           │

│    ▼    ▼    ▼      ▼          ▼                                           │

│  ┌─────┐ ┌─────┐ ┌─────┐ ┌───────┐ ┌─────────┐                           │

│  │IAM  │ │MDM  │ │AUDIT│ │KAFKA  │ │API GTWY │                           │

│  │(W5-8)│ │(W7-10)│ │(W9-11)│ │(W9-10) │ │(W10-11)│                           │

│  └──┬──┘ └──┬──┘ └──┬──┘ └───┬───┘ └────┬────┘                           │

│     │       │       │        │          │                                │

│     └───────┼───────┼────────┼──────────┤                                │

│             │       │        │          │                                │

│             ▼       ▼        ▼          ▼                                │

│           ┌─────────────────────────────────┐                            │

│           │        WORKFLOW & NOTIFICATION  │                            │

│           │          (W11-13)              │                            │

│           └────────────────┬────────────────┘                            │

│                            │                                              │

│                            ▼                                              │

│           ┌─────────────────────────────────┐                            │

│           │       INTEGRATION & TESTING     │                            │

│           │          (W14-18)              │                            │

│           └────────────────┬────────────────┘                            │

│                            │                                              │

│                            ▼                                              │

│           ┌─────────────────────────────────┐                            │

│           │       GO-LIVE & HANDOVER       │                            │

│           │          (W19-20)              │                            │

│           └─────────────────────────────────┘                            │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 4.2.3 Critical Path Analysis

Critical Path: Infrastructure → IAM → MDM → Workflow → Integration → Go-Live

| Aktivitas | Durasi (Minggu) | ES | EF | LS | LF | Float |
| --- | --- | --- | --- | --- | --- | --- |
| Infrastruktur | 4 | 0 | 4 | 0 | 4 | 0 |
| IAM | 4 | 4 | 8 | 4 | 8 | 0 |
| MDM | 4 | 8 | 12 | 8 | 12 | 0 |
| Audit | 3 | 8 | 11 | 9 | 12 | 1 |
| API Gateway | 2 | 8 | 10 | 10 | 12 | 2 |
| Event Bus | 2 | 8 | 10 | 10 | 12 | 2 |
| Workflow | 3 | 12 | 15 | 12 | 15 | 0 |
| Notification | 2 | 12 | 14 | 13 | 15 | 1 |
| Integration Testing | 2 | 15 | 17 | 15 | 17 | 0 |
| Performance Testing | 1 | 17 | 18 | 17 | 18 | 0 |
| Security Testing | 1 | 18 | 19 | 18 | 19 | 0 |
| UAT | 1 | 19 | 20 | 19 | 20 | 0 |
| Deployment & DR | 1 | 20 | 21 | 20 | 21 | 0 |
| Handover | 1 | 21 | 22 | 21 | 22 | 0 |

## 4.3 EFFORT & DURATION ESTIMATION

### 4.3.1 Estimation Methods

| Komponen | Metode Estimasi | Alasan |
| --- | --- | --- |
| Infrastructure | Bottom-up (expert judgment) | Aktivitas terdefinisi jelas, pengalaman sebelumnya |
| IAM | Story Points (Planning Poker) | Agile development, kompleksitas bervariasi |
| MDM | Story Points + Functional Points | 24 entity dengan kompleksitas berbeda |
| Audit | Bottom-up + Expert Judgment | Aktivitas terdefinisi jelas |
| API Gateway | Bottom-up | Konfigurasi vs custom development |
| Event Bus | Bottom-up | Setup dan integrasi |
| Workflow | Story Points | Custom development, kompleksitas tinggi |
| Notification | Story Points + Bottom-up | Multi-channel dengan kompleksitas berbeda |
| Integration Testing | Bottom-up | Aktivitas terdefinisi jelas |

### 4.3.2 Effort Estimation by Sprint

| Sprint | Durasi | Aktivitas | Story Points | Team Size |
| --- | --- | --- | --- | --- |
| Sprint 0 | 1 minggu | Infrastructure Setup | N/A | 5 (DevOps) |
| Sprint 1 | 2 minggu | IAM - Auth & MFA | 30 | 6 |
| Sprint 2 | 2 minggu | IAM - RBAC & SSO | 35 | 6 |
| Sprint 3 | 2 minggu | MDM - Schema & Core | 40 | 6 |
| Sprint 4 | 2 minggu | MDM - Advanced & Import/Export | 35 | 6 |
| Sprint 5 | 2 minggu | Audit & Logging | 30 | 6 |
| Sprint 6 | 2 minggu | API Gateway & Event Bus | 25 | 6 |
| Sprint 7 | 2 minggu | Workflow Engine | 35 | 6 |
| Sprint 8 | 2 minggu | Notification & Integration | 30 | 6 |
| Sprint 9 | 2 minggu | Testing & Quality | 20 | 8 |
| Sprint 10 | 1 minggu | Go-Live & Handover | N/A | 10 |
| Total | 20 minggu |  | 310 SP |  |

### 4.3.3 Velocity Planning

| Fase | Sprint | Planned Velocity | Actual Velocity | Notes |
| --- | --- | --- | --- | --- |
| Fase 1 | Sprint 0 | - | N/A | Infrastructure |
| Fase 2 | Sprint 1 | 25 | - | IAM Part 1 |
|  | Sprint 2 | 30 | - | IAM Part 2 |
| Fase 3 | Sprint 3 | 30 | - | MDM Part 1 |
|  | Sprint 4 | 30 | - | MDM Part 2 |
| Fase 4 | Sprint 5 | 25 | - | Audit |
| Fase 5 | Sprint 6 | 30 | - | Gateway & Event Bus |
| Fase 6 | Sprint 7 | 25 | - | Workflow |
| Fase 7 | Sprint 8 | 25 | - | Notification |
| Fase 8 | Sprint 9 | 20 | - | Testing |
| Fase 9 | Sprint 10 | - | - | Go-Live |

## 4.4 MILESTONE SCHEDULE

### 4.4.1 Major Milestones

| No | Milestone | Kode | Target Date | Deskripsi |
| --- | --- | --- | --- | --- |
| 1 | Project Kick-off | M0 | 01-Oct-2026 | Project Charter disetujui, team onboard |
| 2 | Infrastructure Ready | M1 | 29-Oct-2026 | K8s, CI/CD, Monitoring, Logging siap |
| 3 | IAM Service Complete | M2 | 26-Nov-2026 | Auth, MFA, RBAC, SSO functional |
| 4 | MDM Complete | M3 | 24-Dec-2026 | 24 entities, import/export functional |
| 5 | Audit & Logging Complete | M4 | 14-Jan-2027 | Audit trail, query, export functional |
| 6 | API Gateway & Event Bus | M5 | 28-Jan-2027 | Gateway routing, Kafka functional |
| 7 | Workflow & Notification | M6 | 11-Feb-2027 | 3 workflows, notification functional |
| 8 | Integration & Testing | M7 | 25-Feb-2027 | All services integrated, tested |
| 9 | Go-Live | M8 | 11-Mar-2027 | Production deployment, DR tested |
| 10 | Project Closure | M9 | 25-Mar-2027 | Handover, documentation complete |

### 4.4.2 Milestone Detailed Timeline

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    MILESTONE TIMELINE P-FNE-01                              │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  OCT 2026                                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Week 1-2  │ Infrastructure Setup                                    │    │

│  │ Week 3    │ CI/CD & Monitoring                                     │    │

│  │ Week 4    │ Backup & DR                                            │    │

│  │           │ ▼ M1: Infrastructure Ready (29-Oct-2026)               │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  NOV 2026                                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Week 5-6  │ IAM: Auth & MFA                                        │    │

│  │ Week 7-8  │ IAM: RBAC & SSO                                        │    │

│  │           │ ▼ M2: IAM Complete (26-Nov-2026)                      │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  DEC 2026                                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Week 9-10 │ MDM: Schema & CRUD (Part 1)                           │    │

│  │ Week 11-12│ MDM: Advanced & Import/Export (Part 2)                │    │

│  │           │ ▼ M3: MDM Complete (24-Dec-2026)                      │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  JAN 2027                                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Week 13-14│ Audit & Logging                                        │    │

│  │           │ ▼ M4: Audit Complete (14-Jan-2027)                    │    │

│  │ Week 15-16│ API Gateway & Event Bus                                │    │

│  │           │ ▼ M5: Gateway & Event Bus (28-Jan-2027)               │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  FEB 2027                                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Week 17-18│ Workflow Engine                                        │    │

│  │ Week 19   │ Notification Service                                   │    │

│  │           │ ▼ M6: Workflow & Notification (11-Feb-2027)           │    │

│  │ Week 20   │ Integration & Performance Testing                     │    │

│  │           │ ▼ M7: Integration Ready (25-Feb-2027)                 │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  MAR 2027                                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Week 21   │ UAT & Go-Live                                          │    │

│  │           │ ▼ M8: Go-Live (11-Mar-2027)                           │    │

│  │ Week 22   │ Handover & Closure                                    │    │

│  │           │ ▼ M9: Project Closure (25-Mar-2027)                   │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 4.5 GANTT CHART

### 4.5.1 Project Gantt Chart (Summary View)

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    GANTT CHART P-FNE-01 (SUMMARY)                           │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  FASE           │ OKT │ NOV │ DES │ JAN │ FEB │ MAR │

│──────────────────┼─────┼─────┼─────┼─────┼─────┼─────┤

│                  │     │     │     │     │     │     │

│  INFRASTRUKTUR   │███  │     │     │     │     │     │

│                  │█████│     │     │     │     │     │

│  IAM             │     │█████│██   │     │     │     │

│                  │     │█████│███  │     │     │     │

│  MDM             │     │     │█████│███  │     │     │

│                  │     │     │█████│████ │     │     │

│  AUDIT           │     │     │     │█████│██   │     │

│                  │     │     │     │█████│███  │     │

│  API GATEWAY     │     │     │     │██   │████  │     │

│                  │     │     │     │██   │█████│     │

│  EVENT BUS       │     │     │     │██   │████  │     │

│                  │     │     │     │██   │█████│     │

│  WORKFLOW        │     │     │     │     │█████│██   │

│                  │     │     │     │     │█████│███  │

│  NOTIFICATION    │     │     │     │     │██   │████  │

│                  │     │     │     │     │██   │█████│

│  INTEGRATION     │     │     │     │     │     │█████│

│                  │     │     │     │     │     │█████│

│  GO-LIVE         │     │     │     │     │     │███  │

│                  │     │     │     │     │     │████ │

│──────────────────┼─────┼─────┼─────┼─────┼─────┼─────┤

│  MILESTONES:                                                               │

│  M1: Infrastructure Ready █  M2: IAM Complete █  M3: MDM Complete █      │

│  M4: Audit Complete █  M5: Gateway & Event Bus █  M6: Workflow & Notif █ │

│  M7: Integration Ready █  M8: Go-Live █  M9: Closure █                   │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 4.5.2 Detailed Gantt Chart (Sprint Level)

| Sprint | Activity | Week 5-6 | Week 7-8 | Week 9-10 | Week 11-12 | Week 13-14 | Week 15-16 | Week 17-18 | Week 19-20 | Week 21-22 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S1 | IAM - Auth & MFA | ██████ |  |  |  |  |  |  |  |  |
| S2 | IAM - RBAC & SSO |  | ██████ |  |  |  |  |  |  |  |
| S3 | MDM - Schema & Core |  |  | ██████ |  |  |  |  |  |  |
| S4 | MDM - Advanced & Import |  |  |  | ██████ |  |  |  |  |  |
| S5 | Audit & Logging |  |  |  |  | ██████ |  |  |  |  |
| S6 | API Gateway & Event Bus |  |  |  |  |  | ██████ |  |  |  |
| S7 | Workflow Engine |  |  |  |  |  |  | ██████ |  |  |
| S8 | Notification & Integr |  |  |  |  |  |  |  | ██████ |  |
| S9 | Testing & Quality |  |  |  |  |  |  |  |  | ██████ |
| S10 | Go-Live & Handover |  |  |  |  |  |  |  |  | ██████ |

## 4.6 RESOURCE LOADING & LEVELING

### 4.6.1 Resource Requirements by Role

| Role | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager | 1 | 1 | 1 | 1 | 1 | 5 |
| DevOps Engineer | 3 | 2 | 2 | 2 | 1 | 10 |
| Backend Developer | 2 | 4 | 5 | 5 | 4 | 20 |
| Frontend Developer | 0 | 2 | 3 | 3 | 3 | 11 |
| Security Engineer | 1 | 2 | 2 | 1 | 1 | 7 |
| QA Engineer | 0 | 1 | 1 | 2 | 2 | 6 |
| Total | 7 | 12 | 14 | 14 | 12 | 59 |

### 4.6.2 Resource Loading Chart

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    RESOURCE LOADING CHART P-FNE-01                          │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  Role         │ Month 1 │ Month 2 │ Month 3 │ Month 4 │ Month 5 │

│────────────────┼─────────┼─────────┼─────────┼─────────┼─────────┤

│                │         │         │         │         │         │

│  PM            │ ███████ │ ███████ │ ███████ │ ███████ │ ███████ │

│                │   1     │   1     │   1     │   1     │   1     │

│  DevOps        │ ███████ │ ███████ │ ███████ │ ███████ │ ███████ │

│                │ ███████ │ ██████  │ ██████  │ ██████  │ ███████ │

│                │ ███████ │ ██████  │ ██████  │ ██████  │         │

│                │   3     │   2     │   2     │   2     │   1     │

│  Backend       │ ███████ │ ███████ │ ███████ │ ███████ │ ███████ │

│                │ ███████ │ ███████ │ ███████ │ ███████ │ ███████ │

│                │         │ ███████ │ ███████ │ ███████ │ ███████ │

│                │         │ ███████ │ ███████ │ ███████ │ ███████ │

│                │         │         │ ███████ │ ███████ │         │

│                │   2     │   4     │   5     │   5     │   4     │

│  Frontend      │         │ ███████ │ ███████ │ ███████ │ ███████ │

│                │         │ ███████ │ ███████ │ ███████ │ ███████ │

│                │         │         │ ███████ │ ███████ │ ███████ │

│                │   0     │   2     │   3     │   3     │   3     │

│  Security      │ ███████ │ ███████ │ ███████ │ ███████ │ ███████ │

│                │         │ ███████ │ ███████ │         │         │

│                │   1     │   2     │   2     │   1     │   1     │

│  QA            │         │ ███████ │ ███████ │ ███████ │ ███████ │

│                │         │         │         │ ███████ │ ███████ │

│                │   0     │   1     │   1     │   2     │   2     │

│────────────────┼─────────┼─────────┼─────────┼─────────┼─────────┤

│  Total         │   7     │   12    │   14    │   14    │   12    │

│                │         │         │         │         │         │

└─────────────────────────────────────────────────────────────────────────────┘

### 4.6.3 Resource Leveling

| Bulan | Required | Available | Gap | Action |
| --- | --- | --- | --- | --- |
| Month 1 | 7 | 10 | +3 | Rekrutmen bertahap |
| Month 2 | 12 | 12 | 0 | Optimal |
| Month 3 | 14 | 14 | 0 | Optimal |
| Month 4 | 14 | 14 | 0 | Optimal |
| Month 5 | 12 | 12 | 0 | Optimal |

## 4.7 SCHEDULE CONTROL

### 4.7.1 Earned Value Management (EVM)

| Metrik | Formula | Target |
| --- | --- | --- |
| Planned Value (PV) | Planned % Complete × BAC | Sesuai baseline |
| Earned Value (EV) | Actual % Complete × BAC | ≥ PV |
| Actual Cost (AC) | Actual cost incurred | ≤ BAC |
| Schedule Variance (SV) | EV - PV | ≥ 0 |
| Cost Variance (CV) | EV - AC | ≥ 0 |
| Schedule Performance Index (SPI) | EV / PV | ≥ 0.8 |
| Cost Performance Index (CPI) | EV / AC | ≥ 0.8 |

### 4.7.2 Schedule Reporting

| Jenis Laporan | Frekuensi | Isi | Penerima |
| --- | --- | --- | --- |
| Burndown Chart | Harian | Progress sprint vs planned | Tim Proyek |
| Sprint Report | Setiap Sprint | Sprint backlog, velocity, demo | Stakeholder |
| Weekly Status | Mingguan | Progress, risks, issues | PMO, Sponsor |
| Milestone Report | Per Milestone | Completion status, deliverables | Steering Committee |
| EVM Report | Bulanan | SV, CV, SPI, CPI, forecast | Sponsor, PMO |

### 4.7.3 Schedule Change Control

| Perubahan | Approval | Waktu Respons |
| --- | --- | --- |
| ≤ 5% dari baseline schedule | PM | 1 hari kerja |
| 5-20% dari baseline schedule | Sponsor | 2 hari kerja |
| > 20% dari baseline schedule | Steering Committee | 5 hari kerja |

### 4.7.4 Schedule Recovery Plan

| Situasi | Tindakan | Owner |
| --- | --- | --- |
| Velocity turun > 20% | Review backlog, reprioritisasi | PM + Tech Lead |
| Sprint burndown off-track | Daily scrum focus, remove blockers | Scrum Master |
| Milestone tertunda | Overtime, tambah resource, reduce scope | PM + Sponsor |
| Critical path delay | Fast tracking, crashing | PM + Tech Lead |
| Major blocker | Escalation to Steering Committee | PM |

# BAB 5: MANAJEMEN BIAYA PROYEK

## (PROJECT COST MANAGEMENT)

## 5.1 COST MANAGEMENT APPROACH

### 5.1.1 Pendekatan Umum

Manajemen biaya proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Metodologi Estimasi | Activity-Based Costing (ABC) berdasarkan aktivitas terjadwal |
| Referensi Tarif | Buku Billing Rate INKINDO 2026 untuk biaya personil dan biaya langsung |
| Alat | Spreadsheet untuk perhitungan detail, Jira untuk tracking effort |
| Pengendalian | Earned Value Management (EVM), variance analysis, forecasting |
| Pelaporan | Monthly financial report, budget vs actual analysis |

### 5.1.2 Sumber Referensi Biaya

Mengacu pada Buku Pedoman Standar Minimal Tahun 2026 INKINDO:

- Remunerasi/Biaya Personil (Billing Rate) - Menggunakan tarif standar untuk jenjang jabatan yang sesuai

- Biaya Langsung (Direct Cost) - Menggunakan indeks harga provinsi dan komponen biaya langsung lainnya

- Indeks Provinsi - Menggunakan indeks harga DKI Jakarta sebagai lokasi pelaksanaan proyek (kantor pusat)

## 5.2 COST ESTIMATION

### 5.2.1 Metodologi Estimasi Biaya

Proyek ini menggunakan pendekatan Activity-Based Costing (ABC) di mana biaya dihitung berdasarkan aktivitas yang terjadwal dalam Work Breakdown Structure (WBS).

Rumus Dasar Perhitungan:

text

Total Biaya Proyek = Σ (Biaya Personil) + Σ (Biaya Langsung) + Biaya Overhead + Biaya Lain-lain

Komponen Biaya:

| Komponen | Deskripsi | Sumber Referensi |
| --- | --- | --- |
| A. Biaya Personil (Billing Rate) | Biaya personil berdasarkan jenjang jabatan | INKINDO 2026 |
| B. Biaya Langsung (Direct Cost) | Perjalanan, akomodasi, peralatan, dll. | INKINDO 2026 + Market |
| C. Overhead | Administrasi, manajemen, dll. | 10-15% dari A+B |
| D. Keuntungan (Profit) | Margin yang wajar | 10-15% dari A+B+C |
| E. Pajak | PPN 11% | Peraturan Pajak |

### 5.2.2 Billing Rate INKINDO 2026 (DKI Jakarta)

Berdasarkan Buku INKINDO 2026, berikut adalah tarif Remunerasi/Biaya Personil (Billing Rate) per jam untuk jenjang jabatan yang relevan (dalam Rupiah):

| Jenjang Jabatan | Kode | Tarif per Jam (Rp) | Tarif per Hari (8 jam) | Tarif per Bulan (160 jam) |
| --- | --- | --- | --- | --- |
| Ahli Utama / Senior Expert | AU | 1.250.000 | 10.000.000 | 200.000.000 |
| Ahli Madya / Expert | AM | 950.000 | 7.600.000 | 152.000.000 |
| Ahli Muda / Junior Expert | AJ | 750.000 | 6.000.000 | 120.000.000 |
| Ahli Pratama / Analyst | AP | 550.000 | 4.400.000 | 88.000.000 |
| Tenaga Terampil / Skilled | TT | 375.000 | 3.000.000 | 60.000.000 |
| Tenaga Pendukung / Support | TP | 250.000 | 2.000.000 | 40.000.000 |

Catatan: Tarif di atas menggunakan indeks harga DKI Jakarta dan sudah termasuk biaya overhead dan keuntungan (billing rate all-in).

### 5.2.3 Mapping Tim Proyek ke Jenjang Jabatan

| Peran dalam Tim | Jumlah | Jenjang Jabatan INKINDO | Tarif per Jam (Rp) | Tarif per Bulan (160 jam) |
| --- | --- | --- | --- | --- |
| Project Manager | 1 | Ahli Madya (AM) | 950.000 | 152.000.000 |
| DevOps Lead | 1 | Ahli Madya (AM) | 950.000 | 152.000.000 |
| Backend Lead | 1 | Ahli Madya (AM) | 950.000 | 152.000.000 |
| Frontend Lead | 1 | Ahli Muda (AJ) | 750.000 | 120.000.000 |
| Security Lead | 1 | Ahli Madya (AM) | 950.000 | 152.000.000 |
| DevOps Engineer | 2 | Ahli Muda (AJ) | 750.000 | 120.000.000 |
| Backend Developer | 4 | Ahli Muda (AJ) | 750.000 | 120.000.000 |
| Frontend Developer | 2 | Ahli Muda (AJ) | 750.000 | 120.000.000 |
| Security Engineer | 1 | Ahli Muda (AJ) | 750.000 | 120.000.000 |
| QA Engineer | 2 | Ahli Pratama (AP) | 550.000 | 88.000.000 |

## 5.3 ACTIVITY-BASED BUDGETING

### 5.3.1 Infrastruktur & DevOps (Minggu 1-4)

| Aktivitas | Durasi (Hari) | Personil | Jumlah | Tarif/Hari | Total Biaya |
| --- | --- | --- | --- | --- | --- |
| Environment Provisioning (IaC) | 10 | DevOps Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | DevOps Eng | 2 | 6.000.000 | 120.000.000 |
|  |  | Security Eng | 1 | 6.000.000 | 60.000.000 |
| Kubernetes Cluster Setup | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | DevOps Eng | 2 | 6.000.000 | 60.000.000 |
| CI/CD Pipeline | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | DevOps Eng | 2 | 6.000.000 | 60.000.000 |
|  |  | Security Eng | 1 | 6.000.000 | 30.000.000 |
| Monitoring & Logging | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | DevOps Eng | 2 | 6.000.000 | 60.000.000 |
| Backup & DR | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | DevOps Eng | 1 | 6.000.000 | 30.000.000 |
| Secrets Management | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 38.000.000 |

Subtotal Biaya Personil Infrastruktur:

| Kategori | Total |
| --- | --- |
| DevOps Lead | 228.000.000 |
| DevOps Engineer | 270.000.000 |
| Security Lead | 38.000.000 |
| Security Engineer | 90.000.000 |
| Total Personil | 626.000.000 |

Biaya Langsung Infrastruktur:

| Item | Biaya |
| --- | --- |
| Cloud Infrastructure (AWS/GCP) - 4 bulan | 500.000.000 |
| Software Licenses | 100.000.000 |
| Total Direct Cost | 600.000.000 |

Total Biaya Infrastruktur:

| Komponen | Biaya |
| --- | --- |
| Biaya Personil | 626.000.000 |
| Biaya Langsung | 600.000.000 |
| Total Infrastruktur | 1.226.000.000 |

### 5.3.2 Identity & Access Management (IAM) - Sprint 1-2 (Minggu 5-8)

| Aktivitas | Durasi (Hari) | Personil | Jumlah | Tarif/Hari | Total Biaya |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 (Minggu 5-6): Auth & MFA |  |  |  |  |  |
| User Registration & Auth | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 120.000.000 |
|  |  | Frontend Lead | 1 | 6.000.000 | 60.000.000 |
|  |  | Frontend Dev | 1 | 6.000.000 | 60.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 44.000.000 |
| MFA Implementation | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 60.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| Sprint 2 (Minggu 7-8): RBAC & SSO |  |  |  |  |  |
| RBAC & Permission | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 3 | 6.000.000 | 180.000.000 |
|  |  | Frontend Lead | 1 | 6.000.000 | 60.000.000 |
|  |  | Frontend Dev | 1 | 6.000.000 | 60.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 44.000.000 |
| SSO Implementation | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 60.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| Session Management | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 38.000.000 |

Subtotal Biaya Personil IAM:

| Kategori | Total |
| --- | --- |
| Backend Lead | 266.000.000 |
| Backend Developer | 450.000.000 |
| Frontend Lead | 120.000.000 |
| Frontend Developer | 120.000.000 |
| Security Lead | 266.000.000 |
| QA Engineer | 132.000.000 |
| Total Personil | 1.354.000.000 |

Total Biaya IAM:

| Komponen | Biaya |
| --- | --- |
| Biaya Personil | 1.354.000.000 |
| Biaya Langsung | 50.000.000 |
| Total IAM | 1.404.000.000 |

### 5.3.3 Master Data Management (MDM) - Sprint 3-4 (Minggu 9-12)

| Aktivitas | Durasi (Hari) | Personil | Jumlah | Tarif/Hari | Total Biaya |
| --- | --- | --- | --- | --- | --- |
| Sprint 3 (Minggu 9-10): Schema & Core CRUD |  |  |  |  |  |
| Schema Design (24 entities) | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 3 | 6.000.000 | 180.000.000 |
|  |  | PM | 1 | 7.600.000 | 76.000.000 |
| CRUD Operations (Part 1) | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 3 | 6.000.000 | 180.000.000 |
|  |  | Frontend Lead | 1 | 6.000.000 | 60.000.000 |
|  |  | Frontend Dev | 1 | 6.000.000 | 60.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 44.000.000 |
| Sprint 4 (Minggu 11-12): Advanced & Import/Export |  |  |  |  |  |
| CRUD Operations (Part 2) | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 3 | 6.000.000 | 180.000.000 |
|  |  | Frontend Lead | 1 | 6.000.000 | 60.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 44.000.000 |
| Import/Export Functionality | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 60.000.000 |
|  |  | Frontend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| Duplicate Detection | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 60.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| Versioning | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 1 | 6.000.000 | 30.000.000 |

Subtotal Biaya Personil MDM:

| Kategori | Total |
| --- | --- |
| Project Manager | 76.000.000 |
| Backend Lead | 342.000.000 |
| Backend Developer | 690.000.000 |
| Frontend Lead | 120.000.000 |
| Frontend Developer | 90.000.000 |
| QA Engineer | 132.000.000 |
| Total Personil | 1.450.000.000 |

Total Biaya MDM:

| Komponen | Biaya |
| --- | --- |
| Biaya Personil | 1.450.000.000 |
| Biaya Langsung | 50.000.000 |
| Total MDM | 1.500.000.000 |

### 5.3.4 Audit & Logging - Sprint 5 (Minggu 13-14)

| Aktivitas | Durasi (Hari) | Personil | Jumlah | Tarif/Hari | Total Biaya |
| --- | --- | --- | --- | --- | --- |
| Audit Trail Implementation | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 120.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 44.000.000 |
| Query & Export | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | Frontend Lead | 1 | 6.000.000 | 30.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| Security Logging | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| Retention & Archival | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | DevOps Lead | 1 | 7.600.000 | 38.000.000 |

Subtotal Biaya Personil Audit:

| Kategori | Total |
| --- | --- |
| Backend Lead | 190.000.000 |
| Backend Developer | 150.000.000 |
| Frontend Lead | 30.000.000 |
| Security Lead | 114.000.000 |
| DevOps Lead | 38.000.000 |
| QA Engineer | 88.000.000 |
| Total Personil | 610.000.000 |

Total Biaya Audit:

| Komponen | Biaya |
| --- | --- |
| Biaya Personil | 610.000.000 |
| Biaya Langsung | 30.000.000 |
| Total Audit | 640.000.000 |

### 5.3.5 API Gateway & Event Bus - Sprint 6 (Minggu 15-16)

| Aktivitas | Durasi (Hari) | Personil | Jumlah | Tarif/Hari | Total Biaya |
| --- | --- | --- | --- | --- | --- |
| API Gateway |  |  |  |  |  |
| Gateway Setup (Kong/Traefik) | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 38.000.000 |
| Routing & Rate Limiting | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| Auth at Gateway | 5 | Security Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 1 | 6.000.000 | 30.000.000 |
| Documentation | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
| Event Bus |  |  |  |  |  |
| Kafka Cluster Setup | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Lead | 1 | 7.600.000 | 38.000.000 |
| Publisher/Subscriber | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 60.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| DLQ & Monitoring | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |

Subtotal Biaya Personil API Gateway & Event Bus:

| Kategori | Total |
| --- | --- |
| DevOps Lead | 190.000.000 |
| Backend Lead | 228.000.000 |
| Backend Developer | 90.000.000 |
| Security Lead | 76.000.000 |
| QA Engineer | 66.000.000 |
| Total Personil | 650.000.000 |

Total Biaya API Gateway & Event Bus:

| Komponen | Biaya |
| --- | --- |
| Biaya Personil | 650.000.000 |
| Biaya Langsung | 100.000.000 |
| Total API Gateway & Event Bus | 750.000.000 |

### 5.3.6 Workflow Engine - Sprint 7 (Minggu 17-18)

| Aktivitas | Durasi (Hari) | Personil | Jumlah | Tarif/Hari | Total Biaya |
| --- | --- | --- | --- | --- | --- |
| Workflow Definition | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 120.000.000 |
|  |  | PM | 1 | 7.600.000 | 76.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 44.000.000 |
| Workflow Execution | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 120.000.000 |
|  |  | Frontend Lead | 1 | 6.000.000 | 60.000.000 |
|  |  | Frontend Dev | 1 | 6.000.000 | 60.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 44.000.000 |
| Approval Matrix | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |
| Task Management | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | Frontend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |

Subtotal Biaya Personil Workflow:

| Kategori | Total |
| --- | --- |
| Project Manager | 76.000.000 |
| Backend Lead | 228.000.000 |
| Backend Developer | 300.000.000 |
| Frontend Lead | 60.000.000 |
| Frontend Developer | 90.000.000 |
| QA Engineer | 132.000.000 |
| Total Personil | 886.000.000 |

Total Biaya Workflow:

| Komponen | Biaya |
| --- | --- |
| Biaya Personil | 886.000.000 |
| Biaya Langsung | 40.000.000 |
| Total Workflow | 926.000.000 |

### 5.3.7 Notification Service - Sprint 8 (Minggu 19-20)

| Aktivitas | Durasi (Hari) | Personil | Jumlah | Tarif/Hari | Total Biaya |
| --- | --- | --- | --- | --- | --- |
| Multi-Channel Setup | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 120.000.000 |
|  |  | Security Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 44.000.000 |
| Template Management | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | Frontend Lead | 1 | 6.000.000 | 30.000.000 |
| Preferences & History | 5 | Backend Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Backend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | Frontend Dev | 1 | 6.000.000 | 30.000.000 |
|  |  | QA Engineer | 1 | 4.400.000 | 22.000.000 |

Subtotal Biaya Personil Notification:

| Kategori | Total |
| --- | --- |
| Backend Lead | 152.000.000 |
| Backend Developer | 180.000.000 |
| Frontend Lead | 30.000.000 |
| Frontend Developer | 30.000.000 |
| Security Lead | 76.000.000 |
| QA Engineer | 66.000.000 |
| Total Personil | 534.000.000 |

Total Biaya Notification:

| Komponen | Biaya |
| --- | --- |
| Biaya Personil | 534.000.000 |
| Biaya Langsung | 30.000.000 |
| Total Notification | 564.000.000 |

### 5.3.8 Integration, Testing, UAT & Go-Live - Sprint 9-10 (Minggu 21-22)

| Aktivitas | Durasi (Hari) | Personil | Jumlah | Tarif/Hari | Total Biaya |
| --- | --- | --- | --- | --- | --- |
| Sprint 9 (Minggu 21): Testing |  |  |  |  |  |
| Integration Testing | 10 | Backend Lead | 1 | 7.600.000 | 76.000.000 |
|  |  | Backend Dev | 2 | 6.000.000 | 120.000.000 |
|  |  | QA Engineer | 2 | 4.400.000 | 88.000.000 |
| Performance Testing | 5 | DevOps Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | QA Engineer | 2 | 4.400.000 | 44.000.000 |
| Security Testing | 5 | Security Lead | 1 | 7.600.000 | 38.000.000 |
|  |  | Security Eng | 1 | 6.000.000 | 30.000.000 |
| Sprint 10 (Minggu 22): Go-Live |  |  |  |  |  |
| UAT | 5 | PM | 1 | 7.600.000 | 38.000.000 |
|  |  | QA Engineer | 2 | 4.400.000 | 44.000.000 |
|  |  | Tech Leads | 5 | 7.000.000 | 175.000.000 |
| Production Deployment | 3 | DevOps Lead | 1 | 7.600.000 | 22.800.000 |
|  |  | DevOps Eng | 2 | 6.000.000 | 36.000.000 |
| DR Drill | 2 | DevOps Lead | 1 | 7.600.000 | 15.200.000 |
|  |  | DevOps Eng | 2 | 6.000.000 | 24.000.000 |
|  |  | Security Eng | 1 | 6.000.000 | 12.000.000 |
| Handover | 5 | PM | 1 | 7.600.000 | 38.000.000 |
|  |  | Tech Leads | 5 | 7.000.000 | 175.000.000 |
|  |  | Documentation | 2 | 4.400.000 | 44.000.000 |

Subtotal Biaya Personil Testing & Go-Live:

| Kategori | Total |
| --- | --- |
| Project Manager | 76.000.000 |
| Backend Lead | 76.000.000 |
| Backend Developer | 120.000.000 |
| DevOps Lead | 76.000.000 |
| DevOps Engineer | 60.000.000 |
| Security Lead | 38.000.000 |
| Security Engineer | 42.000.000 |
| Tech Leads (5 orang) | 350.000.000 |
| QA Engineer | 176.000.000 |
| Documentation (2 org) | 44.000.000 |
| Total Personil | 1.058.000.000 |

Total Biaya Testing & Go-Live:

| Komponen | Biaya |
| --- | --- |
| Biaya Personil | 1.058.000.000 |
| Biaya Langsung | 100.000.000 |
| Total Testing & Go-Live | 1.158.000.000 |

## 5.4 TOTAL BUDGET SUMMARY

### 5.4.1 Ringkasan Biaya Per Fase

| No | Fase / Komponen | Biaya Personil | Biaya Langsung | Total |
| --- | --- | --- | --- | --- |
| 1 | Infrastruktur & DevOps | 626.000.000 | 600.000.000 | 1.226.000.000 |
| 2 | Identity & Access Management | 1.354.000.000 | 50.000.000 | 1.404.000.000 |
| 3 | Master Data Management | 1.450.000.000 | 50.000.000 | 1.500.000.000 |
| 4 | Audit & Logging | 610.000.000 | 30.000.000 | 640.000.000 |
| 5 | API Gateway & Event Bus | 650.000.000 | 100.000.000 | 750.000.000 |
| 6 | Workflow Engine | 886.000.000 | 40.000.000 | 926.000.000 |
| 7 | Notification Service | 534.000.000 | 30.000.000 | 564.000.000 |
| 8 | Integration, Testing & Go-Live | 1.058.000.000 | 100.000.000 | 1.158.000.000 |
| 9 | Project Management & Overhead | 200.000.000 | - | 200.000.000 |
| Total Biaya Langsung Proyek | 7.368.000.000 | 1.000.000.000 | 8.368.000.000 |  |

### 5.4.2 Biaya Overhead & Administrasi (10%)

| Komponen | Biaya |
| --- | --- |
| Overhead & Administrasi (10% dari Biaya Langsung) | 836.800.000 |
| Total dengan Overhead | 9.204.800.000 |

### 5.4.3 Biaya Keuntungan (Margin) & Pajak

| Komponen | Biaya |
| --- | --- |
| Keuntungan (12% dari Biaya + Overhead) | 1.104.576.000 |
| Pajak Pertambahan Nilai (PPN 11%) | 1.133.030.336 |
| Total Keseluruhan | 11.442.406.336 |

### 5.4.4 Detail Breakdown per Kategori Personil

| Jenjang Jabatan | Jumlah Orang | Total Bulan | Tarif/Bulan | Total Biaya |
| --- | --- | --- | --- | --- |
| Ahli Madya (PM, Leads) | 5 | 5 | 152.000.000 | 3.800.000.000 |
| Ahli Muda (Developers, Engineers) | 10 | 5 | 120.000.000 | 6.000.000.000 |
| Ahli Pratama (QA, Documentation) | 3 | 5 | 88.000.000 | 1.320.000.000 |
| Total Personil | 18 |  |  | 11.120.000.000 |

Catatan: Perhitungan di atas adalah total akumulasi dari semua aktivitas.

## 5.5 CASH FLOW PROJECTION

### 5.5.1 Cash Flow per Bulan

| Bulan | Aktivitas | Biaya (Rp) | Kumulatif (Rp) |
| --- | --- | --- | --- |
| Bulan 1 (Okt 2026) | Infrastructure Setup | 800.000.000 | 800.000.000 |
| Bulan 2 (Nov 2026) | IAM + MDM Partial | 1.200.000.000 | 2.000.000.000 |
| Bulan 3 (Des 2026) | MDM + Audit | 1.200.000.000 | 3.200.000.000 |
| Bulan 4 (Jan 2027) | API Gateway + Event Bus + Partial Workflow | 1.200.000.000 | 4.400.000.000 |
| Bulan 5 (Feb 2027) | Workflow + Notification + Testing | 1.500.000.000 | 5.900.000.000 |
| Bulan 6 (Mar 2027) | UAT + Go-Live + Handover | 1.200.000.000 | 7.100.000.000 |
| Total Biaya Personil & Langsung |  | 8.368.000.000 |  |
| Overhead (10%) |  | 836.800.000 | 8.000.000.000* |
| Total Biaya (tanpa Pajak) |  | 9.204.800.000 |  |
| Pajak (PPN 11%) |  | 1.133.030.336 |  |
| Grand Total |  | 11.442.406.336 |  |

Keterangan: Overhead dibayarkan secara proporsional setiap bulan.

## 5.6 COST CONTROL

### 5.6.1 Earned Value Management (EVM)

| Metrik | Formula | Target | Tracking |
| --- | --- | --- | --- |
| Planned Value (PV) | Planned % Complete × BAC | Sesuai baseline | Bulanan |
| Earned Value (EV) | Actual % Complete × BAC | ≥ PV | Bulanan |
| Actual Cost (AC) | Actual cost incurred | ≤ BAC | Bulanan |
| Schedule Variance (SV) | EV - PV | ≥ 0 | Bulanan |
| Cost Variance (CV) | EV - AC | ≥ 0 | Bulanan |
| Schedule Performance Index (SPI) | EV / PV | ≥ 0.8 | Bulanan |
| Cost Performance Index (CPI) | EV / AC | ≥ 0.8 | Bulanan |
| Estimate at Completion (EAC) | BAC / CPI | ≤ BAC | Bulanan |

### 5.6.2 Budget Baseline

| Bulan | Planned Value (PV) | Actual Cost (AC) | Earned Value (EV) | SV | CV |
| --- | --- | --- | --- | --- | --- |
| Okt 2026 | 800.000.000 | - | - | - | - |
| Nov 2026 | 1.200.000.000 | - | - | - | - |
| Des 2026 | 1.200.000.000 | - | - | - | - |
| Jan 2027 | 1.200.000.000 | - | - | - | - |
| Feb 2027 | 1.500.000.000 | - | - | - | - |
| Mar 2027 | 1.200.000.000 | - | - | - | - |

### 5.6.3 Cost Control Mechanisms

| No | Mekanisme | Deskripsi | Frekuensi |
| --- | --- | --- | --- |
| 1 | Budget Review | Review actual vs budget | Bulanan |
| 2 | Variance Analysis | Analisis penyimpangan biaya | Bulanan |
| 3 | Forecasting | Proyeksi biaya akhir | Bulanan |
| 4 | Change Control | Perubahan budget melalui CCB | As needed |
| 5 | Resource Optimization | Optimalisasi penggunaan sumber daya | Berkelanjutan |
| 6 | Vendor Management | Negosiasi dan monitoring vendor | As needed |

### 5.6.4 Variance Reporting

| Jenis Pelaporan | Penerima | Frekuensi | Isi |
| --- | --- | --- | --- |
| Monthly Financial Report | Sponsor, PMO | Bulanan | Actual vs Budget, Variance, Forecast |
| Budget Burn Rate | PM | Mingguan | Biaya yang sudah dikeluarkan, sisa budget |
| EVM Report | PM, Sponsor | Bulanan | SV, CV, SPI, CPI, EAC |
| Cash Flow Report | Finance | Bulanan | Arus kas actual vs planned |

# BAB 6: MANAJEMEN KUALITAS PROYEK

## (PROJECT QUALITY MANAGEMENT)

## 6.1 QUALITY MANAGEMENT APPROACH

### 6.1.1 Pendekatan Umum

Manajemen kualitas proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Filosofi | Quality by Design & Continuous Improvement |
| Standar | ISO 9001:2015, ISO 27001:2022, OWASP Top 10, PMBOK Quality Management |
| Metodologi | Quality Assurance (QA) dan Quality Control (QC) terintegrasi dalam sprint |
| Alat | SonarQube, Selenium, JMeter, OWASP ZAP, Jira, Confluence |
| Pengendalian | Quality Gates setiap deployment, Defect Management, UAT |

### 6.1.2 Proses Manajemen Kualitas

text

┌─────────────────────────────────────────────────────────────────────────────┐

│              PROSES MANAJEMEN KUALITAS P-FNE-01                             │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1. PERENCANAAN KUALITAS                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penetapan standar dan metrik kualitas                            │    │

│  │ • Penyusunan Quality Management Plan                               │    │

│  │ • Penetapan acceptance criteria                                   │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  2. JAMINAN KUALITAS (QUALITY ASSURANCE)                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Proses review dan inspeksi                                       │    │

│  │ • Code review (peer review)                                        │    │

│  │ • Dokumentasi standar                                             │    │

│  │ • Training dan onboarding                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  3. PENGENDALIAN KUALITAS (QUALITY CONTROL)                                 │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Unit testing                                                     │    │

│  │ • Integration testing                                              │    │

│  │ • Performance testing                                              │    │

│  │ • Security testing                                                 │    │

│  │ • UAT (User Acceptance Testing)                                    │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  4. PENINGKATAN BERKELANJUTAN                                               │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Sprint retrospective                                             │    │

│  │ • Lessons learned                                                 │    │

│  │ • Process improvement                                             │    │

│  │ • Metrics analysis                                                │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 6.2 QUALITY POLICY & STANDARDS

### 6.2.1 Quality Policy

"Kami berkomitmen untuk menghasilkan produk perangkat lunak berkualitas tinggi yang aman, handal, dan memenuhi kebutuhan pengguna, melalui proses pengembangan yang terstandarisasi dan perbaikan berkelanjutan."

### 6.2.2 Standar Kualitas yang Digunakan

| No | Standar | Deskripsi | Penerapan |
| --- | --- | --- | --- |
| 1 | ISO 9001:2015 | Sistem Manajemen Mutu | Proses pengembangan dan manajemen proyek |
| 2 | ISO 27001:2022 | Keamanan Informasi | Keamanan data dan sistem |
| 3 | OWASP Top 10 | Keamanan Aplikasi Web | Security testing dan code review |
| 4 | IEEE 829 | Dokumentasi Testing | Test plan, test cases, test report |
| 5 | OpenAPI 3.0 | Dokumentasi API | API specification dan documentation |
| 6 | JSON Schema | Validasi Data | Validasi data master dan event schema |
| 7 | Google Java Style Guide | Code Style | Standar penulisan kode Java |
| 8 | ESLint + Prettier | Code Style | Standar penulisan kode TypeScript/JavaScript |
| 9 | Semantic Versioning | Versioning | Versioning API dan library |

### 6.2.3 Code Quality Standards

| Aspek | Standar | Alat |
| --- | --- | --- |
| Code Style | Google Java Style Guide / Airbnb JavaScript Style | Checkstyle / ESLint |
| Code Coverage | Minimal 80% | SonarQube / JaCoCo |
| Code Complexity | Cyclomatic Complexity < 10 | SonarQube |
| Code Duplication | Duplicasi < 3% | SonarQube |
| Code Smells | Zero critical code smells | SonarQube |
| Security Hotspots | Zero critical security hotspots | SonarQube / OWASP ZAP |
| Technical Debt | < 5% dari total effort | SonarQube |

## 6.3 QUALITY METRICS & KPIs

### 6.3.1 Quality Metrics

| No | Metrik | Target | Pengukuran | Frekuensi |
| --- | --- | --- | --- | --- |
| 1 | Code Coverage | ≥ 80% | SonarQube | Per Sprint |
| 2 | Code Quality Gate | Passed | SonarQube | Per Deployment |
| 3 | Security Scan | Zero Critical | OWASP ZAP / Snyk | Per Sprint |
| 4 | API Response Time (Median) | ≤ 500ms | JMeter / Monitoring | Per Milestone |
| 5 | API Response Time (P95) | ≤ 2 detik | JMeter / Monitoring | Per Milestone |
| 6 | System Availability | ≥ 99.9% | Prometheus/Grafana | Harian |
| 7 | Defect Density | < 1 per 1000 LOC | SonarQube / Jira | Per Sprint |
| 8 | Defect Resolution Time | < 2 hari (Critical) | Jira | Per Sprint |
| 9 | Test Pass Rate | ≥ 95% | CI/CD Pipeline | Per Deployment |
| 10 | UAT Satisfaction | ≥ 90% | Survey | Akhir Proyek |
| 11 | API Documentation Coverage | 100% | Swagger/OpenAPI | Per Deployment |
| 12 | Database Query Time | ≤ 200ms | Monitoring | Per Milestone |
| 13 | Event Processing Latency | ≤ 2 detik | Kafka Monitoring | Per Milestone |
| 14 | RPO Compliance | ≤ 15 menit | DR Drill | Per Milestone |
| 15 | RTO Compliance | ≤ 2 jam | DR Drill | Per Milestone |

### 6.3.2 Quality KPIs Dashboard

| KPI | Target | Actual | Status |
| --- | --- | --- | --- |
| Code Coverage | ≥ 80% | - | ⬜ Pending |
| Quality Gate | Passed | - | ⬜ Pending |
| Security Vulnerabilities | 0 Critical | - | ⬜ Pending |
| API Latency (Median) | ≤ 500ms | - | ⬜ Pending |
| System Availability | ≥ 99.9% | - | ⬜ Pending |
| Defect Density | < 1/1000 LOC | - | ⬜ Pending |
| UAT Satisfaction | ≥ 90% | - | ⬜ Pending |

## 6.4 QUALITY ASSURANCE (QA) ACTIVITIES

### 6.4.1 Quality Assurance Activities per Phase

| Fase | QA Activity | Owner | Frekuensi |
| --- | --- | --- | --- |
| Perencanaan | • Quality Management Plan review • Acceptance criteria review • Standards and guidelines training | PM, QA Lead | Awal proyek |
| Pengembangan | • Code review (peer review) • Static code analysis (SonarQube) • Coding standards compliance • Security review (SAST) | Tech Lead, QA Lead | Per Pull Request |
| Testing | • Test plan review • Test case review • Test execution monitoring • Defect management | QA Lead | Per Sprint |
| Deployment | • Deployment checklist review • Environment validation • Configuration validation | DevOps Lead | Per Deployment |
| Go-Live | • Pre-go-live checklist • UAT execution • Post-implementation review | PM, QA Lead | Sebelum Go-Live |

### 6.4.2 Code Review Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    CODE REVIEW PROCESS P-FNE-01                             │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  STEP 1: DEVELOPER                                                          │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Menulis kode dengan mengikuti coding standards                   │    │

│  │ • Menulis unit test (coverage ≥ 80%)                               │    │

│  │ • Menjalankan test secara lokal (semua lulus)                     │    │

│  │ • Membuat pull request ke repository                              │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 2: AUTOMATED CHECKS                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • CI/CD pipeline menjalankan:                                      │    │

│  │   - Unit test                                                      │    │

│  │   - Code coverage (SonarQube)                                     │    │

│  │   - Static code analysis (SonarQube)                              │    │

│  │   - Security scan (SAST)                                          │    │

│  │   - Code style check                                              │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 3: PEER REVIEW                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Minimal 1 reviewer (Tech Lead atau Senior Developer)            │    │

│  │ • Review checklist:                                               │    │

│  │   - Code logic correctness                                        │    │

│  │   - Code style compliance                                          │    │

│  │   - Test coverage adequacy                                         │    │

│  │   - Security considerations                                        │    │

│  │   - Performance implications                                       │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 4: APPROVAL & MERGE                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Reviewer memberikan approval atau feedback                       │    │

│  │ • Developer memperbaiki feedback                                   │    │

│  │ • Merge ke branch utama setelah approval                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.4.3 Code Review Checklist

| No | Aspek | Check |
| --- | --- | --- |
| 1 | Functionality | Kode bekerja sesuai requirement | [ ] |
| 2 | Correctness | Logika benar dan tidak ada bug | [ ] |
| 3 | Test Coverage | Unit test mencakup semua edge cases | [ ] |
| 4 | Code Style | Mengikuti coding standards | [ ] |
| 5 | Readability | Kode mudah dibaca dan dipahami | [ ] |
| 6 | Security | Tidak ada security vulnerability | [ ] |
| 7 | Performance | Tidak ada performance issue | [ ] |
| 8 | Error Handling | Error handling yang baik | [ ] |
| 9 | Logging | Logging yang adequate | [ ] |
| 10 | Documentation | Dokumentasi kode yang cukup | [ ] |

## 6.5 QUALITY CONTROL (QC) ACTIVITIES

### 6.5.1 Testing Strategy

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    TESTING STRATEGY P-FNE-01                                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ┌─────────────────────────────────────────────────────────────────────────┐│

│  │                    TESTING PYRAMID                                      ││

│  │                                                                          ││

│  │        /\                                                               ││

│  │       /  \     E2E Testing (5-10%)                                     ││

│  │      /    \    Manual/Automated E2E testing                            ││

│  │     /──────\                                                            ││

│  │    /        \   Integration Testing (20-30%)                           ││

│  │   /          \  API testing, Service integration testing               ││

│  │  /────────────\                                                         ││

│  │ /              \  Unit Testing (60-70%)                                ││

│  │/                \ Component testing, Coverage ≥ 80%                    ││

│  └─────────────────────────────────────────────────────────────────────────┘│

│                                                                              │

│  ┌─────────────────────────────────────────────────────────────────────────┐│

│  │                    TESTING LEVELS                                       ││

│  │                                                                          ││

│  │  LEVEL 1: UNIT TESTING                                                  ││

│  │  ┌─────────────────────────────────────────────────────────────────┐    ││

│  │  │ • Developer menjalankan unit test setelah coding              │    ││

│  │  │ • JUnit 5 / TestNG untuk Java, Jest untuk TypeScript          │    ││

│  │  │ • Target coverage ≥ 80%                                        │    ││

│  │  └─────────────────────────────────────────────────────────────────┘    ││

│  │                                                                          ││

│  │  LEVEL 2: INTEGRATION TESTING                                            ││

│  │  ┌─────────────────────────────────────────────────────────────────┐    ││

│  │  │ • Testing antar service                                        │    ││

│  │  │ • Spring Boot Test / Testcontainers untuk Java                 │    ││

│  │  │ • Contract testing (Pact)                                      │    ││

│  │  └─────────────────────────────────────────────────────────────────┘    ││

│  │                                                                          ││

│  │  LEVEL 3: API TESTING                                                    ││

│  │  ┌─────────────────────────────────────────────────────────────────┐    ││

│  │  │ • REST API testing menggunakan Postman / Newman               │    ││

│  │  │ • API contract validation                                       │    ││

│  │  │ • Rate limiting testing                                         │    ││

│  │  └─────────────────────────────────────────────────────────────────┘    ││

│  │                                                                          ││

│  │  LEVEL 4: PERFORMANCE TESTING                                            ││

│  │  ┌─────────────────────────────────────────────────────────────────┐    ││

│  │  │ • Load testing menggunakan JMeter                            │    ││

│  │  │ • Stress testing                                                │    ││

│  │  │ • Endurance testing                                             │    ││

│  │  └─────────────────────────────────────────────────────────────────┘    ││

│  │                                                                          ││

│  │  LEVEL 5: SECURITY TESTING                                               ││

│  │  ┌─────────────────────────────────────────────────────────────────┐    ││

│  │  │ • SAST (Static Application Security Testing)                  │    ││

│  │  │ • DAST (Dynamic Application Security Testing)                 │    ││

│  │  │ • Vulnerability scanning (OWASP ZAP)                         │    ││

│  │  └─────────────────────────────────────────────────────────────────┘    ││

│  │                                                                          ││

│  │  LEVEL 6: UAT (User Acceptance Testing)                                  ││

│  │  ┌─────────────────────────────────────────────────────────────────┐    ││

│  │  │ • Business user testing                                        │    ││

│  │  │ • End-to-end scenario testing                                  │    ││

│  │  │ • User satisfaction survey                                     │    ││

│  │  └─────────────────────────────────────────────────────────────────┘    ││

│  │                                                                          ││

│  └─────────────────────────────────────────────────────────────────────────┘│

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.5.2 Test Cases by Module

| Modul | Unit Test Cases | Integration Test Cases | API Test Cases | Performance Test Cases | Security Test Cases |
| --- | --- | --- | --- | --- | --- |
| IAM | 50 | 20 | 30 | 5 | 15 |
| MDM | 80 | 30 | 40 | 5 | 10 |
| Audit | 30 | 15 | 20 | 5 | 5 |
| API Gateway | 20 | 25 | 30 | 10 | 10 |
| Event Bus | 25 | 20 | 15 | 5 | 5 |
| Workflow | 40 | 20 | 25 | 5 | 5 |
| Notification | 30 | 15 | 20 | 5 | 5 |
| Total | 275 | 145 | 180 | 40 | 55 |

### 6.5.3 Quality Gates

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    QUALITY GATES P-FNE-01                                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  GATE 1: CODE COMMIT                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Build success                                                     │    │

│  │ • Unit test pass                                                    │    │

│  │ • Code coverage ≥ 80%                                              │    │

│  │ • No critical code smells                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  GATE 2: CODE REVIEW                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Peer review approved                                              │    │

│  │ • Security review approved                                         │    │

│  │ • Documentation updated                                            │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  GATE 3: DEPLOYMENT TO TEST                                                 │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Integration test pass                                            │    │

│  │ • API test pass                                                    │    │

│  │ • No critical security issues                                      │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  GATE 4: DEPLOYMENT TO STAGING                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Performance test pass                                            │    │

│  │ • Load test pass                                                   │    │

│  │ • UAT test pass                                                    │    │

│  │ • All acceptance criteria met                                     │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  GATE 5: DEPLOYMENT TO PRODUCTION                                           │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Final security scan pass                                         │    │

│  │ • Production smoke test pass                                      │    │

│  │ • Rollback plan ready                                              │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.5.4 Defect Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    DEFECT MANAGEMENT PROCESS P-FNE-01                       │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  STEP 1: DEFECT DETECTION                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Ditemukan oleh developer, QA, atau user                          │    │

│  │ • Defect dilaporkan di Jira                                        │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 2: DEFECT CLASSIFICATION                                               │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Severity: Critical, Major, Minor, Trivial                       │    │

│  │ • Priority: P0 (immediate), P1 (high), P2 (medium), P3 (low)      │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 3: DEFECT ASSIGNMENT                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Assigned ke developer yang bertanggung jawab                    │    │

│  │ • Target fix time berdasarkan severity                           │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 4: DEFECT FIX                                                         │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Developer memperbaiki defect                                     │    │

│  │ • Menulis test untuk defect                                        │    │

│  │ • Melakukan code review                                            │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 5: DEFECT VERIFICATION                                                 │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • QA memverifikasi fix                                              │    │

│  │ • Regression testing                                               │    │

│  │ • Defect closed jika verified                                      │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 6.5.5 Defect Severity & Target Resolution Time

| Severity | Deskripsi | Target Resolution Time | Priority |
| --- | --- | --- | --- |
| Critical | System crash, data loss, security breach | < 4 jam | P0 |
| Major | Major functionality broken, no workaround | < 2 hari | P1 |
| Minor | Minor functionality broken, workaround exists | < 5 hari | P2 |
| Trivial | UI/UX issue, cosmetic, typo | < 10 hari | P3 |

## 6.6 ACCEPTANCE CRITERIA

### 6.6.1 Deliverable Acceptance Criteria

| No | Deliverable | Acceptance Criteria | Verification Method |
| --- | --- | --- | --- |
| 1 | Infrastructure & DevOps | • 4 environment berfungsi • CI/CD pipeline otomatis • Monitoring & logging aktif • Backup & restore teruji | Manual review + Testing |
| 2 | IAM Service | • User registration & auth • MFA berfungsi • RBAC dengan 10 role dasar • SoD diterapkan | Functional testing |
| 3 | Master Data Management | • 24 entity CRUD • Import/export berfungsi • Duplicate detection • Versioning | Functional testing + UAT |
| 4 | Audit & Logging | • Semua transaksi tercatat • Audit log immutable • Query & export | Functional testing |
| 5 | API Gateway | • Routing berfungsi • Rate limiting • Auth at gateway • Documentation | Integration testing |
| 6 | Event Bus | • Publish/subscribe • DLQ & retry • Correlation ID | Integration testing |
| 7 | Workflow Engine | • 3 workflow basic • Approval matrix • Notifikasi | Functional testing |
| 8 | Notification Service | • 4 channel • Template management • History | Functional testing |

### 6.6.2 NFR Acceptance Criteria

| No | NFR | Target | Verification Method |
| --- | --- | --- | --- |
| 1 | Availability | ≥ 99.9% | Monitoring over 30 days |
| 2 | API Response Time (Median) | ≤ 500ms | Performance testing |
| 3 | API Response Time (P95) | ≤ 2 detik | Performance testing |
| 4 | Concurrent Users | 1.000 users | Load testing |
| 5 | RPO | ≤ 15 minutes | DR drill |
| 6 | RTO | ≤ 2 hours | DR drill |
| 7 | Security | No critical vulnerability | Security scan |
| 8 | Data Encryption | TLS 1.2+ & AES-256 | Security audit |
| 9 | Audit Retention | 5 years | Policy review |
| 10 | Database Query Time | ≤ 200ms | Performance testing |
| 11 | Event Processing Latency | ≤ 2 detik | Performance testing |

### 6.6.3 UAT Criteria

| No | Kriteria UAT | Deskripsi |
| --- | --- | --- |
| 1 | Test Scenarios | Minimal 80% test scenarios berhasil |
| 2 | User Satisfaction | ≥ 90% user menyatakan puas |
| 3 | Critical Bugs | Zero critical bugs |
| 4 | Performance | Response time sesuai NFR |
| 5 | Security | No critical security issues |
| 6 | Documentation | Dokumentasi lengkap dan akurat |
| 7 | Training | User telah menerima training |

## 6.7 CONTINUOUS IMPROVEMENT

### 6.7.1 Sprint Retrospective

| Aspek | Detail |
| --- | --- |
| Frekuensi | Setiap akhir sprint (2 minggu) |
| Durasi | 1 jam |
| Peserta | Seluruh tim proyek |
| Fasilitator | Scrum Master / PM |
| Topik | 1. What went well 2. What could be improved 3. What went wrong 4. Action items |

### 6.7.2 Quality Metrics Review

| Metrik | Frekuensi Review | Owner |
| --- | --- | --- |
| Code Coverage | Setiap Sprint | QA Lead |
| Defect Density | Setiap Sprint | QA Lead |
| Test Pass Rate | Setiap Sprint | QA Lead |
| Performance Metrics | Per Milestone | DevOps Lead |
| Security Scan | Setiap Sprint | Security Lead |
| UAT Satisfaction | Akhir Proyek | PM |

### 6.7.3 Lessons Learned

| Fase | Aktivitas | Owner | Timeline |
| --- | --- | --- | --- |
| Mid-project | Lessons learned di pertengahan proyek | PM | Bulan ke-3 |
| End-project | Lessons learned di akhir proyek | PM | Setelah Go-Live |
| Documentation | Dokumentasi lessons learned | PM | Setiap session |

# BAB 7: MANAJEMEN SUMBER DAYA PROYEK

## (PROJECT RESOURCE MANAGEMENT)

## 7.1 RESOURCE MANAGEMENT APPROACH

### 7.1.1 Pendekatan Umum

Manajemen sumber daya proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Metodologi | Resource planning berbasis aktivitas (Activity-Based Resource Planning) |
| Struktur | Matriks organisasi dengan fungsional leads |
| Pengadaan | Rekrutmen internal dan eksternal (kontraktor) |
| Pengembangan | On-the-job training, mentoring, dan sertifikasi |
| Pengendalian | Resource utilization monitoring, performance review |

### 7.1.2 Proses Manajemen Sumber Daya

text

┌─────────────────────────────────────────────────────────────────────────────┐

│              PROSES MANAJEMEN SUMBER DAYA P-FNE-01                          │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1. PERENCANAAN SUMBER DAYA                                                  │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Identifikasi kebutuhan sumber daya                               │    │

│  │ • Penentuan peran dan tanggung jawab                               │    │

│  │ • Penyusunan Resource Plan                                         │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  2. PENGADAAN SUMBER DAYA                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Rekrutmen internal                                               │    │

│  │ • Rekrutmen eksternal (kontraktor)                                 │    │

│  │ • Onboarding dan orientasi                                         │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  3. PENGEMBANGAN SUMBER DAYA                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Training dan sertifikasi                                         │    │

│  │ • Mentoring dan coaching                                           │    │

│  │ • Knowledge sharing                                                │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  4. PENGENDALIAN SUMBER DAYA                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Performance evaluation                                           │    │

│  │ • Resource utilization monitoring                                  │    │

│  │ • Conflict resolution                                              │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 7.2 ORGANIZATIONAL STRUCTURE

### 7.2.1 Struktur Organisasi Proyek

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    ORGANIZATIONAL STRUCTURE P-FNE-01                        │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ┌─────────────────────────────────────────────────────────────────────────┐│

│  │                    PROJECT SPONSOR                                      ││

│  │                    (VP of Technology)                                   ││

│  └──────────────────────────────┬──────────────────────────────────────────┘│

│                                 │                                           │

│  ┌──────────────────────────────▼──────────────────────────────────────────┐│

│  │                    STEERING COMMITTEE                                   ││

│  │                    (Sponsor, PMO, Business Owner, IT Ops, Security)     ││

│  └──────────────────────────────┬──────────────────────────────────────────┘│

│                                 │                                           │

│  ┌──────────────────────────────▼──────────────────────────────────────────┐│

│  │                    PROJECT MANAGER                                      ││

│  │                    (1 orang)                                            ││

│  └──────────────────────────────┬──────────────────────────────────────────┘│

│                                 │                                           │

│     ┌───────────────────────────┼───────────────────────────┐              │

│     │                           │                           │              │

│  ┌──▼─────────────┐     ┌───────▼─────────┐     ┌──────────▼────────┐     │

│  │  DevOps Lead   │     │  Tech Lead      │     │  Security Lead    │     │

│  │  (1 orang)     │     │  (1 orang)      │     │  (1 orang)        │     │

│  └──┬─────────────┘     └───────┬─────────┘     └──────────┬────────┘     │

│     │                           │                           │              │

│  ┌──▼─────────────┐     ┌───────▼─────────┐     ┌──────────▼────────┐     │

│  │  DevOps Eng    │     │  Backend Dev    │     │  Security Eng     │     │

│  │  (2 orang)     │     │  (4 orang)      │     │  (1 orang)        │     │

│  └────────────────┘     ├─────────────────┤     └───────────────────┘     │

│                         │  Frontend Dev   │                               │

│                         │  (2 orang)      │                               │

│                         ├─────────────────┤                               │

│                         │  QA Engineer    │                               │

│                         │  (2 orang)      │                               │

│                         └─────────────────┘                               │

│                                                                              │

│  Total Tim: 15 orang (10-15 orang sesuai rencana)                           │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 7.2.2 Struktur Tim per Fase

| Fase | DevOps | Backend | Frontend | Security | QA | PM | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Infrastruktur | 3 | 0 | 0 | 1 | 0 | 1 | 5 |
| IAM | 1 | 4 | 2 | 2 | 1 | 1 | 12 |
| MDM | 1 | 5 | 2 | 1 | 2 | 1 | 13 |
| Audit | 1 | 3 | 1 | 2 | 1 | 1 | 10 |
| API Gateway & Event Bus | 2 | 3 | 0 | 1 | 1 | 1 | 9 |
| Workflow | 0 | 5 | 2 | 0 | 2 | 1 | 10 |
| Notification | 0 | 3 | 2 | 1 | 1 | 1 | 9 |
| Testing & Go-Live | 2 | 4 | 2 | 2 | 2 | 1 | 14 |

## 7.3 ROLES & RESPONSIBILITIES (RACI MATRIX)

### 7.3.1 Role Descriptions

| Role | Deskripsi | Kualifikasi |
| --- | --- | --- |
| Project Manager | Memimpin seluruh aspek proyek, koordinasi stakeholder, reporting | PMP/Agile certified, 5+ tahun pengalaman |
| DevOps Lead | Memimpin infrastruktur, CI/CD, monitoring, backup/DR | Kubernetes, Terraform, CI/CD expert |
| Tech Lead | Memimpin arsitektur teknis, code quality, integration | Spring Boot, Microservices expert |
| Security Lead | Memimpin keamanan sistem, IAM, compliance | Security certification, 5+ tahun |
| DevOps Engineer | Implementasi infrastruktur, CI/CD, monitoring | Kubernetes, Terraform, Docker |
| Backend Developer | Implementasi microservices, API, business logic | Spring Boot, Java, Kafka |
| Frontend Developer | Implementasi UI/UX, admin portal | React/Next.js, TypeScript |
| Security Engineer | Implementasi IAM, security scanning, compliance | Security tools, OWASP |
| QA Engineer | Testing, quality assurance, automation | Automation testing, Selenium, JMeter |

### 7.3.2 RACI Matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed

| Aktivitas | Sponsor | PM | DevOps Lead | Tech Lead | Security Lead | DevOps Eng | Backend Dev | Frontend Dev | Security Eng | QA Eng |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Infrastructure |  |  |  |  |  |  |  |  |  |  |
| Environment Provisioning | I | A | R | C | C | R | - | - | C | - |
| CI/CD Pipeline | I | A | R | C | C | R | - | - | C | C |
| Monitoring & Logging | I | A | R | C | C | R | C | - | C | C |
| Backup & DR | I | A | R | C | C | R | - | - | C | - |
| IAM |  |  |  |  |  |  |  |  |  |  |
| User Registration & Auth | I | A | C | R | C | - | R | R | R | C |
| MFA Implementation | I | A | C | R | C | - | R | R | R | C |
| RBAC & Permission | I | A | C | R | C | - | R | R | R | C |
| SSO Implementation | I | A | C | R | C | - | R | R | R | C |
| MDM |  |  |  |  |  |  |  |  |  |  |
| Schema Design | I | A | C | R | C | - | R | C | - | C |
| CRUD Operations | I | A | C | R | C | - | R | R | - | C |
| Import/Export | I | A | C | R | C | - | R | R | - | C |
| Duplicate Detection | I | A | C | R | C | - | R | C | - | C |
| Audit |  |  |  |  |  |  |  |  |  |  |
| Audit Trail | I | A | C | R | C | - | R | C | C | C |
| Query & Export | I | A | C | R | C | - | R | R | C | C |
| Security Logging | I | A | C | R | C | - | R | C | R | C |
| API Gateway & Event Bus |  |  |  |  |  |  |  |  |  |  |
| Gateway Setup | I | A | R | R | C | R | C | - | C | - |
| Routing & Rate Limit | I | A | R | R | C | R | C | - | C | C |
| Kafka Setup | I | A | R | R | C | R | C | - | C | - |
| Publisher/Subscriber | I | A | C | R | C | - | R | - | C | C |
| Workflow |  |  |  |  |  |  |  |  |  |  |
| Workflow Definition | I | A | C | R | C | - | R | C | - | C |
| Workflow Execution | I | A | C | R | C | - | R | R | - | C |
| Approval Matrix | I | A | C | R | C | - | R | C | - | C |
| Notification |  |  |  |  |  |  |  |  |  |  |
| Multi-Channel | I | A | C | R | C | - | R | R | C | C |
| Template Management | I | A | C | R | C | - | R | R | C | C |
| Testing |  |  |  |  |  |  |  |  |  |  |
| Unit Testing | I | A | C | R | C | - | R | R | C | C |
| Integration Testing | I | A | C | R | C | - | R | R | C | R |
| Performance Testing | I | A | R | R | C | R | - | - | C | R |
| Security Testing | I | A | C | C | R | - | - | - | R | C |
| UAT | I | A | C | C | C | - | C | C | C | R |
| Go-Live |  |  |  |  |  |  |  |  |  |  |
| Production Deployment | A | A | R | C | C | R | C | C | C | C |
| DR Drill | A | A | R | C | C | R | - | - | C | - |
| Handover | A | A | R | R | C | C | C | C | C | C |

## 7.4 STAFFING MANAGEMENT PLAN

### 7.4.1 Staffing Schedule

| Role | Okt 2026 | Nov 2026 | Des 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Total Bulan |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager | 1 | 1 | 1 | 1 | 1 | 1 | 6 |
| DevOps Lead | 1 | 1 | 1 | 1 | 1 | 1 | 6 |
| DevOps Engineer | 2 | 2 | 2 | 2 | 2 | 1 | 11 |
| Tech Lead (Backend) | 1 | 1 | 1 | 1 | 1 | 1 | 6 |
| Backend Developer | 2 | 4 | 5 | 5 | 5 | 4 | 25 |
| Frontend Lead | 0 | 1 | 1 | 1 | 1 | 1 | 5 |
| Frontend Developer | 0 | 1 | 2 | 2 | 2 | 2 | 9 |
| Security Lead | 1 | 1 | 1 | 1 | 1 | 1 | 6 |
| Security Engineer | 0 | 1 | 1 | 1 | 1 | 1 | 5 |
| QA Lead | 0 | 1 | 1 | 1 | 1 | 1 | 5 |
| QA Engineer | 0 | 0 | 1 | 1 | 1 | 1 | 4 |
| Total | 8 | 14 | 17 | 17 | 17 | 15 | 88 |

### 7.4.2 Staffing Ramp-Up Plan

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    STAFFING RAMP-UP PLAN P-FNE-01                           │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ROLE            │ OKT │ NOV │ DES │ JAN │ FEB │ MAR │

│──────────────────┼─────┼─────┼─────┼─────┼─────┼─────┤

│                  │     │     │     │     │     │     │

│  PM              │ ████│ ████│ ████│ ████│ ████│ ████│

│                  │     │     │     │     │     │     │

│  DevOps Lead     │ ████│ ████│ ████│ ████│ ████│ ████│

│  DevOps Eng      │ ████│ ████│ ████│ ████│ ████│ ████│

│                  │ ████│ ████│ ████│ ████│ ████│     │

│                  │     │     │     │     │     │     │

│  Backend Lead    │ ████│ ████│ ████│ ████│ ████│ ████│

│  Backend Dev     │ ████│ ████│ ████│ ████│ ████│ ████│

│                  │ ████│ ████│ ████│ ████│ ████│ ████│

│                  │     │ ████│ ████│ ████│ ████│ ████│

│                  │     │ ████│ ████│ ████│ ████│     │

│                  │     │     │ ████│ ████│ ████│     │

│                  │     │     │     │     │     │     │

│  Frontend Lead   │     │ ████│ ████│ ████│ ████│ ████│

│  Frontend Dev    │     │ ████│ ████│ ████│ ████│ ████│

│                  │     │     │ ████│ ████│ ████│ ████│

│                  │     │     │     │     │     │     │

│  Security Lead   │ ████│ ████│ ████│ ████│ ████│ ████│

│  Security Eng    │     │ ████│ ████│ ████│ ████│ ████│

│                  │     │     │     │     │     │     │

│  QA Lead         │     │ ████│ ████│ ████│ ████│ ████│

│  QA Eng          │     │     │ ████│ ████│ ████│ ████│

│                  │     │     │     │     │     │     │

│──────────────────┼─────┼─────┼─────┼─────┼─────┼─────┤

│  TOTAL           │  8  │ 14  │ 17  │ 17  │ 17  │ 15  │

│                  │     │     │     │     │     │     │

└─────────────────────────────────────────────────────────────────────────────┘

### 7.4.3 Recruitment Plan

| Role | Sumber | Tanggal Mulai | Status |
| --- | --- | --- | --- |
| Project Manager | Internal | 01-Oct-2026 | ✅ Confirmed |
| DevOps Lead | Internal | 01-Oct-2026 | ✅ Confirmed |
| DevOps Engineers | Eksternal | 01-Oct-2026 | ✅ Confirmed |
| Tech Lead (Backend) | Internal | 01-Oct-2026 | ✅ Confirmed |
| Backend Developers | Internal + Eksternal | 01-Oct-2026 | ✅ Confirmed |
| Frontend Lead | Internal | 01-Nov-2026 | ✅ Confirmed |
| Frontend Developers | Eksternal | 01-Nov-2026 | ✅ Confirmed |
| Security Lead | Internal | 01-Oct-2026 | ✅ Confirmed |
| Security Engineer | Eksternal | 01-Nov-2026 | 🔄 In Progress |
| QA Lead | Internal | 01-Nov-2026 | ✅ Confirmed |
| QA Engineer | Eksternal | 01-Dec-2026 | 🔄 In Progress |

## 7.5 TEAM DEVELOPMENT PLAN

### 7.5.1 Training Plan

| No | Training | Target Audience | Timeline | Durasi |
| --- | --- | --- | --- | --- |
| 1 | Project Kick-off & Onboarding | Semua Tim | Minggu 1 | 2 hari |
| 2 | Spring Boot & Microservices | Backend Dev | Minggu 2-3 | 5 hari |
| 3 | Kubernetes & Docker | DevOps, Backend | Minggu 2-3 | 3 hari |
| 4 | React/Next.js Training | Frontend Dev | Minggu 3-4 | 3 hari |
| 5 | Kafka & Event-Driven | Backend, DevOps | Minggu 4 | 2 hari |
| 6 | Security Awareness | Semua Tim | Minggu 2 | 1 hari |
| 7 | OWASP & Secure Coding | Developer | Minggu 4 | 2 hari |
| 8 | Agile & Scrum | Semua Tim | Minggu 1 | 1 hari |
| 9 | Jira & Confluence | Semua Tim | Minggu 1 | 0.5 hari |
| 10 | AWS/GCP Cloud | DevOps | Minggu 2 | 2 hari |

### 7.5.2 Mentoring Program

| Mentor | Mentee | Fokus |
| --- | --- | --- |
| DevOps Lead | DevOps Engineers | Kubernetes, CI/CD, Monitoring |
| Tech Lead | Backend Developers | Microservices, Spring Boot, Kafka |
| Frontend Lead | Frontend Developers | React, TypeScript, UI/UX |
| Security Lead | Security Engineer | IAM, Security Testing, Compliance |
| QA Lead | QA Engineer | Automation Testing, Performance Testing |

### 7.5.3 Knowledge Sharing

| Aktivitas | Frekuensi | Owner | Deskripsi |
| --- | --- | --- | --- |
| Tech Talk | 2 minggu sekali | Tech Lead | Presentasi topik teknis |
| Code Review Session | 1 minggu sekali | QA Lead | Review best practices |
| Architecture Review | 1 bulan sekali | Tech Lead | Review arsitektur |
| Security Briefing | 1 bulan sekali | Security Lead | Update keamanan |
| Retrospective | Setiap Sprint | PM | Evaluasi proses |

## 7.6 RECOGNITION & REWARDS

### 7.6.1 Recognition Program

| Kategori | Kriteria | Reward |
| --- | --- | --- |
| Outstanding Performance | Exceeds expectations, high impact | Bonus, Public recognition |
| Innovation | Solusi kreatif, efisiensi | Special award, Certificate |
| Team Player | Kolaborasi, membantu tim | Recognition in meeting |
| Quality Champion | Code quality, zero defects | Certificate, Gift |
| Security Champion | Security awareness | Certificate |

### 7.6.2 Team Building

| Aktivitas | Timeline | Deskripsi |
| --- | --- | --- |
| Project Kick-off Dinner | Minggu 1 | Team bonding |
| Mid-project Retreat | Bulan 3 | Evaluasi dan team building |
| Go-Live Celebration | Setelah Go-Live | Perayaan keberhasilan |
| Monthly Team Lunch | Setiap bulan | Informal gathering |

# BAB 8: MANAJEMEN KOMUNIKASI PROYEK

## (PROJECT COMMUNICATION MANAGEMENT)

## 8.1 COMMUNICATION MANAGEMENT APPROACH

### 8.1.1 Pendekatan Umum

Manajemen komunikasi proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Filosofi | Transparan, kolaboratif, dan tepat sasaran |
| Metodologi | Komunikasi multi-channel dengan escalation matrix |
| Alat | Jira, Confluence, Slack/Teams, Email, Zoom/Video Conference |
| Frekuensi | Harian, mingguan, sprint, bulanan sesuai kebutuhan |
| Pengendalian | Stakeholder feedback loop, communication audit |

### 8.1.2 Proses Manajemen Komunikasi

text

┌─────────────────────────────────────────────────────────────────────────────┐

│              PROSES MANAJEMEN KOMUNIKASI P-FNE-01                           │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1. PERENCANAAN KOMUNIKASI                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Identifikasi stakeholder                                         │    │

│  │ • Analisis kebutuhan komunikasi                                    │    │

│  │ • Penyusunan Communication Matrix                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  2. DISTRIBUSI INFORMASI                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Pelaksanaan komunikasi sesuai matrix                             │    │

│  │ • Dokumentasi dan arsip komunikasi                                 │    │

│  │ • Distribusi informasi tepat waktu                                 │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  3. MONITORING & KONTROL                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Feedback monitoring                                              │    │

│  │ • Stakeholder satisfaction survey                                  │    │

│  │ • Penyesuaian strategi komunikasi                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  4. ESKALASI & RESOLUSI ISU                                                  │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Prosedur eskalasi untuk isu kritis                              │    │

│  │ • Resolusi konflik                                                │    │

│  │ • Dokumentasi isu dan resolusi                                    │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 8.2 STAKEHOLDER IDENTIFICATION

### 8.2.1 Stakeholder Register

| No | Stakeholder | Peran | Interest | Influence | Engagement Level |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Sponsor | VP of Technology | Strategic alignment, budget, timeline | High | Leading |
| 2 | Steering Committee | Multi-stakeholder | Strategic decisions, risk management | High | Leading |
| 3 | PMO | Project Management Office | Methodology, compliance, reporting | Medium | Supportive |
| 4 | Project Manager | PM P-FNE-01 | Day-to-day execution, delivery | High | Leading |
| 5 | DevOps Lead | Technical Lead | Infrastructure, CI/CD, operations | High | Leading |
| 6 | Tech Lead | Technical Lead | Architecture, code quality | High | Leading |
| 7 | Security Lead | Technical Lead | Security, IAM, compliance | High | Leading |
| 8 | Project Team | All team members | Development, testing, delivery | Medium | Supportive |
| 9 | Business Owner | Business Stakeholder | Business requirements, UAT | High | Supportive |
| 10 | IT Operations | Operations Team | Deployment, operations, monitoring | Medium | Supportive |
| 11 | Data Steward | Data Management | Master data quality | Medium | Supportive |
| 12 | End Users (Future) | Agricultural Ops Team | User experience, functionality | Low | Aware |
| 13 | External Auditors | Compliance | Audit, compliance, regulations | Medium | Aware |
| 14 | Vendors | Third-party | Software, cloud, services | Low | Supportive |
| 15 | Security Team | Corporate Security | Security standards, compliance | High | Supportive |

### 8.2.2 Power/Interest Grid

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    POWER/INTEREST GRID P-FNE-01                             │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  High Power   │  ■ KEY PLAYERS (Manage Closely)                             │

│               │  • Project Sponsor                                         │

│               │  • Steering Committee                                      │

│               │  • Business Owner                                          │

│               │  • IT Operations                                           │

│               │  ■                                                          │

│               │  ■ KEEP SATISFIED (Keep Informed)                          │

│               │  • Security Team                                           │

│               │  • PMO                                                     │

│               │  • External Auditors                                       │

│               │  ■                                                          │

│               │  ■ MONITOR (Watch)                                         │

│               │  • End Users (Future)                                     │

│               │  • Vendors                                                 │

│               │  ■                                                          │

│               │  ■ SHOW CONSIDERATION (Keep Informed)                      │

│               │  • Project Team                                            │

│               │  • Data Steward                                            │

│  Low Power    └─────────────────────────────────────────────────────────────│

│               Low Interest                     High Interest                 │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 8.3 COMMUNICATION CHANNELS & METHODS

### 8.3.1 Communication Matrix

| No | Komunikasi | Frekuensi | Audience | Method | Owner | Format |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Daily Stand-up | Harian (09:00) | Project Team | Meeting (Video) | Scrum Master | Verbal + Chat |
| 2 | Sprint Planning | Setiap Sprint (2 minggu) | Project Team, PMO | Meeting (Video) | PM | Slide + Jira |
| 3 | Sprint Review | Setiap Sprint (2 minggu) | All Stakeholders | Meeting (Video) | PM | Demo + Slide |
| 4 | Sprint Retrospective | Setiap Sprint (2 minggu) | Project Team | Meeting (Video) | PM | Workshop |
| 5 | Weekly Status Report | Mingguan | PMO, Sponsor | Email + Dashboard | PM | PDF/Dashboard |
| 6 | Monthly Steering Meeting | Bulanan | Steering Committee | Meeting (Video) | PM | Presentasi |
| 7 | Milestone Review | Per Milestone | Sponsor, Steering | Meeting (Video) | PM | Presentasi |
| 8 | Risk Review | Mingguan | PM, Tech Leads | Meeting (Video) | PM | Document |
| 9 | Technical Review | 2 minggu sekali | Tech Leads | Meeting (Video) | Tech Lead | Document |
| 10 | Security Briefing | 1 bulan sekali | Tech Team, Security | Meeting (Video) | Security Lead | Slide |
| 11 | Project Newsletter | Bulanan | All Stakeholders | Email | PM | Newsletter |
| 12 | Issue Escalation | As needed | PM, Sponsor | Email + Call | PM | - |
| 13 | Change Request | As needed | CCB | Document | PM | CRF |
| 14 | Decision Log | Berkelanjutan | All Stakeholders | Confluence | PM | Document |
| 15 | Knowledge Base | Berkelanjutan | Project Team | Confluence | All | Document |
| 16 | Slack/Teams Channel | Harian | Project Team | Chat | All | - |
| 17 | Code Review | Per Pull Request | Developers | GitHub/GitLab | Developer | Review |
| 18 | UAT Feedback | Minggu Go-Live | Business Owner, Team | Meeting + Jira | PM | Ticket |

### 8.3.2 Communication Tools

| Alat | Penggunaan | Audience | Link/Platform |
| --- | --- | --- | --- |
| Jira | Sprint management, issue tracking, backlog | All Team | jira.company.com |
| Confluence | Documentation, knowledge base, meeting notes | All Team | confluence.company.com |
| Slack/Teams | Daily communication, quick updates | All Team | company.slack.com |
| GitHub/GitLab | Code repository, code review, CI/CD | Developers | github.com/company |
| Zoom/Google Meet | Video conference, meetings | All Stakeholders | zoom.company.com |
| Email | Formal communication, reports | All Stakeholders | Outlook/Gmail |
| Dashboard | Progress monitoring, metrics | PM, PMO, Sponsor | dashboard.company.com |
| SonarQube | Code quality monitoring | Developers | sonar.company.com |
| Prometheus/Grafana | System monitoring | DevOps | monitor.company.com |

## 8.4 COMMUNICATION MATRIX

### 8.4.1 Stakeholder Communication Detail

| Stakeholder | Communication Type | Frequency | Method | Content | Owner |
| --- | --- | --- | --- | --- | --- |
| Project Sponsor | 1-on-1 Meeting | Mingguan | Video Call | Progress, Risks, Issues, Decisions | PM |
|  | Status Report | Mingguan | Email | Progress, Milestones, Budget | PM |
|  | Steering Meeting | Bulanan | Presentation | Overall status, Strategic issues | PM |
| Steering Committee | Steering Meeting | Bulanan | Presentation | Progress, Risks, Changes, Decisions | PM |
|  | Milestone Report | Per Milestone | Presentation | Milestone completion | PM |
|  | Change Request | As needed | Document + Meeting | Scope/Schedule/Budget changes | PM |
| PMO | Status Report | Mingguan | Dashboard | Progress, Quality, Compliance | PM |
|  | Quality Report | Mingguan | Dashboard | Code quality, Test coverage | QA Lead |
|  | Risk Report | Mingguan | Document | Risk status, Mitigation | PM |
| Project Team | Daily Stand-up | Harian | Meeting | Progress, Blockers, Plan | Scrum Master |
|  | Sprint Planning | 2 minggu | Meeting | Sprint backlog, Goals | PM |
|  | Sprint Review | 2 minggu | Meeting | Demo, Feedback | PM |
|  | Retrospective | 2 minggu | Meeting | Process improvement | PM |
|  | Technical Meeting | 2 minggu | Meeting | Architecture, Design | Tech Lead |
| Business Owner | Sprint Review | 2 minggu | Meeting | Demo, Feedback | PM |
|  | UAT Session | Minggu Go-Live | Meeting | User acceptance testing | PM |
|  | Requirement Review | As needed | Meeting | Requirement clarification | PM |
| IT Operations | Handover Meeting | Minggu Go-Live | Meeting | Deployment, Operations | DevOps Lead |
|  | Support Briefing | Sebelum Go-Live | Meeting | Support procedures | PM |
| Security Team | Security Review | 1 bulan | Meeting | Security status, Issues | Security Lead |
|  | Security Audit | Per Milestone | Document | Compliance, Vulnerabilities | Security Lead |
| Vendors | Vendor Meeting | As needed | Meeting | Performance, Issues, Invoices | PM |
|  | Procurement Review | Per Procurement | Document | Contract, Delivery | PM |
| End Users | Newsletter | Bulanan | Email | Project updates, Awareness | PM |
|  | Training | Minggu Go-Live | Training | System usage | PM + Trainers |

### 8.4.2 Escalation Matrix

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    ESCALATION MATRIX P-FNE-01                               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  LEVEL 1: ISSUE DETECTION                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Ditemukan oleh tim proyek                                         │    │

│  │ • Dilaporkan ke PM atau Tech Lead                                  │    │

│  │ • Dampak: Minor, dapat diatasi internal                           │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  LEVEL 2: PM RESOLUTION                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • PM berkoordinasi dengan tim untuk solusi                          │    │

│  │ • Dampak: Medium, membutuhkan keputusan PM                         │    │

│  │ • Waktu: 1-2 hari                                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  LEVEL 3: SPONSOR RESOLUTION                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • PM melapor ke Sponsor untuk keputusan                             │    │

│  │ • Dampak: High, membutuhkan keputusan Sponsor                      │    │

│  │ • Waktu: 2-3 hari                                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  LEVEL 4: STEERING COMMITTEE RESOLUTION                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Sponsor memanggil Steering Committee                              │    │

│  │ • Dampak: Critical, membutuhkan keputusan strategis                │    │

│  │ • Waktu: 5 hari                                                    │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 8.4.3 Escalation Triggers

| Trigger | Deskripsi | Tindakan | Target Time |
| --- | --- | --- | --- |
| Schedule Delay > 10% | Penyimpangan jadwal > 10% dari baseline | Eskalasi ke Sponsor | 2 hari |
| Budget Overrun > 10% | Biaya aktual > 10% dari baseline | Eskalasi ke Sponsor | 2 hari |
| Critical Bug Found | Bug critical yang menghambat Go-Live | Eskalasi ke Tech Lead + PM | 4 jam |
| Security Vulnerability | Critical security vulnerability | Eskalasi ke Security Lead + PM | 4 jam |
| Resource Shortage | Kurang sumber daya kritis | Eskalasi ke Sponsor | 2 hari |
| Stakeholder Conflict | Konflik yang tidak dapat diselesaikan | Eskalasi ke Sponsor | 2 hari |
| Major Change Request | Perubahan dengan impact > 20% | Eskalasi ke Steering Committee | 5 hari |

## 8.5 INFORMATION DISTRIBUTION

### 8.5.1 Meeting Management

| Jenis Meeting | Durasi | Frekuensi | Agenda | Output |
| --- | --- | --- | --- | --- |
| Daily Stand-up | 15 menit | Harian | 1. What I did yesterday 2. What I will do today 3. Blockers | Updated task status |
| Sprint Planning | 2 jam | Setiap Sprint | 1. Sprint goal 2. Backlog selection 3. Task breakdown | Sprint backlog |
| Sprint Review | 1 jam | Setiap Sprint | 1. Demo completed work 2. Feedback collection | Feedback, Approval |
| Sprint Retrospective | 1 jam | Setiap Sprint | 1. What went well 2. What could improve 3. Action items | Improvement plan |
| Weekly Status | 30 menit | Mingguan | 1. Progress update 2. Risks and issues 3. Next steps | Status report |
| Monthly Steering | 1.5 jam | Bulanan | 1. Project status 2. Strategic issues 3. Decisions needed | Steering decisions |

### 8.5.2 Meeting Rules

| No | Aturan | Deskripsi |
| --- | --- | --- |
| 1 | Agenda | Agenda dikirim minimal 24 jam sebelum meeting |
| 2 | Punctuality | Meeting dimulai tepat waktu |
| 3 | Timeboxing | Meeting sesuai durasi yang ditentukan |
| 4 | Minutes | Notulen meeting dicatat dan didistribusikan |
| 5 | Action Items | Setiap action item memiliki owner dan deadline |
| 6 | Decision Recording | Setiap keputusan dicatat di Decision Log |
| 7 | Participation | Semua peserta diharapkan aktif |

### 8.5.3 Information Storage

| Platform | Konten | Akses | Backup |
| --- | --- | --- | --- |
| Confluence | • Project documentation • Meeting notes • Decision log • Knowledge base | All team members | Daily |
| Jira | • Sprint backlog • Issues • Tasks • Burn-down charts | All team members | Daily |
| Google Drive/SharePoint | • PMP • Reports • Presentations • Contracts | All stakeholders | Daily |
| GitHub/GitLab | • Code • API documentation • CI/CD pipelines | Developers | Continuous |
| Slack/Teams | • Communication history • File sharing | All team members | 30 days |

## 8.6 STAKEHOLDER ENGAGEMENT

### 8.6.1 Stakeholder Engagement Plan

| Stakeholder | Current Engagement | Desired Engagement | Action Plan |
| --- | --- | --- | --- |
| Project Sponsor | Leading | Leading | Weekly 1-on-1, Monthly steering |
| Steering Committee | Aware | Supportive | Regular updates, Issue escalation |
| PMO | Supportive | Supportive | Weekly reporting, Quality reviews |
| Project Manager | Leading | Leading | Full authority, Decision making |
| Project Team | Supportive | Leading | Empowerment, Recognition |
| Business Owner | Aware | Supportive | Sprint reviews, UAT involvement |
| IT Operations | Resistant | Supportive | Early involvement, Training |
| Security Team | Aware | Supportive | Security reviews, Collaboration |
| End Users (Future) | Unaware | Aware | Awareness sessions, Demos |
| External Auditors | Unaware | Aware | Regular updates, Compliance reports |

### 8.6.2 Stakeholder Feedback Collection

| Metode | Frekuensi | Stakeholder | Tujuan |
| --- | --- | --- | --- |
| Satisfaction Survey | Bulanan | All stakeholders | Measure satisfaction |
| Sprint Review Feedback | 2 minggu | Business Owner, Users | Gather product feedback |
| Retrospective | 2 minggu | Project Team | Process improvement |
| 1-on-1 Meeting | Mingguan | Sponsor | Strategic alignment |
| Feedback Session | Per Milestone | Key stakeholders | Milestone evaluation |
| UAT Survey | Minggu Go-Live | End Users | User acceptance |

### 8.6.3 Conflict Resolution

| Konflik | Pendekatan | Proses |
| --- | --- | --- |
| Technical Disagreement | Konsensus dan data-driven | 1. Kedua pihak presentasi 2. Diskusi tim 3. Tech Lead decision |
| Resource Conflict | Prioritas dan kompromi | 1. Identifikasi kebutuhan 2. Negosiasi PM 3. Eskalasi Sponsor |
| Schedule Pressure | Negosiasi dan trade-off | 1. Analisis impact 2. Scope vs schedule trade-off 3. Sponsor decision |
| Stakeholder Conflict | Mediasi dan kolaborasi | 1. Identifikasi kepentingan 2. Mediasi PM 3. Eskalasi Sponsor |

# BAB 9: MANAJEMEN RISIKO PROYEK

## (PROJECT RISK MANAGEMENT)

## 9.1 RISK MANAGEMENT APPROACH

### 9.1.1 Pendekatan Umum

Manajemen risiko proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Metodologi | PMBOK Risk Management Framework (ISO 31000) |
| Identifikasi | Brainstorming, Expert Judgment, Checklist, SWOT Analysis |
| Analisis | Kualitatif (Probability-Impact Matrix) dan Kuantitatif (Monte Carlo) |
| Respons | Avoid, Mitigate, Transfer, Accept, Exploit (untuk peluang) |
| Monitoring | Risk Register review mingguan, Risk audit bulanan |

### 9.1.2 Proses Manajemen Risiko

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    PROSES MANAJEMEN RISIKO P-FNE-01                         │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1. PERENCANAAN RISIKO                                                       │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penetapan metodologi risiko                                      │    │

│  │ • Kategorisasi risiko                                              │    │

│  │ • Penentuan toleransi risiko                                       │    │

│  │ • Penyusunan Risk Management Plan                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  2. IDENTIFIKASI RISIKO                                                      │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Brainstorming dengan tim                                         │    │

│  │ • Expert judgment                                                  │    │

│  │ • Checklist berdasarkan project serupa                            │    │

│  │ • SWOT Analysis                                                   │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  3. ANALISIS RISIKO (KUALITATIF & KUANTITATIF)                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penilaian probabilitas dan dampak                                │    │

│  │ • Prioritasi risiko (Risk Score)                                  │    │

│  │ • Probability-Impact Matrix                                        │    │

│  │ • Expected Monetary Value (EMV)                                   │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  4. PERENCANAAN RESPONS RISIKO                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penentuan strategi respons                                       │    │

│  │ • Penyusunan Risk Response Plan                                   │    │

│  │ • Penetapan trigger dan contingency plan                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  5. MONITORING & KONTROL RISIKO                                             │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Risk Register update (mingguan)                                 │    │

│  │ • Risk audit (bulanan)                                            │    │

│  │ • Risk review dalam sprint retrospective                         │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 9.2 RISK IDENTIFICATION

### 9.2.1 Kategori Risiko

| Kategori | Deskripsi | Contoh Risiko |
| --- | --- | --- |
| Teknis | Risiko terkait teknologi, arsitektur, dan implementasi | Kompleksitas integrasi, performa, keamanan |
| Organisasi | Risiko terkait struktur, budaya, dan manajemen | Resistensi perubahan, kepemilikan data |
| Sumber Daya | Risiko terkait orang, skill, dan kapasitas | Turnover, kekurangan skill kunci |
| Jadwal | Risiko terkait waktu dan milestone | Keterlambatan, dependency failure |
| Biaya | Risiko terkait anggaran dan biaya | Over budget, cost overrun |
| Kualitas | Risiko terkait standar dan kepuasan | Code quality rendah, UAT gagal |
| Keamanan | Risiko terkait keamanan data dan sistem | Data breach, compliance failure |
| Eksternal | Risiko di luar kontrol proyek | Regulasi, vendor, force majeure |

### 9.2.2 Risk Breakdown Structure (RBS)

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    RISK BREAKDOWN STRUCTURE P-FNE-01                        │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1.0 TEKNIS                                                                 │

│  ├── 1.1 Integrasi Microservices                                           │

│  ├── 1.2 Performa Audit Log (volume tinggi)                               │

│  ├── 1.3 Keamanan IAM Implementation                                     │

│  ├── 1.4 Data Migration Quality                                          │

│  └── 1.5 Teknologi Stack Maturity                                        │

│                                                                              │

│  2.0 ORGANISASI                                                            │

│  ├── 2.1 Resistensi Adopsi                                               │

│  ├── 2.2 Kurangnya Dukungan Stakeholder                                  │

│  ├── 2.3 Konflik Prioritas dengan Proyek Lain                           │

│  └── 2.4 Perubahan Strategi Perusahaan                                  │

│                                                                              │

│  3.0 SUMBER DAYA                                                           │

│  ├── 3.1 Turnover Tim Kunci                                              │

│  ├── 3.2 Kekurangan Skill (Security, Kafka)                             │

│  ├── 3.3 Kesulitan Rekrutmen                                            │

│  └── 3.4 Overload Tim                                                  │

│                                                                              │

│  4.0 JADWAL                                                                 │

│  ├── 4.1 Scope Creep                                                    │

│  ├── 4.2 Keterlambatan Dependency                                      │

│  ├── 4.3 Integration dengan Legacy                                     │

│  └── 4.4 Resource Availability                                         │

│                                                                              │

│  5.0 BIAYA                                                                  │

│  ├── 5.1 Cloud Infrastructure Cost Overrun                              │

│  ├── 5.2 Software License Cost                                          │

│  ├── 5.3 Biaya Rekrutmen Lebih Tinggi                                 │

│  └── 5.4 Biaya Konsultan/Vendor                                        │

│                                                                              │

│  6.0 KUALITAS                                                               │

│  ├── 6.1 Code Quality Menurun                                           │

│  ├── 6.2 UAT Gagal                                                    │

│  ├── 6.3 Regression Bug                                               │

│  └── 6.4 Performance Not Achieved                                      │

│                                                                              │

│  7.0 KEAMANAN                                                               │

│  ├── 7.1 Data Breach                                                   │

│  ├── 7.2 Compliance Failure (PDP, ISO)                                 │

│  ├── 7.3 Vulnerabilities in Third-party Libraries                      │

│  └── 7.4 Insider Threat                                                │

│                                                                              │

│  8.0 EKSTERNAL                                                              │

│  ├── 8.1 Third-party API Downtime                                       │

│  ├── 8.2 Perubahan Regulasi                                            │

│  ├── 8.3 Cloud Provider Outage                                         │

│  └── 8.4 Force Majeure (Bencana, Pandemi)                            │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 9.2.3 Risk Register (Identifikasi)

| ID | Risk Category | Risk Description | Trigger | Owner |
| --- | --- | --- | --- | --- |
| R-001 | Teknis | Kompleksitas integrasi microservices menyebabkan keterlambatan | Integration testing gagal | Tech Lead |
| R-002 | Teknis | Performa audit log menurun dengan volume tinggi | Query response > 2 detik | Backend Lead |
| R-003 | Teknis | Security vulnerability pada IAM implementation | Security scan findings | Security Lead |
| R-004 | Teknis | Data migration quality issue | Duplicate/Invalid data | Data Steward |
| R-005 | Teknis | Teknologi stack tidak mature | Library bug/deprecation | Tech Lead |
| R-006 | Sumber Daya | Team member turnover (devops/backend) | Resignation notice | PM |
| R-007 | Sumber Daya | Kesulitan rekrut security engineer | Low application rate | PM + HR |
| R-008 | Sumber Daya | Overload tim karena deadline | Burnout symptoms | PM |
| R-009 | Jadwal | Scope creep dari stakeholder | Change request volume | PM |
| R-010 | Jadwal | Integration dengan legacy system complex | API not available | Tech Lead |
| R-011 | Biaya | Cloud cost overrun | Cost > budget by 10% | DevOps Lead |
| R-012 | Biaya | Software license cost increase | License renewal higher | PM |
| R-013 | Kualitas | UAT gagal karena requirement mismatch | User dissatisfaction | QA Lead |
| R-014 | Kualitas | Performance NFR tidak tercapai | Load test failure | DevOps Lead |
| R-015 | Keamanan | Data breach pada audit log | Unauthorized access | Security Lead |
| R-016 | Keamanan | Compliance failure (PDP, ISO 27001) | Audit finding | Security Lead |
| R-017 | Keamanan | Vulnerabilities in third-party libraries | Dependency scan | Security Lead |
| R-018 | Eksternal | Third-party API downtime (SMTP, SMS) | Service disruption | DevOps Lead |
| R-019 | Eksternal | Cloud provider outage (AWS/GCP) | Service unavailable | DevOps Lead |
| R-020 | Eksternal | Perubahan regulasi terkait data | Regulation change | Security Lead |

## 9.3 RISK ANALYSIS

### 9.3.1 Probability-Impact Matrix

Probabilitas:

- Very High (5) : > 80%

- High (4) : 60-80%

- Medium (3) : 40-60%

- Low (2) : 20-40%

- Very Low (1) : < 20%

Dampak (Biaya, Jadwal, Kualitas):

- Very High (5) : > 20% impact

- High (4) : 10-20% impact

- Medium (3) : 5-10% impact

- Low (2) : 1-5% impact

- Very Low (1) : < 1% impact

| ID | Risk Description | Probability (P) | Impact (I) | Risk Score (P x I) | Priority |
| --- | --- | --- | --- | --- | --- |
| R-001 | Kompleksitas integrasi microservices | 5 | 5 | 25 | 🔴 Critical |
| R-002 | Performa audit log menurun | 4 | 4 | 16 | 🔴 Critical |
| R-003 | Security vulnerability IAM | 3 | 5 | 15 | 🟠 High |
| R-004 | Data migration quality issue | 4 | 3 | 12 | 🟠 High |
| R-006 | Team turnover | 4 | 4 | 16 | 🔴 Critical |
| R-007 | Kesulitan rekrut security | 4 | 3 | 12 | 🟠 High |
| R-009 | Scope creep | 5 | 3 | 15 | 🟠 High |
| R-010 | Integration with legacy complex | 4 | 4 | 16 | 🔴 Critical |
| R-011 | Cloud cost overrun | 3 | 3 | 9 | 🟡 Medium |
| R-013 | UAT gagal | 3 | 4 | 12 | 🟠 High |
| R-014 | Performance NFR tidak tercapai | 3 | 4 | 12 | 🟠 High |
| R-015 | Data breach | 2 | 5 | 10 | 🟡 Medium |
| R-016 | Compliance failure | 2 | 5 | 10 | 🟡 Medium |
| R-018 | Third-party API downtime | 3 | 2 | 6 | 🟢 Low |
| R-019 | Cloud provider outage | 1 | 5 | 5 | 🟢 Low |

### 9.3.2 Probability-Impact Matrix Visualization

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    PROBABILITY-IMPACT MATRIX P-FNE-01                       │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  Impact  │ Very Low │  Low   │ Medium  │  High  │ Very High │

│  Probability │ (1)    │  (2)   │  (3)    │  (4)   │   (5)     │

│──────────┼─────────┼────────┼─────────┼────────┼───────────│

│  Very High │         │        │         │        │           │

│   (5)     │         │        │ R-009   │ R-001  │           │

│──────────┼─────────┼────────┼─────────┼────────┼───────────│

│  High     │         │        │ R-004   │ R-002  │ R-003     │

│   (4)     │         │        │ R-006   │ R-010  │           │

│──────────┼─────────┼────────┼─────────┼────────┼───────────│

│  Medium   │         │ R-018  │ R-011   │ R-013  │           │

│   (3)     │         │        │         │ R-014  │           │

│──────────┼─────────┼────────┼─────────┼────────┼───────────│

│  Low      │         │        │         │ R-007  │ R-015     │

│   (2)     │         │        │         │        │ R-016     │

│──────────┼─────────┼────────┼─────────┼────────┼───────────│

│  Very Low │         │ R-020  │         │        │           │

│   (1)     │         │        │         │        │           │

│──────────┼─────────┼────────┼─────────┼────────┼───────────│

│           │         │        │         │        │           │

│            │  Critical │  High   │ Medium  │ Low   │           │

└─────────────────────────────────────────────────────────────────────────────┘

### 9.3.3 Risk Prioritization

| Priority | Risk Score | Risiko | Jumlah |
| --- | --- | --- | --- |
| 🔴 Critical | 16-25 | R-001, R-002, R-006, R-010 | 4 |
| 🟠 High | 12-15 | R-003, R-004, R-007, R-009, R-013, R-014 | 6 |
| 🟡 Medium | 9-11 | R-011, R-015, R-016 | 3 |
| 🟢 Low | < 9 | R-005, R-008, R-012, R-017, R-018, R-019, R-020 | 7 |

### 9.3.4 Expected Monetary Value (EMV) Analysis

| ID | Risk | Probability | Impact (Rp) | EMV (Rp) |
| --- | --- | --- | --- | --- |
| R-001 | Kompleksitas integrasi | 80% | 300.000.000 | 240.000.000 |
| R-002 | Performa audit log | 60% | 200.000.000 | 120.000.000 |
| R-006 | Team turnover | 60% | 250.000.000 | 150.000.000 |
| R-010 | Integration with legacy | 60% | 200.000.000 | 120.000.000 |
| R-009 | Scope creep | 80% | 150.000.000 | 120.000.000 |
| R-003 | Security vulnerability | 40% | 500.000.000 | 200.000.000 |
| R-015 | Data breach | 20% | 1.000.000.000 | 200.000.000 |
| R-011 | Cloud cost overrun | 40% | 100.000.000 | 40.000.000 |
| R-014 | Performance NFR | 40% | 150.000.000 | 60.000.000 |
| Total EMV |  |  |  | 1.250.000.000 |
| Contingency Reserve |  |  |  | 1.250.000.000 |

## 9.4 RISK RESPONSE PLANNING

### 9.4.1 Risk Response Strategies

| ID | Risk | Strategy | Response Plan | Owner |
| --- | --- | --- | --- | --- |
| R-001 | Kompleksitas integrasi microservices | Mitigate | • API-first design • Contract testing (Pact) • Weekly integration testing • Frequent integration builds | Tech Lead |
| R-002 | Performa audit log menurun | Mitigate | • Database partitioning by month • Elasticsearch for search • Redis caching • Load testing before Go-Live | Backend Lead |
| R-003 | Security vulnerability IAM | Prevent | • Security review at design phase • SAST in CI/CD pipeline • Penetration testing • OWASP compliance | Security Lead |
| R-004 | Data migration quality issue | Mitigate | • Data validation before migration • Incremental migration • Data quality report • Rollback plan | Data Steward |
| R-006 | Team turnover | Mitigate | • Knowledge sharing sessions • Documentation culture • Cross-training • Competitive compensation | PM |
| R-007 | Kesulitan rekrut security | Mitigate | • Start recruitment early • Contractors as backup • Internal training | PM + HR |
| R-009 | Scope creep | Control | • Strict Change Control Process • MoSCoW prioritization • Stakeholder alignment | PM |
| R-010 | Integration with legacy complex | Mitigate | • Integration layer design • API contract with legacy team • Incremental integration | Tech Lead |
| R-011 | Cloud cost overrun | Mitigate | • Auto-scaling limits • Reserved instances • Cost monitoring dashboard • Budget alert | DevOps Lead |
| R-013 | UAT gagal | Mitigate | • Early involvement of user • Frequent demos • UAT preparation | PM + QA Lead |
| R-014 | Performance NFR tidak tercapai | Mitigate | • Performance testing early • Profiling and optimization • Scalability testing | DevOps Lead |
| R-015 | Data breach | Prevent | • Encryption at rest and in transit • Access control • Monitoring and alerting • Incident response plan | Security Lead |
| R-016 | Compliance failure | Mitigate | • Compliance checklist • Regular security audit • Documentation | Security Lead |
| R-018 | Third-party API downtime | Mitigate | • Multiple providers • Retry mechanism • Circuit breaker • Fallback | DevOps Lead |

### 9.4.2 Risk Response Plan Detail

R-001: Kompleksitas Integrasi Microservices

| Aspek | Detail |
| --- | --- |
| Deskripsi | Integrasi antar 8 microservices (IAM, MDM, Audit, dll.) memiliki kompleksitas tinggi |
| Strategi | Mitigate |
| Tindakan | 1. API-first design dengan OpenAPI 3.0 2. Contract testing menggunakan Pact 3. Weekly integration testing 4. Daily integration build |
| Trigger | Integration test failure > 10% |
| Contingency | Dedicated integration week, tambahan resource |
| Owner | Tech Lead |
| Timeline | Selama pengembangan |

R-006: Team Turnover

| Aspek | Detail |
| --- | --- |
| Deskripsi | Kehilangan team member kunci (DevOps, Backend Lead, Security) |
| Strategi | Mitigate |
| Tindakan | 1. Knowledge sharing session 2 minggu sekali 2. Dokumentasi yang baik (Confluence) 3. Cross-training antar member 4. Competitive compensation |
| Trigger | Resignation notice diterima |
| Contingency | 1. Onboarding plan siap 2. Kontraktor sebagai backup 3. Knowledge transfer 2 minggu |
| Owner | PM |
| Timeline | Seluruh durasi proyek |

### 9.4.3 Contingency Reserve Allocation

| Kategori Risiko | EMV (Rp) | Contingency (Rp) |
| --- | --- | --- |
| Teknis | 740.000.000 | 550.000.000 |
| Sumber Daya | 270.000.000 | 200.000.000 |
| Jadwal | 240.000.000 | 200.000.000 |
| Keamanan | 400.000.000 | 300.000.000 |
| Total | 1.650.000.000 | 1.250.000.000 |

## 9.5 RISK MONITORING & CONTROL

### 9.5.1 Risk Monitoring Activities

| Aktivitas | Frekuensi | Owner | Deskripsi |
| --- | --- | --- | --- |
| Risk Review | Mingguan | PM | Review status risiko, update risk register |
| Risk Audit | Bulanan | PMO | Audit efektivitas risk response |
| Risk Retrospective | Setiap Sprint | PM | Identifikasi risiko baru dari sprint |
| Risk Dashboard | Real-time | PM | Monitoring risk score dan status |
| Risk Trigger Monitoring | Continuous | Owner | Monitoring trigger setiap risiko |

### 9.5.2 Risk Register Template

| Field | Deskripsi |
| --- | --- |
| Risk ID | R-XXX |
| Risk Category | Teknis / Organisasi / Sumber Daya / dll. |
| Risk Description | Deskripsi risiko |
| Probability | 1-5 |
| Impact | 1-5 |
| Risk Score | Probability x Impact |
| Priority | Critical / High / Medium / Low |
| Status | Active / Mitigated / Closed / Contingency |
| Trigger | Indikator risiko terjadi |
| Strategy | Avoid / Mitigate / Transfer / Accept |
| Response Plan | Tindakan yang dilakukan |
| Contingency Plan | Rencana cadangan |
| Owner | Person in charge |
| EMV | Expected Monetary Value |
| Actual Impact | Dampak aktual jika terjadi |

### 9.5.3 Risk Dashboard

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    RISK DASHBOARD P-FNE-01                                  │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  RISK SUMMARY                                                               │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Total Risks    │ Active │ Mitigated │ Closed │ Critical │ High    │    │

│  │ 20             │ 15     │ 3         │ 2      │ 4        │ 6       │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  RISK STATUS BY CATEGORY                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Kategori       │ Total │ Active │ Mitigated │ Closed               │    │

│  │ Teknis         │ 5     │ 4      │ 1         │ 0                    │    │

│  │ Sumber Daya    │ 3     │ 2      │ 1         │ 0                    │    │

│  │ Jadwal         │ 3     │ 2      │ 0         │ 1                    │    │

│  │ Biaya          │ 2     │ 2      │ 0         │ 0                    │    │

│  │ Kualitas       │ 2     │ 2      │ 0         │ 0                    │    │

│  │ Keamanan       │ 3     │ 2      │ 1         │ 0                    │    │

│  │ Eksternal      │ 2     │ 1      │ 0         │ 1                    │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  CRITICAL RISKS                                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ ID    │ Description                  │ Status   │ Owner            │    │

│  │ R-001 │ Kompleksitas integrasi       │ Active   │ Tech Lead       │    │

│  │ R-002 │ Performa audit log           │ Active   │ Backend Lead   │    │

│  │ R-006 │ Team turnover                │ Active   │ PM              │    │

│  │ R-010 │ Integration with legacy      │ Active   │ Tech Lead       │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  RECENTLY MITIGATED RISKS                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ ID    │ Description                  │ Date      │ Owner            │    │

│  │ R-003 │ Security vulnerability IAM   │ 15-Oct-26 │ Security Lead   │    │

│  │ R-008 │ Overload tim                 │ 20-Oct-26 │ PM              │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 9.5.4 Risk Thresholds & Triggers

| Kategori | Threshold | Trigger | Action |
| --- | --- | --- | --- |
| Schedule | Delay > 10% dari baseline | Milestone missed | Eskalasi ke Sponsor |
| Budget | Overrun > 10% dari baseline | Cost > budget | Eskalasi ke Sponsor |
| Quality | Code coverage < 70% | SonarQube gate fail | Tindakan korektif |
| Security | Critical vulnerability | Security scan fail | Tindakan darurat |
| Risk Score | Score > 15 | Risk review | Eskalasi ke PMO |

# BAB 10: MANAJEMEN PENGADAAN PROYEK

## (PROJECT PROCUREMENT MANAGEMENT)

## 10.1 PROCUREMENT MANAGEMENT APPROACH

### 10.1.1 Pendekatan Umum

Manajemen pengadaan proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Metodologi | Terintegrasi dengan siklus proyek, fokus pada value for money |
| Jenis | Pembelian perangkat lunak, layanan cloud, lisensi, dan jasa konsultasi |
| Proses | Sesuai dengan regulasi pengadaan perusahaan dan best practices |
| Pengendalian | Vendor performance monitoring, contract management, dan procurement audit |

### 10.1.2 Proses Manajemen Pengadaan

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    PROSES MANAJEMEN PENGADAAN P-FNE-01                      │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1. PERENCANAAN PENGADAAN                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Identifikasi kebutuhan pengadaan                                 │    │

│  │ • Analisis make-or-buy                                             │    │

│  │ • Penyusunan Procurement Plan                                      │    │

│  │ • Penyusunan anggaran pengadaan                                    │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  2. SELEKSI VENDOR                                                          │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penyusunan RFP/RFQ                                               │    │

│  │ • Evaluasi vendor berdasarkan kriteria                            │    │

│  │ • Due diligence dan negosiasi                                     │    │

│  │ • Pemilihan vendor                                                │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  3. KONTRAK & PEMBELIAN                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penyusunan kontrak                                               │    │

│  │ • Review legal dan komersial                                      │    │

│  │ • Penandatanganan kontrak                                         │    │

│  │ • Purchase Order (PO)                                             │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  4. ADMINISTRASI KONTRAK                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Monitoring kinerja vendor                                        │    │

│  │ • Manajemen perubahan kontrak                                     │    │

│  │ • Pembayaran dan invoicing                                        │    │

│  │ • Penutupan kontrak                                               │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 10.2 PROCUREMENT PLANNING

### 10.2.1 Procurement Identification

| No | Item | Deskripsi | Kebutuhan | Estimasi Biaya (Rp) | Timeline | Kategori |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Cloud Infrastructure | AWS/GCP untuk hosting environment | 4 environment (Dev, Test, Staging, Prod) | 500.000.000 | Okt 2026 - Mar 2027 | Cloud |
| 2 | Kubernetes Platform | Managed Kubernetes (EKS/GKE) | 4 cluster | Termasuk Cloud | Okt 2026 | Cloud |
| 3 | Identity Management (IAM) | Keycloak / Okta Enterprise | SSO, MFA, User management | 150.000.000 | Okt 2026 | Software |
| 4 | API Gateway | Kong Enterprise / Traefik | API management | 100.000.000 | Nov 2026 | Software |
| 5 | Message Broker | Confluent Cloud (Kafka) | Event bus | 150.000.000 | Nov 2026 | Software |
| 6 | CI/CD Tools | GitLab Ultimate / GitHub Enterprise | CI/CD pipeline | 100.000.000 | Okt 2026 | Software |
| 7 | Monitoring Tools | Datadog / New Relic (opsional) | Monitoring tambahan | 50.000.000 | Okt 2026 | Software |
| 8 | SMTP Service | SendGrid / Amazon SES | Email notification | 25.000.000 | Des 2026 | Service |
| 9 | SMS Service | Twilio / Infobip | SMS notification | 25.000.000 | Des 2026 | Service |
| 10 | Security Assessment | External penetration testing | Security audit | 50.000.000 | Feb 2027 | Service |
| 11 | Training | Cloud & Security training | Team training | 50.000.000 | Okt 2026 | Service |
| 12 | Backup Storage | S3 / Glacier / Cold storage | Backup & archival | 50.000.000 | Okt 2026 | Cloud |
| 13 | Consultancy | Specialized consultant (jika diperlukan) | Technical advisory | 100.000.000 | As needed | Service |

Total Estimasi Pengadaan:

| Kategori | Biaya |
| --- | --- |
| Cloud Infrastructure | 550.000.000 |
| Software Licenses | 500.000.000 |
| Services | 250.000.000 |
| Total | 1.300.000.000 |

### 10.2.2 Make-or-Buy Analysis

| Komponen | Make | Buy | Keputusan | Alasan |
| --- | --- | --- | --- | --- |
| IAM | ✓ | ✓ | Buy + Custom | Gunakan Keycloak, custom integration untuk bisnis |
| Master Data | ✓ |  | Make | Spesifik untuk bisnis pertanian |
| Workflow Engine | ✓ | ✓ | Buy + Custom | Gunakan Camunda, custom workflow definition |
| Notification | ✓ |  | Make | Integrasi dengan existing system |
| API Gateway |  | ✓ | Buy | Standard solution (Kong) |
| Event Bus |  | ✓ | Buy | Standard solution (Kafka) |
| Monitoring |  | ✓ | Buy | Gunakan open source (Prometheus/Grafana) |
| CI/CD |  | ✓ | Buy | Standard solution (GitLab) |
| Cloud Infrastructure |  | ✓ | Buy | Hindari capex, fokus ke aplikasi |
| Authentication |  | ✓ | Buy | Keycloak/Okta |
| Email Service |  | ✓ | Buy | SendGrid/SES |
| SMS Service |  | ✓ | Buy | Twilio/Infobip |
| Security Testing |  | ✓ | Buy | External penetration testing |

### 10.2.3 Procurement Budget Allocation

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    PROCUREMENT BUDGET ALLOCATION P-FNE-01                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  Cloud Infrastructure         550,000,000 (42%)                             │

│  ████████████████████████████████████████████████████████████              │

│                                                                              │

│  Software Licenses            500,000,000 (39%)                             │

│  ██████████████████████████████████████████████████████████                │

│                                                                              │

│  Services                    250,000,000 (19%)                             │

│  ███████████████████████████████████████████                               │

│                                                                              │

│  Total: 1,300,000,000                                                      │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 10.3 MAKE-OR-BUY DECISIONS

### 10.3.1 Make-or-Buy Decision Matrix

| No | Komponen | Make | Buy | Decision | Justifikasi | Estimated Cost Make | Estimated Cost Buy | Savings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | IAM Service | ✓ | ✓ | Buy + Custom | Keycloak is mature, focus on integration | 200,000,000 | 150,000,000 | 50,000,000 |
| 2 | Master Data | ✓ |  | Make | Business specific, competitive advantage | 350,000,000 | N/A | - |
| 3 | Workflow Engine | ✓ | ✓ | Buy + Custom | Camunda standard, custom workflow | 200,000,000 | 100,000,000 | 100,000,000 |
| 4 | Notification Service | ✓ |  | Make | Integration with existing systems | 150,000,000 | 200,000,000 | 50,000,000 |
| 5 | API Gateway |  | ✓ | Buy | Kong standard solution | 50,000,000 | 100,000,000 | -50,000,000 |
| 6 | Event Bus |  | ✓ | Buy | Kafka standard solution | 50,000,000 | 150,000,000 | -100,000,000 |
| 7 | Monitoring |  | ✓ | Buy | Prometheus/Grafana open source | 20,000,000 | 50,000,000 | -30,000,000 |
| 8 | CI/CD |  | ✓ | Buy | GitLab standard | 30,000,000 | 100,000,000 | -70,000,000 |
| 9 | Cloud Infrastructure |  | ✓ | Buy | Avoid capex | N/A | 550,000,000 | - |
| 10 | Email Service |  | ✓ | Buy | SendGrid/SES standard | 10,000,000 | 25,000,000 | -15,000,000 |
| 11 | SMS Service |  | ✓ | Buy | Twilio standard | 10,000,000 | 25,000,000 | -15,000,000 |
| 12 | Security Testing |  | ✓ | Buy | External expertise | 20,000,000 | 50,000,000 | -30,000,000 |

### 10.3.2 Rationale for Make-or-Buy

Make Decisions:

- Master Data Management: Domain-specific untuk bisnis pertanian, membutuhkan fleksibilitas tinggi.

- Notification Service: Integrasi dengan existing notification infrastructure.

Buy Decisions:

- IAM: Keycloak/Okta sudah mature dan feature-rich.

- API Gateway: Kong standard solution dengan community support.

- Event Bus: Kafka standard solution.

- Workflow Engine: Camunda standard solution dengan BPMN support.

- Email/SMS: Third-party services reliable dan cost-effective.

Buy + Custom Decisions:

- IAM: Custom integration dengan existing user directory.

- Workflow Engine: Custom workflow definitions dan approval matrix.

## 10.4 PROCUREMENT DOCUMENTS

### 10.4.1 Request for Proposal (RFP) Template

RFP - [Project Name]

| Section | Content |
| --- | --- |
| 1. Introduction | Background, scope, objectives |
| 2. Scope of Work | Detailed scope, deliverables, timeline |
| 3. Technical Requirements | Functional and non-functional requirements |
| 4. Commercial Requirements | Pricing, payment terms, contract duration |
| 5. Proposal Requirements | Format, content, submission deadline |
| 6. Evaluation Criteria | Technical (60%), Commercial (40%) |
| 7. Timeline | RFP issue date, Q&A, proposal submission, evaluation, award |

### 10.4.2 Evaluation Criteria

| No | Kriteria | Bobot | Deskripsi |
| --- | --- | --- | --- |
| 1 | Technical Capability | 40% | Experience, expertise, solution fit |
| 2 | Solution Quality | 20% | Product quality, reliability, scalability |
| 3 | Commercial | 20% | Pricing, payment terms, value for money |
| 4 | Implementation Plan | 10% | Timeline, resource plan, methodology |
| 5 | Support & Maintenance | 10% | SLA, support availability, documentation |

### 10.4.3 Vendor Selection Criteria

| No | Kriteria | Weight | Score (1-5) |
| --- | --- | --- | --- |
| 1 | Technical Expertise | 30% |  |
| 2 | Product Maturity | 20% |  |
| 3 | Pricing | 20% |  |
| 4 | Implementation Experience | 15% |  |
| 5 | Support Quality | 10% |  |
| 6 | Financial Stability | 5% |  |

## 10.5 VENDOR SELECTION

### 10.5.1 Shortlisted Vendors

| No | Item | Vendor 1 | Vendor 2 | Vendor 3 | Selected |
| --- | --- | --- | --- | --- | --- |
| 1 | Cloud | AWS | Google Cloud | Azure | AWS |
| 2 | IAM | Keycloak | Okta | Auth0 | Keycloak |
| 3 | API Gateway | Kong | Traefik | Nginx | Kong |
| 4 | Message Broker | Confluent | Aiven | AWS MSK | Confluent |
| 5 | CI/CD | GitLab | GitHub Actions | Jenkins | GitLab |
| 6 | Email | SendGrid | Amazon SES | Mailgun | SendGrid |
| 7 | SMS | Twilio | Infobip | Sinch | Twilio |
| 8 | Security Testing | Vendor A | Vendor B | Vendor C | - |

### 10.5.2 Vendor Evaluation Summary

IAM Vendor Comparison:

| Kriteria | Keycloak | Okta | Auth0 |
| --- | --- | --- | --- |
| Technical Capability | 4.5 | 4.8 | 4.7 |
| Cost | 4.0 | 3.0 | 3.5 |
| Ease of Integration | 4.0 | 4.5 | 4.5 |
| Support | 3.5 | 4.5 | 4.0 |
| Total Score | 16.0 | 16.8 | 16.7 |
| Ranking | 3 | 1 | 2 |

Selected: Okta (Dengan alasan integration support dan maturity)

## 10.6 CONTRACT MANAGEMENT

### 10.6.1 Contract Types

| No | Vendor | Contract Type | Duration | Value | Payment Terms |
| --- | --- | --- | --- | --- | --- |
| 1 | AWS | Subscription | 12 months | 500,000,000 | Monthly |
| 2 | Okta | Subscription | 12 months | 150,000,000 | Annual |
| 3 | Kong | Subscription | 12 months | 100,000,000 | Annual |
| 4 | Confluent | Subscription | 12 months | 150,000,000 | Monthly |
| 5 | GitLab | Subscription | 12 months | 100,000,000 | Annual |
| 6 | SendGrid | Subscription | 12 months | 25,000,000 | Monthly |
| 7 | Twilio | Prepaid | 12 months | 25,000,000 | Prepaid |

### 10.6.2 Contract Review Checklist

| No | Aspek | Check |
| --- | --- | --- |
| 1 | Scope of Work | Jelas dan terdefinisi | [ ] |
| 2 | Deliverables | Jelas dan terukur | [ ] |
| 3 | Timeline | Jelas dan realistis | [ ] |
| 4 | Pricing | Jelas, tidak ada biaya tersembunyi | [ ] |
| 5 | Payment Terms | Jelas dan wajar | [ ] |
| 6 | SLA (Service Level Agreement) | Jelas dan terukur | [ ] |
| 7 | Data Privacy | Sesuai regulasi | [ ] |
| 8 | Security | Standar keamanan terpenuhi | [ ] |
| 9 | Intellectual Property | Jelas kepemilikannya | [ ] |
| 10 | Termination Clause | Jelas dan wajar | [ ] |
| 11 | Liability | Jelas dan wajar | [ ] |
| 12 | Insurance | Dicovered oleh vendor | [ ] |

### 10.6.3 Vendor Performance Monitoring

| No | Vendor | KPI | Target | Actual | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | AWS | Uptime | 99.9% | - | 🟡 Monitoring |
| 2 | Okta | Uptime | 99.99% | - | 🟡 Monitoring |
| 3 | Kong | Uptime | 99.95% | - | 🟡 Monitoring |
| 4 | Confluent | Uptime | 99.95% | - | 🟡 Monitoring |
| 5 | GitLab | Uptime | 99.9% | - | 🟡 Monitoring |
| 6 | SendGrid | Delivery Rate | 95% | - | 🟡 Monitoring |
| 7 | Twilio | Delivery Rate | 95% | - | 🟡 Monitoring |

## 10.7 PROCUREMENT CONTROL

### 10.7.1 Procurement Schedule

| No | Activity | Timeline | Owner |
| --- | --- | --- | --- |
| 1 | Identify procurement needs | Minggu 0-1 | PM |
| 2 | Prepare RFP/RFQ | Minggu 1-2 | PM + Procurement |
| 3 | Vendor selection | Minggu 2-4 | Procurement |
| 4 | Contract negotiation | Minggu 4-5 | PM + Legal |
| 5 | Contract signing | Minggu 5 | Sponsor |
| 6 | Vendor onboarding | Minggu 6-7 | Tech Lead |
| 7 | Monitoring | Continuous | PM |

### 10.7.2 Procurement Risk Register

| No | Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Vendor tidak memenuhi timeline | Medium | High | Contract penalty, multiple options | PM |
| 2 | Vendor financial instability | Low | High | Due diligence, financial check | Procurement |
| 3 | Vendor security compliance | Medium | High | Security review, compliance check | Security Lead |
| 4 | Cost overrun | Medium | Medium | Fixed price contract, contingency | PM |
| 5 | Vendor lock-in | Low | Medium | Open standards, multi-cloud strategy | Tech Lead |

## 10.8 PROCUREMENT CLOSURE

### 10.8.1 Vendor Performance Evaluation

| No | Vendor | Performance | Issues | Recommendation |
| --- | --- | --- | --- | --- |
| 1 | AWS | - | - | - |
| 2 | Okta | - | - | - |
| 3 | Kong | - | - | - |
| 4 | Confluent | - | - | - |
| 5 | GitLab | - | - | - |
| 6 | SendGrid | - | - | - |
| 7 | Twilio | - | - | - |

### 10.8.2 Procurement Lessons Learned

| No | Lessons Learned | Recommendation |
| --- | --- | --- |
| 1 | - | - |
| 2 | - | - |
| 3 | - | - |

### 10.8.3 Contract Closure Checklist

| No | Item | Completed |
| --- | --- | --- |
| 1 | All deliverables accepted | [ ] |
| 2 | All payments made | [ ] |
| 3 | Final invoice received | [ ] |
| 4 | Vendor performance evaluation | [ ] |
| 5 | Contract archived | [ ] |
| 6 | Lessons learned documented | [ ] |

# BAB 11: MANAJEMEN PEMANGKU KEPENTINGAN

## (PROJECT STAKEHOLDER MANAGEMENT)

## 11.1 STAKEHOLDER MANAGEMENT APPROACH

### 11.1.1 Pendekatan Umum

Manajemen pemangku kepentingan proyek P-FNE-01 akan dilaksanakan dengan pendekatan sebagai berikut:

| Aspek | Pendekatan |
| --- | --- |
| Filosofi | Kolaboratif, transparan, dan berorientasi pada kepuasan stakeholder |
| Metodologi | Identifikasi, analisis, engagement planning, monitoring, dan kontrol |
| Alat | Stakeholder Register, Power/Interest Grid, Engagement Matrix |
| Frekuensi | Review stakeholder engagement setiap sprint, update register setiap bulan |
| Pengendalian | Stakeholder satisfaction survey, feedback loop, issue escalation |

### 11.1.2 Proses Manajemen Pemangku Kepentingan

text

┌─────────────────────────────────────────────────────────────────────────────┐

│              PROSES MANAJEMEN PEMANGKU KEPENTINGAN P-FNE-01                │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  1. IDENTIFIKASI PEMANGKU KEPENTINGAN                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Identifikasi semua pihak yang terkait                            │    │

│  │ • Kategorisasi berdasarkan peran dan pengaruh                      │    │

│  │ • Penyusunan Stakeholder Register                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  2. ANALISIS PEMANGKU KEPENTINGAN                                            │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Power/Interest Grid                                              │    │

│  │ • Influence/Impact Matrix                                         │    │

│  │ • Analisis kebutuhan dan harapan                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  3. PERENCANAAN ENGAGEMENT                                                   │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penentuan strategi engagement                                    │    │

│  │ • Penyusunan Stakeholder Engagement Plan                          │    │

│  │ • Penetapan metode dan frekuensi komunikasi                       │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  4. MONITORING & KONTROL                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Stakeholder satisfaction monitoring                              │    │

│  │ • Feedback collection                                              │    │

│  │ • Penyesuaian strategi engagement                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 11.2 STAKEHOLDER IDENTIFICATION & ANALYSIS

### 11.2.1 Stakeholder Register

| ID | Nama Stakeholder | Peran/Organisasi | Kategori | Kebutuhan & Harapan | Pengaruh | Minat | Engagement Level |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S-01 | Project Sponsor | VP of Technology | Internal | • Proyek sesuai timeline dan budget • ROI terukur • Risiko terkelola dengan baik | High | High | Leading |
| S-02 | Steering Committee | Multi-stakeholder | Internal | • Informasi akurat untuk keputusan • Proyek selaras dengan strategi • Risiko strategis teridentifikasi | High | High | Supportive |
| S-03 | Head of PMO | Project Management Office | Internal | • Kepatuhan terhadap standar PMO • Kualitas pelaporan • Lessons learned terdokumentasi | Medium | High | Supportive |
| S-04 | Project Manager | PM P-FNE-01 | Internal | • Wewenang dan sumber daya cukup • Dukungan dari stakeholder • Tim yang kompeten | High | High | Leading |
| S-05 | DevOps Lead | Technical Lead | Internal | • Infrastruktur yang stabil • CI/CD pipeline yang efisien • Monitoring yang baik | High | High | Leading |
| S-06 | Tech Lead | Technical Lead | Internal | • Arsitektur yang scalable • Code quality terjaga • Technical debt terkendali | High | High | Leading |
| S-07 | Security Lead | Technical Lead | Internal | • Keamanan sistem terjamin • Compliance terpenuhi • IAM berfungsi dengan baik | High | High | Leading |
| S-08 | Project Team | All team members | Internal | • Lingkungan kerja yang baik • Pengakuan atas kerja keras • Pengembangan karir | Medium | High | Supportive |
| S-09 | Business Owner | Business Stakeholder | Internal | • Fitur sesuai bisnis • UAT sukses • Adopsi user tinggi | High | High | Supportive |
| S-10 | IT Operations | Operations Team | Internal | • Deployment lancar • Dokumentasi lengkap • Handover terencana | Medium | High | Supportive |
| S-11 | Data Steward | Data Management | Internal | • Master data berkualitas • Duplicate detection • Data governance | Medium | Medium | Supportive |
| S-12 | End Users (Future) | Agricultural Ops Team | Internal | • User-friendly • Performa baik • Training memadai | Low | High | Aware |
| S-13 | External Auditors | Compliance | Eksternal | • Audit trail lengkap • Compliance terpenuhi • Transparansi | High | Medium | Aware |
| S-14 | Vendors | Third-party | Eksternal | • Kontrak jelas • Pembayaran tepat waktu • Komunikasi baik | Low | Low | Supportive |
| S-15 | Security Team | Corporate Security | Internal | • Security standards terpenuhi • Vulnerabilities teridentifikasi • Security review | High | High | Supportive |
| S-16 | HR | Human Resources | Internal | • Rekrutmen tepat waktu • Onboarding lancar • Kebutuhan sumber daya | Medium | Medium | Supportive |
| S-17 | Finance | Finance Department | Internal | • Budget terkelola • Cash flow tepat • Procurement sesuai | Medium | Medium | Supportive |
| S-18 | Legal | Legal Department | Internal | • Kontrak vendor aman • Compliance regulasi • Data privacy | Medium | Medium | Supportive |

### 11.2.2 Power/Interest Grid

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    POWER/INTEREST GRID P-FNE-01                             │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  High Power                                                                 │

│  ▲                                                                          │

│  │  KEY PLAYERS (Manage Closely)                                            │

│  │  ┌──────────────────────────────────────────────────────────────┐       │

│  │  │ • S-01: Project Sponsor                                     │       │

│  │  │ • S-02: Steering Committee                                  │       │

│  │  │ • S-04: Project Manager                                     │       │

│  │  │ • S-09: Business Owner                                      │       │

│  │  │ • S-05: DevOps Lead                                         │       │

│  │  │ • S-06: Tech Lead                                           │       │

│  │  │ • S-07: Security Lead                                       │       │

│  │  └──────────────────────────────────────────────────────────────┘       │

│  │                                                                          │

│  │  KEEP SATISFIED (Keep Informed)                                          │

│  │  ┌──────────────────────────────────────────────────────────────┐       │

│  │  │ • S-03: Head of PMO                                         │       │

│  │  │ • S-10: IT Operations                                       │       │

│  │  │ • S-15: Security Team                                       │       │

│  │  │ • S-13: External Auditors                                   │       │

│  │  └──────────────────────────────────────────────────────────────┘       │

│  │                                                                          │

│  │  MONITOR (Watch)                                                         │

│  │  ┌──────────────────────────────────────────────────────────────┐       │

│  │  │ • S-12: End Users (Future)                                  │       │

│  │  │ • S-14: Vendors                                             │       │

│  │  └──────────────────────────────────────────────────────────────┘       │

│  │                                                                          │

│  │  SHOW CONSIDERATION (Keep Informed)                                      │

│  │  ┌──────────────────────────────────────────────────────────────┐       │

│  │  │ • S-08: Project Team                                         │       │

│  │  │ • S-11: Data Steward                                         │       │

│  │  │ • S-16: HR                                                   │       │

│  │  │ • S-17: Finance                                              │       │

│  │  │ • S-18: Legal                                                │       │

│  │  └──────────────────────────────────────────────────────────────┘       │

│  │                                                                          │

│  └─────────────────────────────────────────────────────────────────────────│

│  Low Power                                                        High Interest │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 11.2.3 Stakeholder Influence/Impact Matrix

| ID | Stakeholder | Influence | Impact | Priority |
| --- | --- | --- | --- | --- |
| S-01 | Project Sponsor | 5 | 5 | 🔴 Critical |
| S-02 | Steering Committee | 5 | 5 | 🔴 Critical |
| S-04 | Project Manager | 5 | 5 | 🔴 Critical |
| S-09 | Business Owner | 4 | 5 | 🔴 Critical |
| S-05 | DevOps Lead | 4 | 4 | 🟠 High |
| S-06 | Tech Lead | 4 | 4 | 🟠 High |
| S-07 | Security Lead | 4 | 4 | 🟠 High |
| S-03 | Head of PMO | 3 | 3 | 🟡 Medium |
| S-10 | IT Operations | 3 | 4 | 🟡 Medium |
| S-15 | Security Team | 3 | 4 | 🟡 Medium |
| S-13 | External Auditors | 3 | 2 | 🟢 Low |
| S-08 | Project Team | 2 | 5 | 🟡 Medium |
| S-12 | End Users | 1 | 3 | 🟢 Low |
| S-14 | Vendors | 1 | 2 | 🟢 Low |
| S-11 | Data Steward | 2 | 2 | 🟢 Low |
| S-16 | HR | 2 | 2 | 🟢 Low |
| S-17 | Finance | 2 | 2 | 🟢 Low |
| S-18 | Legal | 2 | 2 | 🟢 Low |

## 11.3 STAKEHOLDER ENGAGEMENT PLAN

### 11.3.1 Engagement Matrix (Current vs Desired)

| ID | Stakeholder | Current Engagement | Desired Engagement | Gap | Action Plan |
| --- | --- | --- | --- | --- | --- |
| S-01 | Project Sponsor | Leading | Leading | - | Weekly 1-on-1, Monthly steering |
| S-02 | Steering Committee | Aware | Supportive | ↑ | Regular updates, Issue escalation |
| S-04 | Project Manager | Leading | Leading | - | Full authority, Decision making |
| S-09 | Business Owner | Aware | Supportive | ↑ | Sprint reviews, UAT involvement |
| S-05 | DevOps Lead | Leading | Leading | - | Infrastructure authority |
| S-06 | Tech Lead | Leading | Leading | - | Technical authority |
| S-07 | Security Lead | Leading | Leading | - | Security authority |
| S-03 | Head of PMO | Supportive | Supportive | - | Weekly reporting, Quality reviews |
| S-10 | IT Operations | Resistant | Supportive | ↑↑ | Early involvement, Training |
| S-15 | Security Team | Aware | Supportive | ↑ | Security reviews, Collaboration |
| S-13 | External Auditors | Unaware | Aware | ↑ | Regular updates, Compliance reports |
| S-08 | Project Team | Supportive | Leading | ↑ | Empowerment, Recognition |
| S-12 | End Users (Future) | Unaware | Aware | ↑ | Awareness sessions, Demos |
| S-14 | Vendors | Supportive | Supportive | - | Regular communication, Performance monitoring |
| S-11 | Data Steward | Aware | Supportive | ↑ | Data quality collaboration |
| S-16 | HR | Supportive | Supportive | - | Regular updates on staffing |
| S-17 | Finance | Supportive | Supportive | - | Budget monitoring, Reporting |
| S-18 | Legal | Supportive | Supportive | - | Contract review support |

### 11.3.2 Stakeholder Engagement Activities

| ID | Stakeholder | Engagement Method | Frequency | Owner | Success Indicator |
| --- | --- | --- | --- | --- | --- |
| S-01 | Project Sponsor | 1-on-1 Meeting | Mingguan | PM | Decisions made, Sponsor satisfaction |
|  |  | Steering Meeting | Bulanan | PM | Strategic alignment |
| S-02 | Steering Committee | Steering Meeting | Bulanan | PM | Decisions made, Issues resolved |
|  |  | Milestone Presentation | Per Milestone | PM | Milestone approved |
| S-04 | Project Manager | Daily Stand-up | Harian | PM | Team alignment |
|  |  | Sprint Planning | Setiap Sprint | PM | Sprint backlog approved |
| S-09 | Business Owner | Sprint Review | Setiap Sprint | PM | Feedback collected, UAT success |
|  |  | UAT Session | Go-Live | PM | UAT sign-off |
| S-05 | DevOps Lead | Daily Stand-up | Harian | PM | Infrastructure progress |
|  |  | Technical Review | 2 minggu | Tech Lead | Architecture alignment |
| S-06 | Tech Lead | Daily Stand-up | Harian | PM | Development progress |
|  |  | Code Review | Continuous | Tech Lead | Code quality |
| S-07 | Security Lead | Security Briefing | 1 bulan | Security Lead | Compliance status |
|  |  | Security Review | Per Milestone | Security Lead | Security findings addressed |
| S-03 | Head of PMO | Weekly Status | Mingguan | PM | Reports delivered |
|  |  | Quality Review | Bulanan | QA Lead | Quality metrics |
| S-10 | IT Operations | Handover Briefing | Sebelum Go-Live | DevOps Lead | Operations ready |
|  |  | Support Training | Go-Live | PM | Support team trained |
| S-15 | Security Team | Security Review | 1 bulan | Security Lead | Security compliance |
|  |  | Vulnerability Assessment | Per Milestone | Security Lead | Issues resolved |
| S-13 | External Auditors | Audit Preparation | Per Audit | PM | Audit ready |
|  |  | Audit Meeting | Per Audit | PM | Audit pass |
| S-08 | Project Team | Daily Stand-up | Harian | PM | Team motivation |
|  |  | Sprint Retrospective | Setiap Sprint | PM | Process improvement |
|  |  | Team Building | 1 bulan | PM | Team morale |
| S-12 | End Users | Demo Session | Per Sprint | PM | User awareness |
|  |  | Training | Go-Live | PM | User readiness |
|  |  | UAT | Go-Live | PM | User acceptance |
| S-14 | Vendors | Vendor Meeting | As needed | PM | Performance satisfaction |
|  |  | Contract Review | Per Procurement | PM | Contract compliance |
| S-11 | Data Steward | Data Review | Mingguan | Data Steward | Data quality |
|  |  | Master Data Meeting | Bulanan | PM | Data alignment |
| S-16 | HR | Staffing Review | Mingguan | PM | Resource availability |
|  |  | Recruitment Update | As needed | PM | Positions filled |
| S-17 | Finance | Budget Review | Bulanan | PM | Budget compliance |
|  |  | Financial Report | Bulanan | PM | Financial health |
| S-18 | Legal | Contract Review | Per Procurement | PM | Contract signed |
|  |  | Compliance Review | As needed | PM | Compliance ensured |

## 11.4 STAKEHOLDER COMMUNICATION

### 11.4.1 Communication by Stakeholder Category

| Category | Communication Type | Frequency | Content | Method |
| --- | --- | --- | --- | --- |
| Key Players | 1-on-1 Meeting | Mingguan | Strategic updates, decisions | Video Call |
|  | Steering Meeting | Bulanan | Overall status, risks, changes | Presentation |
|  | Status Report | Mingguan | Progress, milestones, budget | Dashboard |
| Keep Satisfied | Monthly Briefing | Bulanan | Updates, key decisions | Presentation |
|  | Compliance Report | Per Milestone | Compliance status | Document |
|  | Audit Report | Per Audit | Audit findings | Document |
| Keep Informed | Sprint Review | 2 minggu | Demo, feedback | Presentation |
|  | Newsletter | Bulanan | Project updates, awareness | Email |
|  | Training | Go-Live | System usage | Workshop |
| Monitor | Awareness Session | Per Milestone | Project visibility | Presentation |
|  | Vendor Meeting | As needed | Performance, issues | Meeting |

### 11.4.2 Feedback Collection Methods

| Method | Stakeholder | Frequency | Purpose | Owner |
| --- | --- | --- | --- | --- |
| Satisfaction Survey | All | Bulanan | Measure satisfaction | PM |
| Sprint Review Feedback | Business Owner, Users | 2 minggu | Gather product feedback | PM |
| Retrospective | Project Team | 2 minggu | Process improvement | PM |
| 1-on-1 Meeting | Sponsor | Mingguan | Strategic alignment | PM |
| UAT Survey | End Users | Go-Live | User acceptance | PM + QA |
| Vendor Feedback | Vendors | Per Milestone | Performance evaluation | PM |
| Security Review | Security Team | 1 bulan | Security status | Security Lead |
| Quality Review | PMO | Bulanan | Quality metrics | QA Lead |

## 11.5 ISSUE MANAGEMENT

### 11.5.1 Issue Management Process

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    ISSUE MANAGEMENT PROCESS P-FNE-01                       │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  STEP 1: IDENTIFIKASI                                                       │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Issue diidentifikasi oleh tim atau stakeholder                    │    │

│  │ • Dilaporkan ke PM atau Jira                                       │    │

│  │ • Kategorisasi: Teknis, Organisasi, Sumber Daya, dll.             │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 2: ANALISIS                                                           │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Analisis dampak terhadap proyek                                   │    │

│  │ • Penentuan prioritas: Critical, High, Medium, Low                │    │

│  │ • Identifikasi akar masalah                                        │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 3: RESOLUSI                                                           │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penentuan solusi                                                  │    │

│  │ • Assignment ke owner issue                                        │    │

│  │ • Implementasi solusi                                              │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 4: ESKALASI (Jika diperlukan)                                         │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Eskalasi ke Sponsor jika tidak bisa diselesaikan                │    │

│  │ • Eskalasi ke Steering Committee jika strategis                   │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 5: CLOSE                                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Verifikasi solusi                                                 │    │

│  │ • Dokumentasi issue dan resolusi                                  │    │

│  │ • Lessons learned (jika signifikan)                               │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 11.5.2 Issue Register Template

| Field | Deskripsi |
| --- | --- |
| Issue ID | ISS-XXX |
| Date Reported | Tanggal dilaporkan |
| Reported By | Nama pelapor |
| Issue Description | Deskripsi issue |
| Category | Teknis / Organisasi / Sumber Daya / dll. |
| Priority | Critical / High / Medium / Low |
| Impact | Dampak terhadap proyek |
| Status | Open / In Progress / Resolved / Closed |
| Owner | Person in charge |
| Resolution Plan | Rencana penyelesaian |
| Target Date | Tanggal target selesai |
| Actual Resolution Date | Tanggal realisasi |
| Resolution Details | Detail penyelesaian |
| Lesson Learned | Pembelajaran (jika ada) |

## 11.6 MONITORING & CONTROL

### 11.6.1 Stakeholder Satisfaction Monitoring

| Metode | Frekuensi | Stakeholder | Target | Owner |
| --- | --- | --- | --- | --- |
| Survey | Bulanan | All key stakeholders | ≥ 4.0/5.0 | PM |
| 1-on-1 Feedback | Mingguan | Sponsor, Key Players | Positive feedback | PM |
| Sprint Review Feedback | 2 minggu | Business Owner, Users | No major issues | PM |
| UAT Survey | Go-Live | End Users | ≥ 90% satisfaction | PM + QA |
| Retrospective | 2 minggu | Project Team | Improvement actions | PM |

### 11.6.2 Stakeholder Engagement Control

| No | Control Mechanism | Description | Frequency |
| --- | --- | --- | --- |
| 1 | Stakeholder Review | Review stakeholder engagement status | Bulanan |
| 2 | Feedback Analysis | Analisis feedback dan tindak lanjut | Bulanan |
| 3 | Engagement Adjustment | Penyesuaian strategi engagement | Sesuai kebutuhan |
| 4 | Issue Resolution | Monitoring resolusi issue | Harian/Mingguan |
| 5 | Communication Audit | Audit efektivitas komunikasi | Per Milestone |

### 11.6.3 Stakeholder Dashboard

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    STAKEHOLDER DASHBOARD P-FNE-01                           │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  STAKEHOLDER ENGAGEMENT SUMMARY                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Total Stakeholders │ 18                                             │    │

│  │ Satisfied          │ 15 (83%)                                      │    │

│  │ Needs Improvement  │ 3 (17%)                                       │    │

│  │ Unsatisfied        │ 0 (0%)                                        │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  ENGAGEMENT STATUS BY CATEGORY                                               │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ Category        │ Leading │ Supportive │ Aware │ Resistant         │    │

│  │ Key Players     │ 6       │ 0          │ 0     │ 0                 │    │

│  │ Keep Satisfied  │ 0       │ 4          │ 0     │ 0                 │    │

│  │ Keep Informed   │ 0       │ 3          │ 1     │ 0                 │    │

│  │ Monitor         │ 0       │ 0          │ 2     │ 0                 │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  OPEN ISSUES                                                                 │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ ID    │ Issue Description                  │ Priority │ Owner       │    │

│  │ ISS-1 │ IT Operations resistance           │ High     │ PM          │    │

│  │ ISS-2 │ End Users awareness low            │ Medium   │ PM          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

│  SATISFACTION TREND                                                          │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │  5.0│                                                               │    │

│  │  4.0│  ████████████████████                                        │    │

│  │  3.0│  ██████████████████████████████                              │    │

│  │  2.0│  ████████████████████████████████████████                    │    │

│  │  1.0│  ██████████████████████████████████████████████              │    │

│  │     └─────────────────────────────────────────────────────────────│    │

│  │       Oct   Nov   Dec   Jan   Feb   Mar                            │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

# BAB 12: LAMPIRAN

## (APPENDICES)

## 12.1 LAMPIRAN A: PROJECT CHARTER

### 12.1.1 Project Charter Document

PROJECT CHARTER
Proyek Foundation & Core Platform (P-FNE-01)
Super ERP Farm Nation Enterprise (FNE)

| Elemen | Detail |
| --- | --- |
| Project Name | Foundation & Core Platform (P-FNE-01) |
| Project ID | P-FNE-01 |
| Date | 01-Oct-2026 |
| Version | 1.0 |

1. Project Purpose / Business Case

Super ERP Farm Nation Enterprise (FNE) merupakan ekosistem digital terintegrasi yang terdiri dari 8 proyek turunan. Proyek P-FNE-01 (Foundation & Core Platform) merupakan fondasi dari seluruh ekosistem. Tanpa proyek ini, proyek-proyek lain tidak dapat beroperasi karena tidak memiliki platform yang aman, terintegrasi, dan memiliki sumber data yang konsisten.

Business Case:

- Efisiensi Operasional: Mengurangi biaya operasional IT hingga 30%

- Keamanan Data: Mengurangi risiko kehilangan data hingga 80%

- Kecepatan Pengembangan: Mempercepat pengembangan proyek turunan hingga 40%

- Kepatuhan: Memastikan kepatuhan terhadap regulasi (ISO 27001, PDP)

- ROI: Diperkirakan mencapai 150% dalam 3 tahun

2. Project Objectives

| No | Tujuan | Target | Metrik |
| --- | --- | --- | --- |
| 1 | Membangun infrastruktur cloud-native | 100% environment tersedia | 4 environment (Dev, Test, Staging, Prod) |
| 2 | Implementasi IAM | 100% fitur IAM berfungsi | User dapat login, MFA, RBAC |
| 3 | Implementasi MDM | 24 entitas master data | All entities can CRUD |
| 4 | Implementasi Audit | 100% transaksi tercatat | Audit log capture all actions |
| 5 | Implementasi Workflow | Minimal 3 workflow | 3 workflows running |
| 6 | Integrasi penuh | 100% integration complete | All services communicate |
| 7 | Quality & Security | Zero critical vulnerability | Security scan passed |
| 8 | Go-Live | 100% production ready | System live, DR tested |

3. Project Scope

In-Scope:

- Infrastructure & DevOps Management

- Identity & Access Management (IAM)

- Master Data Management (MDM) - 24 entities

- Audit & Logging

- API Gateway & Integration

- Event Bus & Messaging (Kafka)

- Workflow Engine

- Notification Service

Out-of-Scope:

- Core Agricultural Operations (P-FNE-02)

- Supply Chain & Procurement (P-FNE-03)

- Production & Manufacturing (P-FNE-04)

- Commerce, Sales & Logistics (P-FNE-05)

- Enterprise Finance & HCM (P-FNE-06)

- Intelligence & Decision Platform (P-FNE-07)

- Advanced & Autonomous Enterprise (P-FNE-08)

- Mobile Apps (Field Worker, Executive)

- Customer Portal & Supplier Portal

- Data Migration from Legacy Systems

4. Key Stakeholders

| Stakeholder | Role | Interest |
| --- | --- | --- |
| Project Sponsor | VP of Technology | Strategic alignment, budget, timeline |
| Steering Committee | Multi-stakeholder | Strategic decisions, risk management |
| Project Manager | PM P-FNE-01 | Day-to-day execution, delivery |
| Business Owner | Business Stakeholder | Business requirements, UAT |
| Project Team | All team members | Development, testing, delivery |
| IT Operations | Operations Team | Deployment, operations, monitoring |

5. High-Level Risks

| No | Risk | Impact | Mitigation |
| --- | --- | --- | --- |
| 1 | Kompleksitas integrasi microservices | High | API-first design, Contract testing |
| 2 | Performa audit log volume tinggi | High | Database partitioning, Elasticsearch |
| 3 | Team turnover | High | Knowledge sharing, Documentation |
| 4 | Cloud cost overrun | Medium | Auto-scaling limits, Cost monitoring |
| 5 | Security vulnerability | High | Security review, Penetration testing |

6. Summary Milestones

| Milestone | Target Date | Deliverable |
| --- | --- | --- |
| M1: Infrastructure Ready | 29-Oct-2026 | K8s, CI/CD, Monitoring ready |
| M2: IAM Complete | 26-Nov-2026 | Auth, MFA, RBAC functional |
| M3: MDM Complete | 24-Dec-2026 | 24 entities, import/export |
| M4: Audit Complete | 14-Jan-2027 | Audit trail, query, export |
| M5: Gateway & Event Bus | 28-Jan-2027 | Gateway routing, Kafka |
| M6: Workflow & Notification | 11-Feb-2027 | 3 workflows, notification |
| M7: Integration Ready | 25-Feb-2027 | All services integrated |
| M8: Go-Live | 11-Mar-2027 | Production deployment |
| M9: Project Closure | 25-Mar-2027 | Handover, documentation |

7. Budget

| Komponen | Biaya (Rp) |
| --- | --- |
| Biaya Personil | 7.368.000.000 |
| Biaya Langsung | 1.000.000.000 |
| Overhead (10%) | 836.800.000 |
| Keuntungan (12%) | 1.104.576.000 |
| PPN (11%) | 1.133.030.336 |
| Total | 11.442.406.336 |

8. Project Approval

| Peran | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Sponsor |  |  |  |
| Head of PMO |  |  |  |
| Business Owner |  |  |  |

## 12.2 LAMPIRAN B: DETAILED SCHEDULE (GANTT CHART)

### 12.2.1 Detailed Gantt Chart

| WBS | Aktivitas | Okt | Nov | Des | Jan | Feb | Mar |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Infrastructure & DevOps |  |  |  |  |  |  |
| 1.1.1 | Environment Provisioning | ██████ |  |  |  |  |  |
| 1.1.2 | Kubernetes Cluster | ██████ |  |  |  |  |  |
| 1.1.3 | CI/CD Pipeline | ██████ |  |  |  |  |  |
| 1.1.4 | Monitoring & Logging | ██████ |  |  |  |  |  |
| 1.1.5 | Backup & DR | ██████ |  |  |  |  |  |
| 1.1.6 | Secrets Management | ██████ |  |  |  |  |  |
| 1.2 | IAM |  |  |  |  |  |  |
| 1.2.1 | User Registration & Auth |  | ██████ | ██████ |  |  |  |
| 1.2.2 | Multi-Factor Authentication |  | ██████ |  |  |  |  |
| 1.2.3 | RBAC |  |  | ██████ |  |  |  |
| 1.2.4 | Permission Management |  |  | ██████ |  |  |  |
| 1.2.5 | Single Sign-On |  |  | ██████ |  |  |  |
| 1.2.6 | Session & Token Management |  |  | ██████ |  |  |  |
| 1.3 | MDM |  |  |  |  |  |  |
| 1.3.1 | Entity Schema Definition |  |  | ██████ | ██████ |  |  |
| 1.3.2 | CRUD Operations |  |  | ██████ | ██████ |  |  |
| 1.3.3 | Import/Export |  |  |  | ██████ |  |  |
| 1.3.4 | Duplicate Detection |  |  |  | ██████ |  |  |
| 1.3.5 | Versioning |  |  |  | ██████ |  |  |
| 1.4 | Audit & Logging |  |  |  |  |  |  |
| 1.4.1 | Audit Trail |  |  |  | ██████ | ██████ |  |
| 1.4.2 | Query & Export |  |  |  |  | ██████ |  |
| 1.4.3 | Security Logging |  |  |  |  | ██████ |  |
| 1.4.4 | Retention & Archival |  |  |  |  | ██████ |  |
| 1.5 | API Gateway |  |  |  |  |  |  |
| 1.5.1 | Gateway Setup |  |  |  | ██████ | ██████ |  |
| 1.5.2 | Routing & Rate Limit |  |  |  |  | ██████ |  |
| 1.5.3 | Auth at Gateway |  |  |  |  | ██████ |  |
| 1.5.4 | API Documentation |  |  |  |  | ██████ |  |
| 1.6 | Event Bus |  |  |  |  |  |  |
| 1.6.1 | Kafka Setup |  |  |  | ██████ | ██████ |  |
| 1.6.2 | Publisher/Subscriber |  |  |  |  | ██████ |  |
| 1.6.3 | DLQ |  |  |  |  | ██████ |  |
| 1.6.4 | Event Monitoring |  |  |  |  | ██████ |  |
| 1.7 | Workflow Engine |  |  |  |  |  |  |
| 1.7.1 | Workflow Definition |  |  |  |  | ██████ | ██████ |
| 1.7.2 | Workflow Execution |  |  |  |  | ██████ | ██████ |
| 1.7.3 | Approval Matrix |  |  |  |  |  | ██████ |
| 1.7.4 | Task Management |  |  |  |  |  | ██████ |
| 1.8 | Notification |  |  |  |  |  |  |
| 1.8.1 | Multi-Channel |  |  |  |  | ██████ | ██████ |
| 1.8.2 | Template Management |  |  |  |  |  | ██████ |
| 1.8.3 | Preferences & History |  |  |  |  |  | ██████ |
| 1.9 | Integration & Testing |  |  |  |  |  |  |
| 1.9.1 | Integration Testing |  |  |  |  |  | ██████ |
| 1.9.2 | Performance Testing |  |  |  |  |  | ██████ |
| 1.9.3 | Security Testing |  |  |  |  |  | ██████ |
| 1.9.4 | UAT |  |  |  |  |  | ██████ |
| 1.9.5 | Go-Live & Handover |  |  |  |  |  | ██████ |

## 12.3 LAMPIRAN C: DETAILED BUDGET BREAKDOWN

### 12.3.1 Budget Breakdown per Fase

| No | Fase / Komponen | Biaya Personil | Biaya Langsung | Total |
| --- | --- | --- | --- | --- |
| 1 | Infrastruktur & DevOps | 626.000.000 | 600.000.000 | 1.226.000.000 |
| 2 | Identity & Access Management | 1.354.000.000 | 50.000.000 | 1.404.000.000 |
| 3 | Master Data Management | 1.450.000.000 | 50.000.000 | 1.500.000.000 |
| 4 | Audit & Logging | 610.000.000 | 30.000.000 | 640.000.000 |
| 5 | API Gateway & Event Bus | 650.000.000 | 100.000.000 | 750.000.000 |
| 6 | Workflow Engine | 886.000.000 | 40.000.000 | 926.000.000 |
| 7 | Notification Service | 534.000.000 | 30.000.000 | 564.000.000 |
| 8 | Integration, Testing & Go-Live | 1.058.000.000 | 100.000.000 | 1.158.000.000 |
| 9 | Project Management & Overhead | 200.000.000 | - | 200.000.000 |
| Total |  | 7.368.000.000 | 1.000.000.000 | 8.368.000.000 |

### 12.3.2 Biaya Overhead & Administrasi (10%)

| Komponen | Biaya |
| --- | --- |
| Overhead & Administrasi (10% dari Biaya Langsung) | 836.800.000 |
| Total dengan Overhead | 9.204.800.000 |

### 12.3.3 Biaya Keuntungan (Margin) & Pajak

| Komponen | Biaya |
| --- | --- |
| Keuntungan (12% dari Biaya + Overhead) | 1.104.576.000 |
| Pajak Pertambahan Nilai (PPN 11%) | 1.133.030.336 |
| Total Keseluruhan | 11.442.406.336 |

### 12.3.4 Detail Breakdown per Kategori Personil

| Jenjang Jabatan | Jumlah Orang | Total Bulan | Tarif/Bulan | Total Biaya |
| --- | --- | --- | --- | --- |
| Ahli Madya (PM, Leads) | 5 | 5 | 152.000.000 | 3.800.000.000 |
| Ahli Muda (Developers, Engineers) | 10 | 5 | 120.000.000 | 6.000.000.000 |
| Ahli Pratama (QA, Documentation) | 3 | 5 | 88.000.000 | 1.320.000.000 |
| Total Personil | 18 |  |  | 11.120.000.000 |

### 12.3.5 Cash Flow per Bulan

| Bulan | Aktivitas | Biaya (Rp) | Kumulatif (Rp) |
| --- | --- | --- | --- |
| Bulan 1 (Okt 2026) | Infrastructure Setup | 800.000.000 | 800.000.000 |
| Bulan 2 (Nov 2026) | IAM + MDM Partial | 1.200.000.000 | 2.000.000.000 |
| Bulan 3 (Des 2026) | MDM + Audit | 1.200.000.000 | 3.200.000.000 |
| Bulan 4 (Jan 2027) | API Gateway + Event Bus + Partial Workflow | 1.200.000.000 | 4.400.000.000 |
| Bulan 5 (Feb 2027) | Workflow + Notification + Testing | 1.500.000.000 | 5.900.000.000 |
| Bulan 6 (Mar 2027) | UAT + Go-Live + Handover | 1.200.000.000 | 7.100.000.000 |
| Total Biaya Personil & Langsung |  | 8.368.000.000 |  |
| Overhead (10%) |  | 836.800.000 | 8.000.000.000* |
| Total Biaya (tanpa Pajak) |  | 9.204.800.000 |  |
| Pajak (PPN 11%) |  | 1.133.030.336 |  |
| Grand Total |  | 11.442.406.336 |  |

## 12.4 LAMPIRAN D: RACI MATRIX

### 12.4.1 RACI Matrix Lengkap

R = Responsible, A = Accountable, C = Consulted, I = Informed

| Aktivitas | Sponsor | PM | DevOps Lead | Tech Lead | Security Lead | DevOps Eng | Backend Dev | Frontend Dev | Security Eng | QA Eng |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Infrastructure & DevOps |  |  |  |  |  |  |  |  |  |  |
| Environment Provisioning | I | A | R | C | C | R | - | - | C | - |
| CI/CD Pipeline | I | A | R | C | C | R | - | - | C | C |
| Monitoring & Logging | I | A | R | C | C | R | C | - | C | C |
| Backup & DR | I | A | R | C | C | R | - | - | C | - |
| Secrets Management | I | A | R | C | C | R | - | - | C | - |
| IAM |  |  |  |  |  |  |  |  |  |  |
| User Registration & Auth | I | A | C | R | C | - | R | R | R | C |
| MFA Implementation | I | A | C | R | C | - | R | R | R | C |
| RBAC & Permission | I | A | C | R | C | - | R | R | R | C |
| SSO Implementation | I | A | C | R | C | - | R | R | R | C |
| Session Management | I | A | C | R | C | - | R | R | R | C |
| MDM |  |  |  |  |  |  |  |  |  |  |
| Schema Design | I | A | C | R | C | - | R | C | - | C |
| CRUD Operations | I | A | C | R | C | - | R | R | - | C |
| Import/Export | I | A | C | R | C | - | R | R | - | C |
| Duplicate Detection | I | A | C | R | C | - | R | C | - | C |
| Versioning | I | A | C | R | C | - | R | C | - | C |
| Audit & Logging |  |  |  |  |  |  |  |  |  |  |
| Audit Trail | I | A | C | R | C | - | R | C | C | C |
| Query & Export | I | A | C | R | C | - | R | R | C | C |
| Security Logging | I | A | C | R | C | - | R | C | R | C |
| Retention & Archival | I | A | C | R | C | C | R | C | C | C |
| API Gateway |  |  |  |  |  |  |  |  |  |  |
| Gateway Setup | I | A | R | R | C | R | C | - | C | - |
| Routing & Rate Limit | I | A | R | R | C | R | C | - | C | C |
| Auth at Gateway | I | A | R | R | C | R | C | - | R | C |
| API Documentation | I | A | C | R | C | - | R | R | C | C |
| Event Bus |  |  |  |  |  |  |  |  |  |  |
| Kafka Setup | I | A | R | R | C | R | C | - | C | - |
| Publisher/Subscriber | I | A | C | R | C | - | R | - | C | C |
| DLQ & Monitoring | I | A | C | R | C | R | R | - | C | C |
| Workflow |  |  |  |  |  |  |  |  |  |  |
| Workflow Definition | I | A | C | R | C | - | R | C | - | C |
| Workflow Execution | I | A | C | R | C | - | R | R | - | C |
| Approval Matrix | I | A | C | R | C | - | R | C | - | C |
| Task Management | I | A | C | R | C | - | R | R | - | C |
| Notification |  |  |  |  |  |  |  |  |  |  |
| Multi-Channel | I | A | C | R | C | - | R | R | C | C |
| Template Management | I | A | C | R | C | - | R | R | C | C |
| Preferences & History | I | A | C | R | C | - | R | R | C | C |
| Testing & Quality |  |  |  |  |  |  |  |  |  |  |
| Unit Testing | I | A | C | R | C | - | R | R | C | C |
| Integration Testing | I | A | C | R | C | - | R | R | C | R |
| Performance Testing | I | A | R | R | C | R | - | - | C | R |
| Security Testing | I | A | C | C | R | - | - | - | R | C |
| UAT | I | A | C | C | C | - | C | C | C | R |
| Go-Live |  |  |  |  |  |  |  |  |  |  |
| Production Deployment | A | A | R | C | C | R | C | C | C | C |
| DR Drill | A | A | R | C | C | R | - | - | C | - |
| Handover | A | A | R | R | C | C | C | C | C | C |

## 12.5 LAMPIRAN E: RISK REGISTER

### 12.5.1 Risk Register Lengkap

| ID | Risk Category | Risk Description | Prob | Impact | Score | Priority | Status | Trigger | Strategy | Owner | EMV (Rp) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Teknis | Kompleksitas integrasi microservices | 5 | 5 | 25 | Critical | Active | Integration test failure | Mitigate | Tech Lead | 240.000.000 |
| R-002 | Teknis | Performa audit log menurun | 4 | 4 | 16 | Critical | Active | Query > 2 detik | Mitigate | Backend Lead | 120.000.000 |
| R-003 | Teknis | Security vulnerability IAM | 3 | 5 | 15 | High | Active | Security scan findings | Prevent | Security Lead | 200.000.000 |
| R-004 | Teknis | Data migration quality issue | 4 | 3 | 12 | High | Active | Duplicate data | Mitigate | Data Steward | 120.000.000 |
| R-005 | Teknis | Teknologi stack tidak mature | 2 | 2 | 4 | Low | Active | Library bug | Monitor | Tech Lead | 20.000.000 |
| R-006 | Sumber Daya | Team turnover | 4 | 4 | 16 | Critical | Active | Resignation | Mitigate | PM | 150.000.000 |
| R-007 | Sumber Daya | Kesulitan rekrut security | 4 | 3 | 12 | High | Active | Low applicants | Mitigate | PM + HR | 100.000.000 |
| R-008 | Sumber Daya | Overload tim | 3 | 2 | 6 | Low | Active | Burnout symptoms | Mitigate | PM | 40.000.000 |
| R-009 | Jadwal | Scope creep | 5 | 3 | 15 | High | Active | CR volume high | Control | PM | 120.000.000 |
| R-010 | Jadwal | Integration with legacy complex | 4 | 4 | 16 | Critical | Active | API not available | Mitigate | Tech Lead | 120.000.000 |
| R-011 | Biaya | Cloud cost overrun | 3 | 3 | 9 | Medium | Active | Cost > budget | Mitigate | DevOps Lead | 40.000.000 |
| R-012 | Biaya | Software license cost increase | 2 | 2 | 4 | Low | Active | License renewal | Monitor | PM | 20.000.000 |
| R-013 | Kualitas | UAT gagal | 3 | 4 | 12 | High | Active | User dissatisfaction | Mitigate | QA Lead | 150.000.000 |
| R-014 | Kualitas | Performance NFR tidak tercapai | 3 | 4 | 12 | High | Active | Load test failure | Mitigate | DevOps Lead | 60.000.000 |
| R-015 | Keamanan | Data breach | 2 | 5 | 10 | Medium | Active | Unauthorized access | Prevent | Security Lead | 200.000.000 |
| R-016 | Keamanan | Compliance failure | 2 | 5 | 10 | Medium | Active | Audit finding | Mitigate | Security Lead | 100.000.000 |
| R-017 | Keamanan | Vulnerabilities in third-party libraries | 3 | 2 | 6 | Low | Active | Dependency scan | Prevent | Security Lead | 30.000.000 |
| R-018 | Eksternal | Third-party API downtime | 3 | 2 | 6 | Low | Active | Service disruption | Mitigate | DevOps Lead | 20.000.000 |
| R-019 | Eksternal | Cloud provider outage | 1 | 5 | 5 | Low | Active | Service unavailable | Accept | DevOps Lead | 50.000.000 |
| R-020 | Eksternal | Perubahan regulasi | 2 | 3 | 6 | Low | Active | Regulation change | Monitor | Security Lead | 50.000.000 |

## 12.6 LAMPIRAN F: REQUIREMENTS TRACEABILITY MATRIX (RTM)

### 12.6.1 RTM - Infrastructure & DevOps

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-INF-001 | Environment Provisioning | 1.1.1 | TC-INF-001 | P0 | Pending |
| FNE-INF-002 | Container Orchestration | 1.1.2 | TC-INF-002 | P0 | Pending |
| FNE-INF-003 | CI/CD Pipeline | 1.1.3 | TC-INF-003 | P0 | Pending |
| FNE-INF-004 | Service Discovery | 1.1.2 | TC-INF-004 | P1 | Pending |
| FNE-INF-005 | Load Balancing | 1.5.2 | TC-INF-005 | P0 | Pending |
| FNE-INF-006 | Auto-Scaling | 1.1.2 | TC-INF-006 | P1 | Pending |
| FNE-INF-007 | Resource Monitoring | 1.1.4 | TC-INF-007 | P0 | Pending |
| FNE-INF-008 | Log Aggregation | 1.1.4 | TC-INF-008 | P0 | Pending |
| FNE-INF-009 | Distributed Tracing | 1.1.4 | TC-INF-009 | P1 | Pending |
| FNE-INF-010 | Backup Automation | 1.1.5 | TC-INF-010 | P0 | Pending |
| FNE-INF-011 | Disaster Recovery | 1.1.5 | TC-INF-011 | P0 | Pending |
| FNE-INF-012 | Secrets Management | 1.1.6 | TC-INF-012 | P0 | Pending |
| FNE-INF-013 | Environment Configuration | 1.1.1 | TC-INF-013 | P0 | Pending |
| FNE-INF-014 | Health Check | 1.1.4 | TC-INF-014 | P0 | Pending |
| FNE-INF-015 | Graceful Shutdown | 1.1.2 | TC-INF-015 | P1 | Pending |

### 12.6.2 RTM - IAM

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-IAM-001 | User Registration | 1.2.1 | TC-IAM-001 | P0 | Pending |
| FNE-IAM-002 | User Authentication | 1.2.1 | TC-IAM-002 | P0 | Pending |
| FNE-IAM-003 | MFA | 1.2.2 | TC-IAM-003 | P0 | Pending |
| FNE-IAM-004 | SSO | 1.2.5 | TC-IAM-004 | P1 | Pending |
| FNE-IAM-005 | RBAC | 1.2.3 | TC-IAM-005 | P0 | Pending |
| FNE-IAM-006 | Permission Management | 1.2.4 | TC-IAM-006 | P0 | Pending |
| FNE-IAM-007 | SoD | 1.2.3 | TC-IAM-007 | P0 | Pending |
| FNE-IAM-008 | Session Management | 1.2.6 | TC-IAM-008 | P0 | Pending |
| FNE-IAM-009 | Password Policy | 1.2.1 | TC-IAM-009 | P0 | Pending |
| FNE-IAM-010 | Account Lockout | 1.2.1 | TC-IAM-010 | P0 | Pending |
| FNE-IAM-011 | User Deactivation | 1.2.1 | TC-IAM-011 | P0 | Pending |
| FNE-IAM-012 | Access Review | 1.2.3 | TC-IAM-012 | P1 | Pending |
| FNE-IAM-013 | Privileged Access | 1.2.3 | TC-IAM-013 | P0 | Pending |
| FNE-IAM-014 | Service Account | 1.2.1 | TC-IAM-014 | P0 | Pending |
| FNE-IAM-015 | LDAP Integration | 1.2.5 | TC-IAM-015 | P2 | Pending |

### 12.6.3 RTM - MDM

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-MDM-001 | Company Master | 1.3.1, 1.3.2 | TC-MDM-001 | P0 | Pending |
| FNE-MDM-002 | Business Unit | 1.3.1, 1.3.2 | TC-MDM-002 | P0 | Pending |
| FNE-MDM-003 | Location Master | 1.3.1, 1.3.2 | TC-MDM-003 | P0 | Pending |
| FNE-MDM-004 | Organization Structure | 1.3.1, 1.3.2 | TC-MDM-004 | P0 | Pending |
| FNE-MDM-005 | Product Master | 1.3.1, 1.3.2 | TC-MDM-005 | P0 | Pending |
| FNE-MDM-006 | Material Master | 1.3.1, 1.3.2 | TC-MDM-006 | P0 | Pending |
| FNE-MDM-007 | Supplier Master | 1.3.1, 1.3.2 | TC-MDM-007 | P0 | Pending |
| FNE-MDM-008 | Customer Master | 1.3.1, 1.3.2 | TC-MDM-008 | P0 | Pending |
| FNE-MDM-009 | Employee Master | 1.3.1, 1.3.2 | TC-MDM-009 | P0 | Pending |
| FNE-MDM-010 | Asset Master | 1.3.1, 1.3.2 | TC-MDM-010 | P0 | Pending |
| FNE-MDM-011 | Farm Master | 1.3.1, 1.3.2 | TC-MDM-011 | P0 | Pending |
| FNE-MDM-012 | Land Parcel Master | 1.3.1, 1.3.2 | TC-MDM-012 | P0 | Pending |
| FNE-MDM-013 | Crop Master | 1.3.1, 1.3.2 | TC-MDM-013 | P0 | Pending |
| FNE-MDM-014 | Livestock Master | 1.3.1, 1.3.2 | TC-MDM-014 | P0 | Pending |
| FNE-MDM-015 | Warehouse Master | 1.3.1, 1.3.2 | TC-MDM-015 | P0 | Pending |
| FNE-MDM-016 | UOM Master | 1.3.1, 1.3.2 | TC-MDM-016 | P0 | Pending |
| FNE-MDM-017 | Chart of Accounts | 1.3.1, 1.3.2 | TC-MDM-017 | P0 | Pending |
| FNE-MDM-018 | Price List Master | 1.3.1, 1.3.2 | TC-MDM-018 | P0 | Pending |
| FNE-MDM-019 | Tax Configuration | 1.3.1, 1.3.2 | TC-MDM-019 | P0 | Pending |
| FNE-MDM-020 | Master Data Versioning | 1.3.5 | TC-MDM-020 | P1 | Pending |
| FNE-MDM-021 | Master Data Approval | 1.3.5 | TC-MDM-021 | P1 | Pending |
| FNE-MDM-022 | Master Data Import | 1.3.3 | TC-MDM-022 | P1 | Pending |
| FNE-MDM-023 | Master Data Export | 1.3.3 | TC-MDM-023 | P1 | Pending |
| FNE-MDM-024 | Master Data Duplicate Detection | 1.3.4 | TC-MDM-024 | P1 | Pending |

### 12.6.4 RTM - Audit & Logging

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-AUD-001 | Audit Trail Transactions | 1.4.1 | TC-AUD-001 | P0 | Pending |
| FNE-AUD-002 | Audit Trail Access | 1.4.1 | TC-AUD-002 | P0 | Pending |
| FNE-AUD-003 | Audit Trail Master Data | 1.4.1 | TC-AUD-003 | P0 | Pending |
| FNE-AUD-004 | Audit Trail Configuration | 1.4.1 | TC-AUD-004 | P0 | Pending |
| FNE-AUD-005 | Audit Trail Privileged Access | 1.4.1 | TC-AUD-005 | P0 | Pending |
| FNE-AUD-006 | Immutable Audit Log | 1.4.1 | TC-AUD-006 | P0 | Pending |
| FNE-AUD-007 | Audit Log Query | 1.4.2 | TC-AUD-007 | P0 | Pending |
| FNE-AUD-008 | Audit Log Export | 1.4.2 | TC-AUD-008 | P1 | Pending |
| FNE-AUD-009 | Audit Log Retention | 1.4.4 | TC-AUD-009 | P0 | Pending |
| FNE-AUD-010 | Audit Log Archival | 1.4.4 | TC-AUD-010 | P1 | Pending |
| FNE-AUD-011 | Application Logging | 1.4.1 | TC-AUD-011 | P0 | Pending |
| FNE-AUD-012 | Security Logging | 1.4.3 | TC-AUD-012 | P0 | Pending |
| FNE-AUD-013 | Centralized Logging | 1.1.4 | TC-AUD-013 | P0 | Pending |

### 12.6.5 RTM - API Gateway & Integration

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-API-001 | API Gateway | 1.5.1 | TC-API-001 | P0 | Pending |
| FNE-API-002 | Request Routing | 1.5.2 | TC-API-002 | P0 | Pending |
| FNE-API-003 | Rate Limiting | 1.5.2 | TC-API-003 | P0 | Pending |
| FNE-API-004 | Authentication at Gateway | 1.5.3 | TC-API-004 | P0 | Pending |
| FNE-API-005 | API Versioning | 1.5.2 | TC-API-005 | P0 | Pending |
| FNE-API-006 | API Documentation | 1.5.4 | TC-API-006 | P0 | Pending |
| FNE-API-007 | API Monitoring | 1.1.4 | TC-API-007 | P0 | Pending |
| FNE-API-008 | API Health Check | 1.1.4 | TC-API-008 | P0 | Pending |
| FNE-API-009 | Circuit Breaker | 1.5.5 | TC-API-009 | P1 | Pending |
| FNE-API-010 | Retry & Timeout | 1.5.5 | TC-API-010 | P1 | Pending |
| FNE-API-011 | Request Validation | 1.5.2 | TC-API-011 | P0 | Pending |

### 12.6.6 RTM - Event Bus & Messaging

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-EVT-001 | Message Broker | 1.6.1 | TC-EVT-001 | P0 | Pending |
| FNE-EVT-002 | Event Publisher | 1.6.2 | TC-EVT-002 | P0 | Pending |
| FNE-EVT-003 | Event Subscriber | 1.6.2 | TC-EVT-003 | P0 | Pending |
| FNE-EVT-004 | Event Schema | 1.6.2 | TC-EVT-004 | P0 | Pending |
| FNE-EVT-005 | Event Versioning | 1.6.2 | TC-EVT-005 | P1 | Pending |
| FNE-EVT-006 | Event Persistence | 1.6.2 | TC-EVT-006 | P1 | Pending |
| FNE-EVT-007 | Dead Letter Queue | 1.6.3 | TC-EVT-007 | P0 | Pending |
| FNE-EVT-008 | Retry Mechanism | 1.6.3 | TC-EVT-008 | P0 | Pending |
| FNE-EVT-009 | Event Monitoring | 1.6.4 | TC-EVT-009 | P0 | Pending |
| FNE-EVT-010 | Correlation ID | 1.6.2 | TC-EVT-010 | P0 | Pending |

### 12.6.7 RTM - Workflow & Notification

| Req ID | Requirement | WBS | Test Case | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| FNE-WFL-001 | Workflow Definition | 1.7.1 | TC-WFL-001 | P0 | Pending |
| FNE-WFL-002 | Workflow Execution | 1.7.2 | TC-WFL-002 | P0 | Pending |
| FNE-WFL-003 | Approval Matrix | 1.7.3 | TC-WFL-003 | P0 | Pending |
| FNE-WFL-004 | Task Assignment | 1.7.4 | TC-WFL-004 | P0 | Pending |
| FNE-WFL-005 | Task Notification | 1.8.1 | TC-WFL-005 | P0 | Pending |
| FNE-WFL-006 | Approval/Rejection | 1.7.4 | TC-WFL-006 | P0 | Pending |
| FNE-WFL-007 | Workflow Monitoring | 1.7.4 | TC-WFL-007 | P0 | Pending |
| FNE-WFL-008 | Workflow Escalation | 1.7.4 | TC-WFL-008 | P1 | Pending |
| FNE-WFL-009 | Workflow Versioning | 1.7.1 | TC-WFL-009 | P1 | Pending |
| FNE-WFL-010 | Workflow Audit | 1.4.1 | TC-WFL-010 | P0 | Pending |
| FNE-NOT-001 | In-App Notification | 1.8.1 | TC-NOT-001 | P0 | Pending |
| FNE-NOT-002 | Email Notification | 1.8.1 | TC-NOT-002 | P0 | Pending |
| FNE-NOT-003 | SMS Notification | 1.8.1 | TC-NOT-003 | P1 | Pending |
| FNE-NOT-004 | Push Notification | 1.8.1 | TC-NOT-004 | P0 | Pending |
| FNE-NOT-005 | Notification Template | 1.8.2 | TC-NOT-005 | P1 | Pending |
| FNE-NOT-006 | Notification Preference | 1.8.3 | TC-NOT-006 | P1 | Pending |
| FNE-NOT-007 | Notification History | 1.8.4 | TC-NOT-007 | P1 | Pending |
| FNE-NOT-008 | Batch Notification | 1.8.1 | TC-NOT-008 | P1 | Pending |

## 12.7 LAMPIRAN G: ACCEPTANCE CRITERIA CHECKLIST

### 12.7.1 Deliverable Acceptance Criteria Checklist

| No | Deliverable | Acceptance Criteria | Status | Verified By | Date |
| --- | --- | --- | --- | --- | --- |
| 1 | Infrastructure & DevOps |  |  |  |  |
|  | Environment (4 env) | 4 environment berfungsi | ☐ |  |  |
|  | CI/CD Pipeline | Build, test, deploy otomatis | ☐ |  |  |
|  | Monitoring & Logging | Prometheus, Grafana, ELK aktif | ☐ |  |  |
|  | Backup & DR | Backup teruji dan restore berhasil | ☐ |  |  |
| 2 | IAM Service |  |  |  |  |
|  | User Registration | Registrasi user berfungsi | ☐ |  |  |
|  | Authentication | Login dengan username/password | ☐ |  |  |
|  | MFA | Multi-Factor Authentication | ☐ |  |  |
|  | RBAC | Role-Based Access Control | ☐ |  |  |
|  | SoD | Segregation of Duties | ☐ |  |  |
|  | SSO | Single Sign-On | ☐ |  |  |
| 3 | Master Data Management |  |  |  |  |
|  | 24 Entity CRUD | Semua entity dapat CRUD | ☐ |  |  |
|  | Import/Export | Excel/CSV import export | ☐ |  |  |
|  | Duplicate Detection | Deteksi duplikasi | ☐ |  |  |
|  | Versioning | Version tracking | ☐ |  |  |
| 4 | Audit & Logging |  |  |  |  |
|  | Audit Trail | Semua transaksi tercatat | ☐ |  |  |
|  | Query & Export | Search dan export audit log | ☐ |  |  |
|  | Immutable Log | Audit log tidak dapat dimodifikasi | ☐ |  |  |
|  | Retention | 5 tahun retention | ☐ |  |  |
| 5 | API Gateway |  |  |  |  |
|  | Routing | Routing ke service tepat | ☐ |  |  |
|  | Rate Limiting | Rate limiting berfungsi | ☐ |  |  |
|  | Auth at Gateway | Authentication di gateway | ☐ |  |  |
|  | Documentation | OpenAPI/Swagger tersedia | ☐ |  |  |
| 6 | Event Bus |  |  |  |  |
|  | Publish/Subscribe | Event dapat pub/sub | ☐ |  |  |
|  | DLQ | Dead Letter Queue berfungsi | ☐ |  |  |
|  | Retry | Retry mechanism berfungsi | ☐ |  |  |
|  | Correlation ID | Correlation ID tersedia | ☐ |  |  |
| 7 | Workflow Engine |  |  |  |  |
|  | 3 Workflow Basic | 3 workflow berjalan | ☐ |  |  |
|  | Approval Matrix | Approval matrix berfungsi | ☐ |  |  |
|  | Task Management | Assign, approve, reject | ☐ |  |  |
|  | Notifikasi | Notifikasi dikirim | ☐ |  |  |
| 8 | Notification Service |  |  |  |  |
|  | 4 Channel | Email, SMS, Push, In-App | ☐ |  |  |
|  | Template Management | Manage templates | ☐ |  |  |
|  | History | Notification history | ☐ |  |  |

### 12.7.2 NFR Acceptance Criteria Checklist

| No | NFR | Target | Status | Verified By | Date |
| --- | --- | --- | --- | --- | --- |
| 1 | System Availability | ≥ 99.9% | ☐ |  |  |
| 2 | API Response Time (Median) | ≤ 500ms | ☐ |  |  |
| 3 | API Response Time (P95) | ≤ 2 detik | ☐ |  |  |
| 4 | Concurrent Users | 1.000 users | ☐ |  |  |
| 5 | Database Query Time | ≤ 200ms | ☐ |  |  |
| 6 | Authentication Response | ≤ 1 detik | ☐ |  |  |
| 7 | Audit Log Volume | ≥ 10 juta record | ☐ |  |  |
| 8 | RPO | ≤ 15 menit | ☐ |  |  |
| 9 | RTO | ≤ 2 jam | ☐ |  |  |
| 10 | Security Compliance | ISO 27001/OWASP | ☐ |  |  |
| 11 | Data Encryption | TLS 1.2+ & AES-256 | ☐ |  |  |
| 12 | Scalability | Horizontal scaling | ☐ |  |  |
| 13 | Maintainability | Modular architecture | ☐ |  |  |
| 14 | Audit Retention | Minimal 5 tahun | ☐ |  |  |
| 15 | Event Processing Latency | ≤ 2 detik | ☐ |  |  |
| 16 | API Rate Limit | 1.000 request/menit | ☐ |  |  |

## 12.8 LAMPIRAN H: COMMUNICATION MATRIX

### 12.8.1 Communication Matrix Lengkap

| No | Komunikasi | Frekuensi | Audience | Method | Owner | Format |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Daily Stand-up | Harian (09:00) | Project Team | Meeting (Video) | Scrum Master | Verbal + Chat |
| 2 | Sprint Planning | Setiap Sprint | Project Team, PMO | Meeting (Video) | PM | Slide + Jira |
| 3 | Sprint Review | Setiap Sprint | All Stakeholders | Meeting (Video) | PM | Demo + Slide |
| 4 | Sprint Retrospective | Setiap Sprint | Project Team | Meeting (Video) | PM | Workshop |
| 5 | Weekly Status Report | Mingguan | PMO, Sponsor | Email + Dashboard | PM | PDF/Dashboard |
| 6 | Monthly Steering Meeting | Bulanan | Steering Committee | Meeting (Video) | PM | Presentasi |
| 7 | Milestone Review | Per Milestone | Sponsor, Steering | Meeting (Video) | PM | Presentasi |
| 8 | Risk Review | Mingguan | PM, Tech Leads | Meeting (Video) | PM | Document |
| 9 | Technical Review | 2 minggu sekali | Tech Leads | Meeting (Video) | Tech Lead | Document |
| 10 | Security Briefing | 1 bulan sekali | Tech Team, Security | Meeting (Video) | Security Lead | Slide |
| 11 | Project Newsletter | Bulanan | All Stakeholders | Email | PM | Newsletter |
| 12 | Issue Escalation | As needed | PM, Sponsor | Email + Call | PM | - |
| 13 | Change Request | As needed | CCB | Document | PM | CRF |
| 14 | Decision Log | Berkelanjutan | All Stakeholders | Confluence | PM | Document |
| 15 | Knowledge Base | Berkelanjutan | Project Team | Confluence | All | Document |
| 16 | Slack/Teams Channel | Harian | Project Team | Chat | All | - |
| 17 | Code Review | Per Pull Request | Developers | GitHub/GitLab | Developer | Review |
| 18 | UAT Feedback | Minggu Go-Live | Business Owner, Team | Meeting + Jira | PM | Ticket |

### 12.8.2 Escalation Matrix

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    ESCALATION MATRIX P-FNE-01                               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  LEVEL 1: ISSUE DETECTION                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Ditemukan oleh tim proyek                                         │    │

│  │ • Dilaporkan ke PM atau Tech Lead                                  │    │

│  │ • Dampak: Minor, dapat diatasi internal                           │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  LEVEL 2: PM RESOLUTION                                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • PM berkoordinasi dengan tim untuk solusi                          │    │

│  │ • Dampak: Medium, membutuhkan keputusan PM                         │    │

│  │ • Waktu: 1-2 hari                                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  LEVEL 3: SPONSOR RESOLUTION                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • PM melapor ke Sponsor untuk keputusan                             │    │

│  │ • Dampak: High, membutuhkan keputusan Sponsor                      │    │

│  │ • Waktu: 2-3 hari                                                  │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  LEVEL 4: STEERING COMMITTEE RESOLUTION                                     │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Sponsor memanggil Steering Committee                              │    │

│  │ • Dampak: Critical, membutuhkan keputusan strategis                │    │

│  │ • Waktu: 5 hari                                                    │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 12.9 LAMPIRAN I: QUALITY MANAGEMENT PLAN

### 12.9.1 Quality Standards

| No | Standar | Deskripsi | Penerapan |
| --- | --- | --- | --- |
| 1 | ISO 9001:2015 | Sistem Manajemen Mutu | Proses pengembangan dan manajemen proyek |
| 2 | ISO 27001:2022 | Keamanan Informasi | Keamanan data dan sistem |
| 3 | OWASP Top 10 | Keamanan Aplikasi Web | Security testing dan code review |
| 4 | IEEE 829 | Dokumentasi Testing | Test plan, test cases, test report |
| 5 | OpenAPI 3.0 | Dokumentasi API | API specification dan documentation |
| 6 | JSON Schema | Validasi Data | Validasi data master dan event schema |
| 7 | Google Java Style Guide | Code Style | Standar penulisan kode Java |
| 8 | ESLint + Prettier | Code Style | Standar penulisan kode TypeScript/JavaScript |

### 12.9.2 Quality Metrics

| No | Metrik | Target | Pengukuran | Frekuensi |
| --- | --- | --- | --- | --- |
| 1 | Code Coverage | ≥ 80% | SonarQube | Per Sprint |
| 2 | Code Quality Gate | Passed | SonarQube | Per Deployment |
| 3 | Security Scan | Zero Critical | OWASP ZAP / Snyk | Per Sprint |
| 4 | API Response Time (Median) | ≤ 500ms | JMeter / Monitoring | Per Milestone |
| 5 | API Response Time (P95) | ≤ 2 detik | JMeter / Monitoring | Per Milestone |
| 6 | System Availability | ≥ 99.9% | Prometheus/Grafana | Harian |
| 7 | Defect Density | < 1 per 1000 LOC | SonarQube / Jira | Per Sprint |
| 8 | Test Pass Rate | ≥ 95% | CI/CD Pipeline | Per Deployment |
| 9 | UAT Satisfaction | ≥ 90% | Survey | Akhir Proyek |
| 10 | Database Query Time | ≤ 200ms | Monitoring | Per Milestone |
| 11 | RPO Compliance | ≤ 15 menit | DR Drill | Per Milestone |
| 12 | RTO Compliance | ≤ 2 jam | DR Drill | Per Milestone |

### 12.9.3 Quality Gates

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    QUALITY GATES P-FNE-01                                   │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  GATE 1: CODE COMMIT                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Build success                                                     │    │

│  │ • Unit test pass                                                    │    │

│  │ • Code coverage ≥ 80%                                              │    │

│  │ • No critical code smells                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  GATE 2: CODE REVIEW                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Peer review approved                                              │    │

│  │ • Security review approved                                         │    │

│  │ • Documentation updated                                            │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  GATE 3: DEPLOYMENT TO TEST                                                 │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Integration test pass                                            │    │

│  │ • API test pass                                                    │    │

│  │ • No critical security issues                                      │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  GATE 4: DEPLOYMENT TO STAGING                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Performance test pass                                            │    │

│  │ • Load test pass                                                   │    │

│  │ • UAT test pass                                                    │    │

│  │ • All acceptance criteria met                                     │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  GATE 5: DEPLOYMENT TO PRODUCTION                                           │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Final security scan pass                                         │    │

│  │ • Production smoke test pass                                      │    │

│  │ • Rollback plan ready                                              │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

## 12.10 LAMPIRAN J: CHANGE MANAGEMENT PROCEDURE

### 12.10.1 Change Request Form (CRF)

CHANGE REQUEST FORM - P-FNE-01

| Field | Deskripsi |
| --- | --- |
| CRF Number | CRF-XXX (auto-generated) |
| Date Submitted | [DD/MM/YYYY] |
| Submitted By | [Nama, Role] |
| Change Category | [ ] Scope [ ] Schedule [ ] Budget [ ] Resources [ ] Quality [ ] Risk [ ] Technical |
| Change Description | [Deskripsi perubahan yang diusulkan] |
| Reason / Justification | [Alasan perubahan diperlukan] |
| Impact Analysis |  |
| - Scope Impact | [Bertambah/berkurang ruang lingkup] |
| - Schedule Impact | [+ X hari/minggu] |
| - Cost Impact | [+ Rp X] |
| - Quality Impact | [Dampak terhadap kualitas] |
| - Risk Impact | [Risiko baru atau perubahan risiko] |
| Proposed Solution | [Cara implementasi perubahan] |
| Alternatives | [Opsi alternatif (jika ada)] |
| Priority | [ ] Low [ ] Medium [ ] High [ ] Critical |
| Recommendation | [ ] Approve [ ] Reject [ ] Defer |
| Approved By | [Nama, Role, Signature, Date] |
| Implementation Date | [DD/MM/YYYY] |
| Actual Impact | [Realisasi dampak setelah implementasi] |
| Closed By | [Nama, Role, Date] |

### 12.10.2 Change Log

| CRF # | Tanggal | Deskripsi | Kategori | Status | Approved By | Tanggal Implementasi | Actual Impact |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CRF-001 | [Date] | [Description] | [Category] | [Status] | [Name] | [Date] | [Impact] |
| ... | ... | ... | ... | ... | ... | ... | ... |

## 12.11 LAMPIRAN K: STAKEHOLDER REGISTER

### 12.11.1 Stakeholder Register Lengkap

| ID | Nama Stakeholder | Peran/Organisasi | Kategori | Kebutuhan & Harapan | Pengaruh | Minat | Engagement Level |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S-01 | Project Sponsor | VP of Technology | Internal | Proyek sesuai timeline dan budget, ROI terukur, Risiko terkelola | High | High | Leading |
| S-02 | Steering Committee | Multi-stakeholder | Internal | Informasi akurat, Proyek selaras strategi, Risiko strategis | High | High | Supportive |
| S-03 | Head of PMO | Project Management Office | Internal | Kepatuhan standar PMO, Kualitas pelaporan, Lessons learned | Medium | High | Supportive |
| S-04 | Project Manager | PM P-FNE-01 | Internal | Wewenang cukup, Dukungan stakeholder, Tim kompeten | High | High | Leading |
| S-05 | DevOps Lead | Technical Lead | Internal | Infrastruktur stabil, CI/CD efisien, Monitoring baik | High | High | Leading |
| S-06 | Tech Lead | Technical Lead | Internal | Arsitektur scalable, Code quality, Technical debt terkendali | High | High | Leading |
| S-07 | Security Lead | Technical Lead | Internal | Keamanan sistem, Compliance, IAM berfungsi baik | High | High | Leading |
| S-08 | Project Team | All team members | Internal | Lingkungan kerja baik, Pengakuan, Pengembangan karir | Medium | High | Supportive |
| S-09 | Business Owner | Business Stakeholder | Internal | Fitur sesuai bisnis, UAT sukses, Adopsi user tinggi | High | High | Supportive |
| S-10 | IT Operations | Operations Team | Internal | Deployment lancar, Dokumentasi lengkap, Handover terencana | Medium | High | Supportive |
| S-11 | Data Steward | Data Management | Internal | Master data berkualitas, Duplicate detection, Data governance | Medium | Medium | Supportive |
| S-12 | End Users (Future) | Agricultural Ops Team | Internal | User-friendly, Performa baik, Training memadai | Low | High | Aware |
| S-13 | External Auditors | Compliance | Eksternal | Audit trail lengkap, Compliance terpenuhi, Transparansi | High | Medium | Aware |
| S-14 | Vendors | Third-party | Eksternal | Kontrak jelas, Pembayaran tepat waktu, Komunikasi baik | Low | Low | Supportive |
| S-15 | Security Team | Corporate Security | Internal | Security standards, Vulnerabilities teridentifikasi | High | High | Supportive |
| S-16 | HR | Human Resources | Internal | Rekrutmen tepat waktu, Onboarding lancar, Kebutuhan sumber daya | Medium | Medium | Supportive |
| S-17 | Finance | Finance Department | Internal | Budget terkelola, Cash flow tepat, Procurement sesuai | Medium | Medium | Supportive |
| S-18 | Legal | Legal Department | Internal | Kontrak vendor aman, Compliance regulasi, Data privacy | Medium | Medium | Supportive |

## 12.12 LAMPIRAN L: PROCUREMENT DOCUMENTS

### 12.12.1 Procurement Plan

| No | Item | Deskripsi | Kebutuhan | Estimasi Biaya (Rp) | Timeline | Kategori |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Cloud Infrastructure | AWS/GCP untuk hosting environment | 4 environment | 500.000.000 | Okt 2026 - Mar 2027 | Cloud |
| 2 | Kubernetes Platform | Managed Kubernetes (EKS/GKE) | 4 cluster | Termasuk Cloud | Okt 2026 | Cloud |
| 3 | Identity Management (IAM) | Keycloak / Okta Enterprise | SSO, MFA, User management | 150.000.000 | Okt 2026 | Software |
| 4 | API Gateway | Kong Enterprise / Traefik | API management | 100.000.000 | Nov 2026 | Software |
| 5 | Message Broker | Confluent Cloud (Kafka) | Event bus | 150.000.000 | Nov 2026 | Software |
| 6 | CI/CD Tools | GitLab Ultimate / GitHub Enterprise | CI/CD pipeline | 100.000.000 | Okt 2026 | Software |
| 7 | Monitoring Tools | Datadog / New Relic (opsional) | Monitoring tambahan | 50.000.000 | Okt 2026 | Software |
| 8 | SMTP Service | SendGrid / Amazon SES | Email notification | 25.000.000 | Des 2026 | Service |
| 9 | SMS Service | Twilio / Infobip | SMS notification | 25.000.000 | Des 2026 | Service |
| 10 | Security Assessment | External penetration testing | Security audit | 50.000.000 | Feb 2027 | Service |
| 11 | Training | Cloud & Security training | Team training | 50.000.000 | Okt 2026 | Service |
| 12 | Backup Storage | S3 / Glacier / Cold storage | Backup & archival | 50.000.000 | Okt 2026 | Cloud |

### 12.12.2 Make-or-Buy Decision Matrix

| No | Komponen | Make | Buy | Decision | Justifikasi | Estimated Cost Make | Estimated Cost Buy | Savings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | IAM Service | ✓ | ✓ | Buy + Custom | Keycloak mature, focus on integration | 200,000,000 | 150,000,000 | 50,000,000 |
| 2 | Master Data | ✓ |  | Make | Business specific, competitive advantage | 350,000,000 | N/A | - |
| 3 | Workflow Engine | ✓ | ✓ | Buy + Custom | Camunda standard, custom workflow | 200,000,000 | 100,000,000 | 100,000,000 |
| 4 | Notification Service | ✓ |  | Make | Integration with existing systems | 150,000,000 | 200,000,000 | 50,000,000 |
| 5 | API Gateway |  | ✓ | Buy | Kong standard solution | 50,000,000 | 100,000,000 | -50,000,000 |
| 6 | Event Bus |  | ✓ | Buy | Kafka standard solution | 50,000,000 | 150,000,000 | -100,000,000 |
| 7 | Monitoring |  | ✓ | Buy | Prometheus/Grafana open source | 20,000,000 | 50,000,000 | -30,000,000 |
| 8 | CI/CD |  | ✓ | Buy | GitLab standard | 30,000,000 | 100,000,000 | -70,000,000 |
| 9 | Cloud Infrastructure |  | ✓ | Buy | Avoid capex | N/A | 550,000,000 | - |
| 10 | Email Service |  | ✓ | Buy | SendGrid/SES standard | 10,000,000 | 25,000,000 | -15,000,000 |
| 11 | SMS Service |  | ✓ | Buy | Twilio standard | 10,000,000 | 25,000,000 | -15,000,000 |
| 12 | Security Testing |  | ✓ | Buy | External expertise | 20,000,000 | 50,000,000 | -30,000,000 |

## 12.13 LAMPIRAN M: TRAINING PLAN

### 12.13.1 Training Schedule

| No | Training | Target Audience | Timeline | Durasi | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Kick-off & Onboarding | Semua Tim | Minggu 1 | 2 hari | Planned |
| 2 | Spring Boot & Microservices | Backend Dev | Minggu 2-3 | 5 hari | Planned |
| 3 | Kubernetes & Docker | DevOps, Backend | Minggu 2-3 | 3 hari | Planned |
| 4 | React/Next.js Training | Frontend Dev | Minggu 3-4 | 3 hari | Planned |
| 5 | Kafka & Event-Driven | Backend, DevOps | Minggu 4 | 2 hari | Planned |
| 6 | Security Awareness | Semua Tim | Minggu 2 | 1 hari | Planned |
| 7 | OWASP & Secure Coding | Developer | Minggu 4 | 2 hari | Planned |
| 8 | Agile & Scrum | Semua Tim | Minggu 1 | 1 hari | Planned |
| 9 | Jira & Confluence | Semua Tim | Minggu 1 | 0.5 hari | Planned |
| 10 | AWS/GCP Cloud | DevOps | Minggu 2 | 2 hari | Planned |

### 12.13.2 Training Tracking

| No | Training | Completed | Date | Participants | Feedback Score |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Kick-off & Onboarding | ☐ |  |  |  |
| 2 | Spring Boot & Microservices | ☐ |  |  |  |
| 3 | Kubernetes & Docker | ☐ |  |  |  |
| 4 | React/Next.js Training | ☐ |  |  |  |
| 5 | Kafka & Event-Driven | ☐ |  |  |  |
| 6 | Security Awareness | ☐ |  |  |  |
| 7 | OWASP & Secure Coding | ☐ |  |  |  |
| 8 | Agile & Scrum | ☐ |  |  |  |
| 9 | Jira & Confluence | ☐ |  |  |  |
| 10 | AWS/GCP Cloud | ☐ |  |  |  |

## 12.14 LAMPIRAN N: LESSONS LEARNED TEMPLATE

### 12.14.1 Lessons Learned Template

LESSONS LEARNED - P-FNE-01

| Field | Deskripsi |
| --- | --- |
| Session Date | [DD/MM/YYYY] |
| Facilitator | [Nama] |
| Participants | [Daftar peserta] |
| Phase | [Phase proyek] |

1. What Went Well

| No | Lesson Learned | Evidence | Recommendation |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

2. What Could Be Improved

| No | Lesson Learned | Evidence | Recommendation |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

3. What Went Wrong

| No | Lesson Learned | Root Cause | Recommendation |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

4. Key Learnings

| No | Learning | Impact | Action Item |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

5. Recommendations for Future Projects

| No | Recommendation | Priority | Owner |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |

## 12.15 LAMPIRAN O: GLOSSARY

### 12.15.1 Glossary of Terms

| Istilah | Definisi |
| --- | --- |
| API Gateway | Entry point tunggal untuk semua permintaan API, melakukan routing, rate limiting, dan autentikasi |
| CI/CD | Continuous Integration / Continuous Deployment - Proses otomatisasi build, test, dan deploy |
| DLQ | Dead Letter Queue - Antrian untuk pesan yang gagal diproses |
| EVM | Earned Value Management - Metode pengukuran kinerja proyek |
| IAM | Identity and Access Management - Manajemen identitas dan akses pengguna |
| IaC | Infrastructure as Code - Pengelolaan infrastruktur melalui kode |
| Kubernetes | Platform orchestration container |
| MFA | Multi-Factor Authentication - Autentikasi dengan lebih dari satu faktor |
| MDM | Master Data Management - Manajemen data master |
| PMP | Project Management Plan - Rencana manajemen proyek |
| RACI | Responsible, Accountable, Consulted, Informed - Matriks peran dan tanggung jawab |
| RBAC | Role-Based Access Control - Kontrol akses berbasis peran |
| RFP | Request for Proposal - Dokumen permintaan proposal |
| RPO | Recovery Point Objective - Target kehilangan data maksimum |
| RTO | Recovery Time Objective - Target waktu pemulihan |
| SAST | Static Application Security Testing - Pengujian keamanan statis |
| SLA | Service Level Agreement - Perjanjian tingkat layanan |
| SoD | Segregation of Duties - Pemisahan tugas untuk mencegah konflik |
| SPI | Schedule Performance Index - Indeks kinerja jadwal |
| SSO | Single Sign-On - Autentikasi tunggal untuk multiple aplikasi |
| UAT | User Acceptance Testing - Pengujian penerimaan pengguna |
| WBS | Work Breakdown Structure - Struktur dekomposisi pekerjaan |

# BAB 13: PROSES PERUBAHAN DAN PERSETUJUAN

## (CHANGE CONTROL & APPROVAL)

## 13.1 CHANGE CONTROL PROCESS

### 13.1.1 Prosedur Permintaan Perubahan

Proses perubahan terintegrasi (Integrated Change Control) memastikan bahwa setiap perubahan terhadap baseline proyek (scope, schedule, budget) dikelola secara sistematis dan terkendali.

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    CHANGE CONTROL PROCESS P-FNE-01                          │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  STEP 1: IDENTIFIKASI PERUBAHAN                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Setiap stakeholder dapat mengajukan perubahan                     │    │

│  │ • Menggunakan Change Request Form (CRF)                            │    │

│  │ • Mengklasifikasi: Urgency, Impact, Priority                       │    │

│  │ • Owner: Pengaju perubahan                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 2: EVALUASI & ANALISIS                                                │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Project Manager melakukan evaluasi awal                          │    │

│  │ • Analisis dampak:                                                  │    │

│  │   - Scope: Apakah ada perubahan ruang lingkup?                     │    │

│  │   - Schedule: Dampak terhadap jadwal (hari/minggu)                │    │

│  │   - Cost: Dampak terhadap biaya (Rp)                              │    │

│  │   - Quality: Dampak terhadap kualitas                             │    │

│  │   - Risk: Dampak terhadap risiko proyek                           │    │

│  │ • Konsultasi dengan Tech Leads (jika perubahan teknis)             │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 3: REKOMENDASI                                                        │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • PM memberikan rekomendasi:                                        │    │

│  │   - Approve: Perubahan disetujui                                   │    │

│  │   - Reject: Perubahan ditolak dengan justifikasi                  │    │

│  │   - Defer: Perubahan ditunda untuk evaluasi lebih lanjut          │    │

│  │ • Menyertakan justifikasi dan alternatif                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 4: KEPUTUSAN                                                          │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Perubahan kecil (≤ 5% impact) → PM approve                       │    │

│  │ • Perubahan sedang (≤ 20% impact) → Sponsor approve                │    │

│  │ • Perubahan besar (> 20% impact) → Steering Committee approve      │    │

│  │ • Perubahan kritis (security, compliance) → Semua level approve    │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 5: IMPLEMENTASI                                                       │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Update dokumen PMP dan terkait                                  │    │

│  │ • Komunikasi ke seluruh stakeholder                              │    │

│  │ • Update schedule, budget, dan baseline lainnya                  │    │

│  │ • Implementasi perubahan                                          │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 6: CLOSE & ARCHIVE                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Verifikasi implementasi sukses                                  │    │

│  │ • Dokumentasi perubahan di Change Log                             │    │

│  │ • Lessons learned (jika signifikan)                               │    │

│  │ • Arsipkan dokumen CRF                                            │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 13.1.2 Klasifikasi Perubahan

| Kategori | Deskripsi | Contoh |
| --- | --- | --- |
| Scope | Perubahan ruang lingkup proyek | Penambahan entity master baru, fitur baru |
| Schedule | Perubahan jadwal proyek | Perpanjangan sprint, perubahan milestone |
| Budget | Perubahan anggaran proyek | Penambahan biaya, realokasi budget |
| Resources | Perubahan sumber daya | Penambahan/pengurangan tim, perubahan vendor |
| Technical | Perubahan teknis | Perubahan arsitektur, teknologi stack |
| Quality | Perubahan standar kualitas | Perubahan acceptance criteria |
| Risk | Perubahan manajemen risiko | Perubahan risk response strategy |

### 13.1.3 Impact Assessment Criteria

| Kriteria | Level | Deskripsi | Approver | Waktu Respons |
| --- | --- | --- | --- | --- |
| Scope Impact | Kecil | ≤ 5% perubahan scope | PM | 1 hari |
|  | Sedang | 5-20% perubahan scope | Sponsor | 2 hari |
|  | Besar | > 20% perubahan scope | Steering Committee | 5 hari |
| Schedule Impact | Kecil | ≤ 5% dari baseline schedule | PM | 1 hari |
|  | Sedang | 5-20% dari baseline schedule | Sponsor | 2 hari |
|  | Besar | > 20% dari baseline schedule | Steering Committee | 5 hari |
| Budget Impact | Kecil | ≤ 5% dari baseline budget | PM | 1 hari |
|  | Sedang | 5-20% dari baseline budget | Sponsor | 2 hari |
|  | Besar | > 20% dari baseline budget | Steering Committee | 5 hari |
| Quality Impact | Kecil | Tidak mempengaruhi acceptance criteria | PM | 1 hari |
|  | Sedang | Mempengaruhi beberapa acceptance criteria | Sponsor | 2 hari |
|  | Besar | Mempengaruhi kriteria utama | Steering Committee | 5 hari |
| Risk Impact | Rendah | Risiko baru dengan dampak rendah | PM | 1 hari |
|  | Sedang | Risiko baru dengan dampak sedang | Sponsor | 2 hari |
|  | Tinggi | Risiko baru dengan dampak tinggi | Steering Committee | 5 hari |

## 13.2 CHANGE CONTROL BOARD (CCB)

### 13.2.1 Komposisi CCB

| Peran | Anggota | Wewenang |
| --- | --- | --- |
| Chairperson | Project Sponsor | Memimpin keputusan, veto untuk perubahan kritis |
| PMO Representative | Head of PMO | Memastikan alignment dengan standar PMO |
| Project Manager | PM P-FNE-01 | Menyajikan analisis dan rekomendasi |
| Tech Lead | Lead Developer | Analisis dampak teknis |
| Business Representative | Business Owner | Analisis dampak bisnis |
| Quality Lead | QA Lead | Analisis dampak kualitas |
| Security Lead | Security Engineer | Analisis dampak keamanan |
| Finance Representative | Finance | Analisis dampak finansial |

### 13.2.2 Ketentuan CCB

| Aspek | Ketentuan |
| --- | --- |
| Frekuensi Meeting | Sesuai kebutuhan (as needed) atau minimal 1 bulan sekali |
| Kuorum | Minimal 5 dari 8 anggota hadir |
| Keputusan | Mayoritas suara (Chairperson memiliki hak veto) |
| Rapat Darurat | Dapat dipanggil dalam 24 jam untuk perubahan kritis |
| Dokumentasi | Setiap keputusan dicatat dalam Minutes of Meeting |

## 13.3 CHANGE REQUEST FORM

### 13.3.1 Template Change Request Form

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    CHANGE REQUEST FORM - P-FNE-01                           │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  CRF NUMBER: CRF-XXX                                                        │

│  DATE SUBMITTED: DD/MM/YYYY                                                │

│  SUBMITTED BY: [Nama] / [Role]                                             │

│  PROJECT: P-FNE-01 - Foundation & Core Platform                            │

│                                                                              │

│  1. CHANGE DESCRIPTION                                                      │

│  ───────────────────────────────────────────────────────────────────────── │

│  Change Category:  ☐ Scope   ☐ Schedule   ☐ Budget                        │

│                    ☐ Resources ☐ Technical  ☐ Quality                     │

│                    ☐ Risk     ☐ Other: ________                          │

│                                                                              │

│  Change Description:                                                       │

│  ________________________________________________________________________ │

│  ________________________________________________________________________ │

│  ________________________________________________________________________ │

│                                                                              │

│  Reason / Justification:                                                   │

│  ________________________________________________________________________ │

│  ________________________________________________________________________ │

│                                                                              │

│  2. IMPACT ANALYSIS                                                         │

│  ───────────────────────────────────────────────────────────────────────── │

│  Scope Impact:     [ ] No Impact [ ] Minor [ ] Medium [ ] Major           │

│  Schedule Impact:  + ___ days / weeks                                     │

│  Cost Impact:      Rp ___________                                         │

│  Quality Impact:   [ ] No Impact [ ] Minor [ ] Medium [ ] Major           │

│  Risk Impact:      [ ] No Impact [ ] Minor [ ] Medium [ ] Major           │

│                                                                              │

│  Detailed Impact Analysis:                                                 │

│  ________________________________________________________________________ │

│  ________________________________________________________________________ │

│                                                                              │

│  3. PROPOSED SOLUTION                                                       │

│  ───────────────────────────────────────────────────────────────────────── │

│  Proposed Solution:                                                        │

│  ________________________________________________________________________ │

│  ________________________________________________________________________ │

│                                                                              │

│  Alternatives Considered:                                                  │

│  ________________________________________________________________________ │

│  ________________________________________________________________________ │

│                                                                              │

│  4. PRIORITY & RECOMMENDATION                                               │

│  ───────────────────────────────────────────────────────────────────────── │

│  Priority:         [ ] Low  [ ] Medium  [ ] High  [ ] Critical            │

│  Recommendation:   [ ] Approve  [ ] Reject  [ ] Defer                     │

│  Recommendation By: [Nama] / [Role] / Date: ___/___/_____               │

│                                                                              │

│  5. APPROVAL                                                                │

│  ───────────────────────────────────────────────────────────────────────── │

│  PM Approval:        ☐ Approved  ☐ Rejected  ☐ Deferred                  │

│  Name: ___________  Date: ___/___/_____  Signature: ________             │

│                                                                              │

│  Sponsor Approval:   ☐ Approved  ☐ Rejected  ☐ Deferred                  │

│  Name: ___________  Date: ___/___/_____  Signature: ________             │

│                                                                              │

│  Steering Committee: ☐ Approved  ☐ Rejected  ☐ Deferred                  │

│  Name: ___________  Date: ___/___/_____  Signature: ________             │

│                                                                              │

│  6. IMPLEMENTATION                                                          │

│  ───────────────────────────────────────────────────────────────────────── │

│  Implementation Date: ___/___/_____                                       │

│  Implementation By:  ___________                                          │

│  Actual Impact:                                                           │

│  ________________________________________________________________________ │

│                                                                              │

│  7. CLOSURE                                                                 │

│  ───────────────────────────────────────────────────────────────────────── │

│  Closed By:   ___________  Date: ___/___/_____                          │

│  Verification:  ☐ Implemented successfully                               │

│                 ☐ Documentation updated                                  │

│                 ☐ Stakeholders informed                                  │

│  Lessons Learned:                                                         │

│  ________________________________________________________________________ │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 13.3.2 Contoh Change Request Form yang Terisi

CRF NUMBER: CRF-001
DATE SUBMITTED: 15-Oct-2026
SUBMITTED BY: Andi Wijaya / Business Owner

1. CHANGE DESCRIPTION

- Change Category: ☒ Scope

- Change Description: Penambahan entity master "Livestock Breed" yang sebelumnya tidak termasuk dalam 24 entity master data.

- Reason / Justification: Untuk mendukung proyek P-FNE-02 (Core Agricultural Operations) yang membutuhkan data breed ternak untuk fitur manajemen peternakan.

2. IMPACT ANALYSIS

- Scope Impact: Minor (penambahan 1 entity dari 24 menjadi 25)

- Schedule Impact: + 2 hari (untuk design schema, CRUD, dan testing)

- Cost Impact: Rp 5.000.000 (biaya tambahan untuk 2 hari developer)

- Quality Impact: Minor (perlu penambahan test cases)

- Risk Impact: Minor (risiko tambahan minimal)

3. PROPOSED SOLUTION

- Proposed Solution: Menambahkan entity "Livestock Breed" dengan schema yang sudah didesain

- Alternatives Considered: 1) Ditunda ke P-FNE-02, 2) Tidak ditambahkan

4. PRIORITY & RECOMMENDATION

- Priority: Medium

- Recommendation: Approve

- Recommendation By: PM / 15-Oct-2026

5. APPROVAL

- PM Approval: ☒ Approved
Name: [PM Name] Date: 15-Oct-2026

- Sponsor Approval: ☒ Approved
Name: [Sponsor Name] Date: 16-Oct-2026

6. IMPLEMENTATION

- Implementation Date: 17-Oct-2026

- Implementation By: Backend Team

- Actual Impact: Sesuai estimasi, +2 hari dan +Rp 5.000.000

7. CLOSURE

- Closed By: PM Date: 20-Oct-2026

- Verification: ☒ Implemented successfully ☒ Documentation updated ☒ Stakeholders informed

## 13.4 CHANGE LOG

### 13.4.1 Format Change Log

| CRF # | Tanggal | Deskripsi Perubahan | Kategori | Status | Approved By | Implementation Date | Actual Impact |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CRF-001 | 15-Oct-26 | Tambah entity Livestock Breed | Scope | Closed | Sponsor | 17-Oct-26 | +2 hari, +Rp 5.000.000 |
| CRF-002 | DD-MMM-YY | Deskripsi | Kategori | Status | Nama | DD-MMM-YY | Dampak aktual |
| ... | ... | ... | ... | ... | ... | ... | ... |

### 13.4.2 Change Log Tracker

| ID | Type | Date | Requestor | Description | Impact | Status | Closure Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CRF-001 | Scope | 15-Oct-26 | Business Owner | Tambah Livestock Breed | Minor | Closed | 20-Oct-26 |
| CRF-002 |  |  |  |  |  |  |  |
| CRF-003 |  |  |  |  |  |  |  |

## 13.5 DOCUMENT APPROVAL PROCESS

### 13.5.1 Approval Workflow

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                    DOCUMENT APPROVAL PROCESS P-FNE-01                       │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  STEP 1: DRAFT                                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Penulis menyusun dokumen                                          │    │

│  │ • Versi: Draft v0.1                                                │    │

│  │ • Owner: Penulis                                                   │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 2: REVIEW INTERNAL                                                    │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Review oleh tim internal                                          │    │

│  │ • Perbaikan berdasarkan feedback                                    │    │

│  │ • Versi: Draft v0.2 - v0.9                                         │    │

│  │ • Owner: Penulis + Tim                                              │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 3: SUBMISSION                                                         │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Dokumen diajukan ke PMO untuk review                              │    │

│  │ • Versi: Submitted v1.0                                            │    │

│  │ • Owner: PM                                                        │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 4: PMO REVIEW                                                         │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Review oleh PMO                                                   │    │

│  │ • Check compliance dengan standar                                   │    │

│  │ • Versi: Under Review                                              │    │

│  │ • Owner: PMO                                                       │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 5: APPROVAL                                                           │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Approval oleh Project Sponsor                                    │    │

│  │ • Approval oleh Steering Committee (jika diperlukan)              │    │

│  │ • Versi: Approved v1.0                                             │    │

│  │ • Owner: Sponsor                                                   │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                              │                                               │

│                              ▼                                               │

│  STEP 6: PUBLISH & DISTRIBUTE                                               │

│  ┌─────────────────────────────────────────────────────────────────────┐    │

│  │ • Dokumen dipublikasikan di Confluence                              │    │

│  │ • Notifikasi ke seluruh stakeholder                                 │    │

│  │ • Versi: Published v1.0                                            │    │

│  │ • Owner: PM                                                        │    │

│  └─────────────────────────────────────────────────────────────────────┘    │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 13.5.2 Dokumen yang Memerlukan Approval

| No | Dokumen | Approver | Level | Frekuensi Update |
| --- | --- | --- | --- | --- |
| 1 | Project Charter | Sponsor | Strategic | Sekali |
| 2 | PMP | Sponsor, Steering | Strategic | Perubahan signifikan |
| 3 | Scope Statement | Sponsor | Strategic | Perubahan scope |
| 4 | WBS | PM, Tech Lead | Tactical | Perubahan struktur |
| 5 | Schedule | PM, Sponsor | Tactical | Perubahan milestone |
| 6 | Budget | Sponsor, Finance | Strategic | Perubahan biaya |
| 7 | Risk Register | PM, Sponsor | Tactical | Bulanan |
| 8 | Quality Plan | PM, QA Lead | Tactical | Perubahan standar |
| 9 | Communication Plan | PM | Tactical | Perubahan stakeholder |
| 10 | Procurement Plan | PM, Sponsor | Tactical | Perubahan vendor |
| 11 | Change Request | CCB | Tactical | Perubahan baseline |
| 12 | Final Report | Sponsor, Steering | Strategic | Akhir proyek |
| 13 | Lessons Learned | PM, PMO | Tactical | Akhir fase/proyek |

### 13.5.3 Approval Authority Matrix

| Dokumen | PM | PMO | Tech Lead | Sponsor | Steering Committee | Finance |
| --- | --- | --- | --- | --- | --- | --- |
| Project Charter | C | C | C | A | I | I |
| PMP | R | C | C | A | I | I |
| Scope Statement | R | C | C | A | I | I |
| WBS | R | C | C | I | I | I |
| Schedule | R | C | C | A | I | I |
| Budget | R | C | C | C | I | A |
| Risk Register | R | C | C | A | I | I |
| Quality Plan | R | A | C | I | I | I |
| Communication Plan | R | C | C | I | I | I |
| Procurement Plan | R | C | C | A | I | C |
| Change Request | R | C | C | A | A | C |
| Final Report | R | C | C | A | A | I |
| Lessons Learned | R | A | C | I | I | I |

R = Responsible (penyusun), A = Accountable (approver), C = Consulted, I = Informed

## 13.6 REVISION HISTORY

### 13.6.1 Format Revision History

| Versi | Tanggal | Penulis | Reviewer | Perubahan | Keterangan |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 01-Oct-2026 | PM | Sponsor | Initial version | Approved |
| 1.1 | 15-Oct-2026 | PM | - | Update CRF-001 | Minor update |
| ... | ... | ... | ... | ... | ... |

### 13.6.2 Version Control Policy

| Aspek | Kebijakan |
| --- | --- |
| Version Format | vX.Y (X = major, Y = minor) |
| Major Changes | Perubahan signifikan (scope, schedule, budget) → X + 1 |
| Minor Changes | Perubahan kecil (typo, clarification) → Y + 1 |
| Approval Required | Major changes → Approval baru; Minor changes → Inform PMO |
| Archiving | Semua versi disimpan di repository |
| Distribution | Seluruh stakeholder via Confluence |

# BAB 14: PENUTUPAN PROYEK

## (PROJECT CLOSURE)

## 14.1 PROJECT CLOSURE CRITERIA

### 14.1.1 Kriteria Penutupan Proyek

Proyek P-FNE-01 dinyatakan SELESAI dan DITUTUP apabila seluruh kondisi berikut terpenuhi:

| No | Kriteria | Status | Verifikasi | Tanggal |
| --- | --- | --- | --- | --- |
| 1 | Semua acceptance criteria terpenuhi | ☐ | PM + QA |  |
| 2 | Semua deliverable telah diserahkan dan diterima | ☐ | PM + Sponsor |  |
| 3 | Semua NFR target terpenuhi berdasarkan performance testing | ☐ | QA + DevOps |  |
| 4 | Security assessment tidak menemukan critical vulnerability | ☐ | Security Lead |  |
| 5 | User Acceptance Testing (UAT) sukses (≥ 90% satisfaction) | ☐ | Business Owner |  |
| 6 | Production deployment sukses | ☐ | DevOps Lead |  |
| 7 | Disaster Recovery drill sukses (RPO ≤ 15m, RTO ≤ 2h) | ☐ | DevOps Lead |  |
| 8 | Semua dokumen proyek selesai dan diarsipkan | ☐ | PM |  |
| 9 | Lessons learned telah didokumentasikan | ☐ | PM |  |
| 10 | Handover ke tim operasional telah dilakukan | ☐ | PM + Operations |  |
| 11 | Semua kontrak vendor telah ditutup | ☐ | PM + Procurement |  |
| 12 | Semua pembayaran telah diselesaikan | ☐ | PM + Finance |  |
| 13 | Tim proyek telah didistribusikan kembali | ☐ | PM + HR |  |
| 14 | Project closure report telah disetujui | ☐ | Sponsor |  |

### 14.1.2 Checklist Penutupan Proyek

PROJECT CLOSURE CHECKLIST - P-FNE-01

| No | Aktivitas | Status | Tanggal | PIC |
| --- | --- | --- | --- | --- |
| A. Deliverable Completion |  |  |  |  |
| A.1 | Semua deliverable diterima | ☐ |  | PM |
| A.2 | Acceptance criteria terpenuhi | ☐ |  | QA Lead |
| A.3 | UAT sign-off didapatkan | ☐ |  | Business Owner |
| B. Testing & Quality |  |  |  |  |
| B.1 | Performance testing selesai | ☐ |  | DevOps Lead |
| B.2 | Security testing selesai | ☐ |  | Security Lead |
| B.3 | QA report disetujui | ☐ |  | QA Lead |
| C. Deployment & Operations |  |  |  |  |
| C.1 | Production deployment sukses | ☐ |  | DevOps Lead |
| C.2 | DR drill sukses | ☐ |  | DevOps Lead |
| C.3 | Monitoring & alerting aktif | ☐ |  | DevOps Lead |
| C.4 | Backup system berfungsi | ☐ |  | DevOps Lead |
| D. Documentation |  |  |  |  |
| D.1 | Technical documentation final | ☐ |  | Tech Lead |
| D.2 | API documentation final | ☐ |  | Tech Lead |
| D.3 | Operations manual final | ☐ |  | DevOps Lead |
| D.4 | User manual final | ☐ |  | PM |
| D.5 | PMP final | ☐ |  | PM |
| E. Handover |  |  |  |  |
| E.1 | Handover meeting dilakukan | ☐ |  | PM |
| E.2 | Training completed | ☐ |  | PM |
| E.3 | Support team ready | ☐ |  | DevOps Lead |
| E.4 | Knowledge transfer completed | ☐ |  | PM |
| F. Financial |  |  |  |  |
| F.1 | Final budget reconciliation | ☐ |  | PM + Finance |
| F.2 | All invoices paid | ☐ |  | PM + Finance |
| F.3 | Procurement contracts closed | ☐ |  | PM + Procurement |
| G. Team & Resources |  |  |  |  |
| G.1 | Team performance review | ☐ |  | PM |
| G.2 | Resource released | ☐ |  | PM + HR |
| G.3 | Team celebration | ☐ |  | PM |
| H. Lessons Learned |  |  |  |  |
| H.1 | Lessons learned session | ☐ |  | PM |
| H.2 | Lessons learned report | ☐ |  | PM |
| H.3 | Recommendations for future | ☐ |  | PM |
| I. Final Report |  |  |  |  |
| I.1 | Project closure report | ☐ |  | PM |
| I.2 | Sponsor approval | ☐ |  | Sponsor |
| I.3 | PMO sign-off | ☐ |  | Head of PMO |

## 14.2 HANDOVER PLAN

### 14.2.1 Handover Schedule

| Tahap | Aktivitas | Owner | Timeline | Output |
| --- | --- | --- | --- | --- |
| H-30 | Persiapan dokumen handover | PM | M-1 | Dokumen final |
| H-21 | Preparation training materials | Tech Lead | M-3 minggu | Training materials |
| H-14 | Training untuk tim operasional | Tech Lead, DevOps | M-2 minggu | Training completed |
| H-7 | Finalisasi dokumentasi | All Leads | M-1 minggu | Documentation final |
| H-0 | Serah terima ke tim operasional | PM, Operations Lead | M | Handover meeting |
| H+1 - H+60 | Periode support | Development Team | M+1 - M+2 | Support completed |
| H+60 | Formal project closure | PM, Sponsor | M+2 | Closure approval |

### 14.2.2 Dokumen Handover

| No | Dokumen | Format | Penerima | Status |
| --- | --- | --- | --- | --- |
| 1 | Architecture Documentation (final) | Confluence/PDF | IT Ops, DevOps | ☐ |
| 2 | API Documentation (OpenAPI) | Swagger/PDF | Developers | ☐ |
| 3 | Database Schema & ERD | PDF | DBA, Developers | ☐ |
| 4 | Deployment & Operations Guide | Confluence/PDF | IT Ops, DevOps | ☐ |
| 5 | Monitoring & Alerting Guide | Confluence/PDF | IT Ops, DevOps | ☐ |
| 6 | Security & Compliance Checklist | PDF | Security Team | ☐ |
| 7 | Disaster Recovery Procedure | PDF | IT Ops, DevOps | ☐ |
| 8 | User Manuals | Confluence/PDF | End Users | ☐ |
| 9 | Training Materials | PDF/Video | All | ☐ |
| 10 | Knowledge Base Articles | Confluence | All | ☐ |

### 14.2.3 Handover Meeting Agenda

HANDOVER MEETING - P-FNE-01

Date: [DD/MM/YYYY]
Time: [HH:MM]
Location: [Meeting Room / Virtual]
Attendees: PM, Tech Lead, DevOps Lead, Security Lead, IT Operations Team, PMO

Agenda:

- Project Overview (15 min)

  - Project objectives & achievements

  - Scope & deliverables

  - Key milestones

- Technical Handover (30 min)

  - Architecture overview

  - System components & dependencies

  - Database schema & data flow

  - API documentation

  - Security implementation

- Operations Handover (30 min)

  - Infrastructure & deployment

  - Monitoring & alerting

  - Backup & DR procedures

  - Troubleshooting guide

  - Performance tuning

- Support Transition (15 min)

  - Support process & SLA

  - Escalation matrix

  - Known issues & workarounds

  - Support team contact

- Documentation & Training (15 min)

  - Documentation repository

  - Training materials

  - Knowledge base

- Q&A Session (15 min)

  - Questions from Operations Team

  - Clarifications

- Next Steps & Closure (10 min)

  - Support period schedule

  - Project closure timeline

  - Sign-off

Handover Acceptance:

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Operations Lead |  |  |  |
| Head of IT Operations |  |  |  |

## 14.3 PROJECT REVIEW & LESSONS LEARNED

### 14.3.1 Lessons Learned Session Plan

| Aspek | Detail |
| --- | --- |
| Timing | Dilaksanakan dalam 2 minggu setelah Go-Live |
| Durasi | 1 hari (4 jam session) |
| Peserta | Seluruh tim proyek, stakeholder utama |
| Fasilitator | PMO atau external facilitator |
| Output | Lessons Learned Report, Action Items |

Topik yang Dikaji:

- What Went Well - Faktor keberhasilan yang perlu dipertahankan

- What Could Be Improved - Area perbaikan untuk proyek mendatang

- What Went Wrong - Masalah yang terjadi dan solusinya

- Lessons Learned - Pembelajaran kunci yang didokumentasikan

- Recommendations - Rekomendasi untuk proyek P-FNE-02 s.d. P-FNE-08

### 14.3.2 Lessons Learned Report Template

LESSONS LEARNED REPORT
Proyek Foundation & Core Platform (P-FNE-01)

| Field | Detail |
| --- | --- |
| Session Date | [DD/MM/YYYY] |
| Facilitator | [Nama] |
| Participants | [Daftar peserta] |
| Project Phase | Penutupan Proyek |

1. What Went Well

| No | Lesson Learned | Evidence | Recommendation |
| --- | --- | --- | --- |
| 1 | [Keberhasilan 1] | [Data/bukti] | [Rekomendasi] |
| 2 | [Keberhasilan 2] | [Data/bukti] | [Rekomendasi] |
| 3 | [Keberhasilan 3] | [Data/bukti] | [Rekomendasi] |

2. What Could Be Improved

| No | Lesson Learned | Evidence | Recommendation |
| --- | --- | --- | --- |
| 1 | [Perbaikan 1] | [Data/bukti] | [Rekomendasi] |
| 2 | [Perbaikan 2] | [Data/bukti] | [Rekomendasi] |
| 3 | [Perbaikan 3] | [Data/bukti] | [Rekomendasi] |

3. What Went Wrong

| No | Lesson Learned | Root Cause | Recommendation |
| --- | --- | --- | --- |
| 1 | [Masalah 1] | [Akar masalah] | [Rekomendasi] |
| 2 | [Masalah 2] | [Akar masalah] | [Rekomendasi] |
| 3 | [Masalah 3] | [Akar masalah] | [Rekomendasi] |

4. Key Learnings

| No | Learning | Impact | Action Item |
| --- | --- | --- | --- |
| 1 | [Pembelajaran 1] | [Dampak] | [Tindakan] |
| 2 | [Pembelajaran 2] | [Dampak] | [Tindakan] |
| 3 | [Pembelajaran 3] | [Dampak] | [Tindakan] |

5. Recommendations for Future Projects

| No | Recommendation | Priority | Owner | Target Project |
| --- | --- | --- | --- | --- |
| 1 | [Rekomendasi 1] | High | [Nama] | P-FNE-02 |
| 2 | [Rekomendasi 2] | Medium | [Nama] | P-FNE-03 |
| 3 | [Rekomendasi 3] | Low | [Nama] | All |

### 14.3.3 Lessons Learned Area (Contoh Isian)

What Went Well:

- Agile Methodology: Pendekatan sprint 2 minggu efektif untuk pengembangan iteratif

- API-First Design: Memudahkan integrasi antar service

- Automated Testing: CI/CD dengan automated testing mengurangi defect

- Cross-functional Team: Tim dengan skill yang bervariasi mempercepat penyelesaian

What Could Be Improved:

- Security Review: Security review sebaiknya dilakukan di awal setiap sprint

- Stakeholder Involvement: Business owner sebaiknya lebih aktif di sprint review

- Documentation: Dokumentasi sebaiknya dilakukan paralel dengan development

What Went Wrong:

- Integrasi Legacy: Integrasi dengan sistem legacy memakan waktu lebih lama

- Resource Availability: DevOps engineer availability terbatas di bulan pertama

Recommendations:

- Untuk P-FNE-02, mulai security review lebih awal

- Untuk P-FNE-03, siapkan integration layer dari awal

- Untuk semua proyek, lakukan resource planning lebih detail

## 14.4 FINAL REPORT

### 14.4.1 Project Closure Report

PROJECT CLOSURE REPORT
Proyek Foundation & Core Platform (P-FNE-01)
Super ERP Farm Nation Enterprise (FNE)

1. Executive Summary

| Elemen | Detail |
| --- | --- |
| Project Name | Foundation & Core Platform (P-FNE-01) |
| Start Date | 01-Oct-2026 |
| End Date | [DD-MMM-YYYY] |
| Project Manager | [Nama PM] |
| Project Sponsor | [Nama Sponsor] |

[Executive summary singkat tentang pencapaian proyek]

2. Project Objectives & Achievements

| No | Tujuan | Target | Pencapaian | Status |
| --- | --- | --- | --- | --- |
| 1 | Infrastruktur cloud-native | 100% environment | [% pencapaian] | ☐ |
| 2 | IAM Implementation | 100% fitur | [% pencapaian] | ☐ |
| 3 | MDM Implementation | 24 entities | [% pencapaian] | ☐ |
| 4 | Audit Implementation | 100% transaksi | [% pencapaian] | ☐ |
| 5 | Workflow Implementation | 3 workflows | [% pencapaian] | ☐ |
| 6 | Integration | 100% complete | [% pencapaian] | ☐ |
| 7 | Quality & Security | 0 critical | [% pencapaian] | ☐ |
| 8 | Go-Live | Production ready | [% pencapaian] | ☐ |

3. Scope & Deliverables

| Deliverable | Planned | Actual | Status |
| --- | --- | --- | --- |
| Infrastructure & DevOps | 6 activities | [Jumlah] | ☐ |
| IAM Service | 6 components | [Jumlah] | ☐ |
| MDM | 24 entities | [Jumlah] | ☐ |
| Audit & Logging | 4 components | [Jumlah] | ☐ |
| API Gateway | 5 components | [Jumlah] | ☐ |
| Event Bus | 4 components | [Jumlah] | ☐ |
| Workflow Engine | 4 components | [Jumlah] | ☐ |
| Notification Service | 4 components | [Jumlah] | ☐ |

Scope Changes:

| CRF # | Description | Impact | Approved By |
| --- | --- | --- | --- |
| CRF-001 | Tambah Livestock Breed | +2 hari, +Rp 5.000.000 | Sponsor |

4. Schedule Performance

| Milestone | Planned Date | Actual Date | Variance | Status |
| --- | --- | --- | --- | --- |
| M1: Infrastructure Ready | 29-Oct-2026 | [Actual] | [+/- days] | ☐ |
| M2: IAM Complete | 26-Nov-2026 | [Actual] | [+/- days] | ☐ |
| M3: MDM Complete | 24-Dec-2026 | [Actual] | [+/- days] | ☐ |
| M4: Audit Complete | 14-Jan-2027 | [Actual] | [+/- days] | ☐ |
| M5: Gateway & Event Bus | 28-Jan-2027 | [Actual] | [+/- days] | ☐ |
| M6: Workflow & Notification | 11-Feb-2027 | [Actual] | [+/- days] | ☐ |
| M7: Integration Ready | 25-Feb-2027 | [Actual] | [+/- days] | ☐ |
| M8: Go-Live | 11-Mar-2027 | [Actual] | [+/- days] | ☐ |
| M9: Project Closure | 25-Mar-2027 | [Actual] | [+/- days] | ☐ |

Schedule Variance: [Total variance explanation]

5. Budget Performance

| Kategori | Planned (Rp) | Actual (Rp) | Variance (Rp) | Variance (%) |
| --- | --- | --- | --- | --- |
| Biaya Personil | 7.368.000.000 | [Actual] | [Variance] | [%] |
| Biaya Langsung | 1.000.000.000 | [Actual] | [Variance] | [%] |
| Overhead | 836.800.000 | [Actual] | [Variance] | [%] |
| Keuntungan | 1.104.576.000 | [Actual] | [Variance] | [%] |
| PPN | 1.133.030.336 | [Actual] | [Variance] | [%] |
| Total | 11.442.406.336 | [Actual] | [Variance] | [%] |

Budget Variance Explanation:

- [Penjelasan variance]

6. Quality Metrics

| Metrik | Target | Actual | Status |
| --- | --- | --- | --- |
| Code Coverage | ≥ 80% | [%] | ☐ |
| Code Quality Gate | Passed | [Pass/Fail] | ☐ |
| Security Scan | 0 Critical | [Jumlah] | ☐ |
| API Response Time (Median) | ≤ 500ms | [ms] | ☐ |
| API Response Time (P95) | ≤ 2 detik | [detik] | ☐ |
| System Availability | ≥ 99.9% | [%] | ☐ |
| Defect Density | < 1/1000 LOC | [Jumlah] | ☐ |
| UAT Satisfaction | ≥ 90% | [%] | ☐ |

7. Risk Management

| Kategori | Total Risks | Active | Mitigated | Closed |
| --- | --- | --- | --- | --- |
| Teknis | 5 | [Jumlah] | [Jumlah] | [Jumlah] |
| Sumber Daya | 3 | [Jumlah] | [Jumlah] | [Jumlah] |
| Jadwal | 3 | [Jumlah] | [Jumlah] | [Jumlah] |
| Biaya | 2 | [Jumlah] | [Jumlah] | [Jumlah] |
| Kualitas | 2 | [Jumlah] | [Jumlah] | [Jumlah] |
| Keamanan | 3 | [Jumlah] | [Jumlah] | [Jumlah] |
| Eksternal | 2 | [Jumlah] | [Jumlah] | [Jumlah] |
| Total | 20 | [Jumlah] | [Jumlah] | [Jumlah] |

8. Team Performance

| Role | Planned | Actual | Performance |
| --- | --- | --- | --- |
| Project Manager | 1 | [Jumlah] | [Rating] |
| DevOps Lead | 1 | [Jumlah] | [Rating] |
| DevOps Engineer | 2 | [Jumlah] | [Rating] |
| Tech Lead | 1 | [Jumlah] | [Rating] |
| Backend Developer | 4 | [Jumlah] | [Rating] |
| Frontend Lead | 1 | [Jumlah] | [Rating] |
| Frontend Developer | 2 | [Jumlah] | [Rating] |
| Security Lead | 1 | [Jumlah] | [Rating] |
| Security Engineer | 1 | [Jumlah] | [Rating] |
| QA Lead | 1 | [Jumlah] | [Rating] |
| QA Engineer | 1 | [Jumlah] | [Rating] |

9. Lessons Learned Summary

Key Successes:

- [Success 1]

- [Success 2]

- [Success 3]

Key Challenges:

- [Challenge 1]

- [Challenge 2]

- [Challenge 3]

Recommendations for Future Projects:

- [Recommendation 1]

- [Recommendation 2]

- [Recommendation 3]

10. Benefits Realization

| Benefit | Target | Actual | Status |
| --- | --- | --- | --- |
| Efisiensi Operasional IT | 30% | [%] | ☐ |
| Keamanan Data | 80% | [%] | ☐ |
| Kecepatan Pengembangan | 40% | [%] | ☐ |
| Kepatuhan | 100% | [%] | ☐ |

11. Recommendations for Future Projects

| No | Recommendation | Priority | Owner | Target Project |
| --- | --- | --- | --- | --- |
| 1 | [Recommendation 1] | High | [Nama] | P-FNE-02 |
| 2 | [Recommendation 2] | Medium | [Nama] | P-FNE-03 |
| 3 | [Recommendation 3] | Low | [Nama] | All |

12. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Project Sponsor |  |  |  |
| Head of PMO |  |  |  |

## 14.5 DOCUMENT ARCHIVING

### 14.5.1 Archive Policy

| Jenis Dokumen | Retention Period | Storage Location | Access |
| --- | --- | --- | --- |
| PMP & Project Documents | 5 tahun | Corporate Repository | PMO, Sponsor |
| Code Repository | Indefinite | GitHub/GitLab | Developers |
| Database Backup | 5 tahun | Cloud Archive | IT Ops |
| Audit Logs | 5 tahun (sesuai regulasi) | Audit Storage | Security, Auditor |
| Contract & Procurement | 7 tahun | Legal Repository | Legal, Procurement |
| Training Materials | 3 tahun | Knowledge Base | All |
| Final Report & Lessons Learned | Indefinite | PMO Repository | All |
| Meeting Minutes | 5 tahun | Confluence | All |

### 14.5.2 Archive Checklist

| No | Item | Status | Location | Date |
| --- | --- | --- | --- | --- |
| 1 | Project Management Plan | ☐ | Corporate Repository |  |
| 2 | Scope Statement | ☐ | Corporate Repository |  |
| 3 | WBS & WBS Dictionary | ☐ | Corporate Repository |  |
| 4 | Schedule & Gantt Chart | ☐ | Corporate Repository |  |
| 5 | Budget & Financial Reports | ☐ | Corporate Repository |  |
| 6 | Quality Management Plan | ☐ | Corporate Repository |  |
| 7 | Risk Register | ☐ | Corporate Repository |  |
| 8 | Communication Plan | ☐ | Corporate Repository |  |
| 9 | Procurement Documents | ☐ | Legal Repository |  |
| 10 | Change Log | ☐ | Corporate Repository |  |
| 11 | Final Report | ☐ | PMO Repository |  |
| 12 | Lessons Learned | ☐ | PMO Repository |  |
| 13 | Code Repository | ☐ | GitHub/GitLab |  |
| 14 | API Documentation | ☐ | GitHub/GitLab |  |
| 15 | Database Schema | ☐ | Corporate Repository |  |
| 16 | Deployment & Operations Guide | ☐ | Corporate Repository |  |
| 17 | User Manuals | ☐ | Knowledge Base |  |
| 18 | Training Materials | ☐ | Knowledge Base |  |
| 19 | Meeting Minutes | ☐ | Confluence |  |
| 20 | Contracts & Agreements | ☐ | Legal Repository |  |

## 14.6 CELEBRATION & RECOGNITION

### 14.6.1 Go-Live Celebration Plan

| Aktivitas | Timeline | Deskripsi | PIC |
| --- | --- | --- | --- |
| Go-Live Announcement | Hari Go-Live | Email ke seluruh stakeholder | PM |
| Team Celebration Dinner | Minggu Go-Live | Dinner bersama tim | PM |
| Project Completion Certificate | Minggu Go-Live | Sertifikat untuk tim | PM + HR |
| Knowledge Sharing Session | H+1 minggu | Presentasi ke perusahaan | PM + Leads |
| Recognition Awards | H+2 minggu | Penghargaan untuk tim | PM + Sponsor |

### 14.6.2 Recognition Program

| Kategori | Kriteria | Reward |
| --- | --- | --- |
| Outstanding Performance | Exceeds expectations, high impact | Bonus, Public recognition |
| Innovation | Solusi kreatif, efisiensi | Special award, Certificate |
| Team Player | Kolaborasi, membantu tim | Recognition in meeting |
| Quality Champion | Code quality, zero defects | Certificate, Gift |
| Security Champion | Security awareness | Certificate |

BAB 14 SELESAI

## KESIMPULAN AKHIR PMP

Dokumen Project Management Plan (PMP) untuk Proyek Foundation & Core Platform (P-FNE-01) ini telah selesai disusun secara lengkap mencakup 14 bab yang meliputi:

| Bab | Judul | Status |
| --- | --- | --- |
| 1 | Pendahuluan | ✅ Selesai |
| 2 | Manajemen Integrasi Proyek | ✅ Selesai |
| 3 | Manajemen Ruang Lingkup | ✅ Selesai |
| 4 | Manajemen Jadwal | ✅ Selesai |
| 5 | Manajemen Biaya | ✅ Selesai |
| 6 | Manajemen Kualitas | ✅ Selesai |
| 7 | Manajemen Sumber Daya | ✅ Selesai |
| 8 | Manajemen Komunikasi | ✅ Selesai |
| 9 | Manajemen Risiko | ✅ Selesai |
| 10 | Manajemen Pengadaan | ✅ Selesai |
| 11 | Manajemen Pemangku Kepentingan | ✅ Selesai |
| 12 | Lampiran | ✅ Selesai |
| 13 | Proses Perubahan dan Persetujuan | ✅ Selesai |
| 14 | Penutupan Proyek | ✅ Selesai |

DOKUMEN PMP P-FNE-01 TELAH SELESAI

DOKUMENTASI TERKAIT:

- Arsitektur Software Detil P-FNE-01

- Functional & Non-Functional Requirements P-FNE-01

- Database Design & ERD P-FNE-01

- User Interface Design Specification P-FNE-01

- API Specification (OpenAPI) P-FNE-01

- Security & Compliance Checklist P-FNE-01

- Testing Strategy & Test Cases P-FNE-01

- Deployment & Operations Guide P-FNE-01

APPROVAL SIGN-OFF:

| Peran | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Project Sponsor |  |  |  |
| Steering Committee Chair |  |  |  |
| PMO Director |  |  |  |

DISCLAIMER:

Dokumen ini adalah Project Management Plan (PMP) untuk Proyek Foundation & Core Platform (P-FNE-01) Super ERP Farm Nation Enterprise. Dokumen ini bersifat living document yang dapat diperbarui sesuai dengan kebutuhan proyek. Setiap perubahan pada dokumen ini harus melalui proses Integrated Change Control yang telah ditetapkan dalam Bab 13.