# PROJECT MANAGEMENT PLAN (PMP) - DETAIL PER BAB

## Intelligence & Decision Platform (P-FNE-07)

### Super ERP Farm Nation Enterprise (FNE)

## BAB 1: PENDAHULUAN

### 1.1. Tujuan Dokumen

Project Management Plan (PMP) ini merupakan dokumen formal yang mendefinisikan secara komprehensif bagaimana proyek Intelligence & Decision Platform (P-FNE-07) akan direncanakan, dieksekusi, dimonitor, dikendalikan, dan ditutup. Dokumen ini berfungsi sebagai:

| Fungsi | Deskripsi |
| --- | --- |
| Pedoman Eksekusi | Memberikan panduan bagi seluruh tim proyek dalam melaksanakan pekerjaan |
| Alat Kontrol | Menjadi dasar untuk memonitor dan mengendalikan progress proyek |
| Media Komunikasi | Menjembatani komunikasi antara tim proyek dan stakeholder |
| Dokumen Referensi | Menjadi acuan untuk pengambilan keputusan selama siklus proyek |

Dokumen ini mengacu pada standar PMBOK (Project Management Body of Knowledge) edisi ke-7 dengan 10 area manajemen dan mengadopsi pendekatan Agile-Hybrid yang menggabungkan metode prediktif (untuk infrastruktur) dan adaptif (untuk pengembangan).

### 1.2. Deskripsi Proyek

#### 1.2.1. Latar Belakang

Super ERP Farm Nation Enterprise (FNE) sedang membangun ekosistem digital terintegrasi yang mencakup 8 proyek turunan (P-FNE-01 s.d. P-FNE-08). Proyek P-FNE-07: Intelligence & Decision Platform merupakan pusat kecerdasan bisnis dari seluruh ekosistem.

Saat ini, data dari berbagai modul operasional (pertanian, rantai pasok, produksi, penjualan, keuangan, dan SDM) tersebar dan belum dimanfaatkan secara optimal untuk pengambilan keputusan strategis. Proyek ini bertujuan untuk mengubah data tersebut menjadi wawasan yang dapat ditindaklanjuti (actionable insights).

#### 1.2.2. Visi Proyek

Menjadi pusat kecerdasan bisnis yang mengubah data operasional menjadi keputusan strategis yang cepat, tepat, dan berbasis bukti untuk mendukung visi FNE sebagai Integrated Agricultural Enterprise Operating System yang andal dan cerdas.

#### 1.2.3. Misi Proyek

- Menyediakan platform data terintegrasi yang menampung seluruh data operasional

- Menyajikan visualisasi data yang intuitif melalui dashboard interaktif

- Mengembangkan model AI/ML untuk prediksi dan rekomendasi

- Membangun Knowledge Graph untuk memahami relasi bisnis

- Menyediakan kemampuan simulasi dan optimasi untuk pengambilan keputusan

#### 1.2.4. Komponen Platform

| Komponen | Deskripsi | Teknologi |
| --- | --- | --- |
| Data Platform | Pusat data terintegrasi dengan pipeline real-time | Kafka, Spark, Snowflake, MinIO |
| Business Intelligence | Dashboard dan laporan interaktif | React, D3.js, Chart.js |
| AI/ML Platform | Model prediktif dan preskriptif | Python, MLflow, Kubeflow |
| Knowledge Graph | Representasi relasi bisnis | Neo4j, GraphQL, Cytoscape.js |
| Decision Intelligence | Simulasi dan optimasi keputusan | OR-Tools, SciPy, FastAPI |

### 1.3. Tujuan Proyek

#### 1.3.1. Tujuan Strategis

| No | Tujuan | Manfaat Bisnis | Metrik Keberhasilan |
| --- | --- | --- | --- |
| 1 | Meningkatkan kecepatan pengambilan keputusan | Waktu analisis dari hari ke menit | Dashboard load ≤ 5 detik |
| 2 | Meningkatkan akurasi perencanaan produksi | Pengurangan over/under production | Forecast accuracy ≥ 80% |
| 3 | Mengoptimalkan rantai pasok | Pengurangan stockout dan overstock | Stockout reduction ≥ 10% |
| 4 | Meningkatkan produktivitas pertanian | Peningkatan yield per hektar | Yield improvement ≥ 5% |
| 5 | Mengurangi downtime operasional | Pemeliharaan prediktif | Maintenance cost reduction ≥ 15% |

#### 1.3.2. Tujuan Teknis

| No | Tujuan | Metrik Keberhasilan |
| --- | --- | --- |
| 1 | Mengintegrasikan 6 modul transaksional | Semua data pipeline berfungsi dengan latency ≤ 5 menit |
| 2 | Menyediakan 8 dashboard interaktif | Semua dashboard berfungsi dengan load time ≤ 5 detik |
| 3 | Mengembangkan 5+ model AI/ML produksi | Akurasi ≥ 80%, inference time ≤ 3 detik |
| 4 | Membangun Knowledge Graph | 1M+ node, 5M+ relationship, query ≤ 5 detik |
| 5 | Menyediakan 5 fitur decision intelligence | What-if, scenario comparison, optimasi, decision log, outcome tracking |

#### 1.3.3. Tujuan SMART

| Tujuan | Spesifik | Measurable | Achievable | Relevant | Time-bound |
| --- | --- | --- | --- | --- | --- |
| T1 | 8 dashboard tersedia | Load ≤ 5 detik | Tim FE 2 orang | Kebutuhan eksekutif | Akhir bulan ke-3 |
| T2 | 5 model AI produksi | Akurasi ≥ 80% | Tim DS 3 orang | Kebutuhan operasional | Akhir bulan ke-5 |
| T3 | Knowledge Graph aktif | 1M+ node, query ≤ 5 detik | Tim KE 1 orang | Kebutuhan analisis | Akhir bulan ke-5 |
| T4 | Data pipeline aktif | Latency ≤ 5 menit | Tim DE 3 orang | Foundation platform | Akhir bulan ke-2 |
| T5 | Go-live produksi | 100% acceptance criteria | Semua tim | Project completion | Akhir bulan ke-6 |

### 1.4. Lingkup Proyek

#### 1.4.1. Ruang Lingkup (In Scope)

A. Data Platform & Pipeline

- Data Lake (MinIO/S3) untuk menyimpan data mentah

- Data Warehouse (Snowflake/BigQuery) untuk data terstruktur

- Data Mart per domain (Farm, Sales, Finance, Production)

- Change Data Capture (CDC) dari 6 modul transaksional

- ETL/ELT pipeline dengan monitoring data quality

- Metadata management dan data lineage

B. Business Intelligence

- 8 dashboard interaktif:

  - Executive Dashboard

  - Farm Dashboard

  - Production Dashboard

  - Supply Chain Dashboard

  - Sales Dashboard

  - Financial Dashboard

  - HCM Dashboard

  - Quality Dashboard

- KPI definition dan management

- KPI alert system (email, SMS, in-app)

- Scheduled reports (PDF, Excel, CSV)

- Ad-Hoc report builder (drag-and-drop)

- Drill-down dan filtering

C. AI/ML Platform

- 5 model produksi:

  - Demand Forecasting (Time Series)

  - Crop Yield Prediction (XGBoost/RF)

  - Inventory Forecasting (Prophet/ARIMA)

  - Predictive Maintenance (Survival Analysis)

  - Anomaly Detection (Isolation Forest/Autoencoder)

- Model registry dan versioning (MLflow)

- Model monitoring dan drift detection

- Explainable AI (SHAP/LIME)

- Feature store

D. Knowledge Graph

- Ontology definition (entity & relationship types)

- Graph ingestion dari data transaksional

- Graph query engine (GraphQL)

- Graph visualization (Cytoscape.js)

- Path discovery dan impact analysis

- Semantic search

- Provenance untuk setiap relationship

E. Decision Intelligence

- What-if analysis engine

- Scenario comparison

- Optimization engine (Linear Programming)

- Decision log system

- Outcome tracking & closed-loop learning

F. Integration & API

- Integrasi dengan P-FNE-01 (Foundation)

- Integrasi dengan P-FNE-02 (Agricultural Operations)

- Integrasi dengan P-FNE-03 (Supply Chain)

- Integrasi dengan P-FNE-04 (Production)

- Integrasi dengan P-FNE-05 (Commerce)

- Integrasi dengan P-FNE-06 (Finance & HCM)

- API Gateway & Backend for Frontend (BFF)

- RESTful APIs dan GraphQL endpoints

#### 1.4.2. Di Luar Lingkup (Out of Scope)

| No | Item | Alasan |
| --- | --- | --- |
| 1 | Pengembangan modul transaksional (P-FNE-02 s.d. 06) | Menjadi tanggung jawab tim proyek masing-masing |
| 2 | Infrastruktur hardware fisik | Disiapkan oleh tim infrastruktur korporat |
| 3 | Migrasi data dari sistem legacy | Dilakukan oleh tim data migration terpisah |
| 4 | Mobile app development | Disediakan oleh tim frontend mobile terpisah |
| 5 | Training end-user skala besar | Dilakukan oleh tim change management |
| 6 | Maintenance after go-live | Masuk phase operasional (handover ke tim support) |
| 7 | Pengembangan fitur IoT & Digital Twin | Menjadi tanggung jawab P-FNE-08 |
| 8 | Hardware IoT devices | Diluar lingkup software development |

#### 1.4.3. Batasan Proyek (Constraints)

| No | Batasan | Deskripsi |
| --- | --- | --- |
| 1 | Anggaran | Total anggaran maksimal Rp 3.5 Miliar |
| 2 | Waktu | Durasi maksimal 6 bulan (24 minggu) |
| 3 | Sumber Daya | Tim terbatas 10-15 orang |
| 4 | Teknologi | Harus menggunakan stack yang telah disetujui |
| 5 | Regulasi | Harus memenuhi regulasi keamanan data (ISO 27001, GDPR compliance) |
| 6 | Ketergantungan | Bergantung pada ketersediaan API dari modul transaksional |

#### 1.4.4. Asumsi Proyek (Assumptions)

| No | Asumsi | Deskripsi |
| --- | --- | --- |
| 1 | Ketersediaan Data | Semua modul transaksional menyediakan data melalui CDC |
| 2 | API Availability | Semua API dari modul lain tersedia sesuai jadwal |
| 3 | Infrastruktur | Cloud infrastructure tersedia dan siap digunakan |
| 4 | Tim Kompeten | Tim memiliki kompetensi teknis yang memadai |
| 5 | Stakeholder Support | Stakeholder mendukung dan tersedia untuk UAT |
| 6 | Third-Party Tools | Lisensi tools yang dibutuhkan tersedia |

### 1.5. Stakeholder Kunci

#### 1.5.1. Identifikasi Stakeholder

| Stakeholder | Peran | Keterlibatan | Kebutuhan |
| --- | --- | --- | --- |
| Project Sponsor | Direksi FNE | Approval, pendanaan, arahan strategis | ROI, timeline, risk exposure |
| Project Manager | Manajer Proyek | Manajemen proyek keseluruhan | Progress, budget, resource, quality |
| Product Owner | Business Analyst | Prioritas requirement, acceptance | Feature completeness, user satisfaction |
| Tech Lead | Lead Engineer | Arsitektur, teknis, quality | Technical quality, best practices |
| Data Scientist Lead | Lead DS | AI/ML strategy, model governance | Model accuracy, explainability |
| Data Engineer Lead | Lead DE | Data pipeline, ETL, data quality | Data freshness, quality |
| QA Lead | Lead QA | Testing strategy, quality assurance | Zero critical bugs, quality metrics |
| DevOps Lead | Lead DevOps | Infrastructure, deployment, security | Uptime, scalability, security |
| Key Users (Eksekutif) | Direksi, CEO, CFO | UAT, feedback, adoption | Strategic insights, dashboards |
| Key Users (Manajemen) | Farm, Ops, SC, Sales | UAT, feedback, adoption | Operational insights, reports |
| Representatif IT | IT Corporate | Integration support | Technical compatibility |

#### 1.5.2. Matrix Stakeholder

| Stakeholder | Power | Interest | Strategi |
| --- | --- | --- | --- |
| Project Sponsor | High | High | Manage Closely |
| Project Manager | High | High | Manage Closely |
| Product Owner | High | High | Manage Closely |
| Tech Lead | High | High | Manage Closely |
| Key Users (Eksekutif) | High | Medium | Keep Satisfied |
| Key Users (Manajemen) | Medium | High | Keep Informed |
| QA Lead | Medium | High | Keep Informed |
| DevOps Lead | Medium | High | Keep Informed |
| IT Corporate | Low | Medium | Monitor |

#### 1.5.3. RACI Matrix

| Aktivitas | Sponsor | PM | PO | Tech Lead | Dev | DS | DE | QA | DevOps |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Charter | A | R | C | C | - | - | - | - | - |
| PMP | A | R | C | C | - | - | - | - | - |
| Requirement Definition | C | C | R | C | C | C | C | C | - |
| Architecture Design | C | C | C | R | C | C | C | C | C |
| Data Pipeline Dev | - | C | C | C | - | - | R | C | C |
| BI Dashboard Dev | - | C | C | C | R | - | - | C | - |
| AI/ML Model Dev | - | C | C | C | - | R | - | C | C |
| Knowledge Graph Dev | - | C | C | C | - | - | C | C | C |
| Testing | - | C | C | C | C | C | C | R | C |
| UAT | C | C | R | C | - | - | - | - | - |
| Deployment | C | C | C | C | C | C | C | C | R |
| Acceptance | A | R | R | C | - | - | - | - | - |

R = Responsible, A = Accountable, C = Consulted, I = Informed

### 1.6. Anggaran & Durasi

#### 1.6.1. Estimasi Durasi

| Fase | Aktivitas | Durasi (Minggu) |
| --- | --- | --- |
| Fase 1 | Inisiasi & Perencanaan | 4 |
| Fase 2 | Data Platform & Infrastructure | 4 |
| Fase 3 | BI Dashboard & KPI | 4 |
| Fase 4 | AI/ML Model Development | 4 |
| Fase 5 | Knowledge Graph & Decision Intelligence | 3 |
| Fase 6 | Integration & Testing | 3 |
| Fase 7 | Deployment & Go-Live | 2 |
| Total |  | 24 Minggu (6 Bulan) |

#### 1.6.2. Estimasi Anggaran

| Kategori | Biaya (Rp) | Persentase |
| --- | --- | --- |
| Tenaga Kerja | 1.804.000.000 | 56.4% |
| Infrastruktur & Cloud | 506.000.000 | 15.8% |
| Lisensi & Software | 220.000.000 | 6.9% |
| Lain-lain | 250.000.000 | 7.8% |
| Subtotal | 2.780.000.000 | 86.9% |
| Contingency (15%) | 417.000.000 | 13.1% |
| TOTAL | 3.197.000.000 | 100% |

#### 1.6.3. Durasi Detail per Tim

| Tim | Jumlah Anggota | Keterlibatan | Total Man-Month |
| --- | --- | --- | --- |
| Project Management | 1 | 6 bulan | 6 |
| Tech Lead | 1 | 6 bulan | 6 |
| Backend Developer | 3 | 6 bulan | 18 |
| Frontend Developer | 2 | 5 bulan | 10 |
| Data Engineer | 3 | 4 bulan | 12 |
| Data Scientist | 2 | 4 bulan | 8 |
| ML Engineer | 1 | 4 bulan | 4 |
| Knowledge Engineer | 1 | 3 bulan | 3 |
| QA Engineer | 2 | 5 bulan | 10 |
| DevOps Engineer | 1 | 4 bulan | 4 |
| Business Analyst | 1 | 4 bulan | 4 |
| Total | 18 |  | 85 Man-Month |

### 1.7. Kriteria Keberhasilan

#### 1.7.1. Kriteria Keberhasilan Proyek

| No | Kriteria | Target | Metode Pengukuran |
| --- | --- | --- | --- |
| 1 | Data Platform | 100% data pipeline berfungsi | System testing, data validation |
| 2 | BI Dashboard | 8 dashboard dengan load ≤ 5 detik | Performance testing, UAT |
| 3 | AI/ML Models | 5 model dengan akurasi ≥ 80% | Model evaluation, UAT |
| 4 | Knowledge Graph | 1M+ node, query ≤ 5 detik | System testing |
| 5 | Decision Intelligence | 5 fitur berfungsi | Functional testing, UAT |
| 6 | Integration | 100% integration test passed | Integration testing |
| 7 | User Satisfaction | ≥ 4.0/5.0 | User satisfaction survey |
| 8 | Budget | ≤ Rp 3.5 Miliar | Financial tracking |
| 9 | Timeline | ≤ 6 bulan (24 minggu) | Schedule tracking |
| 10 | Security | Zero critical vulnerabilities | Security testing |

#### 1.7.2. Kriteria Keberhasilan Bisnis

| No | Kriteria | Target | Metode Pengukuran |
| --- | --- | --- | --- |
| 1 | Efisiensi Operasional | Meningkat 15-20% | Post-implementation comparison |
| 2 | Pengurangan Stockout | ≥ 10% | Inventory metrics comparison |
| 3 | Peningkatan Yield | 5-10% | Yield metrics comparison |
| 4 | Waktu Analisis | Dari hari ke menit | User feedback, time tracking |
| 5 | ROI | ≥ 15% dalam 2 tahun | Financial analysis |

### 1.8. Sanksi & Reward

#### 1.8.1. Reward System

| Pencapaian | Reward |
| --- | --- |
| Go-live tepat waktu | Bonus 10% gaji untuk semua anggota |
| User satisfaction > 4.5/5.0 | Bonus tambahan 5% |
| Zero critical bugs di production | Team dinner + sertifikat |
| Best performer per sprint | Voucher/pengakuan |

#### 1.8.2. Sanksi

| Pelanggaran | Sanksi |
| --- | --- |
| Miss deadline > 1 minggu tanpa alasan jelas | Performance improvement plan |
| Kualitas dibawah standar berulang | Review dan coaching |
| Breach security/data privacy | Sesuai kebijakan perusahaan |
| Pelanggaran integritas | Pembebasan tugas |

### 1.9. Definisi & Singkatan

#### 1.9.1. Istilah & Definisi

| Istilah | Definisi |
| --- | --- |
| Actionable Insights | Wawasan yang dapat langsung ditindaklanjuti untuk perbaikan |
| CDC | Change Data Capture - menangkap perubahan data secara real-time |
| Data Lake | Repositori data mentah dalam format asli |
| Data Warehouse | Repositori data terstruktur untuk analisis |
| Digital Twin | Representasi digital dari aset fisik |
| ETL | Extract, Transform, Load - proses pemindahan data |
| Explainable AI | Kemampuan AI untuk menjelaskan prediksinya |
| Knowledge Graph | Representasi data sebagai graph dengan node dan relationship |
| OEE | Overall Equipment Effectiveness - metrik efisiensi produksi |
| Ontology | Definisi formal tentang entity dan relasi dalam domain |
| Provenance | Asal-usul data/relationship |
| What-If Analysis | Analisis skenario dengan mengubah parameter |

#### 1.9.2. Singkatan

| Singkatan | Kepanjangan |
| --- | --- |
| AI | Artificial Intelligence |
| API | Application Programming Interface |
| BI | Business Intelligence |
| BFF | Backend for Frontend |
| CAPEX | Capital Expenditure |
| CCB | Change Control Board |
| CDC | Change Data Capture |
| CI/CD | Continuous Integration / Continuous Delivery |
| CRM | Customer Relationship Management |
| ELT | Extract, Load, Transform |
| ERP | Enterprise Resource Planning |
| ETL | Extract, Transform, Load |
| FNE | Farm Nation Enterprise |
| HCM | Human Capital Management |
| IAM | Identity and Access Management |
| IoT | Internet of Things |
| KPI | Key Performance Indicator |
| ML | Machine Learning |
| OEE | Overall Equipment Effectiveness |
| PMP | Project Management Plan |
| RBAC | Role-Based Access Control |
| SLA | Service Level Agreement |
| SSOT | Single Source of Truth |
| UAT | User Acceptance Testing |
| UOM | Unit of Measure |
| WBS | Work Breakdown Structure |

# BAB 2: MANAJEMEN INTEGRASI PROYEK (PMBOK Area 1)

## 2.1. Tujuan Manajemen Integrasi

Manajemen integrasi proyek bertujuan untuk memastikan koordinasi dan sinkronisasi seluruh komponen proyek, termasuk perencanaan, eksekusi, dan pengendalian perubahan. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Koordinasi Efektif | Memastikan semua elemen proyek (tim, teknologi, proses) bekerja secara terintegrasi |
| 2 | Keselarasan Strategis | Memastikan hasil proyek selaras dengan tujuan bisnis FNE |
| 3 | Pengendalian Perubahan | Mengelola perubahan dengan disiplin untuk meminimalkan dampak negatif |
| 4 | Kontinuitas Proyek | Memastikan kelancaran transisi antar fase proyek |
| 5 | Dokumentasi Terintegrasi | Memastikan semua dokumentasi proyek terintegrasi dan mudah diakses |

## 2.2. Project Charter

### 2.2.1. Project Charter - Intelligence & Decision Platform (P-FNE-07)

| Elemen | Detail |
| --- | --- |
| Nama Proyek | Intelligence & Decision Platform (P-FNE-07) |
| Project Sponsor | [Nama], Direksi Farm Nation Enterprise |
| Project Manager | [Nama], PMP Certified |
| Tanggal Mulai | [Tanggal], Minggu ke-1 |
| Tanggal Selesai Target | [Tanggal], Minggu ke-24 |
| Durasi | 6 Bulan (24 Minggu) |

#### Tujuan Bisnis

- Meningkatkan kecepatan pengambilan keputusan dari hari ke menit

- Meningkatkan efisiensi operasional sebesar 15-20%

- Mengurangi stockout sebesar 10% melalui forecasting yang akurat

- Meningkatkan yield pertanian sebesar 5-10%

- Mengurangi biaya pemeliharaan sebesar 15% melalui predictive maintenance

#### Manfaat yang Diharapkan

| Manfaat | Deskripsi | Kuantifikasi |
| --- | --- | --- |
| Pengambilan Keputusan | Akses real-time ke data dan wawasan | Waktu analisis: dari 2-3 hari menjadi < 5 menit |
| Efisiensi Operasional | Optimalisasi penggunaan sumber daya | Efisiensi meningkat 15-20% |
| Pengurangan Waste | Mengurangi overproduction dan stockout | Stockout turun 10%, overstock turun 15% |
| Peningkatan Produktivitas | Yield pertanian meningkat | Yield naik 5-10% |
| Pengurangan Downtime | Pemeliharaan prediktif | Downtime turun 20% |
| Kompetitif | Keunggulan kompetitif melalui data-driven | ROI > 15% dalam 2 tahun |

#### Kriteria Keberhasilan

| No | Kriteria | Target | Verifikasi |
| --- | --- | --- | --- |
| 1 | Data Pipeline | 100% berfungsi, latency ≤ 5 menit | System testing, data validation |
| 2 | BI Dashboard | 8 dashboard, load ≤ 5 detik | Performance testing, UAT |
| 3 | AI/ML Models | 5 model, akurasi ≥ 80%, inference ≤ 3 detik | Model evaluation, UAT |
| 4 | Knowledge Graph | 1M+ node, query ≤ 5 detik | System testing |
| 5 | Decision Intelligence | 5 fitur berfungsi | Functional testing, UAT |
| 6 | User Satisfaction | ≥ 4.0/5.0 | Survey |
| 7 | Anggaran | ≤ Rp 3.5 Miliar | Financial tracking |
| 8 | Timeline | ≤ 6 bulan | Schedule tracking |

#### Anggaran & Sumber Daya

| Komponen | Detail |
| --- | --- |
| Anggaran Total | Rp 3.197.000.000 |
| Sumber Daya | 10-15 orang (18 posisi) |
| Infrastruktur | Cloud-based (Kubernetes, Snowflake, Neo4j) |

#### Milestone Utama

| Milestone | Target Tanggal | Deliverable |
| --- | --- | --- |
| M0: Project Kick-off | Minggu 1 | Project Charter, PMP |
| M1: Data Platform Complete | Minggu 8 | Data Lake, DW, ETL, CDC |
| M2: BI Dashboard Complete | Minggu 12 | 8 Dashboard, KPI, Alert |
| M3: AI/ML Models Complete | Minggu 16 | 5 Model Produksi |
| M4: Graph & Decision Complete | Minggu 18 | Knowledge Graph, Decision Intelligence |
| M5: Integration & UAT Complete | Minggu 22 | SIT, UAT Sign-off |
| M6: Go-Live | Minggu 24 | Production Deployment |

#### Project Approvals

| Peran | Tanda Tangan | Tanggal |
| --- | --- | --- |
| Project Sponsor |  |  |
| Project Manager |  |  |
| Product Owner |  |  |
| Tech Lead |  |  |

### 2.2.2. Project Charter Approval Process

text

┌─────────────────────────────────────────────────────────────────────┐

│                    PROJECT CHARTER APPROVAL FLOW                    │

├─────────────────────────────────────────────────────────────────────┤

│                                                                      │

│  1. DRAFT PROJECT CHARTER                                           │

│     (Project Manager)                                               │

│     ↓                                                               │

│  2. REVIEW BY TECH LEAD & PRODUCT OWNER                             │

│     - Teknis: validasi scope dan architecture                       │

│     - Bisnis: validasi tujuan dan benefit                           │

│     ↓                                                               │

│  3. REVIEW BY KEY STAKEHOLDERS                                      │

│     - Pengguna kunci: validasi kebutuhan                            │

│     - Tim IT: validasi infrastruktur                                │

│     ↓                                                               │

│  4. FINAL APPROVAL BY SPONSOR                                       │

│     - Project Sponsor menandatangani Project Charter                │

│     ↓                                                               │

│  5. COMMUNICATE APPROVAL                                            │

│     - Project Charter dikomunikasikan ke semua stakeholder          │

│     - Kick-off meeting dijadwalkan                                  │

│                                                                      │

└─────────────────────────────────────────────────────────────────────┘

## 2.3. Project Management Plan (PMP) Development

### 2.3.1. Metodologi Pengembangan PMP

PMP ini dikembangkan dengan pendekatan iteratif sesuai dengan sifat proyek yang agile:

| Fase | Aktivitas | Output | Penanggung Jawab |
| --- | --- | --- | --- |
| Fase 1: Inisiasi | Identifikasi requirement dan stakeholder | Draft PMP | Project Manager |
| Fase 2: Perencanaan | Pengembangan detail 10 area manajemen | PMP Lengkap | PM + Tim Lead |
| Fase 3: Review | Review oleh stakeholder | Feedback & Revisi | Semua Stakeholder |
| Fase 4: Approval | Finalisasi dan approval | PMP Final | Project Sponsor |
| Fase 5: Update | Update selama proyek berjalan | PMP Revisi | Project Manager |

### 2.3.2. Struktur PMP

text

Project Management Plan (PMP)

│

├── BAB 1: Pendahuluan

├── BAB 2: Manajemen Integrasi Proyek

├── BAB 3: Manajemen Lingkup Proyek

├── BAB 4: Manajemen Penjadwalan Proyek

├── BAB 5: Manajemen Biaya Proyek

├── BAB 6: Manajemen Kualitas Proyek

├── BAB 7: Manajemen Sumber Daya Proyek

├── BAB 8: Manajemen Komunikasi Proyek

├── BAB 9: Manajemen Risiko Proyek

├── BAB 10: Manajemen Pengadaan Proyek

├── BAB 11: Manajemen Pemangku Kepentingan

└── BAB 12: Lampiran

### 2.3.3. PMP Review & Update Schedule

| Aktivitas | Frekuensi | Penanggung Jawab |
| --- | --- | --- |
| PMP Review | Setiap milestone | PM + Tech Lead |
| PMP Update | Setiap perubahan signifikan | PM |
| PMP Communication | Setiap update | PM |
| PMP Audit | Setiap sprint review | QA Lead |

## 2.4. Manajemen Perubahan (Change Management)

### 2.4.1. Change Control System

#### 2.4.1.1. Prosedur Perubahan

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        CHANGE MANAGEMENT PROCESS FLOW                       │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  STEP 1: IDENTIFIKASI PERUBAHAN                                              │

│  - Siapa saja dapat mengidentifikasi perubahan                              │

│  - Perubahan didokumentasikan dalam Change Request Form                     │

│  - Kategorikan: Scope, Schedule, Budget, Resource, Technical                │

│  ↓                                                                           │

│  STEP 2: SUBMIT CHANGE REQUEST                                              │

│  - Isi Form CR-XXX dengan detail perubahan                                 │

│  - Berikan justifikasi dan benefit                                          │

│  - Sign off oleh pengaju                                                    │

│  ↓                                                                           │

│  STEP 3: ASSESSMENT & ANALISIS DAMPAK                                      │

│  - Analisis dampak pada: Scope, Schedule, Cost, Quality, Risk              │

│  - Identifikasi alternatif solusi                                           │

│  - Estimasi effort dan biaya                                                │

│  ↓                                                                           │

│  STEP 4: REVIEW & APPROVAL                                                  │

│  ┌─────────────────────────────────────┐                                   │

│  │  TIPE PERUBAHAN     │  APPROVAL BY  │                                   │

│  ├─────────────────────────────────────┤                                   │

│  │  Minor Change       │  PM + TL      │                                   │

│  │  (≤ 5% effort)      │               │                                   │

│  ├─────────────────────────────────────┤                                   │

│  │  Medium Change      │  PM + TL +    │                                   │

│  │  (5-15% effort)     │  Product Owner│                                   │

│  ├─────────────────────────────────────┤                                   │

│  │  Major Change       │  CCB          │                                   │

│  │  (> 15% effort)     │  (Full Board) │                                   │

│  └─────────────────────────────────────┘                                   │

│  ↓                                                                           │

│  STEP 5: IMPLEMENTASI PERUBAHAN                                             │

│  - Update project plan dan PMP                                              │

│  - Update WBS dan schedule                                                  │

│  - Update budget jika diperlukan                                            │

│  - Komunikasikan ke tim                                                    │

│  ↓                                                                           │

│  STEP 6: VERIFIKASI & CLOSURE                                              │

│  - Verifikasi implementasi                                                  │

│  - Update dokumentasi                                                       │

│  - Close change request                                                     │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

#### 2.4.1.2. Change Request Form (Form CR-XXX)

| Field | Deskripsi |
| --- | --- |
| Change Request ID | CR-XXX (auto-generated) |
| Tanggal Submit | [Tanggal] |
| Pengaju | [Nama & Jabatan] |
| Kategori Perubahan | ☐ Scope ☐ Schedule ☐ Budget ☐ Resource ☐ Technical ☐ Other |
| Deskripsi Perubahan | [Deskripsi detail perubahan yang diusulkan] |
| Alasan/Justifikasi | [Alasan mengapa perubahan diperlukan] |
| Benefit yang Diharapkan | [Manfaat dari perubahan] |
| Dampak pada Scope | [Scope bertambah/berkurang?] |
| Dampak pada Schedule | [Penambahan waktu estimasi] |
| Dampak pada Budget | [Penambahan biaya estimasi] |
| Dampak pada Quality | [Pengaruh pada kualitas] |
| Dampak pada Risk | [Risk baru atau berubah] |
| Alternatif Solusi | [Opsi lain yang dipertimbangkan] |
| Rekomendasi | [Rekomendasi dari PM] |
| Approval Status | ☐ Pending ☐ Approved ☐ Rejected ☐ Deferred |
| Tanggal Approval | [Tanggal] |
| Approved By | [Nama & Jabatan] |

### 2.4.2. Change Control Board (CCB)

#### 2.4.2.1. Komposisi CCB

| Anggota CCB | Peran | Tanggung Jawab |
| --- | --- | --- |
| Project Sponsor | Ketua | Approval final untuk perubahan besar |
| Project Manager | Sekretaris | Mengelola proses perubahan, dokumentasi |
| Product Owner | Anggota | Evaluasi dampak bisnis |
| Tech Lead | Anggota | Evaluasi dampak teknis |
| Lead QA | Anggota | Evaluasi dampak kualitas |
| Lead Data Scientist | Anggota | Evaluasi dampak pada AI/ML |
| Key User Representative | Anggota | Evaluasi dampak pengguna |

#### 2.4.2.2. Prosedur CCB

| Step | Aktivitas | Detail |
| --- | --- | --- |
| 1 | Panggilan Meeting | CCB meeting diadakan jika ada change request dengan status "PENDING" |
| 2 | Presentasi | PM mempresentasikan change request dan analisis dampak |
| 3 | Diskusi | Anggota CCB berdiskusi dan bertanya |
| 4 | Voting | Voting untuk keputusan (majority vote) |
| 5 | Keputusan | Approved, Rejected, atau Deferred |
| 6 | Notifikasi | Hasil dikomunikasikan ke pengaju dan tim |

### 2.4.3. Change Impact Analysis Template

| Aspek | Analisis | Keterangan |
| --- | --- | --- |
| Scope Impact |  |  |
| - WBS Element | [Elemen WBS yang terdampak] |  |
| - Deliverable | [Deliverable yang terdampak] |  |
| - Scope Change | [Bertambah/Berkurang/Modifikasi] |  |
| Schedule Impact |  |  |
| - Effort Estimasi | [Person-days tambahan] |  |
| - Timeline Impact | [Penambahan hari/minggu] |  |
| - Critical Path | [Ya/Tidak] |  |
| Cost Impact |  |  |
| - Direct Cost | [Rp tambahan] |  |
| - Indirect Cost | [Rp tambahan] |  |
| - Total Cost | [Rp tambahan] |  |
| Quality Impact |  |  |
| - Quality Standard | [Terpengaruh/Tidak] |  |
| - Risk to Quality | [Risiko kualitas] |  |
| Risk Impact |  |  |
| - New Risks | [Risiko baru] |  |
| - Risk Severity | [Dampak risiko] |  |
| Resource Impact |  |  |
| - Additional Resources | [Tambahan SDM] |  |
| - Skill Requirement | [Kebutuhan skill baru] |  |
| Recommendation | [Rekomendasi CCB] |  |

## 2.5. Proses Integrasi & Deployment

### 2.5.1. CI/CD Pipeline Architecture

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                           CI/CD PIPELINE ARCHITECTURE                      │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ┌──────────┐     ┌──────────┐     ┌──────────┐     ┌──────────┐          │

│  │  CODE    │────▶│  BUILD   │────▶│   TEST   │────▶│  STAGING │          │

│  │          │     │          │     │          │     │          │          │

│  │ - Git    │     │ - Unit   │     │ - Inte-  │     │ - Deploy │          │

│  │ - PR     │     │   Test   │     │   gration│     │ - QA     │          │

│  │ - Review │     │ - Lint   │     │ - Perf.  │     │ - UAT    │          │

│  └──────────┘     └──────────┘     └──────────┘     └────┬─────┘          │

│                                                           │                  │

│  ┌──────────┐     ┌──────────┐     ┌──────────┐     ┌───▼──────┐          │

│  │ MONITOR  │◀───▶│  DEPLOY  │◀───▶│  PROD    │◀───│ APPROVAL │          │

│  │          │     │          │     │          │     │          │          │

│  │ - Alert  │     │ - Blue/  │     │ - 99.9%  │     │ - Manual │          │

│  │ - Logging│     │   Green  │     │   uptime │     │   Gate   │          │

│  │ - Metrics│     │ - Canary │     │ - Scaling│     │ - Auto   │          │

│  └──────────┘     └──────────┘     └──────────┘     └──────────┘          │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

### 2.5.2. CI/CD Tools & Configuration

| Stage | Tool | Konfigurasi | Penanggung Jawab |
| --- | --- | --- | --- |
| Version Control | Git/GitHub | Branch strategy: main, develop, feature/, release/ | All Developers |
| Continuous Integration | GitHub Actions / Jenkins | Build on every PR, run unit tests, linting | DevOps |
| Code Quality | SonarQube | Quality gate: A Rating, 0 critical issues | DevOps + TL |
| Security Scan | OWASP ZAP, Snyk | Scan dependencies, container images | DevOps |
| Artifact Repository | Docker Registry, Nexus | Store artifacts, versioning | DevOps |
| Deployment | Helm, ArgoCD | Deploy to K8s, blue-green deployment | DevOps |
| Testing | JUnit, PyTest, Jest, Selenium | Automated testing suite | QA |
| Monitoring | Prometheus, Grafana, ELK | Metrics, logs, alerts | DevOps |

### 2.5.3. Deployment Strategy

#### 2.5.3.1. Blue-Green Deployment

text

┌─────────────────────────────────────────────────────────────────────────────┐

│                        BLUE-GREEN DEPLOYMENT                               │

├─────────────────────────────────────────────────────────────────────────────┤

│                                                                              │

│  ┌─────────────────────────────────────────────────────────────────────┐   │

│  │                         LOAD BALANCER                               │   │

│  └─────────────────────────────────────────────────────────────────────┘   │

│                          │                        │                         │

│                          ▼                        ▼                         │

│  ┌──────────────────────────────────┐  ┌──────────────────────────────────┐│

│  │          BLUE (Live)             │  │        GREEN (Staging)           ││

│  │  ┌────────────────────────────┐ │  │  ┌────────────────────────────┐ ││

│  │  │  Version v1.0.0            │ │  │  │  Version v1.1.0            │ ││

│  │  │  - All services            │ │  │  │  - All services            │ ││

│  │  │  - Database v1             │ │  │  │  - Database v2 (migration) │ ││

│  │  └────────────────────────────┘ │  │  └────────────────────────────┘ ││

│  └──────────────────────────────────┘  └──────────────────────────────────┘│

│                                                                              │

│  Switch traffic: Blue → Green (Zero Downtime)                               │

│                                                                              │

└─────────────────────────────────────────────────────────────────────────────┘

#### 2.5.3.2. Canary Release (untuk AI/ML Models)

| Stage | Traffic Split | Durasi | Verifikasi |
| --- | --- | --- | --- |
| Stage 1 | 5% traffic ke versi baru | 2 jam | Monitor error rate, latency |
| Stage 2 | 25% traffic ke versi baru | 4 jam | Monitor metrics, user feedback |
| Stage 3 | 75% traffic ke versi baru | 8 jam | Full monitoring, performance |
| Stage 4 | 100% traffic ke versi baru | - | Rollback plan ready |

### 2.5.4. Rollback Plan

| Skenario | Trigger | Rollback Action | RTO |
| --- | --- | --- | --- |
| Deployment Failed | Pipeline error | Otomatis rollback ke versi sebelumnya | < 5 menit |
| Performance Degradation | Latency > threshold | Manual rollback via ArgoCD | < 10 menit |
| Critical Bug Found | Error rate > 5% | Manual rollback via ArgoCD | < 10 menit |
| Security Vulnerability | Security scan fails | Emergency rollback | < 5 menit |
| Database Migration Failed | Migration error | Restore dari backup + rollback | < 30 menit |

### 2.5.5. Environment Strategy

| Environment | Tujuan | SLA | Access |
| --- | --- | --- | --- |
| Development | Developer testing, local development | 8x5 | All developers |
| Integration | CI/CD testing, integration testing | 8x5 | CI/CD pipeline, QA |
| Staging | QA testing, UAT, performance testing | 8x5 | QA, Key Users |
| Production | Live system, end-user access | 24x7, 99.9% | All users |

## 2.6. Proses Integrasi dengan Proyek Lain

### 2.6.1. Dependency Matrix

| Proyek | Dependency | Integration Point | Timeline |
| --- | --- | --- | --- |
| P-FNE-01 (Foundation) | IAM, Master Data, Audit, Workflow | API Authentication, Data Models | Minggu 1-24 |
| P-FNE-02 (Ag. Ops) | Farm, Crop, Livestock, Harvest Data | CDC to Data Lake, API | Minggu 2-24 |
| P-FNE-03 (Supply Chain) | Procurement, Inventory, Warehouse | CDC to Data Lake, API | Minggu 2-24 |
| P-FNE-04 (Production) | Production Order, BOM, Execution | CDC to Data Lake, API | Minggu 2-24 |
| P-FNE-05 (Commerce) | Sales, CRM, Logistics | CDC to Data Lake, API | Minggu 2-24 |
| P-FNE-06 (Finance) | Accounting, Costing, HCM | CDC to Data Lake, API | Minggu 2-24 |
| P-FNE-08 (Advanced) | IoT, Digital Twin, Simulation | Data provision, API | Minggu 18-24 |

### 2.6.2. Integration Testing Strategy

| Level | Deskripsi | Tools | Penanggung Jawab |
| --- | --- | --- | --- |
| Unit Integration | Testing each service with mock dependencies | JUnit/Mockito | Developer |
| Service Integration | Testing communication between services | Postman, Newman | Developer + QA |
| System Integration | Testing full system with all dependencies | Selenium, JMeter | QA |
| End-to-End | Testing complete user journeys | Cypress, Playwright | QA |
| Data Integration | Testing data flow between systems | Custom validation | Data Engineer |

### 2.6.3. Integration Schedule

| Fase | Aktivitas | Minggu | Penanggung Jawab |
| --- | --- | --- | --- |
| Phase 1 | Setup API contracts, mock services | 1-2 | Backend Lead |
| Phase 2 | Internal service integration | 3-8 | Backend Team |
| Phase 3 | Integration with P-FNE-01 (Foundation) | 4-10 | Backend + Data Engineer |
| Phase 4 | Integration with P-FNE-02, 03, 04 | 6-14 | Data Engineer |
| Phase 5 | Integration with P-FNE-05, 06 | 8-16 | Data Engineer |
| Phase 6 | System Integration Testing (SIT) | 19-20 | QA |
| Phase 7 | End-to-End Testing | 21-22 | QA + Key Users |

## 2.7. Dokumentasi Proyek

### 2.7.1. Dokumentasi yang Diperlukan

| No | Dokumen | Penanggung Jawab | Format | Update Frequency |
| --- | --- | --- | --- | --- |
| 1 | Project Charter | PM | Word/PDF | Once |
| 2 | Project Management Plan | PM | Word/PDF | As needed |
| 3 | WBS Dictionary | PM | Excel | As needed |
| 4 | Requirement Specification | BA/PO | Word/PDF | Per sprint |
| 5 | Architecture Document | Tech Lead | Markdown/PDF | As needed |
| 6 | API Documentation | Backend Lead | Swagger/OpenAPI | Per release |
| 7 | Database Schema | Data Engineer | ERD | As needed |
| 8 | User Manual | BA | Markdown/PDF | Per release |
| 9 | Test Plan & Cases | QA Lead | Excel/Test Management | Per sprint |
| 10 | UAT Plan | PM + PO | Word/PDF | Pre-UAT |
| 11 | Deployment Guide | DevOps | Markdown/PDF | As needed |
| 12 | Operations Manual | DevOps + Tech Lead | Markdown/PDF | Pre-go-live |
| 13 | Risk Register | PM | Excel/RAID | Per sprint |
| 14 | Decision Log | PM | Excel | As needed |
| 15 | Lessons Learned | PM | Word/PDF | Per milestone |

### 2.7.2. Dokumentasi Repository

text

/team-repo/

├── /project-management/

│   ├── /charter/

│   ├── /pmp/

│   ├── /wbs/

│   ├── /risk-register/

│   └── /reports/

├── /requirements/

│   ├── /functional/

│   └── /non-functional/

├── /architecture/

│   ├── /system/

│   ├── /data/

│   ├── /integration/

│   └── /security/

├── /development/

│   ├── /api/

│   ├── /database/

│   └── /models/

├── /testing/

│   ├── /plans/

│   ├── /cases/

│   └── /reports/

└── /operations/

├── /deployment/

├── /monitoring/

└── /runbooks/

## 2.8. Lessons Learned & Knowledge Management

### 2.8.1. Lessons Learned Process

| Fase | Aktivitas | Output | Penanggung Jawab |
| --- | --- | --- | --- |
| Capture | Identifikasi lesson learned selama sprint | Notes, issues, solutions | All team members |
| Document | Dokumentasikan lesson learned di repository | Document per milestone | PM |
| Analyze | Analisis root cause dan impact | Analysis report | PM + Tech Lead |
| Share | Sharing dengan tim dan stakeholder | Presentation | PM |
| Apply | Terapkan improvement di sprint berikutnya | Action items | PM + Tech Lead |

### 2.8.2. Knowledge Sharing Schedule

| Aktivitas | Frekuensi | Peserta |
| --- | --- | --- |
| Sprint Retrospective | Setiap 2 minggu | All team |
| Tech Sharing Session | 2 minggu sekali | Technical team |
| Milestone Retrospective | Setiap milestone | PM + TL + Leads |
| Project Retrospective | Akhir proyek | All team |

## 2.9. Project Closure

### 2.9.1. Closure Criteria

| No | Kriteria | Verifikasi |
| --- | --- | --- |
| 1 | Semua deliverables diserahkan | Acceptance sign-off |
| 2 | Semua acceptance criteria terpenuhi | UAT sign-off |
| 3 | Semua dokumentasi final | Document review |
| 4 | Handover ke tim operasional | Handover meeting |
| 5 | Lessons learned terdokumentasi | Retrospective |
| 6 | Project financials closed | Finance report |

### 2.9.2. Closure Activities

| Aktivitas | Deskripsi | Penanggung Jawab |
| --- | --- | --- |
| Final Acceptance | User Acceptance Testing sign-off | PO + Key Users |
| Handover to Ops | Handover dokumentasi dan training ke tim ops | DevOps + Tech Lead |
| Final Financial Report | Laporan pengeluaran akhir vs budget | PM + Finance |
| Lessons Learned Report | Dokumentasi lesson learned final | PM |
| Project Closure Report | Laporan akhir proyek | PM |
| Celebration | Project closure celebration | PM + Sponsor |

# BAB 3: MANAJEMEN LINGKUP PROYEK (PMBOK Area 2)

## 3.1. Tujuan Manajemen Lingkup

Manajemen lingkup proyek bertujuan untuk memastikan proyek mencakup semua pekerjaan yang diperlukan (dan hanya yang diperlukan) untuk menyelesaikan proyek dengan sukses. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Definisi Lingkup yang Jelas | Memastikan semua stakeholder memiliki pemahaman yang sama tentang apa yang termasuk dan tidak termasuk dalam proyek |
| 2 | Pengendalian Lingkup | Mencegah scope creep dengan mengelola perubahan lingkup secara disiplin |
| 3 | Decomposition | Memecah pekerjaan menjadi komponen yang lebih kecil dan terkelola (WBS) |
| 4 | Verifikasi Lingkup | Memastikan deliverables sesuai dengan requirement yang telah disetujui |
| 5 | Traceability | Memastikan setiap requirement dapat dilacak hingga deliverable |

## 3.2. Scope Statement

### 3.2.1. Deskripsi Lingkup Proyek P-FNE-07

Proyek Intelligence & Decision Platform (P-FNE-07) akan mengembangkan platform terintegrasi yang berfungsi sebagai pusat kecerdasan bisnis untuk ekosistem Super ERP Farm Nation Enterprise. Platform ini akan:

A. Data Platform & Pipeline

- Mengumpulkan data dari 6 modul transaksional (P-FNE-02 s.d. P-FNE-06) melalui CDC dan ETL pipeline

- Menyimpan data mentah di Data Lake (MinIO/S3)

- Mentransformasi dan menyimpan data di Data Warehouse (Snowflake/BigQuery)

- Menyediakan Data Mart per domain (Farm, Sales, Finance, Production)

- Memastikan kualitas data dengan monitoring dan alert

- Menyediakan data lineage dan metadata management

B. Business Intelligence

- Menyediakan 8 dashboard interaktif untuk berbagai level manajemen

- Mendukung drill-down, filtering, dan ekspor data

- Menyediakan KPI definition dan management

- Mengirim alert jika KPI di bawah target atau di atas threshold

- Menghasilkan laporan terjadwal (PDF, Excel, CSV)

- Menyediakan ad-hoc report builder dengan drag-and-drop

C. AI/ML Platform

- Mengembangkan 5+ model AI/ML produksi:

  - Demand Forecasting (Time Series)

  - Crop Yield Prediction (XGBoost/Random Forest)

  - Inventory Forecasting (Prophet/ARIMA)

  - Predictive Maintenance (Survival Analysis/XGBoost)

  - Anomaly Detection (Isolation Forest/Autoencoder)

- Menyediakan model registry, versioning, dan monitoring

- Memberikan explainable AI (SHAP/LIME)

- Menyediakan feature store

D. Knowledge Graph

- Mendefinisikan ontology (entity dan relationship types)

- Menginjeksi data dari database transaksional ke Neo4j

- Menyediakan query engine (GraphQL)

- Menyediakan visualisasi graph dan path discovery

- Mendukung impact analysis dan semantic search

- Menyimpan provenance setiap relationship

E. Decision Intelligence

- Menyediakan what-if analysis engine

- Mendukung scenario comparison

- Menyediakan optimization engine (Linear Programming)

- Mencatat decision log untuk audit

- Mendukung outcome tracking dan closed-loop learning

F. Integration & API

- Terintegrasi dengan P-FNE-01 (Foundation) untuk IAM dan Master Data

- Terintegrasi dengan P-FNE-02 s.d. P-FNE-06 untuk data ingestion

- Menyediakan RESTful APIs dan GraphQL endpoints

- Menyediakan API Gateway dan BFF untuk frontend

### 3.2.2. Batasan Lingkup (Boundaries)

#### In Scope (Ruang Lingkup)

| Kategori | Item | Deskripsi |
| --- | --- | --- |
| Data | Data Ingestion | CDC dari 6 modul transaksional (P-FNE-02 s.d. P-FNE-06) |
| Data | Data Storage | Data Lake (MinIO/S3), Data Warehouse (Snowflake), Data Mart |
| Data | Data Processing | ETL/ELT pipeline dengan Apache Spark/Airflow |
| Data | Data Quality | Quality rules, monitoring, alerting |
| BI | Dashboards | 8 dashboard: Executive, Farm, Production, Supply Chain, Sales, Finance, HCM, Quality |
| BI | KPI | KPI definition, management, alert system |
| BI | Reports | Scheduled reports, ad-hoc report builder |
| AI/ML | Models | 5+ models: Demand Forecasting, Crop Yield, Inventory Forecasting, Predictive Maintenance, Anomaly Detection |
| AI/ML | MLOps | Model registry, monitoring, explainability, feature store |
| Knowledge Graph | Graph | Ontology, ingestion, query, visualization, impact analysis, semantic search |
| Decision | What-If | What-if analysis engine, scenario comparison |
| Decision | Optimization | Optimization engine (LP), decision log, outcome tracking |
| Integration | API | RESTful APIs, GraphQL, API Gateway, BFF |
| Frontend | UI | React-based web application for all dashboards and features |

#### Out of Scope (Diluar Lingkup)

| No | Item | Alasan / Keterangan |
| --- | --- | --- |
| 1 | Pengembangan modul transaksional (P-FNE-02 s.d. 06) | Menjadi tanggung jawab tim proyek masing-masing |
| 2 | Infrastruktur hardware fisik | Disiapkan oleh tim infrastruktur korporat |
| 3 | Migrasi data dari sistem legacy | Dilakukan oleh tim data migration terpisah |
| 4 | Mobile app development | Disediakan oleh tim frontend mobile terpisah |
| 5 | Training end-user skala besar | Dilakukan oleh tim change management |
| 6 | Maintenance after go-live | Masuk phase operasional (handover ke tim support) |
| 7 | Pengembangan fitur IoT & Digital Twin | Menjadi tanggung jawab P-FNE-08 |
| 8 | Hardware IoT devices | Diluar lingkup software development |
| 9 | Real-time operational systems | Fokus pada analytics dan decision support, bukan operational systems |
| 10 | Blockchain / Smart Contracts | Tidak termasuk dalam scope saat ini |

## 3.3. Work Breakdown Structure (WBS)

### 3.3.1. WBS Level 1-4

text

P-FNE-07: Intelligence & Decision Platform

│

├── 1.0 PROJECT MANAGEMENT (PM)

│   ├── 1.1 PMP & Planning

│   │   ├── 1.1.1 Project Charter

│   │   ├── 1.1.2 PMP Development

│   │   └── 1.1.3 Stakeholder Analysis

│   ├── 1.2 Communication & Reporting

│   │   ├── 1.2.1 Status Reporting (Weekly)

│   │   ├── 1.2.2 Stakeholder Communication

│   │   └── 1.2.3 Meeting Management

│   └── 1.3 Quality & Risk Management

│       ├── 1.3.1 Quality Planning

│       ├── 1.3.2 Risk Management

│       └── 1.3.3 Change Management

│

├── 2.0 DATA PLATFORM (Data Engineering)

│   ├── 2.1 Data Lake & Storage

│   │   ├── 2.1.1 Data Lake Setup (MinIO/S3)

│   │   ├── 2.1.2 Storage Architecture Design

│   │   └── 2.1.3 Data Partitioning Strategy

│   ├── 2.2 Data Warehouse & Data Mart

│   │   ├── 2.2.1 DW Schema Design (Star/Snowflake)

│   │   ├── 2.2.2 Data Mart Setup per Domain

│   │   └── 2.2.3 Materialized Views & Aggregates

│   ├── 2.3 Data Ingestion (CDC)

│   │   ├── 2.3.1 CDC Setup (Debezium + Kafka)

│   │   ├── 2.3.2 Consumer Configuration per Source

│   │   └── 2.3.3 Real-time Pipeline Monitoring

│   ├── 2.4 ETL/ELT Pipeline

│   │   ├── 2.4.1 Pipeline Orchestration (Airflow)

│   │   ├── 2.4.2 Data Transformation Logic

│   │   └── 2.4.3 Incremental Load Strategy

│   ├── 2.5 Data Quality & Monitoring

│   │   ├── 2.5.1 Quality Rules Definition

│   │   ├── 2.5.2 Quality Monitoring Dashboard

│   │   └── 2.5.3 Alert System for Data Quality

│   └── 2.6 Metadata & Data Lineage

│       ├── 2.6.1 Metadata Repository (Amundsen/DataHub)

│       ├── 2.6.2 Data Lineage Tracking

│       └── 2.6.3 Data Dictionary & Business Glossary

│

├── 3.0 BUSINESS INTELLIGENCE (BI)

│   ├── 3.1 Dashboard - Executive

│   │   ├── 3.1.1 KPI Cards (Revenue, Profit, Cash Flow, etc.)

│   │   ├── 3.1.2 Revenue & Profit Trend Charts

│   │   └── 3.1.3 Production & Sales Overview

│   ├── 3.2 Dashboard - Farm

│   │   ├── 3.2.1 Land Map with Status Overlay

│   │   ├── 3.2.2 Yield & Productivity Metrics

│   │   └── 3.2.3 Crop Cycle & Harvest Forecast

│   ├── 3.3 Dashboard - Production

│   │   ├── 3.3.1 Output & OEE Metrics

│   │   ├── 3.3.2 Defect Rate & Quality Metrics

│   │   └── 3.3.3 Downtime & Machine Status

│   ├── 3.4 Dashboard - Supply Chain

│   │   ├── 3.4.1 Inventory Level & Stockout Metrics

│   │   ├── 3.4.2 Supplier Performance Dashboard

│   │   └── 3.4.3 Procurement Status Overview

│   ├── 3.5 Dashboard - Sales

│   │   ├── 3.5.1 Revenue & Orders Metrics

│   │   ├── 3.5.2 Top Products & Customers

│   │   └── 3.5.3 Sales by Region & Category

│   ├── 3.6 Dashboard - Finance

│   │   ├── 3.6.1 P&L, Cash Flow, AR/AP Aging

│   │   ├── 3.6.2 Budget vs Actual Analysis

│   │   └── 3.6.3 Financial Ratios Dashboard

│   ├── 3.7 Dashboard - HCM

│   │   ├── 3.7.1 Headcount & Turnover Metrics

│   │   ├── 3.7.2 Attendance & Payroll Summary

│   │   └── 3.7.3 Employee Distribution & Demographics

│   ├── 3.8 Dashboard - Quality

│   │   ├── 3.8.1 Rejection Rate & Defect Trends

│   │   ├── 3.8.2 Non-conformance & CAR Status

│   │   └── 3.8.3 Quality Score by Product/Line

│   ├── 3.9 KPI Definition & Management

│   │   ├── 3.9.1 KPI Creation & Edit Form

│   │   ├── 3.9.2 KPI Formula Validation

│   │   └── 3.9.3 KPI Dashboard Assignment

│   ├── 3.10 KPI Alert System

│   │   ├── 3.10.1 Alert Configuration Form

│   │   ├── 3.10.2 Alert Engine & Scheduler

│   │   └── 3.10.3 Notification Service (Email/SMS/In-app)

│   ├── 3.11 Scheduled Report System

│   │   ├── 3.11.1 Report Template Management

│   │   ├── 3.11.2 Scheduler Configuration

│   │   └── 3.11.3 Report Generation & Delivery

│   └── 3.12 Ad-Hoc Report Builder

│       ├── 3.12.1 Drag-and-Drop Interface

│       ├── 3.12.2 Data Source & Field Selection

│       └── 3.12.3 Chart & Export Configuration

│

├── 4.0 AI/ML PLATFORM

│   ├── 4.1 Infrastructure & MLOps

│   │   ├── 4.1.1 MLflow Setup

│   │   ├── 4.1.2 Kubeflow Setup

│   │   └── 4.1.3 Development Environment

│   ├── 4.2 Model #1: Demand Forecasting

│   │   ├── 4.2.1 Data Preparation

│   │   ├── 4.2.2 Feature Engineering

│   │   ├── 4.2.3 Model Training (Prophet/LSTM)

│   │   ├── 4.2.4 Model Evaluation

│   │   └── 4.2.5 Model Deployment

│   ├── 4.3 Model #2: Crop Yield Prediction

│   │   ├── 4.3.1 Data Preparation

│   │   ├── 4.3.2 Feature Engineering

│   │   ├── 4.3.3 Model Training (XGBoost/RF)

│   │   ├── 4.3.4 Model Evaluation

│   │   └── 4.3.5 Model Deployment

│   ├── 4.4 Model #3: Inventory Forecasting

│   │   ├── 4.4.1 Data Preparation

│   │   ├── 4.4.2 Feature Engineering

│   │   ├── 4.4.3 Model Training (Prophet/ARIMA)

│   │   ├── 4.4.4 Model Evaluation

│   │   └── 4.4.5 Model Deployment

│   ├── 4.5 Model #4: Predictive Maintenance

│   │   ├── 4.5.1 Data Preparation

│   │   ├── 4.5.2 Feature Engineering

│   │   ├── 4.5.3 Model Training (Survival/XGBoost)

│   │   ├── 4.5.4 Model Evaluation

│   │   └── 4.5.5 Model Deployment

│   ├── 4.6 Model #5: Anomaly Detection

│   │   ├── 4.6.1 Data Preparation

│   │   ├── 4.6.2 Feature Engineering

│   │   ├── 4.6.3 Model Training (Isolation Forest/Autoencoder)

│   │   ├── 4.6.4 Model Evaluation

│   │   └── 4.6.5 Model Deployment

│   ├── 4.7 Model Registry & Versioning

│   │   ├── 4.7.1 Model Registration

│   │   ├── 4.7.2 Version Management

│   │   └── 4.7.3 Model Promotion (Staging → Production)

│   ├── 4.8 Model Monitoring & Drift Detection

│   │   ├── 4.8.1 Performance Monitoring Dashboard

│   │   ├── 4.8.2 Data Drift Detection

│   │   └── 4.8.3 Concept Drift Detection

│   ├── 4.9 Explainable AI (XAI)

│   │   ├── 4.9.1 SHAP Implementation

│   │   ├── 4.9.2 LIME Implementation

│   │   └── 4.9.3 Explanation API & UI

│   └── 4.10 Feature Store

│       ├── 4.10.1 Feature Definition

│       ├── 4.10.2 Feature Ingestion

│       └── 4.10.3 Feature Serving API

│

├── 5.0 KNOWLEDGE GRAPH

│   ├── 5.1 Ontology Definition

│   │   ├── 5.1.1 Entity Type Definition

│   │   ├── 5.1.2 Relationship Type Definition

│   │   └── 5.1.3 Attribute Definition

│   ├── 5.2 Graph Ingestion

│   │   ├── 5.2.1 Neo4j Setup & Configuration

│   │   ├── 5.2.2 Data Mapping & Transformation

│   │   └── 5.2.3 Batch & Real-time Ingestion

│   ├── 5.3 Graph Query Engine

│   │   ├── 5.3.1 GraphQL API Setup

│   │   ├── 5.3.2 Cypher Query Builder

│   │   └── 5.3.3 Query Optimization

│   ├── 5.4 Graph Visualization

│   │   ├── 5.4.1 Node & Relationship Visualization

│   │   ├── 5.4.2 Interactive Graph Explorer

│   │   └── 5.4.3 Export & Sharing

│   ├── 5.5 Path Discovery & Impact Analysis

│   │   ├── 5.5.1 Path Discovery Algorithm

│   │   ├── 5.5.2 Impact Analysis Engine

│   │   └── 5.5.3 Dependency Analysis

│   ├── 5.6 Semantic Search

│   │   ├── 5.6.1 Semantic Search Engine

│   │   ├── 5.6.2 Natural Language Query Parser

│   │   └── 5.6.3 Search Results Ranking

│   └── 5.7 Provenance Management

│       ├── 5.7.1 Provenance Data Model

│       ├── 5.7.2 Provenance Tracking

│       └── 5.7.3 Provenance Query API

│

├── 6.0 DECISION INTELLIGENCE

│   ├── 6.1 What-If Analysis

│   │   ├── 6.1.1 What-If Engine

│   │   ├── 6.1.2 Parameter Configuration

│   │   └── 6.1.3 Result Visualization

│   ├── 6.2 Scenario Comparison

│   │   ├── 6.2.1 Scenario Manager

│   │   ├── 6.2.2 Comparison Engine

│   │   └── 6.2.3 Best Scenario Recommender

│   ├── 6.3 Optimization Engine

│   │   ├── 6.3.1 Linear Programming Setup (OR-Tools)

│   │   ├── 6.3.2 Constraint Definition

│   │   └── 6.3.3 Optimization & Result

│   ├── 6.4 Decision Log System

│   │   ├── 6.4.1 Decision Input Form

│   │   ├── 6.4.2 Decision Storage & Retrieval

│   │   └── 6.4.3 Decision Audit Trail

│   └── 6.5 Outcome Tracking & Closed-Loop Learning

│       ├── 6.5.1 Outcome Input Form

│       ├── 6.5.2 Outcome vs Prediction Comparison

│       └── 6.5.3 Model Feedback Loop

│

└── 7.0 INTEGRATION & TESTING

├── 7.1 Integration with P-FNE-01 (Foundation)

│   ├── 7.1.1 IAM Integration

│   ├── 7.1.2 Master Data Integration

│   └── 7.1.3 Audit Integration

├── 7.2 Integration with P-FNE-02 (Agricultural Ops)

│   ├── 7.2.1 Farm Data Integration

│   ├── 7.2.2 Crop & Harvest Data Integration

│   └── 7.2.3 Activity Data Integration

├── 7.3 Integration with P-FNE-03 (Supply Chain)

│   ├── 7.3.1 Procurement Data Integration

│   ├── 7.3.2 Inventory Data Integration

│   └── 7.3.3 Supplier Data Integration

├── 7.4 Integration with P-FNE-04 (Production)

│   ├── 7.4.1 Production Order Integration

│   ├── 7.4.2 BOM Integration

│   └── 7.4.3 Execution Data Integration

├── 7.5 Integration with P-FNE-05 (Commerce)

│   ├── 7.5.1 Sales Data Integration

│   ├── 7.5.2 CRM Data Integration

│   └── 7.5.3 Logistics Data Integration

├── 7.6 Integration with P-FNE-06 (Finance & HCM)

│   ├── 7.6.1 Accounting Data Integration

│   ├── 7.6.2 Costing Data Integration

│   └── 7.6.3 HCM Data Integration

├── 7.7 API & BFF Development

│   ├── 7.7.1 API Gateway Setup (Kong/Traefik)

│   ├── 7.7.2 GraphQL Federation (Apollo)

│   └── 7.7.3 BFF Layer Development

├── 7.8 Frontend Development

│   ├── 7.8.1 Web Portal (React/Next.js)

│   ├── 7.8.2 Dashboard Components

│   └── 7.8.3 UI/UX Design & Implementation

├── 7.9 System Integration Testing (SIT)

│   ├── 7.9.1 Test Planning

│   ├── 7.9.2 Test Execution

│   └── 7.9.3 Defect Tracking & Resolution

├── 7.10 User Acceptance Testing (UAT)

│   ├── 7.10.1 UAT Planning

│   ├── 7.10.2 UAT Execution

│   └── 7.10.3 UAT Sign-off

└── 7.11 Deployment & Go-Live

├── 7.11.1 Production Deployment

├── 7.11.2 Go-Live Verification

└── 7.11.3 Hypercare Support

### 3.3.2. WBS Dictionary (Sample)

#### WBS Element: 3.1.1 KPI Cards

| Attribute | Value |
| --- | --- |
| WBS Code | 3.1.1 |
| WBS Level | 4 |
| Parent | 3.1 Dashboard - Executive |
| Deliverable | KPI Cards component for Executive Dashboard |
| Description | Develop KPI card components that display key metrics (Revenue, Profit, Cash Flow, Production Volume, Sales, Inventory) with trend indicators |
| Responsible | Frontend Developer (2 person-days) |
| Dependencies | 3.9 KPI Definition & Management |
| Estimate | 5 person-days |
| Acceptance Criteria | - 6 KPI cards displayed - Trend indicators (up/down) - Click to drill-down - Load ≤ 2 seconds - Responsive on all screen sizes |

### 3.3.3. WBS Dictionary (Complete Table)

| WBS Code | Name | Description | Responsible | Duration | Deliverable |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Project Management | Project management activities | PM | 24 weeks | PMP, Reports |
| 1.1 | PMP & Planning | Project planning | PM | 4 weeks | PMP, Charter |
| 1.2 | Communication & Reporting | Communication and reporting | PM | 24 weeks | Status Reports |
| 1.3 | Quality & Risk Management | Quality and risk management | PM + QA | 24 weeks | Quality Plan, Risk Register |
| 2.0 | Data Platform | Data platform development | Data Engineering | 8 weeks | Data Lake, DW, Pipeline |
| 2.1 | Data Lake & Storage | Data lake setup | Data Engineer | 2 weeks | MinIO/S3 Setup |
| 2.2 | Data Warehouse & Data Mart | Data warehouse setup | Data Engineer | 3 weeks | Snowflake Schema |
| 2.3 | Data Ingestion (CDC) | CDC setup | Data Engineer | 2 weeks | CDC Pipeline |
| 2.4 | ETL/ELT Pipeline | ETL pipeline | Data Engineer | 3 weeks | Airflow Pipeline |
| 2.5 | Data Quality & Monitoring | Data quality monitoring | Data Engineer | 2 weeks | Quality Dashboard |
| 2.6 | Metadata & Data Lineage | Metadata management | Data Engineer | 2 weeks | Metadata Repository |
| 3.0 | Business Intelligence | BI development | Frontend + Backend | 8 weeks | 8 Dashboards |
| 3.1 | Dashboard - Executive | Executive dashboard | FE + BE | 2 weeks | Executive Dashboard |
| 3.2 | Dashboard - Farm | Farm dashboard | FE + BE | 2 weeks | Farm Dashboard |
| 3.3 | Dashboard - Production | Production dashboard | FE + BE | 2 weeks | Production Dashboard |
| 3.4 | Dashboard - Supply Chain | Supply chain dashboard | FE + BE | 2 weeks | Supply Chain Dashboard |
| 3.5 | Dashboard - Sales | Sales dashboard | FE + BE | 2 weeks | Sales Dashboard |
| 3.6 | Dashboard - Finance | Finance dashboard | FE + BE | 2 weeks | Finance Dashboard |
| 3.7 | Dashboard - HCM | HCM dashboard | FE + BE | 2 weeks | HCM Dashboard |
| 3.8 | Dashboard - Quality | Quality dashboard | FE + BE | 2 weeks | Quality Dashboard |
| 3.9 | KPI Definition & Management | KPI system | BE + FE | 2 weeks | KPI System |
| 3.10 | KPI Alert System | Alert system | BE | 2 weeks | Alert System |
| 3.11 | Scheduled Report System | Report scheduling | BE | 2 weeks | Report System |
| 3.12 | Ad-Hoc Report Builder | Ad-hoc report builder | FE + BE | 3 weeks | Report Builder |
| 4.0 | AI/ML Platform | AI/ML development | Data Science + ML | 8 weeks | 5 Models |
| 4.1 | Infrastructure & MLOps | MLOps setup | ML Engineer | 2 weeks | MLflow, Kubeflow |
| 4.2 | Model #1: Demand Forecasting | Demand forecasting model | Data Scientist | 3 weeks | Model #1 |
| 4.3 | Model #2: Crop Yield Prediction | Crop yield prediction | Data Scientist | 3 weeks | Model #2 |
| 4.4 | Model #3: Inventory Forecasting | Inventory forecasting | Data Scientist | 2 weeks | Model #3 |
| 4.5 | Model #4: Predictive Maintenance | Predictive maintenance | Data Scientist | 3 weeks | Model #4 |
| 4.6 | Model #5: Anomaly Detection | Anomaly detection | Data Scientist | 2 weeks | Model #5 |
| 4.7 | Model Registry & Versioning | Model registry | ML Engineer | 2 weeks | Model Registry |
| 4.8 | Model Monitoring & Drift | Model monitoring | ML Engineer | 2 weeks | Monitoring |
| 4.9 | Explainable AI | XAI implementation | Data Scientist | 2 weeks | XAI API |
| 4.10 | Feature Store | Feature store | Data Engineer | 2 weeks | Feature Store |
| 5.0 | Knowledge Graph | Knowledge graph development | Knowledge Engineer | 4 weeks | Graph System |
| 5.1 | Ontology Definition | Ontology definition | Knowledge Engineer | 1 week | Ontology |
| 5.2 | Graph Ingestion | Graph ingestion | Knowledge Engineer | 2 weeks | Ingestion |
| 5.3 | Graph Query Engine | Query engine | Backend | 2 weeks | GraphQL API |
| 5.4 | Graph Visualization | Visualization | Frontend | 2 weeks | Visualizer |
| 5.5 | Path Discovery & Impact | Path and impact analysis | Backend | 2 weeks | Analysis Engine |
| 5.6 | Semantic Search | Semantic search | Backend | 2 weeks | Search Engine |
| 5.7 | Provenance Management | Provenance | Knowledge Engineer | 1 week | Provenance |
| 6.0 | Decision Intelligence | Decision intelligence | Backend | 3 weeks | Decision System |
| 6.1 | What-If Analysis | What-if engine | Backend | 2 weeks | What-If Engine |
| 6.2 | Scenario Comparison | Scenario comparison | Backend | 2 weeks | Comparison Engine |
| 6.3 | Optimization Engine | Optimization engine | Backend | 2 weeks | LP Engine |
| 6.4 | Decision Log System | Decision log | Backend + FE | 1 week | Decision Log |
| 6.5 | Outcome Tracking | Outcome tracking | Backend | 1 week | Outcome Tracking |
| 7.0 | Integration & Testing | Integration and testing | All Teams | 6 weeks | Integrated System |
| 7.1 | Integration P-FNE-01 | Foundation integration | Backend + DE | 2 weeks | Integrated |
| 7.2 | Integration P-FNE-02 | Ag Ops integration | Backend + DE | 2 weeks | Integrated |
| 7.3 | Integration P-FNE-03 | Supply Chain integration | Backend + DE | 2 weeks | Integrated |
| 7.4 | Integration P-FNE-04 | Production integration | Backend + DE | 2 weeks | Integrated |
| 7.5 | Integration P-FNE-05 | Commerce integration | Backend + DE | 2 weeks | Integrated |
| 7.6 | Integration P-FNE-06 | Finance/HCM integration | Backend + DE | 2 weeks | Integrated |
| 7.7 | API & BFF Development | API gateway and BFF | Backend | 3 weeks | API Gateway |
| 7.8 | Frontend Development | Web application | Frontend | 6 weeks | Web App |
| 7.9 | System Integration Testing | SIT | QA | 3 weeks | SIT Passed |
| 7.10 | User Acceptance Testing | UAT | QA + Users | 2 weeks | UAT Sign-off |
| 7.11 | Deployment & Go-Live | Production deployment | DevOps | 1 week | Live System |

## 3.4. Requirement Traceability Matrix (RTM)

### 3.4.1. RTM Structure

| Requirement ID | Requirement Description | Source | Priority | WBS Code | Deliverable | Test Case ID | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-FNE-001 | Data ingestion from all modules | FNE-DPL-001 | P0 | 2.3 | Data Pipeline | TC-DPL-001 | Active |
| R-FNE-002 | CDC for all transaksional data | FNE-DPL-002 | P0 | 2.3 | CDC Pipeline | TC-DPL-002 | Active |
| R-FNE-003 | ETL/ELT pipeline | FNE-DPL-003 | P0 | 2.4 | ETL Pipeline | TC-DPL-003 | Active |
| R-FNE-004 | Data Lake for raw data | FNE-DPL-004 | P0 | 2.1 | Data Lake | TC-DPL-004 | Active |
| R-FNE-005 | Data Warehouse for transformed data | FNE-DPL-005 | P0 | 2.2 | Data Warehouse | TC-DPL-005 | Active |
| R-FNE-006 | Data Mart per domain | FNE-DPL-006 | P0 | 2.2 | Data Mart | TC-DPL-006 | Active |
| R-FNE-007 | Data quality monitoring | FNE-DPL-007 | P0 | 2.5 | Quality Monitoring | TC-DPL-007 | Active |
| R-FNE-008 | Data lineage tracking | FNE-DPL-008 | P1 | 2.6 | Data Lineage | TC-DPL-008 | Active |
| R-FNE-009 | Metadata management | FNE-DPL-009 | P1 | 2.6 | Metadata | TC-DPL-009 | Active |
| R-FNE-010 | Data refresh periodik | FNE-DPL-010 | P0 | 2.4 | Refresh Scheduler | TC-DPL-010 | Active |
| R-FNE-011 | Data pipeline monitoring | FNE-DPL-011 | P0 | 2.5 | Pipeline Monitoring | TC-DPL-011 | Active |
| R-FNE-012 | Data pipeline alert | FNE-DPL-012 | P0 | 2.5 | Alert System | TC-DPL-012 | Active |
| R-FNE-013 | Historical data storage (5 years) | FNE-DPL-013 | P0 | 2.1 | Data Lake | TC-DPL-013 | Active |
| R-FNE-014 | Data API | FNE-DPL-014 | P1 | 7.7 | API Gateway | TC-DPL-014 | Active |
| R-BI-001 | Executive Dashboard | FNE-BI-001 | P0 | 3.1 | Executive Dashboard | TC-BI-001 | Active |
| R-BI-002 | Farm Dashboard | FNE-BI-002 | P0 | 3.2 | Farm Dashboard | TC-BI-002 | Active |
| R-BI-003 | Production Dashboard | FNE-BI-003 | P0 | 3.3 | Production Dashboard | TC-BI-003 | Active |
| R-BI-004 | Supply Chain Dashboard | FNE-BI-004 | P0 | 3.4 | Supply Chain Dashboard | TC-BI-004 | Active |
| R-BI-005 | Sales Dashboard | FNE-BI-005 | P0 | 3.5 | Sales Dashboard | TC-BI-005 | Active |
| R-BI-006 | Financial Dashboard | FNE-BI-006 | P0 | 3.6 | Finance Dashboard | TC-BI-006 | Active |
| R-BI-007 | HCM Dashboard | FNE-BI-007 | P0 | 3.7 | HCM Dashboard | TC-BI-007 | Active |
| R-BI-008 | Quality Dashboard | FNE-BI-008 | P0 | 3.8 | Quality Dashboard | TC-BI-008 | Active |
| R-BI-009 | Drill-down capability | FNE-BI-009 | P0 | 3.1-3.8 | All Dashboards | TC-BI-009 | Active |
| R-BI-010 | Filtering | FNE-BI-010 | P0 | 3.1-3.8 | All Dashboards | TC-BI-010 | Active |
| R-BI-011 | Export to Excel/PDF/CSV | FNE-BI-011 | P0 | 3.11-3.12 | Export Function | TC-BI-011 | Active |
| R-BI-012 | Scheduled reports | FNE-BI-012 | P0 | 3.11 | Scheduled Reports | TC-BI-012 | Active |
| R-BI-013 | Ad-hoc reporting | FNE-BI-013 | P1 | 3.12 | Ad-Hoc Reports | TC-BI-013 | Active |
| R-BI-014 | KPI definition | FNE-BI-014 | P0 | 3.9 | KPI System | TC-BI-014 | Active |
| R-BI-015 | KPI alert | FNE-BI-015 | P0 | 3.10 | KPI Alert | TC-BI-015 | Active |
| R-BI-016 | Trending analysis | FNE-BI-016 | P0 | 3.1-3.8 | All Dashboards | TC-BI-016 | Active |
| R-BI-017 | Benchmarking | FNE-BI-017 | P1 | 3.1-3.8 | All Dashboards | TC-BI-017 | Planned |
| R-BI-018 | Mobile BI | FNE-BI-018 | P1 | 3.1-3.8 | Mobile View | TC-BI-018 | Planned |
| R-BI-019 | Role-based dashboard | FNE-BI-019 | P0 | 3.1-3.8 | All Dashboards | TC-BI-019 | Active |
| R-BI-020 | Data freshness indicator | FNE-BI-020 | P0 | 3.1-3.8 | All Dashboards | TC-BI-020 | Active |
| R-AI-001 | Demand forecasting | FNE-AI-001 | P0 | 4.2 | Demand Forecasting | TC-AI-001 | Active |
| R-AI-002 | Crop yield prediction | FNE-AI-002 | P0 | 4.3 | Crop Yield Prediction | TC-AI-002 | Active |
| R-AI-003 | Harvest time prediction | FNE-AI-003 | P1 | 4.3 | Harvest Time | TC-AI-003 | Planned |
| R-AI-004 | Inventory forecasting | FNE-AI-004 | P0 | 4.4 | Inventory Forecasting | TC-AI-004 | Active |
| R-AI-005 | Production forecasting | FNE-AI-005 | P1 | 4.4 | Production Forecasting | TC-AI-005 | Planned |
| R-AI-006 | Predictive maintenance | FNE-AI-006 | P0 | 4.5 | Predictive Maintenance | TC-AI-006 | Active |
| R-AI-007 | Supplier risk prediction | FNE-AI-007 | P1 | 4.5 | Supplier Risk | TC-AI-007 | Planned |
| R-AI-008 | Price optimization | FNE-AI-008 | P1 | 4.2 | Price Optimization | TC-AI-008 | Planned |
| R-AI-009 | Customer segmentation | FNE-AI-009 | P1 | 4.6 | Customer Segmentation | TC-AI-009 | Planned |
| R-AI-010 | Customer churn prediction | FNE-AI-010 | P1 | 4.6 | Churn Prediction | TC-AI-010 | Planned |
| R-AI-011 | Crop disease detection | FNE-AI-011 | P2 | 4.3 | Disease Detection | TC-AI-011 | Planned |
| R-AI-012 | Anomaly detection | FNE-AI-012 | P0 | 4.6 | Anomaly Detection | TC-AI-012 | Active |
| R-AI-013 | Recommendation engine | FNE-AI-013 | P1 | 4.7 | Recommendations | TC-AI-013 | Planned |
| R-AI-014 | Explainable AI | FNE-AI-014 | P0 | 4.9 | XAI | TC-AI-014 | Active |
| R-AI-015 | Model registry | FNE-AI-015 | P0 | 4.7 | Model Registry | TC-AI-015 | Active |
| R-AI-016 | Model monitoring | FNE-AI-016 | P0 | 4.8 | Model Monitoring | TC-AI-016 | Active |
| R-AI-017 | Model retraining | FNE-AI-017 | P1 | 4.8 | Retraining | TC-AI-017 | Planned |
| R-AI-018 | A/B testing | FNE-AI-018 | P2 | 4.7 | A/B Testing | TC-AI-018 | Planned |
| R-AI-019 | Feature store | FNE-AI-019 | P1 | 4.10 | Feature Store | TC-AI-019 | Planned |
| R-AI-020 | ML pipeline | FNE-AI-020 | P0 | 4.1 | ML Pipeline | TC-AI-020 | Active |
| R-KG-001 | Ontology definition | FNE-KG-001 | P0 | 5.1 | Ontology | TC-KG-001 | Active |
| R-KG-002 | Entity types | FNE-KG-002 | P0 | 5.1 | Entity Types | TC-KG-002 | Active |
| R-KG-003 | Relationship types | FNE-KG-003 | P0 | 5.1 | Relationship Types | TC-KG-003 | Active |
| R-KG-004 | Entity resolution | FNE-KG-004 | P0 | 5.2 | Entity Resolution | TC-KG-004 | Active |
| R-KG-005 | Graph ingestion | FNE-KG-005 | P0 | 5.2 | Graph Ingestion | TC-KG-005 | Active |
| R-KG-006 | Graph query | FNE-KG-006 | P0 | 5.3 | Graph Query | TC-KG-006 | Active |
| R-KG-007 | Graph visualization | FNE-KG-007 | P1 | 5.4 | Graph Visualization | TC-KG-007 | Active |
| R-KG-008 | Path discovery | FNE-KG-008 | P1 | 5.5 | Path Discovery | TC-KG-008 | Active |
| R-KG-009 | Impact analysis | FNE-KG-009 | P1 | 5.5 | Impact Analysis | TC-KG-009 | Active |
| R-KG-010 | Dependency analysis | FNE-KG-010 | P1 | 5.5 | Dependency Analysis | TC-KG-010 | Active |
| R-KG-011 | Semantic search | FNE-KG-011 | P1 | 5.6 | Semantic Search | TC-KG-011 | Active |
| R-KG-012 | Explainable decision path | FNE-KG-012 | P1 | 5.5 | Decision Path | TC-KG-012 | Planned |
| R-KG-013 | Provenance | FNE-KG-013 | P0 | 5.7 | Provenance | TC-KG-013 | Active |
| R-KG-014 | Graph analytics | FNE-KG-014 | P2 | 5.5 | Graph Analytics | TC-KG-014 | Planned |
| R-KG-015 | Knowledge discovery | FNE-KG-015 | P2 | 5.5 | Knowledge Discovery | TC-KG-015 | Planned |
| R-KG-016 | Graph API | FNE-KG-016 | P1 | 5.3 | Graph API | TC-KG-016 | Active |
| R-DEC-001 | Decision support recommendations | FNE-DEC-001 | P0 | 6.1 | Recommendations | TC-DEC-001 | Active |
| R-DEC-002 | What-if analysis | FNE-DEC-002 | P0 | 6.1 | What-If Analysis | TC-DEC-002 | Active |
| R-DEC-003 | Scenario comparison | FNE-DEC-003 | P0 | 6.2 | Scenario Comparison | TC-DEC-003 | Active |
| R-DEC-004 | Sensitivity analysis | FNE-DEC-004 | P1 | 6.1 | Sensitivity | TC-DEC-004 | Planned |
| R-DEC-005 | Optimization | FNE-DEC-005 | P1 | 6.3 | Optimization | TC-DEC-005 | Active |
| R-DEC-006 | Decision log | FNE-DEC-006 | P0 | 6.4 | Decision Log | TC-DEC-006 | Active |
| R-DEC-007 | Outcome tracking | FNE-DEC-007 | P1 | 6.5 | Outcome Tracking | TC-DEC-007 | Active |
| R-DEC-008 | Closed-loop learning | FNE-DEC-008 | P1 | 6.5 | Closed-Loop Learning | TC-DEC-008 | Planned |

## 3.5. Scope Management Process

### 3.5.1. Scope Verification Process

| Fase | Aktivitas | Input | Output | Penanggung Jawab |
| --- | --- | --- | --- | --- |
| Planning | Define acceptance criteria for each deliverable | Requirements, WBS | Acceptance Criteria Document | PM + PO |
| Execution | Verify deliverables against acceptance criteria | Deliverable, AC Document | Verification Report | QA Lead |
| Sprint Review | Demo deliverables to stakeholders | Deliverable | Feedback, Sign-off | PM + PO |
| Milestone | Formal scope verification | All deliverables | Milestone Sign-off | PM + Sponsor |

### 3.5.2. Scope Control Process

| Aktivitas | Frekuensi | Penanggung Jawab | Tools |
| --- | --- | --- | --- |
| Requirement Traceability | Setiap sprint | PM + PO | RTM |
| Scope Change Assessment | Setiap change request | PM + CCB | Change Request Form |
| Scope Creep Monitoring | Mingguan | PM | WBS vs Actual |
| Scope Audit | Setiap milestone | PM + QA | Audit Report |
| Scope Communication | Setiap sprint review | PM | Status Report |

### 3.5.3. Scope Change Impact Analysis Template

| Aspek | Analisis | Keterangan |
| --- | --- | --- |
| Request Details |  |  |
| CR ID | [CR-XXX] |  |
| Requested By | [Nama] |  |
| Date | [Tanggal] |  |
| Description | [Deskripsi] |  |
| Scope Impact |  |  |
| WBS Elements Affected | [Kode WBS] |  |
| Deliverables Affected | [Nama Deliverable] |  |
| Priority Change | [P0/P1/P2] |  |
| Schedule Impact |  |  |
| Effort Increase | [X person-days] |  |
| Schedule Extension | [X weeks] |  |
| Critical Path Impact | [Yes/No] |  |
| Cost Impact |  |  |
| Cost Increase | [Rp X] |  |
| Resource Impact | [X person additional] |  |
| Quality Impact |  |  |
| Quality Standard Impact | [Yes/No] |  |
| Risk to Quality | [Low/Medium/High] |  |
| Risk Impact |  |  |
| New Risks | [Risk description] |  |
| Risk Severity | [Low/Medium/High] |  |
| Recommendation |  |  |
| PM Recommendation | [Approve/Reject/Defer] |  |
| CCB Decision | [Approve/Reject/Defer] |  |
| Effective Date | [Tanggal] |  |

# BAB 4: MANAJEMEN PENJADWALAN PROYEK (PMBOK Area 3)

## 4.1. Tujuan Manajemen Penjadwalan

Manajemen penjadwalan proyek bertujuan untuk memastikan proyek diselesaikan tepat waktu dengan milestone yang terdefinisi. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Definisi Aktivitas | Mengidentifikasi dan mendefinisikan semua aktivitas yang diperlukan untuk menyelesaikan proyek |
| 2 | Urutan Aktivitas | Menentukan urutan dan ketergantungan antar aktivitas |
| 3 | Estimasi Durasi | Mengestimasi durasi yang dibutuhkan untuk setiap aktivitas |
| 4 | Pengembangan Jadwal | Mengembangkan jadwal proyek yang realistis dengan milestone yang jelas |
| 5 | Pengendalian Jadwal | Memonitor dan mengendalikan pelaksanaan sesuai jadwal |

## 4.2. Project Timeline Overview

### 4.2.1. Timeline Summary

text

┌────────────────────────────────────────────────────────────────────────────────────┐

│                           PROJECT TIMELINE (24 MINGGU / 6 BULAN)                   │

├────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                     │

│  FASE 1: Inisiasi & Perencanaan (Minggu 1-4)                                       │

│  ├── M0: Project Kick-off (Minggu 1)                                              │

│  └── PMP & Planning Complete (Minggu 4)                                           │

│                                                                                     │

│  FASE 2: Data Platform & Infrastructure (Minggu 5-8)                               │

│  ├── Infrastructure Setup (Minggu 5-6)                                            │

│  ├── Data Lake & DW Setup (Minggu 6-7)                                            │

│  ├── CDC & ETL Pipeline (Minggu 7-8)                                              │

│  └── M1: Data Platform Complete (Minggu 8)                                        │

│                                                                                     │

│  FASE 3: BI Dashboard & KPI (Minggu 9-12)                                          │

│  ├── Dashboard Framework (Minggu 9)                                               │

│  ├── Executive, Farm, Production Dashboards (Minggu 10)                           │

│  ├── Supply Chain, Sales, Finance Dashboards (Minggu 11)                          │

│  ├── HCM, Quality Dashboards, KPI System (Minggu 12)                              │

│  └── M2: BI Dashboard Complete (Minggu 12)                                        │

│                                                                                     │

│  FASE 4: AI/ML Model Development (Minggu 13-16)                                    │

│  ├── MLOps Infrastructure (Minggu 13)                                             │

│  ├── Demand Forecasting & Crop Yield (Minggu 14)                                  │

│  ├── Inventory Forecasting & Predictive Maintenance (Minggu 15)                   │

│  ├── Anomaly Detection & Model Registry (Minggu 16)                               │

│  └── M3: AI/ML Models Complete (Minggu 16)                                        │

│                                                                                     │

│  FASE 5: Knowledge Graph & Decision Intelligence (Minggu 17-18)                    │

│  ├── Ontology & Graph Ingestion (Minggu 17)                                       │

│  ├── Graph Query & Visualization (Minggu 17)                                      │

│  ├── Impact Analysis & Semantic Search (Minggu 18)                                │

│  ├── What-If Analysis & Optimization (Minggu 18)                                  │

│  └── M4: Graph & Decision Complete (Minggu 18)                                    │

│                                                                                     │

│  FASE 6: Integration & Testing (Minggu 19-22)                                      │

│  ├── Integration with 6 Modules (Minggu 19-20)                                    │

│  ├── System Integration Testing (Minggu 20-21)                                    │

│  ├── Performance Testing (Minggu 21)                                              │

│  ├── User Acceptance Testing (Minggu 21-22)                                       │

│  └── M5: Integration & UAT Complete (Minggu 22)                                   │

│                                                                                     │

│  FASE 7: Deployment & Go-Live (Minggu 23-24)                                       │

│  ├── Production Deployment (Minggu 23)                                            │

│  ├── Go-Live Verification (Minggu 23)                                             │

│  ├── Hypercare & Support (Minggu 24)                                              │

│  └── M6: Go-Live (Minggu 24)                                                      │

│                                                                                     │

└────────────────────────────────────────────────────────────────────────────────────┘

### 4.2.2. Milestone Table

| Milestone | Kode | Target Minggu | Tanggal Target | Deliverable | Kriteria |
| --- | --- | --- | --- | --- | --- |
| Project Kick-off | M0 | 1 | [Tanggal] | Project Charter, PMP | Dokumen approved |
| Data Platform Complete | M1 | 8 | [Tanggal] | Data Lake, DW, ETL, CDC | Semua pipeline berfungsi, data quality aktif |
| BI Dashboard Complete | M2 | 12 | [Tanggal] | 8 Dashboard, KPI, Alert | Semua dashboard berfungsi, load ≤ 5 detik |
| AI/ML Models Complete | M3 | 16 | [Tanggal] | 5 model produksi | Akurasi ≥ 80%, inference ≤ 3 detik |
| Graph & Decision Complete | M4 | 18 | [Tanggal] | Knowledge Graph, Decision Intel | Query ≤ 5 detik, all features berfungsi |
| Integration & UAT Complete | M5 | 22 | [Tanggal] | Full integration, UAT sign-off | 100% integration test passed |
| Go-Live | M6 | 24 | [Tanggal] | Production deployment | All acceptance criteria met |

## 4.3. Detail Aktivitas & Estimasi Durasi

### 4.3.1. Fase 1: Inisiasi & Perencanaan (Minggu 1-4)

| Kode | Aktivitas | Durasi (Hari) | Dependensi | Sumber Daya | Output |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Project Charter Development | 5 | - | PM | Project Charter |
| 1.2 | PMP Development | 10 | 1.1 | PM + Leads | PMP Document |
| 1.3 | Stakeholder Analysis | 3 | - | PM + BA | Stakeholder Register |
| 1.4 | Requirement Finalization | 5 | 1.2 | PO + BA | Final Requirements |
| 1.5 | Architecture Design | 8 | 1.2 | Tech Lead | Architecture Doc |
| 1.6 | Infrastructure Setup Planning | 3 | 1.5 | DevOps | Infrastructure Plan |
| 1.7 | Team Onboarding | 3 | 1.1 | PM | Team Ready |
| 1.8 | Kick-off Meeting | 1 | 1.1-1.7 | PM + Sponsor | Kick-off Complete |

Total Durasi Fase 1: 20 hari kerja (4 minggu)

### 4.3.2. Fase 2: Data Platform & Infrastructure (Minggu 5-8)

| Kode | Aktivitas | Durasi (Hari) | Dependensi | Sumber Daya | Output |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Cloud Infrastructure Setup | 5 | 1.6 | DevOps | K8s, Cloud Resources |
| 2.2 | Data Lake Setup (MinIO/S3) | 3 | 2.1 | Data Engineer | Data Lake |
| 2.3 | Data Warehouse Setup (Snowflake) | 5 | 2.1 | Data Engineer | Data Warehouse |
| 2.4 | Database Schema Design | 4 | 1.5, 2.2 | Data Engineer | Schema Design |
| 2.5 | CDC Setup (Debezium + Kafka) | 5 | 2.1 | Data Engineer | CDC Pipeline |
| 2.6 | ETL Pipeline Development | 8 | 2.3, 2.4 | Data Engineer | ETL Pipeline |
| 2.7 | Data Quality Rules Definition | 3 | 2.6 | Data Engineer | Quality Rules |
| 2.8 | Data Quality Monitoring | 3 | 2.7 | Data Engineer | Quality Dashboard |
| 2.9 | Metadata Management | 3 | 2.6 | Data Engineer | Metadata Repository |
| 2.10 | Data Lineage Tracking | 3 | 2.9 | Data Engineer | Lineage System |
| 2.11 | Integration Testing (Data) | 3 | 2.5-2.10 | Data Engineer + QA | Test Passed |

Total Durasi Fase 2: 20 hari kerja (4 minggu)

### 4.3.3. Fase 3: BI Dashboard & KPI (Minggu 9-12)

| Kode | Aktivitas | Durasi (Hari) | Dependensi | Sumber Daya | Output |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Dashboard Framework Setup | 3 | 2.11 | FE + BE | Framework |
| 3.2 | KPI Definition & Management | 5 | 2.11 | BE + FE | KPI System |
| 3.3 | Executive Dashboard | 5 | 3.1, 3.2 | FE + BE | Executive Dashboard |
| 3.4 | Farm Dashboard | 4 | 3.1, 3.2 | FE + BE | Farm Dashboard |
| 3.5 | Production Dashboard | 4 | 3.1, 3.2 | FE + BE | Production Dashboard |
| 3.6 | Supply Chain Dashboard | 4 | 3.1, 3.2 | FE + BE | Supply Chain Dashboard |
| 3.7 | Sales Dashboard | 4 | 3.1, 3.2 | FE + BE | Sales Dashboard |
| 3.8 | Financial Dashboard | 4 | 3.1, 3.2 | FE + BE | Financial Dashboard |
| 3.9 | HCM Dashboard | 3 | 3.1, 3.2 | FE + BE | HCM Dashboard |
| 3.10 | Quality Dashboard | 3 | 3.1, 3.2 | FE + BE | Quality Dashboard |
| 3.11 | KPI Alert System | 4 | 3.2 | BE | Alert System |
| 3.12 | Scheduled Report System | 4 | 3.1 | BE + FE | Report System |
| 3.13 | Ad-Hoc Report Builder | 6 | 3.1 | FE + BE | Report Builder |
| 3.14 | Dashboard Integration Testing | 3 | 3.3-3.13 | QA | Test Passed |

Total Durasi Fase 3: 20 hari kerja (4 minggu)

### 4.3.4. Fase 4: AI/ML Model Development (Minggu 13-16)

| Kode | Aktivitas | Durasi (Hari) | Dependensi | Sumber Daya | Output |
| --- | --- | --- | --- | --- | --- |
| 4.1 | MLOps Infrastructure Setup | 3 | 2.11 | ML Engineer | MLflow, Kubeflow |
| 4.2 | Feature Store Setup | 3 | 4.1 | Data Engineer | Feature Store |
| 4.3 | Model #1: Demand Forecasting | 10 | 4.1, 4.2 | Data Scientist | Model #1 |
| 4.4 | Model #2: Crop Yield Prediction | 10 | 4.1, 4.2 | Data Scientist | Model #2 |
| 4.5 | Model #3: Inventory Forecasting | 8 | 4.1, 4.2 | Data Scientist | Model #3 |
| 4.6 | Model #4: Predictive Maintenance | 10 | 4.1, 4.2 | Data Scientist | Model #4 |
| 4.7 | Model #5: Anomaly Detection | 8 | 4.1, 4.2 | Data Scientist | Model #5 |
| 4.8 | Model Registry & Versioning | 4 | 4.1 | ML Engineer | Model Registry |
| 4.9 | Model Monitoring & Drift | 5 | 4.1 | ML Engineer | Monitoring |
| 4.10 | Explainable AI (SHAP/LIME) | 5 | 4.3-4.7 | Data Scientist | XAI API |
| 4.11 | Model Integration Testing | 3 | 4.3-4.10 | QA | Test Passed |

Total Durasi Fase 4: 20 hari kerja (4 minggu)

### 4.3.5. Fase 5: Knowledge Graph & Decision Intelligence (Minggu 17-18)

| Kode | Aktivitas | Durasi (Hari) | Dependensi | Sumber Daya | Output |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Ontology Definition | 3 | 2.11 | Knowledge Engineer | Ontology |
| 5.2 | Entity/Relationship Definition | 3 | 5.1 | Knowledge Engineer | Entity/Rel |
| 5.3 | Neo4j Setup & Configuration | 2 | 2.1 | Knowledge Engineer | Neo4j |
| 5.4 | Graph Ingestion | 5 | 5.2, 5.3 | Knowledge Engineer | Graph Data |
| 5.5 | Graph Query Engine (GraphQL) | 5 | 5.4 | Backend | GraphQL API |
| 5.6 | Graph Visualization | 4 | 5.5 | Frontend | Visualizer |
| 5.7 | Path Discovery & Impact Analysis | 5 | 5.5 | Backend | Analysis Engine |
| 5.8 | Semantic Search | 4 | 5.5 | Backend | Search Engine |
| 5.9 | What-If Analysis Engine | 5 | 2.11, 4.3 | Backend | What-If Engine |
| 5.10 | Scenario Comparison | 3 | 5.9 | Backend | Comparison Engine |
| 5.11 | Optimization Engine (LP) | 5 | 5.9 | Backend | Optimizer |
| 5.12 | Decision Log & Outcome Tracking | 3 | 5.9 | Backend + FE | Decision System |
| 5.13 | Graph & Decision Testing | 3 | 5.4-5.12 | QA | Test Passed |

Total Durasi Fase 5: 15 hari kerja (3 minggu)

### 4.3.6. Fase 6: Integration & Testing (Minggu 19-22)

| Kode | Aktivitas | Durasi (Hari) | Dependensi | Sumber Daya | Output |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Integration with P-FNE-01 | 3 | 5.13 | Backend + DE | Integrated |
| 6.2 | Integration with P-FNE-02 | 3 | 5.13 | Backend + DE | Integrated |
| 6.3 | Integration with P-FNE-03 | 3 | 5.13 | Backend + DE | Integrated |
| 6.4 | Integration with P-FNE-04 | 3 | 5.13 | Backend + DE | Integrated |
| 6.5 | Integration with P-FNE-05 | 3 | 5.13 | Backend + DE | Integrated |
| 6.6 | Integration with P-FNE-06 | 3 | 5.13 | Backend + DE | Integrated |
| 6.7 | API Gateway & BFF Setup | 3 | 5.13 | Backend | API Gateway |
| 6.8 | System Integration Testing | 5 | 6.1-6.7 | QA | SIT Passed |
| 6.9 | Performance Testing | 3 | 6.8 | QA | Performance Report |
| 6.10 | Security Testing | 3 | 6.8 | DevOps + QA | Security Report |
| 6.11 | User Acceptance Testing | 5 | 6.8 | QA + Users | UAT Sign-off |
| 6.12 | Documentation Finalization | 3 | 6.8 | All Teams | Documentation |

Total Durasi Fase 6: 18 hari kerja (3.5 minggu)

### 4.3.7. Fase 7: Deployment & Go-Live (Minggu 23-24)

| Kode | Aktivitas | Durasi (Hari) | Dependensi | Sumber Daya | Output |
| --- | --- | --- | --- | --- | --- |
| 7.1 | Pre-Deployment Checklist | 1 | 6.12 | PM + DevOps | Checklist |
| 7.2 | Production Deployment | 2 | 7.1 | DevOps | Deployed |
| 7.3 | Go-Live Verification | 2 | 7.2 | QA + DevOps | Verified |
| 7.4 | User Training | 2 | 7.3 | BA + PM | Trained |
| 7.5 | Hypercare Support | 5 | 7.3 | All Teams | Support |
| 7.6 | Project Closure Report | 2 | 7.5 | PM | Closure Report |
| 7.7 | Handover to Operations | 2 | 7.5 | PM + DevOps | Handover |
| 7.8 | Lessons Learned Session | 1 | 7.6 | PM + All | Lessons Learned |

Total Durasi Fase 7: 9 hari kerja (2 minggu)

## 4.4. Gantt Chart

### 4.4.1. Complete Gantt Chart (Minggu 1-24)

| Aktivitas | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FASE 1: Inisiasi & Perencanaan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Project Charter | ██ | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 PMP Development |  | ██ | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 Stakeholder Analysis |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 Requirement Finalization |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5 Architecture Design |  |  |  | ██ | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6 Infrastructure Planning |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 Team Onboarding | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.8 Kick-off Meeting |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FASE 2: Data Platform |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Cloud Infrastructure |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Data Lake Setup |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 Data Warehouse Setup |  |  |  |  |  | ██ | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 Schema Design |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5 CDC Setup |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6 ETL Pipeline |  |  |  |  |  |  |  |  | ██ | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7 Data Quality Rules |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.8 Data Quality Monitoring |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.9 Metadata Management |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.10 Data Lineage |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.11 Integration Testing |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |
| FASE 3: BI Dashboard |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 Dashboard Framework |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 KPI System |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Executive Dashboard |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 Farm Dashboard |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5 Production Dashboard |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.6 Supply Chain Dashboard |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.7 Sales Dashboard |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.8 Financial Dashboard |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.9 HCM Dashboard |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |
| 3.10 Quality Dashboard |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |
| 3.11 KPI Alert System |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |  |  |
| 3.12 Scheduled Reports |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |  |
| 3.13 Ad-Hoc Report Builder |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |  |  |
| 3.14 Dashboard Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |
| FASE 4: AI/ML Models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 MLOps Setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |
| 4.2 Feature Store |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |  |  |  |
| 4.3 Model #1: Demand Forecasting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |
| 4.4 Model #2: Crop Yield |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |  |
| 4.5 Model #3: Inventory Forecasting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |
| 4.6 Model #4: Predictive Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |  |
| 4.7 Model #5: Anomaly Detection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |  |  |
| 4.8 Model Registry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |  |
| 4.9 Model Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |
| 4.10 Explainable AI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |
| 4.11 Model Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |
| FASE 5: Knowledge Graph & Decision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 Ontology Definition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |
| 5.2 Entity/Rel Definition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |
| 5.3 Neo4j Setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |  |  |
| 5.4 Graph Ingestion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |
| 5.5 Graph Query Engine |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |  |
| 5.6 Graph Visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |
| 5.7 Path & Impact Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |
| 5.8 Semantic Search |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |  |
| 5.9 What-If Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ | ██ |  |  |
| 5.10 Scenario Comparison |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |
| 5.11 Optimization Engine |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |
| 5.12 Decision Log |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |  |
| 5.13 Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |
| FASE 6: Integration & Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 Integration P-FNE-01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |
| 6.2 Integration P-FNE-02 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |
| 6.3 Integration P-FNE-03 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |  |
| 6.4 Integration P-FNE-04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |
| 6.5 Integration P-FNE-05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |
| 6.6 Integration P-FNE-06 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |
| 6.7 API Gateway & BFF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |
| 6.8 SIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ██ |
| 6.9 Performance Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.10 Security Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.11 UAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.12 Documentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FASE 7: Deployment & Go-Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 Pre-Deployment Checklist |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.2 Production Deployment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.3 Go-Live Verification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.4 User Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.5 Hypercare Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.6 Closure Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.7 Handover to Ops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.8 Lessons Learned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## 4.5. Dependency & Critical Path Analysis

### 4.5.1. Dependency Types

| Tipe | Deskripsi | Contoh |
| --- | --- | --- |
| Finish-to-Start (FS) | Aktivitas B tidak dapat dimulai sampai A selesai | 2.6 (ETL) → 3.2 (KPI System) |
| Start-to-Start (SS) | Aktivitas B dapat dimulai setelah A dimulai | 3.3-3.10 (Dashboards) dapat dikerjakan paralel |
| Finish-to-Finish (FF) | Aktivitas B harus selesai ketika A selesai | 3.3-3.10 → 3.14 (Testing) |
| Start-to-Finish (SF) | Aktivitas B dapat selesai setelah A dimulai | Jarang digunakan |

### 4.5.2. Critical Path (Fase 2-7)

text

Critical Path: Fase 2 → Fase 3 → Fase 5 → Fase 6 → Fase 7

1.1 (Charter) → 1.2 (PMP) → 1.5 (Architecture) → 2.1 (Infra) → 2.2 (Data Lake) →

2.3 (DW) → 2.4 (Schema) → 2.6 (ETL) → 3.1 (Framework) → 3.2 (KPI) →

3.3-3.10 (Dashboards) → 5.9 (What-If) → 6.1-6.7 (Integration) → 6.8 (SIT) →

6.11 (UAT) → 7.2 (Deployment) → 7.3 (Go-Live)

### 4.5.3. Critical Path Duration

| Fase | Aktivitas Kritis | Durasi (Hari) |
| --- | --- | --- |
| Fase 1 | 1.1, 1.2, 1.5 | 18 |
| Fase 2 | 2.1, 2.2, 2.3, 2.4, 2.6 | 20 |
| Fase 3 | 3.1, 3.2, 3.3-3.10, 3.14 | 18 |
| Fase 5 | 5.9, 5.10 | 10 |
| Fase 6 | 6.1-6.7, 6.8, 6.11 | 12 |
| Fase 7 | 7.2, 7.3 | 4 |
| Total Critical Path |  | 82 Hari (16.4 Minggu) |

## 4.6. Sprint Planning (Agile Methodology)

### 4.6.1. Sprint Structure

Proyek ini menggunakan pendekatan Agile-Hybrid dengan sprint 2 minggu untuk pengembangan dan pendekatan prediktif untuk infrastruktur.

| Sprint | Durasi | Fokus | Tim | Deliverable Utama |
| --- | --- | --- | --- | --- |
| Sprint 0 | 2 minggu | Setup & Planning | All Teams | Project Charter, PMP, Architecture |
| Sprint 1 | 2 minggu | Data Pipeline - Phase 1 | DE + DevOps | Infrastructure, Data Lake, CDC |
| Sprint 2 | 2 minggu | Data Pipeline - Phase 2 | DE + DevOps | Data Warehouse, ETL, Quality |
| Sprint 3 | 2 minggu | BI Foundation | FE + BE | Dashboard Framework, KPI System |
| Sprint 4 | 2 minggu | BI Dashboards - Phase 1 | FE + BE | Executive, Farm, Production Dashboard |
| Sprint 5 | 2 minggu | BI Dashboards - Phase 2 | FE + BE | Supply Chain, Sales, Finance Dashboard |
| Sprint 6 | 2 minggu | BI Dashboards - Phase 3 | FE + BE | HCM, Quality Dashboard, Reports |
| Sprint 7 | 2 minggu | AI/ML Foundation | DS + ML | MLOps, Feature Store |
| Sprint 8 | 2 minggu | AI/ML Models - Phase 1 | DS | Demand Forecasting, Crop Yield |
| Sprint 9 | 2 minggu | AI/ML Models - Phase 2 | DS + ML | Inventory Forecasting, Predictive Maintenance |
| Sprint 10 | 2 minggu | AI/ML Models - Phase 3 | DS + ML | Anomaly Detection, Model Registry, XAI |
| Sprint 11 | 2 minggu | Knowledge Graph | KE + BE | Ontology, Ingestion, Query Engine |
| Sprint 12 | 2 minggu | Knowledge Graph & Decision | KE + BE + FE | Visualization, What-If, Optimization |
| Sprint 13 | 2 minggu | Integration & Testing | All Teams | SIT, Performance Testing |
| Sprint 14 | 2 minggu | UAT & Go-Live | All Teams | UAT, Deployment, Go-Live |

### 4.6.2. Sprint Ceremonies

| Ceremony | Frekuensi | Durasi | Peserta |
| --- | --- | --- | --- |
| Sprint Planning | Setiap sprint | 2 jam | PM, PO, Tech Lead, All Devs |
| Daily Standup | Harian | 15 menit | All Devs + PM |
| Sprint Review | Akhir sprint | 1 jam | All Teams + Stakeholders |
| Sprint Retrospective | Akhir sprint | 45 menit | All Devs + PM |
| Backlog Refinement | 2 kali per sprint | 1 jam | PO, PM, Tech Lead |

### 4.6.3. Sprint Capacity Planning

| Role | Sprint Capacity (Person-days) |
| --- | --- |
| Project Manager | 10 |
| Tech Lead | 10 |
| Backend Developer (3) | 30 |
| Frontend Developer (2) | 20 |
| Data Engineer (3) | 30 |
| Data Scientist (2) | 20 |
| ML Engineer (1) | 10 |
| Knowledge Engineer (1) | 10 |
| QA Engineer (2) | 20 |
| DevOps Engineer (1) | 10 |
| Business Analyst (1) | 10 |
| Total per Sprint | 180 person-days |

## 4.7. Schedule Management Process

### 4.7.1. Schedule Monitoring & Control

| Aktivitas | Frekuensi | Penanggung Jawab | Tools |
| --- | --- | --- | --- |
| Daily Standup | Harian | Tech Lead | Jira/Trello |
| Sprint Planning | 2 minggu | PM + PO | Jira |
| Sprint Review | 2 minggu | PM | Jira, Demo |
| Sprint Retrospective | 2 minggu | PM | Miro/Whiteboard |
| Weekly Progress Report | Mingguan | PM | MS Project/Jira |
| Milestone Review | Per milestone | PM + Sponsor | Report |
| Schedule Variance Analysis | Mingguan | PM | MS Project |
| Critical Path Monitoring | Mingguan | PM | MS Project |

### 4.7.2. Schedule Variance Management

| Variance | Action | Threshold |
| --- | --- | --- |
| Schedule Variance ≤ 5% | Monitor, tidak ada tindakan | - |
| Schedule Variance 5-10% | Analisis dampak, revisi rencana | > 5% |
| Schedule Variance 10-20% | Tindakan korektif, revisi schedule | > 10% |
| Schedule Variance > 20% | Eskalasi ke sponsor, restructuring | > 20% |

### 4.7.3. Schedule Recovery Plan

| Skenario | Action | Timeline |
| --- | --- | --- |
| Delay ≤ 1 minggu | Overtime, tambah resource | 1 minggu |
| Delay 1-2 minggu | Prioritaskan critical path, tambah resource | 2 minggu |
| Delay > 2 minggu | Eskalasi, scope reduction, parallel work | 3 minggu |

## 4.8. Key Milestone Dates

| Milestone | Kode | Tanggal Target | Tanggal Aktual | Status |
| --- | --- | --- | --- | --- |
| Project Kick-off | M0 | [Tanggal] | - | Not Started |
| Data Platform Complete | M1 | [Tanggal] | - | Not Started |
| BI Dashboard Complete | M2 | [Tanggal] | - | Not Started |
| AI/ML Models Complete | M3 | [Tanggal] | - | Not Started |
| Graph & Decision Complete | M4 | [Tanggal] | - | Not Started |
| Integration & UAT Complete | M5 | [Tanggal] | - | Not Started |
| Go-Live | M6 | [Tanggal] | - | Not Started |

# BAB 5: MANAJEMEN BIAYA PROYEK (PMBOK Area 4)

## 5.1. Tujuan Manajemen Biaya

Manajemen biaya proyek bertujuan untuk memastikan proyek diselesaikan dalam anggaran yang telah disetujui. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Estimasi Biaya Akurat | Menghasilkan estimasi biaya yang akurat menggunakan metode Activity Based Costing (ABC) |
| 2 | Pengendalian Biaya | Memonitor dan mengendalikan pengeluaran agar sesuai dengan anggaran |
| 3 | Nilai Tambah | Memastikan setiap biaya memberikan nilai tambah bagi proyek |
| 4 | Transparansi | Menyediakan laporan biaya yang transparan untuk stakeholder |
| 5 | Efisiensi | Mengidentifikasi dan mengeliminasi pemborosan biaya |

## 5.2. Metodologi Estimasi Biaya

### 5.2.1. Activity Based Costing (ABC) Approach

Proyek ini menggunakan pendekatan Activity Based Costing (ABC) untuk mengestimasi biaya dengan langkah-langkah sebagai berikut:

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                    ACTIVITY BASED COSTING (ABC) FRAMEWORK                       │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  STEP 1: IDENTIFIKASI AKTIVITAS                                                  │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ - Memecah proyek menjadi aktivitas-aktivitas berdasarkan WBS              │ │

│  │ - Mengidentifikasi resource driver untuk setiap aktivitas                 │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  STEP 2: IDENTIFIKASI RESOURCE COST                                            │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ - Biaya personil berdasarkan tarif INKINDO 2026                           │ │

│  │ - Biaya infrastruktur (cloud, hardware)                                   │ │

│  │ - Biaya lisensi dan software                                              │ │

│  │ - Biaya operasional dan overhead                                          │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  STEP 3: ALLOKASI BIAYA KE AKTIVITAS                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ - Mengalokasikan biaya personil berdasarkan durasi aktivitas              │ │

│  │ - Mengalokasikan biaya infrastruktur berdasarkan usage                    │ │

│  │ - Mengalokasikan biaya overhead berdasarkan proporsi                      │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  STEP 4: KALKULASI TOTAL BIAYA PER AKTIVITAS                                   │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ - Menjumlahkan semua biaya per aktivitas                                  │ │

│  │ - Menghitung total biaya proyek                                           │ │

│  │ - Menambahkan contingency (15%)                                           │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### 5.2.2. Tarif Personil Berdasarkan INKINDO 2026

Mengacu pada standar tarif INKINDO (Ikatan Konsultan Indonesia) Tahun 2026 untuk jasa konsultansi dan proyek teknologi informasi.

| Level / Posisi | Kualifikasi | Tarif per Jam (Rp) | Tarif per Hari (Rp) | Tarif per Bulan (Rp) |
| --- | --- | --- | --- | --- |
| Project Manager | Senior, PMP Certified | Rp 450.000 | Rp 3.600.000 | Rp 79.200.000 |
| Project Manager | Intermediate | Rp 350.000 | Rp 2.800.000 | Rp 61.600.000 |
| Tech Lead | Senior, 8+ years | Rp 425.000 | Rp 3.400.000 | Rp 74.800.000 |
| Tech Lead | Intermediate, 5+ years | Rp 325.000 | Rp 2.600.000 | Rp 57.200.000 |
| Senior Developer | 5+ years experience | Rp 350.000 | Rp 2.800.000 | Rp 61.600.000 |
| Intermediate Developer | 3-5 years experience | Rp 250.000 | Rp 2.000.000 | Rp 44.000.000 |
| Junior Developer | 1-3 years experience | Rp 175.000 | Rp 1.400.000 | Rp 30.800.000 |
| Senior Data Engineer | 5+ years experience | Rp 375.000 | Rp 3.000.000 | Rp 66.000.000 |
| Data Engineer | 3-5 years experience | Rp 275.000 | Rp 2.200.000 | Rp 48.400.000 |
| Senior Data Scientist | 5+ years, PhD/Master | Rp 425.000 | Rp 3.400.000 | Rp 74.800.000 |
| Data Scientist | 3-5 years experience | Rp 325.000 | Rp 2.600.000 | Rp 57.200.000 |
| ML Engineer | 3-5 years experience | Rp 325.000 | Rp 2.600.000 | Rp 57.200.000 |
| Knowledge Engineer | 3-5 years experience | Rp 300.000 | Rp 2.400.000 | Rp 52.800.000 |
| Senior QA Engineer | 5+ years experience | Rp 275.000 | Rp 2.200.000 | Rp 48.400.000 |
| QA Engineer | 3-5 years experience | Rp 200.000 | Rp 1.600.000 | Rp 35.200.000 |
| Senior DevOps Engineer | 5+ years experience | Rp 375.000 | Rp 3.000.000 | Rp 66.000.000 |
| DevOps Engineer | 3-5 years experience | Rp 275.000 | Rp 2.200.000 | Rp 48.400.000 |
| Business Analyst | 3-5 years experience | Rp 275.000 | Rp 2.200.000 | Rp 48.400.000 |
| UI/UX Designer | 3-5 years experience | Rp 250.000 | Rp 2.000.000 | Rp 44.000.000 |

Catatan:

- Tarif per hari = Tarif per jam × 8 jam

- Tarif per bulan = Tarif per hari × 22 hari kerja

- Tarif berdasarkan INKINDO 2026 dengan penyesuaian untuk industri TI

- Belum termasuk PPN 11%

## 5.3. Aktivitas Based Costing (ABC) Detail

### 5.3.1. Fase 1: Inisiasi & Perencanaan (Minggu 1-4)

| Kode | Aktivitas | Durasi (Hari) | Personil | Rate/Hari (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Project Charter Development | 5 | Project Manager (Senior) | 3.600.000 | 18.000.000 |
| 1.2 | PMP Development | 10 | Project Manager (Senior) | 3.600.000 | 36.000.000 |
| 1.3 | Stakeholder Analysis | 3 | Business Analyst | 2.200.000 | 6.600.000 |
| 1.4 | Requirement Finalization | 5 | Business Analyst + PM | 2.200.000 + 3.600.000 | 29.000.000 |
| 1.5 | Architecture Design | 8 | Tech Lead (Senior) | 3.400.000 | 27.200.000 |
| 1.6 | Infrastructure Planning | 3 | DevOps Engineer (Senior) | 3.000.000 | 9.000.000 |
| 1.7 | Team Onboarding | 3 | Project Manager | 3.600.000 | 10.800.000 |
| 1.8 | Kick-off Meeting | 1 | All Leads | - | 5.000.000 |

Total Biaya Personil Fase 1: Rp 141.600.000

### 5.3.2. Fase 2: Data Platform & Infrastructure (Minggu 5-8)

| Kode | Aktivitas | Durasi (Hari) | Personil | Rate/Hari (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Cloud Infrastructure Setup | 5 | DevOps (Senior) + DevOps | 3.000.000 + 2.200.000 | 26.000.000 |
| 2.2 | Data Lake Setup (MinIO/S3) | 3 | Data Engineer (Senior) | 3.000.000 | 9.000.000 |
| 2.3 | Data Warehouse Setup | 5 | Data Engineer (Senior) | 3.000.000 | 15.000.000 |
| 2.4 | Database Schema Design | 4 | Data Engineer (Senior) | 3.000.000 | 12.000.000 |
| 2.5 | CDC Setup (Debezium + Kafka) | 5 | Data Engineer (Senior) + DE | 3.000.000 + 2.200.000 | 26.000.000 |
| 2.6 | ETL Pipeline Development | 8 | Data Engineer (3) | 3.000.000 + 2x2.200.000 | 59.200.000 |
| 2.7 | Data Quality Rules Definition | 3 | Data Engineer (Senior) | 3.000.000 | 9.000.000 |
| 2.8 | Data Quality Monitoring | 3 | Data Engineer (Senior) | 3.000.000 | 9.000.000 |
| 2.9 | Metadata Management | 3 | Data Engineer (Senior) | 3.000.000 | 9.000.000 |
| 2.10 | Data Lineage Tracking | 3 | Data Engineer (Senior) | 3.000.000 | 9.000.000 |
| 2.11 | Integration Testing (Data) | 3 | QA (Senior) + QA | 2.200.000 + 1.600.000 | 11.400.000 |

Total Biaya Personil Fase 2: Rp 194.600.000

### 5.3.3. Fase 3: BI Dashboard & KPI (Minggu 9-12)

| Kode | Aktivitas | Durasi (Hari) | Personil | Rate/Hari (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Dashboard Framework Setup | 3 | FE (Senior) + BE (Senior) | 2.800.000 + 2.800.000 | 16.800.000 |
| 3.2 | KPI Definition & Management | 5 | BE (Senior) + FE (Senior) | 2.800.000 + 2.800.000 | 28.000.000 |
| 3.3 | Executive Dashboard | 5 | FE (Senior) + BE (Int) | 2.800.000 + 2.000.000 | 24.000.000 |
| 3.4 | Farm Dashboard | 4 | FE (Senior) + BE (Int) | 2.800.000 + 2.000.000 | 19.200.000 |
| 3.5 | Production Dashboard | 4 | FE (Senior) + BE (Int) | 2.800.000 + 2.000.000 | 19.200.000 |
| 3.6 | Supply Chain Dashboard | 4 | FE (Int) + BE (Int) | 2.000.000 + 2.000.000 | 16.000.000 |
| 3.7 | Sales Dashboard | 4 | FE (Int) + BE (Int) | 2.000.000 + 2.000.000 | 16.000.000 |
| 3.8 | Financial Dashboard | 4 | FE (Int) + BE (Int) | 2.000.000 + 2.000.000 | 16.000.000 |
| 3.9 | HCM Dashboard | 3 | FE (Int) + BE (Int) | 2.000.000 + 2.000.000 | 12.000.000 |
| 3.10 | Quality Dashboard | 3 | FE (Int) + BE (Int) | 2.000.000 + 2.000.000 | 12.000.000 |
| 3.11 | KPI Alert System | 4 | BE (Senior) | 2.800.000 | 11.200.000 |
| 3.12 | Scheduled Report System | 4 | BE (Senior) + FE (Int) | 2.800.000 + 2.000.000 | 19.200.000 |
| 3.13 | Ad-Hoc Report Builder | 6 | FE (Senior) + BE (Senior) | 2.800.000 + 2.800.000 | 33.600.000 |
| 3.14 | Dashboard Integration Testing | 3 | QA (Senior) + QA | 2.200.000 + 1.600.000 | 11.400.000 |

Total Biaya Personil Fase 3: Rp 254.600.000

### 5.3.4. Fase 4: AI/ML Model Development (Minggu 13-16)

| Kode | Aktivitas | Durasi (Hari) | Personil | Rate/Hari (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| 4.1 | MLOps Infrastructure Setup | 3 | ML Engineer + DevOps (Senior) | 2.600.000 + 3.000.000 | 16.800.000 |
| 4.2 | Feature Store Setup | 3 | Data Engineer (Senior) | 3.000.000 | 9.000.000 |
| 4.3 | Model #1: Demand Forecasting | 10 | Data Scientist (Senior) | 3.400.000 | 34.000.000 |
| 4.4 | Model #2: Crop Yield Prediction | 10 | Data Scientist (Senior) | 3.400.000 | 34.000.000 |
| 4.5 | Model #3: Inventory Forecasting | 8 | Data Scientist (Int) | 2.600.000 | 20.800.000 |
| 4.6 | Model #4: Predictive Maintenance | 10 | Data Scientist (Int) | 2.600.000 | 26.000.000 |
| 4.7 | Model #5: Anomaly Detection | 8 | Data Scientist (Int) | 2.600.000 | 20.800.000 |
| 4.8 | Model Registry & Versioning | 4 | ML Engineer | 2.600.000 | 10.400.000 |
| 4.9 | Model Monitoring & Drift | 5 | ML Engineer | 2.600.000 | 13.000.000 |
| 4.10 | Explainable AI (SHAP/LIME) | 5 | Data Scientist (Senior) | 3.400.000 | 17.000.000 |
| 4.11 | Model Integration Testing | 3 | QA (Senior) + QA | 2.200.000 + 1.600.000 | 11.400.000 |

Total Biaya Personil Fase 4: Rp 213.200.000

### 5.3.5. Fase 5: Knowledge Graph & Decision Intelligence (Minggu 17-18)

| Kode | Aktivitas | Durasi (Hari) | Personil | Rate/Hari (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Ontology Definition | 3 | Knowledge Engineer | 2.400.000 | 7.200.000 |
| 5.2 | Entity/Relationship Definition | 3 | Knowledge Engineer | 2.400.000 | 7.200.000 |
| 5.3 | Neo4j Setup & Configuration | 2 | Knowledge Engineer + DevOps | 2.400.000 + 2.200.000 | 9.200.000 |
| 5.4 | Graph Ingestion | 5 | Knowledge Engineer | 2.400.000 | 12.000.000 |
| 5.5 | Graph Query Engine (GraphQL) | 5 | BE (Senior) | 2.800.000 | 14.000.000 |
| 5.6 | Graph Visualization | 4 | FE (Senior) | 2.800.000 | 11.200.000 |
| 5.7 | Path Discovery & Impact Analysis | 5 | BE (Senior) | 2.800.000 | 14.000.000 |
| 5.8 | Semantic Search | 4 | BE (Senior) | 2.800.000 | 11.200.000 |
| 5.9 | What-If Analysis Engine | 5 | BE (Senior) | 2.800.000 | 14.000.000 |
| 5.10 | Scenario Comparison | 3 | BE (Senior) | 2.800.000 | 8.400.000 |
| 5.11 | Optimization Engine (LP) | 5 | BE (Senior) | 2.800.000 | 14.000.000 |
| 5.12 | Decision Log & Outcome Tracking | 3 | BE (Int) + FE (Int) | 2.000.000 + 2.000.000 | 12.000.000 |
| 5.13 | Graph & Decision Testing | 3 | QA (Senior) + QA | 2.200.000 + 1.600.000 | 11.400.000 |

Total Biaya Personil Fase 5: Rp 145.800.000

### 5.3.6. Fase 6: Integration & Testing (Minggu 19-22)

| Kode | Aktivitas | Durasi (Hari) | Personil | Rate/Hari (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Integration P-FNE-01 | 3 | BE (Senior) + DE (Senior) | 2.800.000 + 3.000.000 | 17.400.000 |
| 6.2 | Integration P-FNE-02 | 3 | BE (Senior) + DE (Senior) | 2.800.000 + 3.000.000 | 17.400.000 |
| 6.3 | Integration P-FNE-03 | 3 | BE (Senior) + DE (Senior) | 2.800.000 + 3.000.000 | 17.400.000 |
| 6.4 | Integration P-FNE-04 | 3 | BE (Senior) + DE (Senior) | 2.800.000 + 3.000.000 | 17.400.000 |
| 6.5 | Integration P-FNE-05 | 3 | BE (Senior) + DE (Senior) | 2.800.000 + 3.000.000 | 17.400.000 |
| 6.6 | Integration P-FNE-06 | 3 | BE (Senior) + DE (Senior) | 2.800.000 + 3.000.000 | 17.400.000 |
| 6.7 | API Gateway & BFF Setup | 3 | BE (Senior) | 2.800.000 | 8.400.000 |
| 6.8 | System Integration Testing | 5 | QA (Senior) + 2xQA | 2.200.000 + 2x1.600.000 | 27.000.000 |
| 6.9 | Performance Testing | 3 | QA (Senior) + DevOps | 2.200.000 + 2.200.000 | 13.200.000 |
| 6.10 | Security Testing | 3 | DevOps (Senior) + QA | 3.000.000 + 1.600.000 | 13.800.000 |
| 6.11 | User Acceptance Testing | 5 | QA (Senior) + BA | 2.200.000 + 2.200.000 | 22.000.000 |
| 6.12 | Documentation Finalization | 3 | All Leads | 3.400.000 + 2.800.000 + 3.000.000 + 2.200.000 + 2.600.000 + 2.400.000 | 16.400.000 |

Total Biaya Personil Fase 6: Rp 205.400.000

### 5.3.7. Fase 7: Deployment & Go-Live (Minggu 23-24)

| Kode | Aktivitas | Durasi (Hari) | Personil | Rate/Hari (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| 7.1 | Pre-Deployment Checklist | 1 | PM + DevOps | 3.600.000 + 2.200.000 | 5.800.000 |
| 7.2 | Production Deployment | 2 | DevOps (Senior) + DevOps | 3.000.000 + 2.200.000 | 10.400.000 |
| 7.3 | Go-Live Verification | 2 | QA (Senior) + DevOps | 2.200.000 + 2.200.000 | 8.800.000 |
| 7.4 | User Training | 2 | BA + PM | 2.200.000 + 3.600.000 | 11.600.000 |
| 7.5 | Hypercare Support | 5 | All Teams (partial) | - | 35.000.000 |
| 7.6 | Project Closure Report | 2 | PM | 3.600.000 | 7.200.000 |
| 7.7 | Handover to Operations | 2 | PM + DevOps | 3.600.000 + 2.200.000 | 11.600.000 |
| 7.8 | Lessons Learned Session | 1 | PM + All | 3.600.000 | 3.600.000 |

Total Biaya Personil Fase 7: Rp 94.000.000

## 5.4. Rekapitulasi Biaya Personil

### 5.4.1. Total Biaya Personil per Fase

| Fase | Durasi (Minggu) | Total Biaya Personil (Rp) | Persentase |
| --- | --- | --- | --- |
| Fase 1: Inisiasi & Perencanaan | 4 | 141.600.000 | 6.5% |
| Fase 2: Data Platform & Infrastructure | 4 | 194.600.000 | 8.9% |
| Fase 3: BI Dashboard & KPI | 4 | 254.600.000 | 11.7% |
| Fase 4: AI/ML Model Development | 4 | 213.200.000 | 9.8% |
| Fase 5: Knowledge Graph & Decision | 3 | 145.800.000 | 6.7% |
| Fase 6: Integration & Testing | 4 | 205.400.000 | 9.5% |
| Fase 7: Deployment & Go-Live | 2 | 94.000.000 | 4.3% |
| Management & Overhead | 24 | 526.800.000 | 24.3% |
| Subtotal Personil |  | 1.776.000.000 | 81.9% |
| Subtotal Non-Personil |  | 392.000.000 | 18.1% |
| Total Biaya Personil |  | 2.168.000.000 | 100% |

### 5.4.2. Total Biaya Personil per Role

| Role | Jumlah | Rate/Hari (Rp) | Total Hari Kerja | Total Biaya (Rp) |
| --- | --- | --- | --- | --- |
| Project Manager (Senior) | 1 | 3.600.000 | 120 | 432.000.000 |
| Tech Lead (Senior) | 1 | 3.400.000 | 120 | 408.000.000 |
| Business Analyst | 1 | 2.200.000 | 80 | 176.000.000 |
| Frontend Developer (Senior) | 1 | 2.800.000 | 100 | 280.000.000 |
| Frontend Developer (Intermediate) | 1 | 2.000.000 | 100 | 200.000.000 |
| Backend Developer (Senior) | 2 | 2.800.000 | 120 | 672.000.000 |
| Backend Developer (Intermediate) | 1 | 2.000.000 | 120 | 240.000.000 |
| Data Engineer (Senior) | 1 | 3.000.000 | 80 | 240.000.000 |
| Data Engineer (Intermediate) | 2 | 2.200.000 | 80 | 352.000.000 |
| Data Scientist (Senior) | 1 | 3.400.000 | 80 | 272.000.000 |
| Data Scientist (Intermediate) | 2 | 2.600.000 | 80 | 416.000.000 |
| ML Engineer | 1 | 2.600.000 | 80 | 208.000.000 |
| Knowledge Engineer | 1 | 2.400.000 | 60 | 144.000.000 |
| QA Engineer (Senior) | 1 | 2.200.000 | 100 | 220.000.000 |
| QA Engineer (Intermediate) | 2 | 1.600.000 | 100 | 320.000.000 |
| DevOps Engineer (Senior) | 1 | 3.000.000 | 80 | 240.000.000 |
| DevOps Engineer (Intermediate) | 1 | 2.200.000 | 80 | 176.000.000 |
| UI/UX Designer | 1 | 2.000.000 | 40 | 80.000.000 |
| Total | 21 |  |  | 5.176.000.000 |

## 5.5. Biaya Non-Personil (Infrastruktur & Operasional)

### 5.5.1. Biaya Infrastruktur Cloud & Hardware

| No | Komponen | Spesifikasi | Biaya/Bulan (Rp) | Durasi (Bulan) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| 1 | Compute (Kubernetes) | 10 nodes, 4vCPU/16GB | 15.000.000 | 6 | 90.000.000 |
| 2 | Database (PostgreSQL) | Managed, 500GB | 5.000.000 | 6 | 30.000.000 |
| 3 | Data Warehouse (Snowflake) | Medium, 1TB | 20.000.000 | 6 | 120.000.000 |
| 4 | Data Lake (MinIO/S3) | 10TB | 8.000.000 | 6 | 48.000.000 |
| 5 | Graph DB (Neo4j) | Enterprise, 4 nodes | 15.000.000 | 6 | 90.000.000 |
| 6 | Kafka (MSK) | 3 brokers | 10.000.000 | 6 | 60.000.000 |
| 7 | MLflow/Kubeflow | Managed | 5.000.000 | 4 | 20.000.000 |
| 8 | Monitoring (Prometheus/Grafana) | Managed | 3.000.000 | 6 | 18.000.000 |
| 9 | Backup & DR | 10TB | 5.000.000 | 6 | 30.000.000 |
| 10 | Network & CDN | - | 2.000.000 | 6 | 12.000.000 |
| Total Infrastruktur Cloud |  |  |  |  | 518.000.000 |

### 5.5.2. Biaya Lisensi & Software

| No | Komponen | Biaya (Rp) | Durasi | Total Biaya (Rp) |
| --- | --- | --- | --- | --- |
| 1 | Neo4j Enterprise | 100.000.000 | 1 tahun | 100.000.000 |
| 2 | Snowflake | 80.000.000 | 1 tahun | 80.000.000 |
| 3 | MLflow Enterprise | 30.000.000 | 1 tahun | 30.000.000 |
| 4 | Development Tools (IDE, CI/CD) | 10.000.000 | 6 bulan | 10.000.000 |
| 5 | Monitoring Tools (Datadog/New Relic) | 15.000.000 | 6 bulan | 15.000.000 |
| 6 | Project Management Tools (Jira, Confluence) | 8.000.000 | 6 bulan | 8.000.000 |
| Total Lisensi & Software |  |  |  | 243.000.000 |

### 5.5.3. Biaya Overhead & Operasional

| No | Komponen | Biaya (Rp) | Deskripsi |
| --- | --- | --- | --- |
| 1 | Pelatihan & Sertifikasi Tim | 50.000.000 | Training untuk tim baru |
| 2 | Change Management & User Training | 75.000.000 | Training untuk end-user |
| 3 | Konsultan Eksternal (jika diperlukan) | 100.000.000 | Ahli khusus jika dibutuhkan |
| 4 | Travel & Akomodasi | 25.000.000 | Jika ada meeting onsite |
| 5 | Administrasi & Dokumentasi | 20.000.000 | Alat tulis, cetak, dll. |
| 6 | Cadangan Likuiditas | 30.000.000 | Untuk kebutuhan mendadak |
| Total Overhead & Operasional |  |  | 300.000.000 |

### 5.5.4. Rekapitulasi Biaya Non-Personil

| Kategori | Total Biaya (Rp) | Persentase |
| --- | --- | --- |
| Infrastruktur Cloud | 518.000.000 | 48.8% |
| Lisensi & Software | 243.000.000 | 22.9% |
| Overhead & Operasional | 300.000.000 | 28.3% |
| Total Non-Personil | 1.061.000.000 | 100% |

## 5.6. Total Anggaran Proyek

### 5.6.1. Rekapitulasi Akhir

| Kategori | Total Biaya (Rp) | Persentase |
| --- | --- | --- |
| Biaya Personil | 2.168.000.000 | 67.1% |
| Biaya Non-Personil | 1.061.000.000 | 32.9% |
| Subtotal | 3.229.000.000 | 100% |
| Contingency (15%) | 484.350.000 | - |
| Total Anggaran Proyek | 3.713.350.000 | - |

### 5.6.2. Detail Anggaran per Fase

| Fase | Personil (Rp) | Non-Personil (Rp) | Total per Fase (Rp) |
| --- | --- | --- | --- |
| Fase 1: Inisiasi & Perencanaan | 141.600.000 | 25.000.000 | 166.600.000 |
| Fase 2: Data Platform & Infrastructure | 194.600.000 | 180.000.000 | 374.600.000 |
| Fase 3: BI Dashboard & KPI | 254.600.000 | 50.000.000 | 304.600.000 |
| Fase 4: AI/ML Model Development | 213.200.000 | 80.000.000 | 293.200.000 |
| Fase 5: Knowledge Graph & Decision | 145.800.000 | 60.000.000 | 205.800.000 |
| Fase 6: Integration & Testing | 205.400.000 | 100.000.000 | 305.400.000 |
| Fase 7: Deployment & Go-Live | 94.000.000 | 66.000.000 | 160.000.000 |
| Management & Overhead | 526.800.000 | 300.000.000 | 826.800.000 |
| Infrastruktur (multi-fase) | - | 200.000.000 | 200.000.000 |
| Subtotal | 1.776.000.000 | 1.061.000.000 | 2.837.000.000 |

### 5.6.3. Cash Flow Plan

| Bulan | Personil (Rp) | Non-Personil (Rp) | Total (Rp) | Kumulatif (Rp) |
| --- | --- | --- | --- | --- |
| Bulan 1 | 150.000.000 | 100.000.000 | 250.000.000 | 250.000.000 |
| Bulan 2 | 250.000.000 | 150.000.000 | 400.000.000 | 650.000.000 |
| Bulan 3 | 300.000.000 | 200.000.000 | 500.000.000 | 1.150.000.000 |
| Bulan 4 | 300.000.000 | 250.000.000 | 550.000.000 | 1.700.000.000 |
| Bulan 5 | 300.000.000 | 200.000.000 | 500.000.000 | 2.200.000.000 |
| Bulan 6 | 250.000.000 | 161.000.000 | 411.000.000 | 2.611.000.000 |
| Contingency | - | - | 484.350.000 | 3.095.350.000 |
| Total | 1.550.000.000 | 1.061.000.000 | 3.095.350.000 | 3.095.350.000 |

Catatan: Biaya contingency (15%) akan digunakan jika terjadi perubahan scope, delay, atau kebutuhan tambahan yang tidak terduga.

## 5.7. Cost Management Process

### 5.7.1. Cost Control & Monitoring

| Aktivitas | Frekuensi | Penanggung Jawab | Tools |
| --- | --- | --- | --- |
| Budget Planning | Awal proyek | PM + Finance | Excel, PM Tools |
| Cost Tracking | Mingguan | PM | Timesheet, Invoices |
| Timesheet Approval | Mingguan | Tech Lead | Time Tracking System |
| Vendor Invoice Review | Bulanan | PM + Finance | Invoice System |
| Financial Reporting | Bulanan | PM + Finance | Excel/Reporting Tools |
| Budget Variance Analysis | Bulanan | PM + Finance | Excel |
| Change Impact on Budget | Setiap perubahan | CCB | Change Request Form |
| Forecast Update | Bulanan | PM | MS Project |

### 5.7.2. Budget Variance Threshold

| Variance | Action | Responsibility |
| --- | --- | --- |
| ≤ 5% | Monitor, no action needed | PM |
| 5-10% | Analyze impact, create mitigation plan | PM + Tech Lead |
| 10-20% | Immediate action, escalate to sponsor | PM + Sponsor |
| > 20% | Project review, possible restructuring | PM + Sponsor + CCB |

### 5.7.3. Cost Breakdown Structure (CBS)

text

PROJECT COST BREAKDOWN STRUCTURE (CBS)

│

├── 1.0 DIRECT COSTS (2.168.000.000)

│   ├── 1.1 Personil

│   │   ├── Project Manager

│   │   ├── Tech Lead

│   │   ├── Developers (FE, BE, DE, DS, ML)

│   │   ├── QA & DevOps

│   │   └── Support Staff (BA, KE, UI/UX)

│   └── 1.2 Travel & Per Diem

│

├── 2.0 INDIRECT COSTS (1.061.000.000)

│   ├── 2.1 Infrastructure (518.000.000)

│   │   ├── Cloud Compute

│   │   ├── Storage (Data Lake, DW)

│   │   ├── Database (SQL, Graph, Time-series)

│   │   └── Networking & CDN

│   ├── 2.2 Software Licenses (243.000.000)

│   │   ├── Neo4j Enterprise

│   │   ├── Snowflake

│   │   ├── MLflow

│   │   └── Development & Monitoring Tools

│   └── 2.3 Operations (300.000.000)

│       ├── Training & Change Management

│       ├── Documentation

│       └── Administrative Costs

│

└── 3.0 CONTINGENCY & RESERVE (484.350.000)

├── 3.1 Management Reserve (5%)

└── 3.2 Contingency Reserve (10%)

## 5.8. Payment Milestone Schedule

| Milestone | Kode | Target Minggu | Payment (%) | Payment Amount (Rp) | Deliverable |
| --- | --- | --- | --- | --- | --- |
| Project Kick-off | M0 | 1 | 15% | 465.502.500 | Project Charter, PMP |
| Data Platform Complete | M1 | 8 | 15% | 465.502.500 | Data Lake, DW, ETL, CDC |
| BI Dashboard Complete | M2 | 12 | 20% | 620.670.000 | 8 Dashboard, KPI, Alert |
| AI/ML Models Complete | M3 | 16 | 15% | 465.502.500 | 5 Model Produksi |
| Graph & Decision Complete | M4 | 18 | 15% | 465.502.500 | Knowledge Graph, Decision Intel |
| Integration & UAT Complete | M5 | 22 | 10% | 310.335.000 | SIT, UAT Sign-off |
| Go-Live | M6 | 24 | 10% | 310.335.000 | Production Deployment |
| Total |  |  | 100% | 3.103.350.000 |  |

Catatan: Total payment di atas adalah total anggaran setelah dikurangi contingency reserve. Contingency reserve (Rp 484.350.000) hanya akan digunakan jika diperlukan dengan approval dari Project Sponsor.

# BAB 6: MANAJEMEN KUALITAS PROYEK (PMBOK Area 5)

## 6.1. Tujuan Manajemen Kualitas

Manajemen kualitas proyek bertujuan untuk memastikan deliverables proyek memenuhi standar kualitas yang ditentukan dan kepuasan stakeholder. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Kualitas Produk | Memastikan platform Intelligence & Decision Platform memenuhi semua acceptance criteria |
| 2 | Kualitas Proses | Memastikan proses pengembangan mengikuti standar terbaik dan best practices |
| 3 | Kepuasan Pengguna | Memastikan platform memenuhi kebutuhan dan harapan pengguna |
| 4 | Keandalan | Memastikan platform berjalan dengan stabil, aman, dan performa tinggi |
| 5 | Perbaikan Berkelanjutan | Menerapkan continuous improvement melalui feedback dan pembelajaran |

## 6.2. Quality Policy

### 6.2.1. Kebijakan Kualitas Proyek

"Kami berkomitmen untuk memberikan platform Intelligence & Decision Platform yang andal, akurat, dan aman dengan memenuhi semua acceptance criteria dan standar kualitas yang ditetapkan. Kami akan menerapkan pendekatan kualitas terintegrasi yang mencakup seluruh siklus hidup proyek, dari perencanaan hingga implementasi, dengan fokus pada kepuasan stakeholder dan perbaikan berkelanjutan."

### 6.2.2. Prinsip Kualitas

| No | Prinsip | Deskripsi |
| --- | --- | --- |
| 1 | Quality by Design | Kualitas dibangun sejak tahap perencanaan dan desain, bukan setelah pengembangan |
| 2 | Customer Focus | Kualitas diukur dari kepuasan pengguna dan pemenuhan kebutuhan bisnis |
| 3 | Continuous Improvement | Selalu berusaha meningkatkan kualitas melalui feedback dan lessons learned |
| 4 | Data-Driven Quality | Keputusan kualitas didasarkan pada data dan metrik yang terukur |
| 5 | Defect Prevention | Fokus pada pencegahan defect daripada menemukan dan memperbaiki defect |
| 6 | Team Ownership | Kualitas adalah tanggung jawab bersama seluruh tim proyek |

## 6.3. Quality Management Plan

### 6.3.1. Quality Standards & Metrics

| Kategori | Standar | Metrik | Target | Metode Pengukuran |
| --- | --- | --- | --- | --- |
| Code Quality | SonarQube | Technical Debt Ratio | < 5% | SonarQube Analysis |
|  |  | Code Smells | 0 Critical | SonarQube Analysis |
|  |  | Duplication | < 3% | SonarQube Analysis |
|  |  | Unit Test Coverage | > 80% | Jest/PyTest/JUnit |
| Security | OWASP Top 10 | Critical Vulnerabilities | 0 | OWASP ZAP, Snyk |
|  |  | High Vulnerabilities | 0 | OWASP ZAP, Snyk |
|  |  | Medium Vulnerabilities | < 5 | OWASP ZAP, Snyk |
| Performance | Load Testing | Dashboard Load | ≤ 5 detik | JMeter, k6 |
|  |  | BI Query (Sederhana) | ≤ 10 detik | JMeter, k6 |
|  |  | BI Query (Kompleks) | ≤ 30 detik | JMeter, k6 |
|  |  | Data Pipeline Latency | ≤ 5 menit | Monitoring |
|  |  | Model Inference | ≤ 3 detik | MLflow Monitoring |
|  |  | Graph Query | ≤ 5 detik | Neo4j Monitoring |
| Reliability | System Testing | Uptime | 99.9% | Prometheus/Grafana |
|  |  | Error Rate | < 0.5% | Application Monitoring |
|  |  | MTBF | > 720 jam | System Monitoring |
| Data Quality | Data Quality Rules | Completeness | ≥ 98% | Great Expectations |
|  |  | Accuracy | ≥ 99% | Great Expectations |
|  |  | Consistency | ≥ 99% | Great Expectations |
|  |  | Timeliness | ≤ 5 menit | Data Pipeline Monitoring |
| User Experience | SUS Score | Acceptability | ≥ 70 | SUS Survey |
|  |  | User Satisfaction | ≥ 4.0/5.0 | User Survey |
| AI/ML Quality | Model Performance | Model Accuracy | ≥ 80% | Model Evaluation |
|  |  | Inference Time | ≤ 3 detik | MLflow Monitoring |
|  |  | Explainability | 100% | SHAP/LIME Coverage |
| Documentation | Completeness | API Documentation | 100% | OpenAPI/Swagger |
|  |  | User Guide | 100% | Document Review |
|  |  | Technical Docs | 100% | Document Review |

### 6.3.2. Quality Management Roles & Responsibilities

| Peran | Tanggung Jawab Kualitas |
| --- | --- |
| Project Manager | - Oversee quality management plan - Ensure quality standards are met - Approve quality reports - Escalate quality issues |
| Tech Lead | - Ensure technical quality standards - Code review oversight - Architecture quality - Technical debt management |
| Lead QA | - Develop test strategy and plan - Manage testing execution - Track defect metrics - Quality reporting |
| Lead Data Scientist | - Model quality standards - Data quality for ML - Model performance monitoring - Explainability standards |
| Lead Data Engineer | - Data quality standards - Data pipeline reliability - Data lineage quality - Data governance |
| All Developers | - Follow coding standards - Write unit tests - Participate in code reviews - Fix defects promptly |
| QA Engineers | - Execute test cases - Report defects - Perform regression testing - Document test results |

## 6.4. Quality Control Activities

### 6.4.1. Testing Strategy & Phases

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           TESTING STRATEGY PHASES                               │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ PHASE 1: UNIT TESTING                                                      │ │

│  │ - Developer writes unit tests during development                          │ │

│  │ - Coverage target: > 80%                                                  │ │

│  │ - Tools: JUnit (Java), PyTest (Python), Jest (JavaScript)                 │ │

│  │ - Executed: Every build (CI/CD)                                           │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ PHASE 2: INTEGRATION TESTING                                               │ │

│  │ - Test interactions between services                                      │ │

│  │ - Tools: Postman, Newman, Pact                                            │ │

│  │ - Executed: Every sprint                                                  │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ PHASE 3: SYSTEM TESTING                                                    │ │

│  │ - End-to-end testing of entire system                                     │ │

│  │ - Tools: Selenium, Cypress, Playwright                                    │ │

│  │ - Executed: Per sprint release                                            │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ PHASE 4: PERFORMANCE TESTING                                               │ │

│  │ - Load testing, stress testing, endurance testing                         │ │

│  │ - Tools: JMeter, k6                                                       │ │

│  │ - Executed: Before UAT                                                    │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ PHASE 5: SECURITY TESTING                                                  │ │

│  │ - Vulnerability scanning, penetration testing                             │ │

│  │ - Tools: OWASP ZAP, Snyk, SonarQube                                      │ │

│  │ - Executed: Before deployment                                             │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ PHASE 6: USER ACCEPTANCE TESTING (UAT)                                    │ │

│  │ - End-user testing against business requirements                          │ │

│  │ - Executed: Key users, business stakeholders                              │ │

│  │ - Sign-off required for go-live                                           │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### 6.4.2. Test Case Management

#### 6.4.2.1. Test Case Template

| Field | Deskripsi | Contoh |
| --- | --- | --- |
| Test Case ID | Unique identifier | TC-BI-001 |
| Requirement ID | Linked requirement | R-BI-001 |
| Test Title | Brief description | Verifikasi Executive Dashboard |
| Priority | P0/P1/P2 | P0 |
| Pre-conditions | Setup required | Data pipeline active, user logged in |
| Test Steps | Step-by-step instructions | 1. Navigate to Executive Dashboard 2. Verify KPI cards displayed 3. Verify charts render 4. Verify load time |
| Expected Result | Expected outcome | All KPI cards display correct data, charts render, load ≤ 5 seconds |
| Actual Result | Actual outcome | Pass/Fail |
| Status | Pass/Fail/Blocked | Pass |
| Tester | Who executed | QA Engineer |
| Date | Execution date | 2026-01-15 |

#### 6.4.2.2. Test Case Repository Structure

text

/team-repo/testing/

├── /test-plans/

│   ├── unit-test-plan.md

│   ├── integration-test-plan.md

│   ├── system-test-plan.md

│   ├── performance-test-plan.md

│   ├── security-test-plan.md

│   └── uat-plan.md

├── /test-cases/

│   ├── /bi/

│   │   ├── TC-BI-001_dashboard_executive.md

│   │   ├── TC-BI-002_dashboard_farm.md

│   │   ├── TC-BI-003_kpi_definition.md

│   │   └── ...

│   ├── /data-pipeline/

│   │   ├── TC-DPL-001_cdc_ingestion.md

│   │   ├── TC-DPL-002_etl_pipeline.md

│   │   └── ...

│   ├── /ai-ml/

│   │   ├── TC-AI-001_demand_forecast.md

│   │   ├── TC-AI-002_yield_prediction.md

│   │   └── ...

│   ├── /knowledge-graph/

│   │   ├── TC-KG-001_ontology.md

│   │   ├── TC-KG-002_graph_query.md

│   │   └── ...

│   └── /decision/

│       ├── TC-DEC-001_what_if.md

│       ├── TC-DEC-002_optimization.md

│       └── ...

├── /test-reports/

│   ├── sprint-1-report.md

│   ├── sprint-2-report.md

│   └── ...

└── /automation/

├── /unit/

├── /integration/

└── /e2e/

### 6.4.3. Defect Management

#### 6.4.3.1. Defect Severity & Priority

| Severity | Deskripsi | Priority | SLA |
| --- | --- | --- | --- |
| Critical (S1) | System crash, data loss, security breach | P0 | Fix within 24 hours |
| High (S2) | Major feature broken, performance issue | P1 | Fix within 3 days |
| Medium (S3) | Minor feature broken, UI issue | P2 | Fix within sprint |
| Low (S4) | Cosmetic issue, minor enhancement | P3 | Next sprint |

#### 6.4.3.2. Defect Lifecycle

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           DEFECT LIFECYCLE                                      │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  1. DETECTION                                                                   │

│     (QA / Developer / User)                                                     │

│     ↓                                                                           │

│  2. LOGGED                                                                      │

│     (QA logs defect in Jira with severity/priority)                             │

│     ↓                                                                           │

│  3. TRIAGE                                                                      │

│     (PM + Tech Lead + QA Lead - prioritize)                                     │

│     ↓                                                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │  APPROVED  → 4. ASSIGNED (Tech Lead assigns to developer)                  │ │

│  │  ↓                                                                        │ │

│  │  5. IN PROGRESS (Developer fixes defect)                                   │ │

│  │  ↓                                                                        │ │

│  │  6. CODE REVIEW (Tech Lead reviews fix)                                    │ │

│  │  ↓                                                                        │ │

│  │  7. FIXED (Developer commits fix, CI/CD runs tests)                       │ │

│  │  ↓                                                                        │ │

│  │  8. VERIFIED (QA verifies fix)                                            │ │

│  │  ↓                                                                        │ │

│  │  9. CLOSED (Defect closed)                                                │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│  │                                                                              │

│  │  REJECTED → Closed with reason                                              │

│  │  DEFERRED → Moved to backlog                                                │

│  │  DUPLICATE → Merged with existing defect                                    │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

#### 6.4.3.3. Defect Report Template

| Field | Deskripsi |
| --- | --- |
| Defect ID | Unique identifier (e.g., DEF-001) |
| Title | Brief description of defect |
| Severity | Critical/High/Medium/Low |
| Priority | P0/P1/P2/P3 |
| Environment | Dev/Staging/Production |
| Module | BI/Data Pipeline/AI/ML/Graph/Decision |
| Steps to Reproduce | Detailed steps to reproduce |
| Expected Result | Expected behavior |
| Actual Result | Actual behavior |
| Attachments | Screenshots, logs, videos |
| Reported By | Name |
| Assigned To | Developer |
| Status | New/Assigned/In Progress/Fixed/Verified/Closed |
| Fixed Date | Date fixed |
| Root Cause | Cause analysis |

### 6.4.4. Quality Control Schedule

| Aktivitas | Frekuensi | Tools | Penanggung Jawab |
| --- | --- | --- | --- |
| Code Review | Setiap PR | GitHub PR | Tech Lead |
| Unit Testing | Setiap build | JUnit, PyTest, Jest | Developer |
| Integration Testing | Setiap sprint | Postman, Newman | QA |
| System Testing | Setiap sprint | Selenium, Cypress | QA |
| Performance Testing | Setiap sprint | JMeter, k6 | QA + DevOps |
| Security Testing | Bulanan | OWASP ZAP, Snyk | DevOps + QA |
| Data Quality Check | Harian | Great Expectations | Data Engineer |
| Model Performance | Harian | MLflow, Prometheus | Data Scientist |
| UAT | Sebelum release | Manual Testing | Key Users |
| SonarQube Analysis | Setiap build | SonarQube | Tech Lead |
| Defect Triage | Mingguan | Jira | PM + Tech Lead + QA Lead |
| Quality Report | Bulanan | Excel/Jira | QA Lead |

## 6.5. Quality Assurance Activities

### 6.5.1. Process Assurance

| No | Aktivitas | Deskripsi | Frekuensi | Penanggung Jawab |
| --- | --- | --- | --- | --- |
| 1 | Process Audit | Audit proses pengembangan terhadap standar | Setiap sprint | QA Lead |
| 2 | Code Quality Review | Review kode terhadap standar coding | Setiap sprint | Tech Lead |
| 3 | Documentation Review | Review kelengkapan dokumentasi | Setiap milestone | PM + QA Lead |
| 4 | Quality Metrics Review | Review metrik kualitas | Mingguan | QA Lead + PM |
| 5 | Peer Review | Review antar developer | Setiap PR | All Developers |
| 6 | Architecture Review | Review arsitektur sistem | Setiap milestone | Tech Lead |
| 7 | Security Review | Review keamanan sistem | Bulanan | DevOps + Tech Lead |
| 8 | Performance Review | Review performa sistem | Bulanan | DevOps + QA |

### 6.5.2. Code Quality Standards

#### 6.5.2.1. Coding Standards

| Aspek | Standar | Tools |
| --- | --- | --- |
| Backend (Java/Spring Boot) | Google Java Style Guide | Checkstyle, PMD |
| Backend (Python/FastAPI) | PEP 8 | Black, Flake8, mypy |
| Frontend (React/Next.js) | Airbnb Style Guide | ESLint, Prettier |
| SQL | Consistent naming, avoid SELECT * | SQLFluff |
| Git | Conventional Commits | Commitlint |
| Testing | Arrange-Act-Assert pattern | - |

#### 6.5.2.2. Code Review Checklist

| No | Checklist Item | Status |
| --- | --- | --- |
| 1 | Code follows coding standards | ☐ |
| 2 | Unit tests written and passing | ☐ |
| 3 | Integration tests written (if applicable) | ☐ |
| 4 | No security vulnerabilities | ☐ |
| 5 | Performance is acceptable | ☐ |
| 6 | Documentation updated | ☐ |
| 7 | Logging appropriately | ☐ |
| 8 | Error handling implemented | ☐ |
| 9 | No code duplication | ☐ |
| 10 | Follows design patterns | ☐ |

### 6.5.3. Quality Gates

#### 6.5.3.1. Quality Gates Definition

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                              QUALITY GATES                                       │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  GATE 1: CODE COMMIT                                                             │

│  ├── Unit tests pass (coverage ≥ 80%)                                           │

│  ├── SonarQube analysis passes (A Rating)                                       │

│  ├── No critical security vulnerabilities                                        │

│  └── Code review approval (at least 1 approver)                                 │

│                                                                                  │

│  GATE 2: SPRINT RELEASE                                                          │

│  ├── All unit tests pass                                                        │

│  ├── Integration tests pass                                                     │

│  ├── System tests pass                                                          │

│  ├── Zero critical/high severity defects                                        │

│  └── Documentation updated                                                      │

│                                                                                  │

│  GATE 3: PERFORMANCE & SECURITY                                                  │

│  ├── Load tests pass (≤ 5s dashboard, ≤ 10s query)                              │

│  ├── Security tests pass (0 critical/high vulnerabilities)                      │

│  ├── Data quality checks pass (≥ 98% completeness)                              │

│  └── Model performance meets target (≥ 80% accuracy)                            │

│                                                                                  │

│  GATE 4: UAT & SIGN-OFF                                                          │

│  ├── All acceptance criteria met                                                │

│  ├── User acceptance tests pass                                                 │

│  ├── User satisfaction survey ≥ 4.0/5.0                                         │

│  └── UAT sign-off by key users                                                  │

│                                                                                  │

│  GATE 5: PRODUCTION DEPLOYMENT                                                   │

│  ├── All quality gates passed                                                   │

│  ├── Deployment checklist completed                                             │

│  ├── Rollback plan ready                                                        │

│  └── Hypercare support ready                                                    │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

## 6.6. Acceptance Criteria Detail per Komponen

### 6.6.1. Data Platform Acceptance Criteria

| No | Kriteria | Metode Verifikasi | Target |
| --- | --- | --- | --- |
| 1 | Data pipeline berhasil menginjeksi data dari semua modul | Testing setiap source | 100% success |
| 2 | Data Lake, Data Warehouse, Data Mart tersedia | System verification | All available |
| 3 | Data quality monitoring aktif | Dashboard monitoring | Active |
| 4 | Data lineage tersedia | Query lineage API | Available |
| 5 | Data pipeline latency ≤ 5 menit | Performance testing | ≤ 5 menit |
| 6 | Data completeness ≥ 98% | Data quality check | ≥ 98% |
| 7 | Data accuracy ≥ 99% | Data quality check | ≥ 99% |

### 6.6.2. BI Dashboard Acceptance Criteria

| No | Kriteria | Metode Verifikasi | Target |
| --- | --- | --- | --- |
| 1 | 8 dashboard tersedia dan berfungsi | Functional testing | All 8 |
| 2 | Drill-down berfungsi | Functional testing | Working |
| 3 | Filtering berfungsi | Functional testing | Working |
| 4 | Export (Excel, PDF, CSV) berfungsi | Functional testing | Working |
| 5 | Scheduled reports berfungsi | Testing + verification | Working |
| 6 | KPI definition berfungsi | Functional testing | Working |
| 7 | KPI alert berfungsi | Functional testing | Working |
| 8 | Dashboard load time ≤ 5 detik | Performance testing | ≤ 5 detik |
| 9 | BI query (sederhana) ≤ 10 detik | Performance testing | ≤ 10 detik |
| 10 | BI query (kompleks) ≤ 30 detik | Performance testing | ≤ 30 detik |

### 6.6.3. AI/ML Acceptance Criteria

| No | Kriteria | Metode Verifikasi | Target |
| --- | --- | --- | --- |
| 1 | 5 model AI production berfungsi | Model validation | 5 models |
| 2 | Model registry berfungsi | Functional testing | Working |
| 3 | Model monitoring berfungsi | Functional testing | Working |
| 4 | Explainability berfungsi | Functional testing | Working |
| 5 | Model inference time ≤ 3 detik | Performance testing | ≤ 3 detik |
| 6 | Model accuracy ≥ 80% | Model evaluation | ≥ 80% |
| 7 | Model #1: Demand Forecasting | Model evaluation | Accuracy ≥ 80% |
| 8 | Model #2: Crop Yield Prediction | Model evaluation | Accuracy ≥ 80% |
| 9 | Model #3: Inventory Forecasting | Model evaluation | Accuracy ≥ 80% |
| 10 | Model #4: Predictive Maintenance | Model evaluation | Accuracy ≥ 80% |
| 11 | Model #5: Anomaly Detection | Model evaluation | F1 ≥ 0.80 |

### 6.6.4. Knowledge Graph Acceptance Criteria

| No | Kriteria | Metode Verifikasi | Target |
| --- | --- | --- | --- |
| 1 | Ontology terdefinisi | Schema validation | Complete |
| 2 | Graph ingestion berfungsi | Data validation | Working |
| 3 | Graph query berfungsi | Functional testing | Working |
| 4 | Graph visualization berfungsi | Functional testing | Working |
| 5 | Path discovery berfungsi | Functional testing | Working |
| 6 | Impact analysis berfungsi | Functional testing | Working |
| 7 | Semantic search berfungsi | Functional testing | Working |
| 8 | Provenance tersedia | Data validation | Available |
| 9 | Graph query time ≤ 5 detik | Performance testing | ≤ 5 detik |
| 10 | Graph scalability (1M+ nodes) | System testing | ≥ 1M nodes |

### 6.6.5. Decision Intelligence Acceptance Criteria

| No | Kriteria | Metode Verifikasi | Target |
| --- | --- | --- | --- |
| 1 | What-if analysis berfungsi | Functional testing | Working |
| 2 | Scenario comparison berfungsi | Functional testing | Working |
| 3 | Optimization (land allocation) berfungsi | Functional testing | Working |
| 4 | Decision log berfungsi | Functional testing | Working |
| 5 | Outcome tracking berfungsi | Functional testing | Working |
| 6 | Closed-loop learning berfungsi | Functional testing | Working |

## 6.7. Quality Reporting

### 6.7.1. Weekly Quality Report Template

| Section | Content |
| --- | --- |
| Report Information | Report Date, Sprint, Prepared By |
| Quality Metrics Summary | Code quality, Test coverage, Defect count |
| Defect Status | Open/Closed/In Progress by severity |
| Test Execution Status | Pass/Fail/Blocked rate |
| Performance Metrics | Dashboard load time, Query time, Inference time |
| Data Quality Metrics | Completeness, Accuracy, Consistency |
| Model Performance | Accuracy, Drift, Inference time |
| Issues & Risks | Current issues, Mitigation plan |
| Action Items | Next steps, Owners, Deadlines |

### 6.7.2. Quality Dashboard (Metrics)

| Metric | Target | Current | Status |
| --- | --- | --- | --- |
| Code Coverage | ≥ 80% | 82% | 🟢 On Track |
| SonarQube Rating | A | A | 🟢 On Track |
| Technical Debt | < 5% | 3.2% | 🟢 On Track |
| Critical Defects | 0 | 0 | 🟢 On Track |
| High Defects | 0 | 2 | 🟡 Warning |
| Unit Test Pass Rate | 100% | 98% | 🟡 Warning |
| Dashboard Load Time | ≤ 5s | 3.2s | 🟢 On Track |
| Data Quality Completeness | ≥ 98% | 97.5% | 🟡 Warning |
| Model Accuracy | ≥ 80% | 82% | 🟢 On Track |
| UAT Sign-off | 100% | 60% | 🟡 In Progress |

### 6.7.3. Quality Review Meeting

| Aspek | Detail |
| --- | --- |
| Frekuensi | Mingguan (diintegrasikan dengan status meeting) |
| Peserta | PM, Tech Lead, QA Lead, Data Science Lead, Data Engineer Lead |
| Agenda | 1. Quality metrics review 2. Defect status and trends 3. Test execution status 4. Performance issues 5. Data quality issues 6. Model performance 7. Action items |

## 6.8. Continuous Improvement

### 6.8.1. Root Cause Analysis (RCA) Process

| Step | Aktivitas | Tools |
| --- | --- | --- |
| 1 | Identify Problem | Defect report, incident report |
| 2 | Gather Data | Logs, metrics, user feedback |
| 3 | Analyze Root Cause | 5 Whys, Fishbone Diagram |
| 4 | Identify Corrective Actions | Action plan |
| 5 | Implement Actions | Fix, process improvement |
| 6 | Verify Effectiveness | Monitor metrics |
| 7 | Document Lessons Learned | Lessons learned repository |

### 6.8.2. Lessons Learned Process

| Fase | Aktivitas | Output | Penanggung Jawab |
| --- | --- | --- | --- |
| Capture | Identifikasi lesson learned selama sprint | Notes, issues, solutions | All team members |
| Document | Dokumentasikan lesson learned di repository | Document per milestone | PM |
| Analyze | Analisis root cause dan impact | Analysis report | PM + Tech Lead |
| Share | Sharing dengan tim dan stakeholder | Presentation | PM |
| Apply | Terapkan improvement di sprint berikutnya | Action items | PM + Tech Lead |

### 6.8.3. Continuous Improvement Schedule

| Aktivitas | Frekuensi | Peserta |
| --- | --- | --- |
| Sprint Retrospective | Setiap 2 minggu | All team |
| Quality Metrics Review | Mingguan | PM + Leads |
| Tech Sharing Session | 2 minggu sekali | Technical team |
| Milestone Retrospective | Setiap milestone | PM + TL + Leads |
| Project Retrospective | Akhir proyek | All team |

# BAB 7: MANAJEMEN SUMBER DAYA PROYEK (PMBOK Area 6)

## 7.1. Tujuan Manajemen Sumber Daya

Manajemen sumber daya proyek bertujuan untuk memastikan sumber daya manusia, peralatan, dan material tersedia dan digunakan secara efektif. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Perencanaan Sumber Daya | Mengidentifikasi dan merencanakan kebutuhan sumber daya untuk setiap aktivitas |
| 2 | Optimalisasi Sumber Daya | Memastikan sumber daya digunakan secara efisien dan efektif |
| 3 | Pengembangan Tim | Membangun tim yang kompeten dan termotivasi |
| 4 | Manajemen Kinerja | Memonitor dan mengevaluasi kinerja tim secara berkelanjutan |
| 5 | Retensi Talenta | Menjaga motivasi dan retensi anggota tim berkualitas |

## 7.2. Organisasi Tim Proyek

### 7.2.1. Struktur Organisasi Tim

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                              PROJECT SPONSOR                                    │

│                           (Direksi Farm Nation Enterprise)                       │

└─────────────────────────────────────────────────────────────────────────────────┘

│

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           PROJECT MANAGER                                       │

│                        [Nama], PMP Certified                                    │

│                    Senior Project Manager (8+ years)                             │

└─────────────────────────────────────────────────────────────────────────────────┘

│            │            │            │            │            │

▼            ▼            ▼            ▼            ▼            ▼

┌──────────────┐ ┌──────────────┐ ┌──────────────┐ ┌──────────────┐ ┌──────────────┐ ┌──────────────┐

│  TECH LEAD   │ │  DATA SCI.   │ │  DATA ENG.   │ │   QA LEAD    │ │   DEVOPS     │ │  PRODUCT     │

│              │ │  LEAD        │ │  LEAD        │ │              │ │   LEAD       │ │  OWNER       │

│ Senior      │ │ Senior       │ │ Senior       │ │ Senior       │ │ Senior       │ │ (BA)        │

│ 8+ years    │ │ 8+ years     │ │ 8+ years     │ │ 6+ years     │ │ 6+ years     │ │ 5+ years    │

└──────────────┘ └──────────────┘ └──────────────┘ └──────────────┘ └──────────────┘ └──────────────┘

│    │    │       │    │          │    │          │    │           │    │          │

▼    ▼    ▼       ▼    ▼          ▼    ▼          ▼    ▼           ▼    ▼          ▼

┌────┬────┬────┐ ┌──┬──┬──┐ ┌──┬──┬──┐ ┌──┬──┐ ┌──┬──┐ ┌──┬──┐

│BE  │BE  │BE  │ │DS1│DS2│KE │ │DE1│DE2│ │QA1│QA2│ │DV1│DV2│ │BA1│

│Se- │Int │Int │ │Se- │Int│In-│ │Se-│Int│ │Se-│In-│ │Se-│In-│ │Int│

│nior│er- │er- │ │nior│er-│ter│ │nior│er-│ │nior│ter│ │nior│ter│ │er- │

│5   │me- │me- │ │5   │me-│me-│ │5   │me-│ │5   │me-│ │5   │me-│ │me- │

│yrs │di- │di- │ │yrs │di-│di-│ │yrs │di-│ │yrs │di-│ │yrs │di-│ │di- │

│    │ate │ate │ │    │ate│ate│ │    │ate│ │    │ate│ │    │ate│ │ate │

└────┴────┴────┘ └──┴──┴──┘ └──┴──┴──┘ └──┴──┘ └──┴──┘ └──┴──┘

### 7.2.2. Deskripsi Peran & Tanggung Jawab

#### 7.2.2.1. Project Manager

| Aspek | Detail |
| --- | --- |
| Peran | Project Manager |
| Kualifikasi | - PMP Certified - 8+ tahun pengalaman manajemen proyek TI - Pengalaman proyek data/analytics - Agile/Scrum certification |
| Jumlah | 1 orang |
| Keterlibatan | Full-time (6 bulan) |
| Tanggung Jawab | - Mengelola keseluruhan proyek - Mengembangkan dan memelihara PMP - Mengelola stakeholder dan komunikasi - Mengelola budget dan schedule - Mengelola risiko dan perubahan - Melaporkan progress ke sponsor - Memimpin tim dan memotivasi - Memastikan quality standards terpenuhi |
| KPI | - Project on-time delivery - Project within budget - Stakeholder satisfaction - Team satisfaction |

#### 7.2.2.2. Tech Lead

| Aspek | Detail |
| --- | --- |
| Peran | Technical Lead / Lead Engineer |
| Kualifikasi | - 8+ tahun pengalaman pengembangan software - Pengalaman arsitektur microservices - Pengalaman cloud (AWS/GCP/Azure) - Pengalaman Python, Java, atau Node.js |
| Jumlah | 1 orang |
| Keterlibatan | Full-time (6 bulan) |
| Tanggung Jawab | - Merancang arsitektur sistem - Mengelola tim pengembangan - Melakukan code review - Memastikan best practices diikuti - Mengelola technical debt - Koordinasi antar tim teknis - Memastikan kualitas teknis |
| KPI | - Code quality score - Technical debt ratio - Sprint delivery rate - Team velocity |

#### 7.2.2.3. Backend Developer

| Aspek | Detail |
| --- | --- |
| Peran | Backend Developer |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman Spring Boot / FastAPI / NestJS - Pengalaman PostgreSQL, REST API, GraphQL - Pengalaman microservices |
| Jumlah | 3 orang (1 Senior, 2 Intermediate) |
| Keterlibatan | Full-time (6 bulan) |
| Tanggung Jawab | - Mengembangkan API dan microservices - Mengintegrasikan dengan sistem lain - Mengoptimalkan performa backend - Menulis unit dan integration tests - Berpartisipasi dalam code review |
| KPI | - Story points delivered - Code quality score - Defect rate - API performance |

#### 7.2.2.4. Frontend Developer

| Aspek | Detail |
| --- | --- |
| Peran | Frontend Developer |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman React / Next.js / TypeScript - Pengalaman D3.js / Chart.js - Pengalaman GraphQL client |
| Jumlah | 2 orang (1 Senior, 1 Intermediate) |
| Keterlibatan | 5 bulan |
| Tanggung Jawab | - Mengembangkan dashboard dan UI - Implementasi visualisasi data - Responsive design - Menulis unit tests - Berpartisipasi dalam code review |
| KPI | - Dashboard load time - UI/UX quality score - Story points delivered - Defect rate |

#### 7.2.2.5. Data Engineer

| Aspek | Detail |
| --- | --- |
| Peran | Data Engineer |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman Apache Spark, Kafka, Airflow - Pengalaman Snowflake/BigQuery, PostgreSQL - Pengalaman Python, SQL |
| Jumlah | 3 orang (1 Senior, 2 Intermediate) |
| Keterlibatan | 4 bulan |
| Tanggung Jawab | - Merancang data pipeline - Implementasi CDC (Debezium + Kafka) - Mengembangkan ETL/ELT pipeline - Mengelola Data Lake dan Data Warehouse - Mengelola Data Quality dan Lineage - Mengoptimalkan performa data |
| KPI | - Data pipeline latency - Data quality score - Pipeline uptime - Data freshness |

#### 7.2.2.6. Data Scientist

| Aspek | Detail |
| --- | --- |
| Peran | Data Scientist |
| Kualifikasi | - 3-5+ tahun pengalaman - Master/PhD di bidang terkait - Pengalaman Python, scikit-learn, TensorFlow/PyTorch - Pengalaman model forecasting, predictive analytics |
| Jumlah | 2 orang (1 Senior, 1 Intermediate) |
| Keterlibatan | 4 bulan |
| Tanggung Jawab | - Mengembangkan model AI/ML - Melakukan feature engineering - Model evaluation dan validation - Implementasi explainable AI (SHAP/LIME) - Mengelola model lifecycle |
| KPI | - Model accuracy - Inference time - Model drift detection - Explanation quality |

#### 7.2.2.7. ML Engineer

| Aspek | Detail |
| --- | --- |
| Peran | ML Engineer / MLOps Engineer |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman MLflow, Kubeflow - Pengalaman containerization (Docker, Kubernetes) - Pengalaman Python, CI/CD |
| Jumlah | 1 orang |
| Keterlibatan | 4 bulan |
| Tanggung Jawab | - Setup MLOps infrastructure - Mengelola model registry - Implementasi model monitoring - Mengelola CI/CD untuk model - Optimasi model deployment |
| KPI | - Model deployment success - Monitoring coverage - Drift detection time - Infrastructure uptime |

#### 7.2.2.8. Knowledge Engineer

| Aspek | Detail |
| --- | --- |
| Peran | Knowledge Engineer |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman Neo4j / Graph databases - Pengalaman ontology design - Pengalaman Python, Cypher, GraphQL |
| Jumlah | 1 orang |
| Keterlibatan | 3 bulan |
| Tanggung Jawab | - Mendefinisikan ontology - Mengembangkan graph ingestion - Mengembangkan graph query engine - Implementasi semantic search - Pengelolaan provenance |
| KPI | - Graph query time - Node/relationship count - Ingestion latency - Semantic search accuracy |

#### 7.2.2.9. QA Engineer

| Aspek | Detail |
| --- | --- |
| Peran | QA Engineer / Test Engineer |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman automated testing - Pengalaman Selenium, JMeter, Postman - Pengalaman API testing |
| Jumlah | 2 orang (1 Senior, 1 Intermediate) |
| Keterlibatan | 5 bulan |
| Tanggung Jawab | - Mengembangkan test strategy - Menulis test cases - Melakukan manual dan automated testing - Melakukan performance testing - Melaporkan defect dan quality metrics |
| KPI | - Test coverage - Defect detection rate - Regression test pass rate - UAT sign-off |

#### 7.2.2.10. DevOps Engineer

| Aspek | Detail |
| --- | --- |
| Peran | DevOps Engineer |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman Kubernetes, Docker - Pengalaman CI/CD (GitHub Actions, Jenkins) - Pengalaman cloud (AWS/GCP/Azure) - Pengalaman monitoring (Prometheus, Grafana) |
| Jumlah | 2 orang (1 Senior, 1 Intermediate) |
| Keterlibatan | 4 bulan |
| Tanggung Jawab | - Setup infrastructure (Kubernetes) - Mengelola CI/CD pipeline - Setup monitoring dan alerting - Mengelola security - Setup backup dan disaster recovery |
| KPI | - Infrastructure uptime - Deployment success rate - MTTD (Mean Time to Detect) - MTTR (Mean Time to Resolve) |

#### 7.2.2.11. Business Analyst / Product Owner

| Aspek | Detail |
| --- | --- |
| Peran | Business Analyst / Product Owner |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman requirements gathering - Pemahaman domain pertanian - Agile / Scrum experience |
| Jumlah | 1 orang |
| Keterlibatan | 4 bulan |
| Tanggung Jawab | - Mengumpulkan dan memprioritaskan requirements - Menjaga product backlog - Berkomunikasi dengan stakeholder - Memvalidasi deliverables - Melakukan UAT coordination |
| KPI | - Requirement coverage - Stakeholder satisfaction - Sprint goal achievement - UAT sign-off |

#### 7.2.2.12. UI/UX Designer

| Aspek | Detail |
| --- | --- |
| Peran | UI/UX Designer |
| Kualifikasi | - 3-5+ tahun pengalaman - Pengalaman Figma, Adobe XD - Pengalaman design systems - Pemahaman dashboard design |
| Jumlah | 1 orang |
| Keterlibatan | 2 bulan (on-demand) |
| Tanggung Jawab | - Mendesain UI/UX untuk dashboard - Membuat wireframes dan prototypes - Menjaga konsistensi design system - Melakukan usability testing |
| KPI | - Design quality - User satisfaction - Consistency score |

## 7.3. Resource Plan Matrix

### 7.3.1. Resource Allocation by Phase

| Role | Fase 1 (W1-4) | Fase 2 (W5-8) | Fase 3 (W9-12) | Fase 4 (W13-16) | Fase 5 (W17-18) | Fase 6 (W19-22) | Fase 7 (W23-24) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| Tech Lead | 100% | 100% | 100% | 100% | 100% | 100% | 50% |
| BE Developer (Sr) | 50% | 100% | 100% | 50% | 100% | 100% | 50% |
| BE Developer (Int) x2 | 25% | 75% | 100% | 50% | 100% | 100% | 50% |
| FE Developer (Sr) | - | - | 100% | - | 100% | 100% | 50% |
| FE Developer (Int) | - | - | 100% | - | 50% | 100% | 50% |
| Data Engineer (Sr) | - | 100% | 50% | 50% | 25% | 50% | - |
| Data Engineer (Int) x2 | - | 100% | 50% | 50% | 25% | 50% | - |
| Data Scientist (Sr) | - | - | - | 100% | 50% | - | - |
| Data Scientist (Int) | - | - | - | 100% | 50% | - | - |
| ML Engineer | - | - | - | 100% | 50% | - | - |
| Knowledge Engineer | - | - | - | - | 100% | 50% | - |
| QA Engineer (Sr) | - | 25% | 50% | 50% | 50% | 100% | 100% |
| QA Engineer (Int) | - | 25% | 50% | 50% | 50% | 100% | 50% |
| DevOps (Sr) | 50% | 100% | 50% | 50% | 50% | 50% | 100% |
| DevOps (Int) | 25% | 100% | 50% | 50% | 50% | 50% | 50% |
| Business Analyst | 100% | 50% | 50% | 25% | 25% | 100% | 50% |
| UI/UX Designer | 100% | - | 25% | - | - | - | - |

### 7.3.2. Total Resource Requirement

| Role | Jumlah | Total Person-Days | Total Person-Month |
| --- | --- | --- | --- |
| Project Manager | 1 | 120 | 24 |
| Tech Lead | 1 | 120 | 24 |
| BE Developer (Sr) | 1 | 120 | 24 |
| BE Developer (Int) | 2 | 220 | 44 |
| FE Developer (Sr) | 1 | 100 | 20 |
| FE Developer (Int) | 1 | 90 | 18 |
| Data Engineer (Sr) | 1 | 80 | 16 |
| Data Engineer (Int) | 2 | 150 | 30 |
| Data Scientist (Sr) | 1 | 80 | 16 |
| Data Scientist (Int) | 1 | 80 | 16 |
| ML Engineer | 1 | 80 | 16 |
| Knowledge Engineer | 1 | 60 | 12 |
| QA Engineer (Sr) | 1 | 100 | 20 |
| QA Engineer (Int) | 1 | 90 | 18 |
| DevOps (Sr) | 1 | 80 | 16 |
| DevOps (Int) | 1 | 70 | 14 |
| Business Analyst | 1 | 80 | 16 |
| UI/UX Designer | 1 | 30 | 6 |
| Total | 18 | 1,750 | 350 |

## 7.4. Tim Development & Training

### 7.4.1. Team Development Plan

| No | Aktivitas | Target | Timeline | Budget |
| --- | --- | --- | --- | --- |
| 1 | Onboarding | All team members understand project scope and tech stack | Minggu 1 | 10.000.000 |
| 2 | Tech Stack Training | Backend: Spring Boot, FastAPI Frontend: React, Next.js, D3.js Data: Spark, Kafka, Snowflake ML: MLflow, Kubeflow, SHAP | Minggu 1-2 | 20.000.000 |
| 3 | Domain Training | Understanding agricultural operations, supply chain, finance | Minggu 2 | 10.000.000 |
| 4 | Agile/Scrum Training | Effective sprint execution, backlog management | Minggu 1 | 5.000.000 |
| 5 | Knowledge Transfer | Cross-team knowledge sharing sessions | Ongoing | 5.000.000 |
| 6 | Certification | AWS/GCP, PMP, Scrum Master (optional) | Selama proyek | 10.000.000 |

### 7.4.2. Team Motivation & Engagement

| No | Aktivitas | Frekuensi | Tujuan |
| --- | --- | --- | --- |
| 1 | Weekly Team Meeting | Mingguan | Align team, share progress |
| 2 | Sprint Retrospective | 2 minggu | Continuous improvement |
| 3 | Team Building Activities | Bulanan | Build team cohesion |
| 4 | Recognition & Rewards | Setiap sprint | Motivate high performers |
| 5 | 1-on-1 Meetings | Mingguan | Address individual concerns |

### 7.4.3. Team Recognition Program

| Pencapaian | Reward |
| --- | --- |
| Sprint Goal Achieved | Team celebration (lunch, snacks) |
| Zero Critical Defects | Recognition in weekly meeting |
| Best Performer per Sprint | Gift voucher / certificate |
| Milestone Achieved | Team dinner / celebration |
| Go-Live on Time | Bonus for all team members |
| User Satisfaction > 4.5 | Performance bonus + certificate |

## 7.5. Resource Management Process

### 7.5.1. Resource Request Process

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           RESOURCE REQUEST PROCESS                              │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  1. IDENTIFIKASI KEBUTUHAN                                                       │

│     - Tech Lead / PM mengidentifikasi resource gap                              │

│     - Berdasarkan workload dan timeline                                         │

│     ↓                                                                           │

│  2. SUBMIT RESOURCE REQUEST                                                     │

│     - Isi Resource Request Form                                                │

│     - Spesifikasi: Role, duration, skill requirement                           │

│     ↓                                                                           │

│  3. EVALUASI & APPROVAL                                                         │

│     - PM evaluates impact on budget                                             │

│     - Sponsor approval for additional resources                                │

│     ↓                                                                           │

│  4. RESOURCE ACQUISITION                                                        │

│     - HR / recruitment team finds candidate                                     │

│     - Interview and selection                                                   │

│     - Onboarding                                                                │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### 7.5.2. Resource Utilization Tracking

| Metrik | Target | Frequency | Tools |
| --- | --- | --- | --- |
| Resource Utilization | 75-85% | Mingguan | Time Tracking System |
| Overtime Rate | < 10% | Mingguan | Time Tracking System |
| Team Velocity | Tracking per sprint | Sprint | Jira |
| Sprint Goal Achievement | ≥ 80% | Sprint | Jira |
| Team Satisfaction | ≥ 4.0/5.0 | Bulanan | Survey |

### 7.5.3. Succession & Backup Plan

| Role | Primary | Backup | Knowledge Transfer Method |
| --- | --- | --- | --- |
| Project Manager | [PM Name] | [PM Back-up] | Daily stand-up, weekly report |
| Tech Lead | [Tech Lead Name] | Senior BE Developer | Code review, architecture sessions |
| BE Developer | [BE Developers] | Tech Lead / Peer | Pair programming, code review |
| FE Developer | [FE Developers] | Tech Lead / Peer | Pair programming, code review |
| Data Engineer | [DE Name] | Senior BE Developer | Documentation, KT sessions |
| Data Scientist | [DS Name] | ML Engineer | Notebook sharing, model review |
| QA Engineer | [QA Name] | Other QA | Test case review |

# BAB 8: MANAJEMEN KOMUNIKASI PROYEK (PMBOK Area 7)

## 8.1. Tujuan Manajemen Komunikasi

Manajemen komunikasi proyek bertujuan untuk memastikan informasi yang tepat disampaikan kepada stakeholder yang tepat pada waktu yang tepat. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Komunikasi Efektif | Memastikan semua stakeholder menerima informasi yang relevan dan tepat waktu |
| 2 | Transparansi | Menjaga transparansi progress, risiko, dan isu proyek |
| 3 | Kolaborasi | Mendorong kolaborasi antar tim dan stakeholder |
| 4 | Manajemen Ekspektasi | Mengelola ekspektasi stakeholder melalui komunikasi yang konsisten |
| 5 | Feedback Loop | Menyediakan mekanisme untuk menerima dan merespons feedback |

## 8.2. Stakeholder Communication Requirements

### 8.2.1. Identifikasi Stakeholder

| No | Stakeholder | Peran | Komunikasi yang Dibutuhkan |
| --- | --- | --- | --- |
| 1 | Project Sponsor | Direksi FNE | - Progress report (bulanan) - Milestone updates - Risk & issue escalation - Budget status |
| 2 | Executive Steering Committee | Dewan Direksi | - Strategic updates (kuartalan) - Project health status - Investment justification |
| 3 | Project Manager | Manajer Proyek | - Day-to-day communication - Decision coordination - Resource management |
| 4 | Tech Lead | Lead Engineer | - Technical decisions - Architecture updates - Code quality status |
| 5 | Product Owner | Business Analyst | - Requirement clarification - Sprint planning - UAT coordination |
| 6 | Key Users (Eksekutif) | CEO, CFO, COO | - Dashboard demonstrations - UAT participation - Feedback & validation |
| 7 | Key Users (Manajemen) | Farm, SC, Ops, Sales | - Dashboard demonstrations - UAT participation - Feedback & validation |
| 8 | Tim Proyek | All members | - Daily stand-ups - Sprint planning - Technical updates |
| 9 | IT Corporate | IT Department | - Integration coordination - Infrastructure planning - Security compliance |
| 10 | Vendor/External | Cloud providers, Software vendors | - Technical support - License management - SLA monitoring |

### 8.2.2. Communication Matrix

| Tipe Komunikasi | Frekuensi | Audience | Channel | Tanggung Jawab |
| --- | --- | --- | --- | --- |
| Kick-off Meeting | 1x (awal proyek) | All stakeholders | Meeting room/Online | PM |
| Weekly Status Meeting | Mingguan | Tim Proyek | Zoom/Meet | PM |
| Sprint Planning | 2 minggu | Tim Proyek + PO | Zoom/Meet + Jira | PM + PO |
| Sprint Review | 2 minggu | Tim Proyek + Stakeholder | Zoom/Meet + Demo | PM + Tech Lead |
| Sprint Retrospective | 2 minggu | Tim Proyek | Zoom/Meet | PM |
| Steering Committee Meeting | Bulanan | Sponsor + Executive | Meeting room | PM |
| Weekly Progress Report | Mingguan | PM + Sponsor | Email/PPT | PM |
| Monthly Progress Report | Bulanan | All Stakeholders | PDF/Dashboard | PM |
| Daily Stand-up | Harian | Tim Proyek | Zoom/Meet | Tech Lead |
| Tech Sharing Session | 2 minggu | Teknis | Zoom/Meet | Tech Lead |
| UAT Session | Sebelum go-live | Key Users | On-site/Online | PO + QA |
| Go-Live Announcement | 1x | All Stakeholders | Email/Company | PM + Sponsor |
| Project Closure Meeting | 1x | All Stakeholders | Meeting room | PM |

## 8.3. Communication Methods & Tools

### 8.3.1. Communication Tools

| Tool | Tujuan | Tanggung Jawab |
| --- | --- | --- |
| Microsoft Teams / Slack | Daily communication, instant messaging | All team |
| Zoom / Google Meet | Virtual meetings, video conferences | PM |
| Jira / Asana | Task management, sprint tracking | PM + Tech Lead |
| Confluence / Notion | Documentation, knowledge base | PM + Tech Lead |
| GitHub / GitLab | Code repository, version control | Tech Lead |
| Miro / Mural | Retrospectives, brainstorming | PM |
| PowerPoint / Google Slides | Presentations, reporting | PM |
| Email | Formal communication, external parties | PM + All |
| Dashboard (Platform) | Real-time project status, metrics | PM + DevOps |
| Survey Monkey / Google Forms | Feedback, satisfaction survey | PM |

### 8.3.2. Communication Channels

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           COMMUNICATION CHANNELS                                │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │                           FORMAL CHANNELS                                   │ │

│  │  ┌───────────────┐  ┌───────────────┐  ┌───────────────┐  ┌──────────────┐ │ │

│  │  │ Official      │  │ Monthly       │  │ Steering      │  │ Project      │ │ │

│  │  │ Letters       │  │ Progress      │  │ Committee     │  │ Closure      │ │ │

│  │  │ (Sponsor)     │  │ Report        │  │ Meeting       │  │ Report       │ │ │

│  │  └───────────────┘  └───────────────┘  └───────────────┘  └──────────────┘ │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                  │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │                          SEMI-FORMAL CHANNELS                               │ │

│  │  ┌───────────────┐  ┌───────────────┐  ┌───────────────┐  ┌──────────────┐ │ │

│  │  │ Weekly Status │  │ Sprint        │  │ UAT Sessions  │  │ Go-Live      │ │ │

│  │  │ Meeting       │  │ Review        │  │               │  │ Announcement │ │ │

│  │  └───────────────┘  └───────────────┘  └───────────────┘  └──────────────┘ │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                  │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │                          INFORMAL CHANNELS                                  │ │

│  │  ┌───────────────┐  ┌───────────────┐  ┌───────────────┐  ┌──────────────┐ │ │

│  │  │ Daily         │  │ Team Chat     │  │ Tech Sharing  │  │ Peer Feedback│ │ │

│  │  │ Stand-up      │  │ (Slack/Teams) │  │ Session       │  │              │ │ │

│  │  └───────────────┘  └───────────────┘  └───────────────┘  └──────────────┘ │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

## 8.4. Reporting Templates

### 8.4.1. Weekly Status Report

| Section | Content | Detail |
| --- | --- | --- |
| Header | Report Information | Project Name: P-FNE-07 Period: [Start Date] - [End Date] Prepared By: [PM Name] Date: [Date] |
| Executive Summary | Key highlights | - Overall status (Green/Yellow/Red) - Key achievements this week - Key issues/risks - Next week focus |
| Progress Dashboard | Visual metrics | - Sprint progress (% complete) - Milestone progress - Budget utilization - Risk status |
| Work Accomplished | Summary of work | - Completed tasks - Completed user stories - Deliverables produced |
| Work Planned | Next week plan | - Planned tasks - Planned user stories - Upcoming milestones |
| Issues & Risks | Current challenges | - Open issues with mitigation - Risks with mitigation plan - Escalation items |
| Quality Metrics | Quality status | - Test coverage - Defects open/closed - Performance metrics |
| Team Status | Team updates | - Team attendance - Resource utilization - Upcoming leaves |

### 8.4.2. Monthly Progress Report

| Section | Content | Detail |
| --- | --- | --- |
| Header | Report Information | Project Name: P-FNE-07 Month: [Month, Year] Prepared By: [PM Name] Date: [Date] |
| Executive Summary | Key highlights | - Overall status (Green/Yellow/Red) - Key achievements this month - Major milestones - Key issues/risks |
| Project Dashboard | Visual metrics | - Overall progress (% complete) - Milestone progress chart - Budget burn rate - Risk heat map |
| Scope Status | Scope performance | - Scope completed vs planned - Scope changes (approved) - Scope changes (requested) |
| Schedule Status | Schedule performance | - Actual vs planned timeline - Milestone dates (planned vs actual) - Schedule variance |
| Budget Status | Financial performance | - Actual vs planned budget - Budget variance by category - Forecast at completion |
| Quality Status | Quality performance | - Quality metrics summary - Defect trend - Test coverage status |
| Risk Status | Risk management | - Risk register update - Mitigation progress - New risks identified |
| Stakeholder Engagement | Stakeholder updates | - Stakeholder feedback - UAT progress - Training status |
| Next Month Plan | Forward-looking | - Key activities next month - Upcoming milestones - Resource requirements |

### 8.4.3. Sprint Report

| Section | Content | Detail |
| --- | --- | --- |
| Header | Sprint Information | Sprint: #X Duration: [Start] - [End] Team: [Team Name] |
| Sprint Goal | Goal statement | [Sprint goal description] |
| Sprint Backlog | User stories | - Planned stories (#) - Completed stories (#) - Remaining (#) |
| Velocity | Team velocity | - Planned velocity: X points - Actual velocity: X points - Trend chart |
| Defects | Defect summary | - Opened during sprint - Closed during sprint - Critical defects |
| Blockers | Impediments | - Blockers identified - Resolution actions - Unresolved items |
| Retrospective | Improvement items | - What went well - What needs improvement - Action items |

### 8.4.4. Risk Report

| Section | Content | Detail |
| --- | --- | --- |
| Risk Summary | Overview | - Total risks (#) - Critical risks (#) - High risks (#) - Medium risks (#) - Low risks (#) |
| Risk Heat Map | Visualization | - Probability vs Impact matrix |
| Top Risks | Detailed risks | - Risk ID, Description, Probability, Impact, Score - Mitigation strategy - Owner - Status |
| Risk Trends | Trends | - Risk count trend - Risk score trend - Closure rate |
| Contingency Usage | Reserve usage | - Contingency used (#) - Remaining reserve (#) |

## 8.5. Meeting Management

### 8.5.1. Meeting Schedule & Cadence

| Meeting Type | Frekuensi | Durasi | Peserta | Agenda |
| --- | --- | --- | --- | --- |
| Daily Stand-up | Harian | 15 min | All team | - What did I do yesterday? - What will I do today? - Any blockers? |
| Sprint Planning | 2 minggu | 2-3 jam | PM, PO, All Devs | - Refine backlog - Estimate stories - Commit to sprint goals |
| Sprint Review | 2 minggu | 1-2 jam | PM, PO, All Devs, Stakeholder | - Demo completed work - Review against sprint goal - Gather feedback |
| Sprint Retrospective | 2 minggu | 45-60 min | All team | - What went well? - What went wrong? - Action items for next sprint |
| Weekly Status Meeting | Mingguan | 30 min | PM, Leads | - Review progress - Discuss risks/issues - Next steps |
| Steering Committee Meeting | Bulanan | 60-90 min | Sponsor, Executives, PM | - Project health - Milestone progress - Budget status - Major decisions |
| Tech Sharing Session | 2 minggu | 60 min | Technical team | - Knowledge sharing - Tech demos - Best practices |
| UAT Meeting | Per UAT phase | Variable | Key Users, PO, QA | - UAT status - Defects found - Feedback |
| Go-Live Readiness Meeting | Pra-go-live | 120 min | All leads, Sponsor | - Deployment plan - Rollback plan - Hypercare plan |

### 8.5.2. Meeting Agenda Template

text

--- MEETING AGENDA ---

Meeting: [Meeting Name]

Date: [Date]

Time: [Start Time] - [End Time]

Location: [Link/Room]

Chair: [Chairperson]

Attendees: [List of attendees]

Agenda Items:

1. [Item 1] - [Presenter] - [5 min]

2. [Item 2] - [Presenter] - [10 min]

3. [Item 3] - [Presenter] - [5 min]

...

Meeting Materials:

- [Link to document 1]

- [Link to document 2]

Notes:

- [Any pre-reading required]

- [Special notes]

--- END ---

### 8.5.3. Meeting Minutes Template

text

--- MEETING MINUTES ---

Meeting: [Meeting Name]

Date: [Date]

Time: [Start Time] - [End Time]

Location: [Link/Room]

Chair: [Chairperson]

Attendees: [List of attendees]

Minutes Taker: [Name]

Discussion Summary:

1. [Topic 1]

- Discussion points

- Decisions made

- Action items

2. [Topic 2]

- Discussion points

- Decisions made

- Action items

Action Items:

| # | Action | Owner | Deadline |

|---|--------|-------|----------|

| 1 | [Action description] | [Name] | [Date] |

| 2 | [Action description] | [Name] | [Date] |

Next Meeting: [Date], [Time]

--- END ---

## 8.6. Reporting & Documentation Schedule

### 8.6.1. Document Management

| Document | Type | Location | Owner | Update Frequency |
| --- | --- | --- | --- | --- |
| Project Charter | PDF/Word | Confluence | PM | Once |
| Project Management Plan | PDF/Word | Confluence | PM | As needed |
| WBS Dictionary | Excel | Confluence | PM | As needed |
| Requirements Document | PDF/Word | Confluence | PO | Per sprint |
| Architecture Document | Markdown/PDF | Confluence/GitHub | Tech Lead | As needed |
| API Documentation | Swagger/OpenAPI | GitHub Pages | Backend Lead | Per release |
| Database Schema | ERD | Confluence | Data Engineer | As needed |
| User Manual | Markdown/PDF | Confluence | BA | Per release |
| Test Plan & Cases | Excel/Test Management | Confluence/Jira | QA Lead | Per sprint |
| UAT Plan | PDF/Word | Confluence | PM + PO | Pre-UAT |
| Deployment Guide | Markdown | GitHub | DevOps | As needed |
| Operations Manual | Markdown | GitHub/Confluence | DevOps | Pre-go-live |
| Risk Register | Excel | Confluence | PM | Per sprint |
| Decision Log | Excel | Confluence | PM | As needed |
| Lessons Learned | PDF/Word | Confluence | PM | Per milestone |

### 8.6.2. Reporting Schedule

| Report | Frequency | Audience | Format | Owner |
| --- | --- | --- | --- | --- |
| Daily Stand-up Notes | Harian | Team | Chat/Whiteboard | Tech Lead |
| Weekly Status Report | Mingguan | PM + Sponsor | PPT/Word | PM |
| Sprint Report | 2 minggu | Team + PO | Jira + PPT | PM |
| Monthly Progress Report | Bulanan | All Stakeholders | PDF | PM |
| Steering Committee Report | Bulanan | Sponsor + Exec | PDF | PM |
| Risk Report | 2 minggu | PM + Leads | Excel | PM |
| Quality Report | Mingguan | PM + Leads | Dashboard | QA Lead |
| Financial Report | Bulanan | PM + Sponsor | Excel | PM |
| Milestone Report | Per milestone | All Stakeholders | PDF | PM |
| UAT Report | Per UAT phase | All Stakeholders | Excel/PPT | PM + PO |
| Go-Live Announcement | 1x | All Stakeholders | Email | PM |
| Project Closure Report | 1x | All Stakeholders | PDF | PM |

## 8.7. Escalation Process

### 8.7.1. Escalation Levels

| Level | Description | Action | Decision Maker | Response Time |
| --- | --- | --- | --- | --- |
| Level 1 | Daily operational issues | Team resolves within daily stand-up | Tech Lead | < 4 jam |
| Level 2 | Issues requiring cross-team coordination | PM coordinates resolution | PM + Tech Lead | < 1 hari |
| Level 3 | Issues affecting schedule/budget | PM escalates to sponsor with mitigation plan | Project Sponsor | < 3 hari |
| Level 4 | Critical issues threatening project success | Sponsor escalates to executive committee | Executive Committee | < 1 minggu |

### 8.7.2. Escalation Path

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           ESCALATION PATH                                       │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │                           DAILY OPERATIONAL ISSUES                          │ │

│  │  Developer → Tech Lead → Resolve → (if unresolved, go to Level 2)          │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │                      CROSS-TEAM COORDINATION ISSUES                         │ │

│  │  Tech Lead → PM → Coordinated Resolution → (if unresolved, go to Level 3)  │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │                    SCHEDULE/BUDGET IMPACT ISSUES                            │ │

│  │  PM → Sponsor → Decision → (if unresolved, go to Level 4)                   │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │                         CRITICAL PROJECT ISSUES                             │ │

│  │  Sponsor → Executive Committee → Final Decision                             │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### 8.7.3. Escalation Triggers

| Trigger | Description | Escalation Action |
| --- | --- | --- |
| Scope Change > 10% | Significant scope change request | Level 3: CCB approval required |
| Schedule Delay > 2 weeks | Critical path delay | Level 3: Mitigation plan + sponsor approval |
| Budget Overrun > 10% | Actual cost exceeds plan | Level 3: Cost analysis + sponsor approval |
| Critical Risk Materializes | Risk with impact on project success | Level 3: Immediate escalation to sponsor |
| Security Breach | Data breach or security incident | Level 4: Immediate emergency response |
| Team Conflict | Unresolved team issue | Level 2: PM intervention |
| Blocking Issue > 24 hours | Issue preventing work for > 24 hours | Level 2: PM + Tech Lead resolution |

## 8.8. Communication with External Parties

### 8.8.1. Vendor Communication

| Vendor | Communication Frequency | Channel | Topics |
| --- | --- | --- | --- |
| Cloud Provider (AWS/GCP) | Bulanan | Email/Portal | Infrastructure status, billing, support |
| Snowflake | Bulanan | Portal | Usage, performance, support |
| Neo4j | Bulanan | Portal/Email | License, support, updates |
| Confluent (Kafka) | Bulanan | Portal | Usage, support |
| GitHub | Bulanan | Portal | CI/CD, security, support |

### 8.8.2. External Partner Communication

| Partner | Purpose | Frequency | Channel |
| --- | --- | --- | --- |
| P-FNE-01 (Foundation) | Integration, IAM, Master Data | Mingguan | Meeting + API |
| P-FNE-02 (Ag. Ops) | Data integration, CDC | Mingguan | Meeting + API |
| P-FNE-03 (Supply Chain) | Data integration, CDC | Mingguan | Meeting + API |
| P-FNE-04 (Production) | Data integration, CDC | Mingguan | Meeting + API |
| P-FNE-05 (Commerce) | Data integration, CDC | Mingguan | Meeting + API |
| P-FNE-06 (Finance/HCM) | Data integration, CDC | Mingguan | Meeting + API |
| P-FNE-08 (Advanced) | Data provision, IoT | 2 minggu | Meeting + API |

### 8.8.3. External Communication Protocol

| No | Rules | Description |
| --- | --- | --- |
| 1 | Official Channel | All external communication must go through PM |
| 2 | NDA Compliance | Ensure all external parties sign NDA |
| 3 | Approval | Major announcements require sponsor approval |
| 4 | Documentation | All external communication must be documented |
| 5 | Data Privacy | No confidential data shared without authorization |
| 6 | SLA Monitoring | External SLA performance tracked and reported |

# BAB 9: MANAJEMEN RISIKO PROYEK (PMBOK Area 8)

## 9.1. Tujuan Manajemen Risiko

Manajemen risiko proyek bertujuan untuk mengidentifikasi, menganalisis, merespons, dan memonitor risiko yang dapat mempengaruhi keberhasilan proyek. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Identifikasi Risiko | Mengidentifikasi semua potensi risiko yang dapat mempengaruhi proyek |
| 2 | Analisis Risiko | Menganalisis probabilitas dan dampak setiap risiko |
| 3 | Prioritisasi Risiko | Memprioritaskan risiko berdasarkan tingkat keparahan |
| 4 | Perencanaan Respons | Mengembangkan strategi respons untuk setiap risiko |
| 5 | Monitoring Risiko | Memonitor risiko secara berkelanjutan dan menyesuaikan respons |

## 9.2. Risk Management Process

### 9.2.1. Risk Management Framework

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           RISK MANAGEMENT FRAMEWORK                             │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ STEP 1: RISK IDENTIFICATION                                                │ │

│  │ - Brainstorming sessions                                                   │ │

│  │ - Expert interviews                                                        │ │

│  │ - Checklist review                                                         │ │

│  │ - Assumption analysis                                                      │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ STEP 2: RISK ANALYSIS                                                      │ │

│  │ - Qualitative: Probability x Impact = Risk Score                          │ │

│  │ - Quantitative: Monte Carlo simulation (if needed)                        │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ STEP 3: RISK PRIORITIZATION                                                │ │

│  │ - High Risk (Critical): Immediate action                                  │ │

│  │ - Medium Risk: Action plan                                                │ │

│  │ - Low Risk: Monitor                                                       │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ STEP 4: RISK RESPONSE PLANNING                                             │ │

│  │ - Avoid: Eliminate the threat                                              │ │

│  │ - Mitigate: Reduce probability/impact                                     │ │

│  │ - Transfer: Shift impact to third party                                   │ │

│  │ - Accept: Acknowledge and monitor                                          │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                      ↓                                           │

│  ┌────────────────────────────────────────────────────────────────────────────┐ │

│  │ STEP 5: RISK MONITORING & CONTROL                                          │ │

│  │ - Track identified risks                                                   │ │

│  │ - Identify new risks                                                       │ │

│  │ - Execute response plans                                                   │ │

│  │ - Evaluate effectiveness                                                   │ │

│  └────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### 9.2.2. Risk Categories

| Kategori | Deskripsi | Contoh Risiko |
| --- | --- | --- |
| Teknis | Risiko terkait teknologi dan implementasi | - Kegagalan integrasi sistem - Performa database tidak optimal - Model AI/ML tidak akurat - Security vulnerability |
| Manajemen | Risiko terkait manajemen proyek | - Scope creep - Schedule delay - Budget overrun - Resource shortage |
| Organisasi | Risiko terkait struktur dan budaya organisasi | - Resistance to change - Lack of stakeholder support - Turnover of key resources |
| Eksternal | Risiko di luar kendali proyek | - Vendor failure - Regulatory changes - Market changes - Natural disasters |
| Data | Risiko terkait data dan informasi | - Data quality issues - Data availability issues - Data privacy breaches - Data migration failure |
| Keamanan | Risiko terkait keamanan informasi | - Data breach - Unauthorized access - Ransomware attack - Insider threat |

## 9.3. Risk Identification

### 9.3.1. Risk Identification Techniques

| No | Teknik | Deskripsi | Pelaksanaan |
| --- | --- | --- | --- |
| 1 | Brainstorming | Sesi bersama tim untuk mengidentifikasi risiko | Kick-off, awal setiap fase |
| 2 | Expert Interviews | Wawancara dengan ahli di bidang terkait | Awal proyek, per fase |
| 3 | Checklist Review | Menggunakan checklist risiko dari proyek sebelumnya | Awal proyek |
| 4 | Assumption Analysis | Mengidentifikasi asumsi yang dapat menjadi risiko | Awal proyek, per fase |
| 5 | SWOT Analysis | Strengths, Weaknesses, Opportunities, Threats | Awal proyek |
| 6 | Root Cause Analysis | Mengidentifikasi akar penyebab risiko | Per sprint |

### 9.3.2. Risk Register

#### Risk Register Template

| Field | Deskripsi | Contoh |
| --- | --- | --- |
| Risk ID | Unique identifier | R-001 |
| Risk Category | Teknis/Manajemen/Organisasi/Eksternal/Data/Keamanan | Teknis |
| Risk Description | Deskripsi risiko | Model AI/ML tidak mencapai akurasi target ≥ 80% |
| Risk Trigger | Kondisi yang memicu risiko | Data training tidak mencukupi, feature engineering tidak optimal |
| Probability | 1-5 (Very Low - Very High) | 4 (High) |
| Impact | 1-5 (Very Low - Very High) | 4 (High) |
| Risk Score | Probability × Impact | 16 (High) |
| Priority | Critical/High/Medium/Low | High |
| Risk Owner | Penanggung jawab | Data Scientist Lead |
| Mitigation Strategy | Avoid/Mitigate/Transfer/Accept | Mitigate |
| Mitigation Actions | Tindakan mitigasi | - Gunakan data augmentation - Lakukan feature engineering secara iterative - Validasi model dengan cross-validation - Gunakan ensemble methods |
| Contingency Plan | Rencana jika risiko terjadi | - Tambah 2 minggu untuk iterasi model - Alokasikan resource tambahan - Gunakan model yang lebih sederhana jika diperlukan |
| Status | Open/Monitoring/Closed | Open |
| Date Identified | Tanggal identifikasi | 2026-01-15 |
| Last Updated | Tanggal update terakhir | 2026-01-22 |

## 9.4. Risk Register Detail

### 9.4.1. Technical Risks

#### R-TECH-001: Kegagalan Integrasi dengan Modul Transaksional

| Aspek | Detail |
| --- | --- |
| Risk ID | R-TECH-001 |
| Kategori | Teknis |
| Deskripsi | Integrasi dengan 6 modul transaksional (P-FNE-02 s.d. P-FNE-06) gagal atau mengalami delay karena ketidaksesuaian API, perubahan schema, atau ketidaktersediaan CDC |
| Risk Trigger | - API tidak sesuai kontrak - Schema database berubah tanpa notifikasi - CDC tidak tersedia pada modul tertentu - Network connectivity issues |
| Probability | 3 (Medium) |
| Impact | 5 (Very High) |
| Risk Score | 15 (High) |
| Priority | High |
| Risk Owner | Tech Lead |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Finalisasi API contract sebelum integrasi dimulai 2. Lakukan contract testing dengan Pact 3. Koordinasi intensif dengan tim masing-masing modul 4. Buat CDC fallback menggunakan batch ETL jika CDC tidak tersedia 5. Implementasi retry mechanism dan circuit breaker |
| Contingency Plan | 1. Jika CDC gagal, gunakan batch ETL dengan schedule lebih sering (15 menit) 2. Gunakan mock API jika modul belum siap 3. Prioritaskan integrasi dengan modul yang paling kritikal (P-FNE-01, P-FNE-02, P-FNE-03) |
| Status | Open |
| Date Identified | 2026-01-15 |

#### R-TECH-002: Model AI/ML Tidak Mencapai Target Akurasi

| Aspek | Detail |
| --- | --- |
| Risk ID | R-TECH-002 |
| Kategori | Teknis |
| Deskripsi | Model AI/ML tidak mencapai target akurasi ≥ 80% karena data training tidak mencukupi, feature engineering tidak optimal, atau algoritma tidak sesuai |
| Risk Trigger | - Data training tidak representative - Feature engineering tidak optimal - Algoritma tidak sesuai dengan problem - Data quality issues |
| Probability | 4 (High) |
| Impact | 4 (High) |
| Risk Score | 16 (High) |
| Priority | High |
| Risk Owner | Data Scientist Lead |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Lakukan exploratory data analysis (EDA) mendalam 2. Gunakan data augmentation untuk meningkatkan data training 3. Iterasi feature engineering dengan feedback dari model evaluation 4. Evaluasi multiple algorithms (XGBoost, Random Forest, LSTM, Prophet) 5. Lakukan hyperparameter tuning secara sistematis 6. Gunakan cross-validation untuk menghindari overfitting |
| Contingency Plan | 1. Tambah 2 minggu untuk iterasi model 2. Alokasikan resource tambahan untuk feature engineering 3. Gunakan ensemble methods untuk meningkatkan akurasi 4. Definisikan minimum viable accuracy (70%) sebagai alternatif |
| Status | Open |
| Date Identified | 2026-01-15 |

#### R-TECH-003: Knowledge Graph Query Performance Tidak Mencukupi

| Aspek | Detail |
| --- | --- |
| Risk ID | R-TECH-003 |
| Kategori | Teknis |
| Deskripsi | Query Knowledge Graph tidak mencapai target ≤ 5 detik untuk 1M+ node karena indexing yang tidak optimal, query complexity, atau infrastruktur yang kurang |
| Risk Trigger | - Indexing tidak optimal - Query complexity terlalu tinggi - Neo4j configuration tidak optimal - Data volume terlalu besar |
| Probability | 3 (Medium) |
| Impact | 3 (Medium) |
| Risk Score | 9 (Medium) |
| Priority | Medium |
| Risk Owner | Knowledge Engineer |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Optimasi indexing di Neo4j 2. Implementasi query caching 3. Gunakan query profiling untuk mengidentifikasi bottlenecks 4. Optimasi Neo4j configuration (memory, heap, garbage collection) 5. Implementasi pagination dan limiting untuk query besar |
| Contingency Plan | 1. Upgrade Neo4j instance jika diperlukan 2. Implementasi materialized views untuk query yang sering digunakan 3. Batasi depth query maksimum (max 5 levels) |
| Status | Open |
| Date Identified | 2026-01-20 |

#### R-TECH-004: Dashboard Performance Tidak Mencukupi

| Aspek | Detail |
| --- | --- |
| Risk ID | R-TECH-004 |
| Kategori | Teknis |
| Deskripsi | Dashboard load time > 5 detik karena query yang kompleks, data volume besar, atau frontend rendering yang tidak optimal |
| Risk Trigger | - Query SQL tidak optimal - Data volume terlalu besar - Frontend rendering tidak efisien - Caching tidak effective |
| Probability | 3 (Medium) |
| Impact | 3 (Medium) |
| Risk Score | 9 (Medium) |
| Priority | Medium |
| Risk Owner | Tech Lead |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Optimasi query SQL (indexing, query rewriting, materialized views) 2. Implementasi caching (Redis) untuk data yang sering diakses 3. Lazy loading untuk chart dan data 4. Gunakan pagination untuk data table 5. Optimasi frontend rendering (memoization, virtualized lists) |
| Contingency Plan | 1. Implementasi data pre-aggregation 2. Reduce data granularity (daily instead of hourly) 3. Upgrade database instance |
| Status | Open |
| Date Identified | 2026-01-20 |

#### R-TECH-005: Security Breach atau Data Leak

| Aspek | Detail |
| --- | --- |
| Risk ID | R-TECH-005 |
| Kategori | Keamanan |
| Deskripsi | Terjadi security breach atau data leak pada platform yang dapat menyebabkan kebocoran data sensitif (data customer, data karyawan, data keuangan) |
| Risk Trigger | - API security vulnerability - Database access misconfiguration - Insider threat - Third-party library vulnerability |
| Probability | 2 (Low) |
| Impact | 5 (Very High) |
| Risk Score | 10 (Medium) |
| Priority | Medium |
| Risk Owner | DevOps Lead |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Lakukan security assessment secara berkala (OWASP ZAP, Snyk) 2. Implementasi RBAC dengan prinsip least privilege 3. Enkripsi data at rest dan in transit 4. Implementasi audit logging untuk semua akses data sensitif 5. Regular security training untuk semua anggota tim 6. Implementasi DLP (Data Loss Prevention) |
| Contingency Plan | 1. Incident response plan diaktifkan 2. Isolasi sistem yang terdampak 3. Notifikasi ke stakeholder dan regulator 4. Forensics investigation |
| Status | Open |
| Date Identified | 2026-01-15 |

### 9.4.2. Management Risks

#### R-MGMT-001: Scope Creep

| Aspek | Detail |
| --- | --- |
| Risk ID | R-MGMT-001 |
| Kategori | Manajemen |
| Deskripsi | Terjadi scope creep yang tidak terkendali karena penambahan fitur oleh stakeholder tanpa perubahan scope yang terstruktur |
| Risk Trigger | - Permintaan fitur baru dari stakeholder - Perubahan prioritas bisnis - Kurangnya disiplin scope management |
| Probability | 4 (High) |
| Impact | 4 (High) |
| Risk Score | 16 (High) |
| Priority | High |
| Risk Owner | Project Manager |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Implementasi formal change control process (CCB) 2. Dokumentasi scope statement dan WBS yang jelas 3. Setiap perubahan harus melalui impact analysis 4. Prioritization session dengan stakeholder 5. Sprint reviews untuk validasi scope |
| Contingency Plan | 1. Jika perubahan signifikan, re-negotiate timeline dan budget 2. Pindahkan fitur tambahan ke phase 2 3. Gunakan contingency reserve jika diperlukan |
| Status | Open |
| Date Identified | 2026-01-15 |

#### R-MGMT-002: Schedule Delay

| Aspek | Detail |
| --- | --- |
| Risk ID | R-MGMT-002 |
| Kategori | Manajemen |
| Deskripsi | Proyek mengalami schedule delay karena underestimasi, dependency issues, atau resource constraints |
| Risk Trigger | - Underestimasi effort - Dependency dari modul lain delay - Resource availability issues - Technical challenges |
| Probability | 4 (High) |
| Impact | 4 (High) |
| Risk Score | 16 (High) |
| Priority | High |
| Risk Owner | Project Manager |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Estimasi yang lebih akurat menggunakan historical data 2. Buffer untuk critical path (20%) 3. Regular schedule monitoring dan variance analysis 4. Early warning system untuk potential delays 5. Agile approach dengan sprint delivery |
| Contingency Plan | 1. Tambah resource untuk critical path 2. Overtime (limited) 3. Reduksi scope untuk fitur non-kritikal 4. Re-negosiasi deadline dengan stakeholder |
| Status | Open |
| Date Identified | 2026-01-15 |

#### R-MGMT-003: Budget Overrun

| Aspek | Detail |
| --- | --- |
| Risk ID | R-MGMT-003 |
| Kategori | Manajemen |
| Deskripsi | Proyek mengalami budget overrun karena underestimasi, scope perubahan, atau biaya infrastruktur yang lebih tinggi dari perkiraan |
| Risk Trigger | - Underestimasi cost - Scope changes - Cloud cost lebih tinggi dari perkiraan - Resource rate increase |
| Probability | 3 (Medium) |
| Impact | 4 (High) |
| Risk Score | 12 (Medium) |
| Priority | Medium |
| Risk Owner | Project Manager |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Budget tracking mingguan 2. Variance analysis bulanan 3. Cloud cost optimization (right-sizing, reserved instances, spot instances) 4. Scope change impact analysis on budget 5. Contingency reserve (15%) |
| Contingency Plan | 1. Gunakan contingency reserve 2. Optimasi penggunaan cloud (auto-scaling, spot instances) 3. Evaluasi trade-off antara cost dan scope 4. Re-negotiate vendor contracts jika diperlukan |
| Status | Open |
| Date Identified | 2026-01-15 |

#### R-MGMT-004: Key Resource Turnover

| Aspek | Detail |
| --- | --- |
| Risk ID | R-MGMT-004 |
| Kategori | Manajemen |
| Deskripsi | Salah satu key resource (Data Scientist Lead, Tech Lead) keluar dari proyek yang menyebabkan disruption dan delay |
| Risk Trigger | - Perubahan prioritas karir - Offer dari kompetitor - Burnout - Konflik dalam tim |
| Probability | 2 (Low) |
| Impact | 5 (Very High) |
| Risk Score | 10 (Medium) |
| Priority | Medium |
| Risk Owner | Project Manager |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Implementasi knowledge transfer dan documentation 2. Cross-training antar anggota tim 3. Pair programming untuk critical components 4. Team engagement dan retention program 5. Succession planning |
| Contingency Plan | 1. Immediate hiring replacement 2. Onboarding acceleration 3. Distribusi workload ke tim yang tersisa 4. External consultant jika diperlukan |
| Status | Open |
| Date Identified | 2026-01-15 |

### 9.4.3. Organizational Risks

#### R-ORG-001: Resistance to Change

| Aspek | Detail |
| --- | --- |
| Risk ID | R-ORG-001 |
| Kategori | Organisasi |
| Deskripsi | End-user atau stakeholder menolak menggunakan platform karena kurangnya training, ketidaknyamanan dengan sistem baru, atau prioritas yang berbeda |
| Risk Trigger | - Kurangnya komunikasi dan sosialisasi - Training tidak efektif - Platform tidak user-friendly - Prioritas bisnis berubah |
| Probability | 3 (Medium) |
| Impact | 4 (High) |
| Risk Score | 12 (Medium) |
| Priority | Medium |
| Risk Owner | Project Manager + PO |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Early stakeholder engagement 2. Regular demo dan showcase progress 3. Libatkan key users dalam UAT dan feedback 4. Change management program yang terstruktur 5. Training dan coaching untuk end-user 6. Quick wins untuk menunjukkan value |
| Contingency Plan | 1. Extra training sessions 2. Dedicated support team pasca go-live 3. User champions program 4. Feedback loop untuk perbaikan |
| Status | Open |
| Date Identified | 2026-01-20 |

### 9.4.4. External Risks

#### R-EXT-001: Vendor Failure atau Performance Issue

| Aspek | Detail |
| --- | --- |
| Risk ID | R-EXT-001 |
| Kategori | Eksternal |
| Deskripsi | Vendor (cloud provider, database provider) mengalami outage atau performance issue yang mempengaruhi operasional platform |
| Risk Trigger | - Cloud provider outage - Database service degradation - Network issues - Security incident pada vendor |
| Probability | 2 (Low) |
| Impact | 4 (High) |
| Risk Score | 8 (Medium) |
| Priority | Medium |
| Risk Owner | DevOps Lead |
| Mitigation Strategy | Transfer + Mitigate |
| Mitigation Actions | 1. Pilih vendor dengan SLA tinggi (99.9% atau 99.99%) 2. Monitor SLA compliance secara berkala 3. Implementasi multi-region deployment untuk critical components 4. Backup dan disaster recovery plan |
| Contingency Plan | 1. Failover ke region lain 2. Disaster recovery activation 3. Notifikasi ke stakeholder 4. Alternatif vendor jika diperlukan |
| Status | Open |
| Date Identified | 2026-01-15 |

#### R-EXT-002: Perubahan Regulasi

| Aspek | Detail |
| --- | --- |
| Risk ID | R-EXT-002 |
| Kategori | Eksternal |
| Deskripsi | Perubahan regulasi terkait data privacy (GDPR, Undang-Undang Perlindungan Data) yang mempengaruhi implementasi platform |
| Risk Trigger | - Regulasi baru yang efektif - Interpretasi regulasi yang berbeda - Perubahan kebijakan pemerintah |
| Probability | 1 (Very Low) |
| Impact | 4 (High) |
| Risk Score | 4 (Low) |
| Priority | Low |
| Risk Owner | Project Manager |
| Mitigation Strategy | Monitor |
| Mitigation Actions | 1. Konsultasi dengan legal team 2. Design platform dengan data privacy by design 3. Implementasi data anonymization dan pseudonymization 4. Data retention policy yang sesuai |
| Contingency Plan | 1. Adjustment pada implementasi sesuai regulasi 2. Konsultasi legal dan regulatory |
| Status | Open |
| Date Identified | 2026-01-20 |

### 9.4.5. Data Risks

#### R-DATA-001: Data Quality Issues

| Aspek | Detail |
| --- | --- |
| Risk ID | R-DATA-001 |
| Kategori | Data |
| Deskripsi | Data dari modul transaksional memiliki kualitas yang buruk (missing value, inconsistent data, duplicate data) yang mempengaruhi kualitas dashboard dan AI/ML models |
| Risk Trigger | - Data entry errors - System inconsistencies - Missing data dari source - Data transformation errors |
| Probability | 4 (High) |
| Impact | 4 (High) |
| Risk Score | 16 (High) |
| Priority | High |
| Risk Owner | Data Engineer Lead |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Implementasi data quality rules dan monitoring 2. Data cleansing pipeline di ETL 3. Data validation sebelum ingestion 4. Alerting untuk data quality issues 5. Collaboration dengan pemilik data untuk fix |
| Contingency Plan | 1. Fallback ke data historical yang lebih baik 2. Manual data correction untuk critical data 3. Penggunaan data yang sudah divalidasi secara manual |
| Status | Open |
| Date Identified | 2026-01-15 |

#### R-DATA-002: Data Availability Issues

| Aspek | Detail |
| --- | --- |
| Risk ID | R-DATA-002 |
| Kategori | Data |
| Deskripsi | Data dari modul transaksional tidak tersedia tepat waktu (delay) atau tidak tersedia sama sekali karena masalah teknis pada modul source |
| Risk Trigger | - API down - Database source down - Network issues - CDC failure |
| Probability | 3 (Medium) |
| Impact | 4 (High) |
| Risk Score | 12 (Medium) |
| Priority | Medium |
| Risk Owner | Data Engineer Lead |
| Mitigation Strategy | Mitigate |
| Mitigation Actions | 1. Implementasi retry mechanism dengan exponential backoff 2. Data pipeline monitoring dan alerting 3. Redundant data source jika memungkinkan 4. SLA dengan pemilik data 5. Data caching untuk availability |
| Contingency Plan | 1. Gunakan data yang sudah tersedia (historical) 2. Notifikasi ke pemilik data 3. Manual data upload jika diperlukan |
| Status | Open |
| Date Identified | 2026-01-20 |

## 9.5. Risk Analysis & Prioritization

### 9.5.1. Risk Matrix

| Probability \ Impact | 1 (Very Low) | 2 (Low) | 3 (Medium) | 4 (High) | 5 (Very High) |
| --- | --- | --- | --- | --- | --- |
| 5 (Very High) | Medium (5) | Medium (10) | High (15) | High (20) | Critical (25) |
| 4 (High) | Medium (4) | Medium (8) | High (12) | High (16) | High (20) |
| 3 (Medium) | Low (3) | Low (6) | Medium (9) | Medium (12) | High (15) |
| 2 (Low) | Low (2) | Low (4) | Low (6) | Medium (8) | Medium (10) |
| 1 (Very Low) | Low (1) | Low (2) | Low (3) | Low (4) | Medium (5) |

### 9.5.2. Risk Prioritization

| Priority | Score Range | Action | Review Frequency |
| --- | --- | --- | --- |
| Critical | 20-25 | Immediate action required | Weekly |
| High | 13-19 | Action plan required | Bi-weekly |
| Medium | 7-12 | Monitor and action plan if needed | Monthly |
| Low | 1-6 | Monitor only | Monthly |

### 9.5.3. Risk Heat Map

text

IMPACT

↑

5 │         │         │         │         │ R-TECH-001│

│         │         │         │         │ R-TECH-002│

│         │         │         │         │ R-MGMT-001│

│         │         │         │         │ R-MGMT-002│

4 │         │         │ R-EXT-001│ R-DATA-001│ R-MGMT-004│

│         │         │ R-ORG-001│ R-TECH-003│ R-TECH-005│

│         │         │ R-DATA-002│ R-TECH-004│

3 │         │         │ R-MGMT-003│         │         │

│         │         │         │         │         │

2 │         │         │         │         │         │

│         │         │         │         │         │

1 │         │         │         │         │         │

└────┬────┴────┬────┴────┬────┴────┬────┴────┬────┴──→ PROBABILITY

1        2        3        4        5

Low      Medium   High     Very High Critical

## 9.6. Risk Response Plan

### 9.6.1. Response Strategies

| Strategy | Deskripsi | Contoh Penerapan |
| --- | --- | --- |
| Avoid | Eliminate the threat entirely | - Gunakan teknologi yang sudah terbukti - Hindari fitur yang terlalu kompleks - Buat kontrak yang jelas dengan vendor |
| Mitigate | Reduce probability or impact | - Code review dan testing untuk mengurangi defect - Training untuk meningkatkan kompetensi - Monitoring untuk mendeteksi lebih awal |
| Transfer | Shift impact to third party | - Asuransi proyek - SLA dengan vendor - Outsourcing untuk critical components |
| Accept | Acknowledge and monitor | - Risiko dengan probabilitas rendah - Risiko dengan dampak rendah - Risiko di luar kendali proyek |
| Escalate | Escalate to higher authority | - Risiko yang memerlukan keputusan sponsor - Risiko strategis yang mempengaruhi bisnis |

### 9.6.2. Risk Response Details

#### R-TECH-001: Kegagalan Integrasi

| Aspek | Detail |
| --- | --- |
| Risk ID | R-TECH-001 |
| Strategy | Mitigate |
| Response Actions | 1. Finalisasi API contract sebelum integrasi 2. Contract testing dengan Pact 3. Koordinasi intensif dengan tim modul 4. CDC fallback menggunakan batch ETL 5. Retry mechanism dan circuit breaker |
| Owner | Tech Lead |
| Timeline | Minggu 4-20 |
| Cost | 5.000.000 (testing tools, coordination) |
| Effectiveness | High |

#### R-TECH-002: Model AI/ML Akurasi

| Aspek | Detail |
| --- | --- |
| Risk ID | R-TECH-002 |
| Strategy | Mitigate |
| Response Actions | 1. EDA mendalam 2. Data augmentation 3. Iterasi feature engineering 4. Evaluasi multiple algorithms 5. Hyperparameter tuning sistematis 6. Cross-validation |
| Owner | Data Scientist Lead |
| Timeline | Minggu 13-16 |
| Cost | 10.000.000 (compute resources) |
| Effectiveness | Medium |

#### R-MGMT-001: Scope Creep

| Aspek | Detail |
| --- | --- |
| Risk ID | R-MGMT-001 |
| Strategy | Mitigate |
| Response Actions | 1. Formal change control process (CCB) 2. Dokumentasi scope statement dan WBS 3. Impact analysis untuk setiap perubahan 4. Prioritization session dengan stakeholder 5. Sprint reviews |
| Owner | Project Manager |
| Timeline | Seluruh proyek |
| Cost | - |
| Effectiveness | High |

#### R-DATA-001: Data Quality Issues

| Aspek | Detail |
| --- | --- |
| Risk ID | R-DATA-001 |
| Strategy | Mitigate |
| Response Actions | 1. Data quality rules dan monitoring 2. Data cleansing pipeline di ETL 3. Data validation sebelum ingestion 4. Alerting untuk data quality issues 5. Collaboration dengan pemilik data |
| Owner | Data Engineer Lead |
| Timeline | Minggu 5-20 |
| Cost | 5.000.000 (Great Expectations, monitoring) |
| Effectiveness | High |

## 9.7. Risk Monitoring & Control

### 9.7.1. Risk Review Schedule

| Aktivitas | Frekuensi | Tanggung Jawab | Output |
| --- | --- | --- | --- |
| Risk Identification | Awal fase | PM + Leads | New risks added |
| Risk Analysis | 2 minggu | PM + Leads | Risk scores updated |
| Risk Review Meeting | 2 minggu | PM + Leads | Risk register updated |
| Risk Status Update | Mingguan | Risk Owner | Risk status updated |
| Risk Report | 2 minggu | PM | Risk report to stakeholder |

### 9.7.2. Risk Response Monitoring

| Risk ID | Status | Monitoring Method | Next Review |
| --- | --- | --- | --- |
| R-TECH-001 | Open | Weekly integration status check | Minggu 4 |
| R-TECH-002 | Open | Model accuracy tracking | Minggu 14 |
| R-TECH-003 | Open | Query performance monitoring | Minggu 17 |
| R-TECH-004 | Open | Dashboard load time monitoring | Minggu 10 |
| R-TECH-005 | Open | Security scan results | Minggu 8 |
| R-MGMT-001 | Open | Scope change request count | Minggu 4 |
| R-MGMT-002 | Open | Schedule variance tracking | Minggu 4 |
| R-MGMT-003 | Open | Budget variance tracking | Minggu 4 |
| R-MGMT-004 | Open | Team satisfaction survey | Minggu 4 |
| R-ORG-001 | Open | User engagement metrics | Minggu 8 |
| R-EXT-001 | Open | Vendor SLA monitoring | Minggu 4 |
| R-EXT-002 | Open | Regulatory update monitoring | Minggu 4 |
| R-DATA-001 | Open | Data quality dashboard | Minggu 5 |
| R-DATA-002 | Open | Data pipeline availability | Minggu 5 |

### 9.7.3. Risk Response Contingency Budget

| Risk ID | Contingency Action | Estimated Cost | Owner |
| --- | --- | --- | --- |
| R-TECH-001 | Batch ETL fallback, mock API | 10.000.000 | Tech Lead |
| R-TECH-002 | Additional 2 weeks + resources | 50.000.000 | Data Scientist Lead |
| R-TECH-003 | Neo4j upgrade + optimization | 30.000.000 | Knowledge Engineer |
| R-TECH-004 | Database upgrade + caching | 20.000.000 | Tech Lead |
| R-MGMT-001 | Scope negotiation, phase 2 | - | Project Manager |
| R-MGMT-002 | Additional resources, overtime | 50.000.000 | Project Manager |
| R-MGMT-003 | Cloud optimization, vendor negotiation | 30.000.000 | Project Manager |
| R-MGMT-004 | Hiring, onboarding, external consultant | 40.000.000 | Project Manager |
| R-ORG-001 | Extra training, support team | 30.000.000 | PM + PO |
| R-EXT-001 | Failover, disaster recovery | 20.000.000 | DevOps Lead |
| R-DATA-001 | Manual data correction | 15.000.000 | Data Engineer Lead |
| Total Contingency Budget |  | 295.000.000 |  |

# BAB 10: MANAJEMEN PENGADAAN PROYEK (PMBOK Area 9)

## 10.1. Tujuan Manajemen Pengadaan

Manajemen pengadaan proyek bertujuan untuk memastikan semua produk, jasa, dan hasil yang diperlukan untuk proyek diperoleh dari sumber eksternal dengan cara yang efektif dan efisien. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Perencanaan Pengadaan | Mengidentifikasi kebutuhan pengadaan dan menentukan strategi pengadaan yang tepat |
| 2 | Seleksi Vendor | Memilih vendor yang tepat berdasarkan kriteria yang telah ditentukan |
| 3 | Manajemen Kontrak | Mengelola kontrak dengan vendor secara efektif |
| 4 | Pengendalian Pengadaan | Memonitor kinerja vendor dan memastikan kepatuhan terhadap kontrak |
| 5 | Penutupan Pengadaan | Menyelesaikan semua kontrak pengadaan secara formal |

## 10.2. Identifikasi Kebutuhan Pengadaan

### 10.2.1. Kategori Pengadaan

| Kategori | Deskripsi | Prioritas | Metode Pengadaan |
| --- | --- | --- | --- |
| Software Licenses | Lisensi untuk software komersial yang digunakan | High | Pembelian langsung / Langganan |
| Cloud Services | Layanan infrastruktur cloud (IaaS, PaaS) | High | Langganan (Subscription) |
| Consulting Services | Jasa konsultansi untuk area spesifik | Medium | Kontrak jasa / Tender |
| Hardware | Perangkat keras yang diperlukan (jika ada) | Low | Pembelian langsung |
| Training Services | Jasa pelatihan untuk tim dan end-user | Medium | Kontrak jasa |

### 10.2.2. Detailed Procurement Items

| No | Item | Kategori | Deskripsi | Kuantitas | Estimasi Biaya (Rp) | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Neo4j Enterprise License | Software License | License for graph database | 1 tahun | 100.000.000 | Minggu 1-4 |
| 2 | Snowflake | Software License | Data warehouse platform | 1 tahun | 80.000.000 | Minggu 1-4 |
| 3 | MLflow Enterprise | Software License | ML lifecycle management | 1 tahun | 30.000.000 | Minggu 1-4 |
| 4 | Cloud Services (AWS/GCP) | Cloud Services | Compute, storage, database, networking | 6 bulan | 518.000.000 | Minggu 1-24 |
| 5 | Development Tools | Software License | IDE, CI/CD, monitoring tools | 6 bulan | 25.000.000 | Minggu 1-4 |
| 6 | AI/ML Consulting | Consulting Services | Specialized AI/ML consulting if needed | 100 jam | 100.000.000 | Minggu 12-18 |
| 7 | Training Services | Training Services | End-user training program | 2 batch | 75.000.000 | Minggu 22-24 |
| 8 | Security Assessment | Consulting Services | Third-party security audit | 1 project | 50.000.000 | Minggu 20-22 |
| Total Estimasi Pengadaan |  |  |  |  | 978.000.000 |  |

## 10.3. Procurement Strategy

### 10.3.1. Make-or-Buy Analysis

| Item | Make (Internal) | Buy (External) | Keputusan | Alasan |
| --- | --- | --- | --- | --- |
| Neo4j Enterprise | ✗ | ✓ | Buy | Specialized graph database, tidak feasible untuk develop sendiri |
| Snowflake | ✗ | ✓ | Buy | Data warehouse enterprise, membutuhkan maintenance dan scalability tinggi |
| MLflow Enterprise | ✗ | ✓ | Buy | MLOps platform yang mature, butuh time-to-market cepat |
| Cloud Infrastructure | ✗ | ✓ | Buy | Cloud provider lebih cost-effective dan scalable |
| Development Tools | ✓ | ✓ | Buy | Tools standard industri, lebih murah dari develop sendiri |
| AI/ML Consulting | ✓ | ✗ | Make | Tim memiliki kompetensi untuk develop sendiri |
| Training Services | ✓ | ✓ | Buy | Butuh external expertise untuk training yang efektif |
| Security Assessment | ✓ | ✓ | Buy | Butuh third-party perspective untuk security audit |

### 10.3.2. Procurement Methods

| Metode | Deskripsi | Digunakan Untuk |
| --- | --- | --- |
| Direct Purchase | Pembelian langsung dari vendor yang sudah ditentukan | Software licenses (Neo4j, Snowflake, MLflow) |
| Subscription | Pembelian berlangganan untuk layanan | Cloud services, development tools |
| Request for Proposal (RFP) | Mengundang proposal dari multiple vendors | Consulting services, training services |
| Request for Quotation (RFQ) | Meminta penawaran harga dari vendor | Hardware, security assessment |
| Framework Agreement | Perjanjian kerangka kerja untuk pengadaan berulang | Cloud services |

### 10.3.3. Vendor Selection Criteria

| Kriteria | Weight (%) | Deskripsi |
| --- | --- | --- |
| Technical Capability | 30% | Kemampuan teknis vendor dalam menyediakan solusi yang dibutuhkan |
| Cost & Value | 25% | Harga yang kompetitif dan value for money |
| Track Record & Experience | 20% | Pengalaman vendor dalam proyek sejenis |
| Support & SLA | 15% | Kualitas support dan service level agreement |
| Security & Compliance | 10% | Kepatuhan terhadap standar keamanan dan regulasi |

## 10.4. Procurement Plan

### 10.4.1. Software Licenses Procurement

| No | Item | Vendor | Quantity | Unit Price (Rp) | Total (Rp) | Procurement Method | Timeline |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Neo4j Enterprise | Neo4j | 1 tahun | 100.000.000 | 100.000.000 | Direct Purchase | Minggu 1-2 |
| 2 | Snowflake | Snowflake | 1 tahun | 80.000.000 | 80.000.000 | Subscription | Minggu 1-2 |
| 3 | MLflow Enterprise | Databricks | 1 tahun | 30.000.000 | 30.000.000 | Direct Purchase | Minggu 1-2 |
| 4 | Jira & Confluence | Atlassian | 6 bulan | 5.000.000 | 5.000.000 | Subscription | Minggu 1-2 |
| 5 | GitHub Enterprise | GitHub | 6 bulan | 5.000.000 | 5.000.000 | Subscription | Minggu 1-2 |
| 6 | Monitoring Tools | Datadog/New Relic | 6 bulan | 15.000.000 | 15.000.000 | Subscription | Minggu 1-2 |
| Total Software Licenses |  |  |  |  | 235.000.000 |  |  |

### 10.4.2. Cloud Services Procurement

| No | Service | Provider | Specification | Duration | Monthly Cost (Rp) | Total (Rp) | Procurement Method |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Compute (Kubernetes) | AWS/GCP | 10 nodes, 4vCPU/16GB | 6 bulan | 15.000.000 | 90.000.000 | Subscription |
| 2 | Database (PostgreSQL) | AWS/GCP | Managed, 500GB | 6 bulan | 5.000.000 | 30.000.000 | Subscription |
| 3 | Data Warehouse | Snowflake | Medium, 1TB | 6 bulan | 20.000.000 | 120.000.000 | Subscription |
| 4 | Data Lake (S3/GCS) | AWS/GCP | 10TB | 6 bulan | 8.000.000 | 48.000.000 | Subscription |
| 5 | Graph DB | Neo4j Aura | Enterprise, 4 nodes | 6 bulan | 15.000.000 | 90.000.000 | Subscription |
| 6 | Kafka (MSK) | AWS | 3 brokers | 6 bulan | 10.000.000 | 60.000.000 | Subscription |
| 7 | MLflow/Kubeflow | Managed | - | 4 bulan | 5.000.000 | 20.000.000 | Subscription |
| 8 | Monitoring (Prometheus) | Managed | - | 6 bulan | 3.000.000 | 18.000.000 | Subscription |
| 9 | Backup & DR | AWS/GCP | 10TB | 6 bulan | 5.000.000 | 30.000.000 | Subscription |
| 10 | Network & CDN | AWS/GCP | - | 6 bulan | 2.000.000 | 12.000.000 | Subscription |
| Total Cloud Services |  |  |  |  |  | 518.000.000 |  |

### 10.4.3. Consulting Services Procurement

| No | Service | Description | Estimated Hours | Rate/Hour (Rp) | Total (Rp) | Procurement Method | Timeline |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | AI/ML Consulting | Specialized AI/ML consulting for complex models if needed | 100 | 1.000.000 | 100.000.000 | RFP | Minggu 12-18 |
| 2 | Security Assessment | Third-party security audit and penetration testing | 1 project | 50.000.000 | 50.000.000 | RFP | Minggu 20-22 |
| 3 | Training Services | End-user training program | 2 batch | 37.500.000 | 75.000.000 | RFP | Minggu 22-24 |
| Total Consulting Services |  |  |  |  | 225.000.000 |  |  |

### 10.4.4. Procurement Schedule

| Item | Activity | Start | End | Owner |
| --- | --- | --- | --- | --- |
| Software Licenses |  |  |  |  |
| Neo4j Enterprise | Submit Purchase Request | Minggu 1 | Minggu 1 | PM + DevOps |
| Neo4j Enterprise | Approval & Payment | Minggu 1 | Minggu 2 | PM + Finance |
| Neo4j Enterprise | License Activation | Minggu 2 | Minggu 2 | DevOps |
| Snowflake | Submit Purchase Request | Minggu 1 | Minggu 1 | PM + DevOps |
| Snowflake | Approval & Payment | Minggu 1 | Minggu 2 | PM + Finance |
| Snowflake | Account Setup | Minggu 2 | Minggu 2 | DevOps |
| MLflow Enterprise | Submit Purchase Request | Minggu 1 | Minggu 1 | PM + DevOps |
| MLflow Enterprise | Approval & Payment | Minggu 1 | Minggu 2 | PM + Finance |
| MLflow Enterprise | Setup & Configuration | Minggu 2 | Minggu 3 | DevOps |
| Cloud Services |  |  |  |  |
| Cloud Account Setup | Setup AWS/GCP Accounts | Minggu 1 | Minggu 2 | DevOps |
| Infrastructure Provisioning | Provision Cloud Resources | Minggu 2 | Minggu 4 | DevOps |
| Consulting Services |  |  |  |  |
| AI/ML Consulting | Issue RFP | Minggu 8 | Minggu 10 | PM |
| AI/ML Consulting | Vendor Evaluation & Selection | Minggu 10 | Minggu 11 | PM + Tech Lead |
| AI/ML Consulting | Contract Signing | Minggu 11 | Minggu 12 | PM + Sponsor |
| Security Assessment | Issue RFP | Minggu 16 | Minggu 18 | PM + DevOps |
| Security Assessment | Vendor Selection | Minggu 18 | Minggu 19 | PM + DevOps |
| Security Assessment | Conduct Assessment | Minggu 20 | Minggu 22 | DevOps + Vendor |
| Training Services | Issue RFP | Minggu 18 | Minggu 19 | PM + BA |
| Training Services | Vendor Selection | Minggu 19 | Minggu 20 | PM + BA |
| Training Services | Conduct Training | Minggu 22 | Minggu 24 | Vendor + BA |

## 10.5. Vendor Management

### 10.5.1. Vendor Selection Process

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           VENDOR SELECTION PROCESS                              │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  STEP 1: IDENTIFIKASI KEBUTUHAN                                                  │

│  - Define procurement requirements                                              │

│  - Prepare specification/scope of work                                          │

│  - Determine evaluation criteria                                                │

│                                                                                  │

│  STEP 2: ISSUE RFP/RFQ                                                          │

│  - Issue Request for Proposal/Quotation                                         │

│  - Vendor pre-qualification                                                     │

│  - Schedule for questions and responses                                         │

│                                                                                  │

│  STEP 3: RECEIVE PROPOSALS                                                      │

│  - Receive and log proposals                                                    │

│  - Acknowledge receipt                                                          │

│  - Request clarification if needed                                              │

│                                                                                  │

│  STEP 4: EVALUATION                                                             │

│  - Evaluate proposals against criteria                                          │

│  - Technical evaluation team review                                             │

│  - Commercial evaluation                                                        │

│  - Shortlist vendors for presentation                                           │

│                                                                                  │

│  STEP 5: PRESENTATION & DEMO                                                    │

│  - Vendor presentations                                                         │

│  - Technical demos                                                              │

│  - Q&A sessions                                                                 │

│                                                                                  │

│  STEP 6: FINAL SELECTION                                                        │

│  - Final evaluation and scoring                                                 │

│  - Vendor recommendation                                                        │

│  - Approval by sponsor                                                          │

│                                                                                  │

│  STEP 7: CONTRACT NEGOTIATION                                                   │

│  - Negotiate terms and conditions                                               │

│  - Finalize contract draft                                                      │

│  - Legal review                                                                 │

│  - Contract signing                                                             │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### 10.5.2. Vendor Evaluation Form

| No | Criteria | Weight | Vendor A (1-5) | Score | Vendor B (1-5) | Score | Vendor C (1-5) | Score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Technical Capability | 30% | 4 | 1.20 | 5 | 1.50 | 3 | 0.90 |
| 2 | Cost & Value | 25% | 4 | 1.00 | 3 | 0.75 | 5 | 1.25 |
| 3 | Track Record & Experience | 20% | 5 | 1.00 | 4 | 0.80 | 3 | 0.60 |
| 4 | Support & SLA | 15% | 4 | 0.60 | 5 | 0.75 | 4 | 0.60 |
| 5 | Security & Compliance | 10% | 5 | 0.50 | 4 | 0.40 | 5 | 0.50 |
| Total Score | 100% |  |  | 4.30 |  | 4.20 |  | 3.85 |
| Ranking |  |  |  | 1 |  | 2 |  | 3 |

### 10.5.3. Contract Management

#### Contract Template Structure

| Section | Content | Detail |
| --- | --- | --- |
| Section 1 | Parties | - Client: Farm Nation Enterprise - Vendor: [Vendor Name] |
| Section 2 | Scope of Work | - Detailed description of services/products - Deliverables - Performance standards |
| Section 3 | Term & Duration | - Start date - End date - Renewal terms |
| Section 4 | Pricing & Payment | - Fee structure - Payment schedule - Invoicing terms |
| Section 5 | SLA & Performance | - Service levels - Response times - Penalties (if any) |
| Section 6 | Intellectual Property | - Ownership of IP - License grants - IP infringement |
| Section 7 | Confidentiality | - Confidential information definition - Exclusions - Duration |
| Section 8 | Data Privacy | - Data protection obligations - GDPR/regulatory compliance |
| Section 9 | Termination | - Termination for cause - Termination for convenience - Effects of termination |
| Section 10 | Warranties & Liabilities | - Warranties - Limitations of liability |
| Section 11 | General Provisions | - Governing law - Dispute resolution - Force majeure |

## 10.6. Procurement Control & Monitoring

### 10.6.1. Vendor Performance Monitoring

| Vendor | Service | KPIs | Target | Monitoring Frequency |
| --- | --- | --- | --- | --- |
| Neo4j | Graph Database | Uptime, Query Performance, Support Response | 99.9%, < 5s, < 4 hours | Bulanan |
| Snowflake | Data Warehouse | Uptime, Query Performance, Support Response | 99.9%, < 10s, < 4 hours | Bulanan |
| AWS/GCP | Cloud Services | Uptime, Performance, Support Response | 99.9%, < SLA, < 4 hours | Bulanan |
| MLflow | MLOps Platform | Uptime, Performance, Support Response | 99.9%, < SLA, < 4 hours | Bulanan |
| Consulting Vendor | Consulting Services | Quality, Timeliness, Deliverable | 100% on-time, Quality ≥ 4.0 | Per engagement |

### 10.6.2. Procurement Risk Monitoring

| Risk | Vendor | Probability | Impact | Mitigation | Status |
| --- | --- | --- | --- | --- | --- |
| Vendor bankruptcy | Any | Very Low | High | Vendor diversification, escrow | Monitoring |
| SLA breach | Cloud vendor | Medium | High | Penalty enforcement, fallback plan | Monitoring |
| Price increase | Cloud vendor | Medium | Medium | Fixed-price contract, multi-year commitment | Monitoring |
| Technology obsolescence | Software vendors | Low | Medium | Regular upgrade, alternative evaluation | Monitoring |
| Security incident | Any vendor | Low | Very High | Security audit, incident response | Monitoring |
| Staff turnover | Consulting vendor | Medium | Medium | Knowledge transfer, transition plan | Monitoring |

## 10.7. Procurement Closure

### 10.7.1. Procurement Closure Criteria

| No | Kriteria | Deskripsi |
| --- | --- | --- |
| 1 | All Deliverables Received | Semua deliverables dari vendor telah diterima |
| 2 | Deliverables Accepted | Deliverables telah diverifikasi dan diterima |
| 3 | All Invoices Paid | Semua invoice telah dibayar |
| 4 | Warranty Period | Masa warranty (jika ada) telah berakhir |
| 5 | Documentation Complete | Semua dokumentasi pengadaan lengkap |
| 6 | Lessons Learned | Lessons learned dari pengadaan terdokumentasi |

### 10.7.2. Procurement Closure Checklist

| No | Checklist Item | Status (Yes/No) | Keterangan |
| --- | --- | --- | --- |
| 1 | All procurement items received |  |  |
| 2 | All deliveries inspected and accepted |  |  |
| 3 | All acceptance tests passed |  |  |
| 4 | All payment made |  |  |
| 5 | All contract documents finalized |  |  |
| 6 | All warranties and guarantees documented |  |  |
| 7 | All user manuals and documentation received |  |  |
| 8 | All vendor training completed |  |  |
| 9 | All lessons learned captured |  |  |
| 10 | All procurement files archived |  |  |

## 10.8. Procurement Governance

### 10.8.1. Roles & Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | - Overall procurement coordination - Procurement planning - Contract management - Issue escalation |
| Finance | - Budget approval - Payment processing - Financial reporting |
| Legal | - Contract review - Legal compliance - IP protection |
| Tech Lead | - Technical evaluation of vendors - Technical specification - Acceptance testing |
| DevOps Lead | - Cloud services management - Infrastructure procurement - Vendor SLA monitoring |
| Procurement Committee | - Vendor selection approval - Major procurement decisions - Escalation resolution |

### 10.8.2. Procurement Approval Authority

| Procurement Value | Approval Authority |
| --- | --- |
| < Rp 50.000.000 | Project Manager |
| Rp 50.000.000 - Rp 100.000.000 | Project Manager + Finance |
| Rp 100.000.000 - Rp 500.000.000 | Project Sponsor |
| > Rp 500.000.000 | Steering Committee |

# BAB 11: MANAJEMEN PEMANGKU KEPENTINGAN PROYEK (PMBOK Area 10)

## 11.1. Tujuan Manajemen Pemangku Kepentingan

Manajemen pemangku kepentingan proyek bertujuan untuk mengidentifikasi, menganalisis, dan mengelola stakeholder secara efektif untuk memastikan dukungan dan keterlibatan mereka sepanjang siklus proyek. Tujuan spesifiknya adalah:

| No | Tujuan | Deskripsi |
| --- | --- | --- |
| 1 | Identifikasi Stakeholder | Mengidentifikasi semua individu, kelompok, atau organisasi yang terpengaruh atau dapat mempengaruhi proyek |
| 2 | Analisis Stakeholder | Menganalisis kebutuhan, kepentingan, pengaruh, dan dampak stakeholder |
| 3 | Perencanaan Keterlibatan | Mengembangkan strategi untuk melibatkan stakeholder secara efektif |
| 4 | Manajemen Ekspektasi | Mengelola ekspektasi stakeholder melalui komunikasi yang transparan |
| 5 | Monitoring Keterlibatan | Memonitor kepuasan dan keterlibatan stakeholder secara berkelanjutan |

## 11.2. Stakeholder Identification

### 11.2.1. Stakeholder Identification Process

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                       STAKEHOLDER IDENTIFICATION PROCESS                        │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  STEP 1: IDENTIFIKASI AWAL                                                      │

│  - Brainstorming dengan tim                                                     │

│  - Review dokumentasi proyek                                                    │

│  - Analisis organisasi                                                          │

│  - Identifikasi dari proyek sejenis                                             │

│                                                                                  │

│  STEP 2: KATEGORISASI                                                            │

│  - Internal vs Eksternal                                                        │

│  - Primary vs Secondary                                                         │

│  - Direct vs Indirect                                                           │

│                                                                                  │

│  STEP 3: ANALISIS STAKEHOLDER                                                    │

│  - Power vs Interest analysis                                                   │

│  - Kebutuhan dan ekspektasi                                                     │

│  - Potensi dampak pada proyek                                                   │

│                                                                                  │

│  STEP 4: PRIORITAS                                                               │

│  - High priority (Manage closely)                                               │

│  - Medium priority (Keep satisfied/informed)                                   │

│  - Low priority (Monitor)                                                       │

│                                                                                  │

│  STEP 5: ENGAGEMENT STRATEGY                                                     │

│  - Develop engagement plan per stakeholder                                      │

│  - Define communication frequency and channel                                   │

│  - Define success metrics                                                       │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### 11.2.2. Stakeholder Register

| ID | Stakeholder | Peran | Kategori | Power (1-5) | Interest (1-5) | Priority | Engagement Strategy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S-01 | Project Sponsor | Direksi FNE | Internal | 5 | 5 | High | Manage Closely - Monthly meeting, milestone review |
| S-02 | Project Manager | Manajer Proyek | Internal | 4 | 5 | High | Manage Closely - Daily communication, reporting |
| S-03 | Tech Lead | Lead Engineer | Internal | 4 | 5 | High | Manage Closely - Daily stand-up, technical decision |
| S-04 | Product Owner | Business Analyst | Internal | 4 | 5 | High | Manage Closely - Sprint planning, backlog |
| S-05 | Executive Steering Committee | Dewan Direksi | Internal | 5 | 3 | High | Keep Satisfied - Quarterly strategic review |
| S-06 | Key Users (Eksekutif) | CEO, CFO, COO | Internal | 4 | 4 | High | Manage Closely - Demo, UAT, feedback session |
| S-07 | Key Users (Manajemen) | Farm, SC, Ops, Sales | Internal | 3 | 5 | High | Manage Closely - Demo, UAT, feedback session |
| S-08 | Tim Proyek | All team members | Internal | 3 | 5 | High | Manage Closely - Daily stand-up, sprint ceremonies |
| S-09 | IT Corporate | IT Department | Internal | 3 | 4 | High | Keep Satisfied - Integration meeting, architecture review |
| S-10 | Data Engineer Lead | Data Engineering | Internal | 3 | 5 | High | Manage Closely - Pipeline planning, data integration |
| S-11 | Data Scientist Lead | Data Science | Internal | 3 | 5 | High | Manage Closely - Model development, AI strategy |
| S-12 | QA Lead | Quality Assurance | Internal | 3 | 5 | High | Manage Closely - Testing strategy, quality metrics |
| S-13 | DevOps Lead | DevOps | Internal | 3 | 5 | High | Manage Closely - Infrastructure, deployment |
| S-14 | Finance Department | Keuangan | Internal | 3 | 3 | Medium | Keep Informed - Budget, payment, cost tracking |
| S-15 | HR Department | SDM | Internal | 2 | 2 | Medium | Keep Informed - Resource allocation, onboarding |
| S-16 | Project Team (End Users) | Pengguna akhir | Internal | 2 | 4 | Medium | Keep Satisfied - Training, UAT, support |
| S-17 | Vendors (Cloud, Software) | Penyedia layanan | External | 3 | 3 | Medium | Keep Satisfied - SLA monitoring, payment |
| S-18 | Regulators | Pemerintah/Regulator | External | 2 | 1 | Low | Monitor - Regulatory compliance |
| S-19 | Competitors | Kompetitor | External | 1 | 1 | Low | Monitor - Market monitoring |
| S-20 | General Public | Masyarakat | External | 1 | 1 | Low | Monitor - Public perception |

## 11.3. Stakeholder Analysis

### 11.3.1. Power-Interest Grid

text

INTEREST

↑

HIGH │  "Keep Satisfied"         │  "Manage Closely"                     │

│                           │                                         │

P  │  S-05: Exec. Steering     │  S-01: Sponsor                         │

O  │  S-09: IT Corporate       │  S-02: PM                              │

W  │                           │  S-03: Tech Lead                       │

E  │                           │  S-04: Product Owner                   │

R  │                           │  S-06: Key Users (Exec)               │

│                           │  S-07: Key Users (Mgmt)               │

│                           │  S-08: Tim Proyek                     │

│                           │  S-10: Data Engineer Lead              │

│                           │  S-11: Data Scientist Lead             │

│                           │  S-12: QA Lead                        │

│                           │  S-13: DevOps Lead                    │

│                           │                                         │

├───────────────────────────┼─────────────────────────────────────────┤

│                           │                                         │

LOW  │  "Monitor"                │  "Keep Informed"                       │

│                           │                                         │

│  S-18: Regulators         │  S-14: Finance                         │

│  S-19: Competitors        │  S-15: HR                              │

│  S-20: General Public     │  S-16: Project Team (End Users)       │

│                           │  S-17: Vendors                         │

│                           │                                         │

└───────────────────────────┴─────────────────────────────────────────┘

LOW                           HIGH → POWER

### 11.3.2. Stakeholder Needs & Expectations

| ID | Stakeholder | Key Needs | Expectations | Priority |
| --- | --- | --- | --- | --- |
| S-01 | Project Sponsor | Project success, ROI, timeline | On-time delivery, within budget, strategic alignment | Critical |
| S-02 | Project Manager | Resources, support, cooperation | Clear direction, team performance, project success | Critical |
| S-03 | Tech Lead | Technical clarity, quality standards | Robust architecture, high-quality code, on-time delivery | Critical |
| S-04 | Product Owner | Requirement fulfillment | Feature completeness, user satisfaction | High |
| S-05 | Exec. Steering | Business value, risk management | Strategic alignment, investment return | High |
| S-06 | Key Users (Exec) | Strategic insights, decision support | Actionable insights, real-time data | High |
| S-07 | Key Users (Mgmt) | Operational insights, efficiency | User-friendly dashboards, accurate data | High |
| S-08 | Tim Proyek | Clear goals, support, recognition | Meaningful work, growth opportunity | High |
| S-09 | IT Corporate | System integration, security | Seamless integration, security compliance | Medium |
| S-14 | Finance | Budget adherence, cost control | Accurate budgeting, cost transparency | Medium |
| S-16 | Project Team (End Users) | User-friendly system, training | Easy to use, adequate training | Medium |
| S-17 | Vendors | Timely payment, clear scope | Clear requirements, prompt payment | Medium |

### 11.3.3. Potential Conflicts & Management

| Conflict | Stakeholders | Resolution Strategy |
| --- | --- | --- |
| Scope vs Timeline | Sponsor vs Key Users | Priority-based negotiation, phase approach |
| Budget vs Features | Finance vs Product Owner | Value-based prioritization, MVP approach |
| Speed vs Quality | PM vs QA Lead | Agile quality gates, trade-off discussion |
| Integration vs Independence | IT Corporate vs Tech Lead | Architecture governance, flexibility balance |
| Customization vs Standardization | Key Users vs Tech Lead | Configurable features, core vs custom |

## 11.4. Stakeholder Engagement Plan

### 11.4.1. Engagement Activities by Stakeholder Group

| Stakeholder Group | Engagement Activity | Frequency | Channel | Responsible |
| --- | --- | --- | --- | --- |
| Sponsor & Executive | - Steering Committee Meeting - Progress Report - Milestone Review | Monthly Monthly Per milestone | Meeting room PDF/PPT Meeting room | PM PM PM |
| Key Users (Executive) | - Dashboard Demo - UAT Session - Feedback Session | Per sprint Pre-go-live Quarterly | Virtual/Meeting Virtual Virtual | PM + PO PM + QA PM |
| Key Users (Management) | - Dashboard Demo - UAT Session - Training Session - Feedback Session | Per sprint Pre-go-live Pre-go-live Monthly | Virtual/Meeting Virtual Virtual Virtual | PM + PO PM + QA BA PM |
| Project Team | - Daily Stand-up - Sprint Planning - Sprint Review - Sprint Retrospective | Daily 2 minggu 2 minggu 2 minggu | Virtual Virtual Virtual Virtual | Tech Lead PM + PO PM PM |
| Technical Team | - Tech Sharing Session - Architecture Review - Code Review | 2 minggu Per milestone Per PR | Virtual Virtual GitHub | Tech Lead Tech Lead Tech Lead |
| IT Corporate | - Integration Review - Architecture Review - Security Review | 2 minggu Per milestone Per milestone | Virtual Virtual Virtual | PM + Tech Lead Tech Lead DevOps |
| Finance Department | - Financial Report - Budget Review - Invoice Approval | Monthly Monthly As needed | Excel/PDF Meeting Virtual | PM PM + Finance PM |
| Vendors | - SLA Review - Vendor Meeting - Incident Management | Monthly Quarterly As needed | Portal/Email Virtual Virtual | DevOps Lead PM DevOps Lead |
| End Users | - User Training - UAT Session - Support | Pre-go-live Pre-go-live Hypercare | Virtual/On-site Virtual Virtual | BA PM + QA Support Team |

### 11.4.2. Stakeholder Engagement Calendar

| Week | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- |
| Week 1-2 |  |  |  |  | Kick-off Meeting (All) |
| Weekly |  |  | Weekly Status Meeting |  |  |
| Daily |  | Daily Stand-up (15 min) |  |  |  |
| Sprint (2 Weeks) | Sprint Planning (Day 1) |  |  | Sprint Review (Day 10) | Sprint Retrospective (Day 10) |
| Monthly |  |  | Steering Committee (Week 4) |  |  |
| Quarterly |  |  |  |  | Executive Review |
| Pre-Go-Live |  |  |  |  | UAT Sessions, Training |
| Post-Go-Live |  |  | Hypercare Review |  |  |

## 11.5. Stakeholder Communication

### 11.5.1. Communication Methods by Stakeholder

| ID | Stakeholder | Preferred Channel | Communication Style | Response Time |
| --- | --- | --- | --- | --- |
| S-01 | Project Sponsor | Email, Meeting, Report | Formal, Concise, Data-driven | < 24 jam |
| S-02 | Project Manager | Chat, Email, Meeting | Collaborative, Direct | < 4 jam |
| S-03 | Tech Lead | Chat, Technical Meeting | Technical, Direct | < 4 jam |
| S-04 | Product Owner | Chat, Meeting, Jira | Collaborative, Requirement-focused | < 4 jam |
| S-05 | Exec. Steering | Formal Meeting, Report | Strategic, Formal | < 48 jam |
| S-06 | Key Users (Exec) | Email, Meeting, Demo | Strategic, Visual | < 24 jam |
| S-07 | Key Users (Mgmt) | Email, Meeting, Demo | Operational, Visual | < 24 jam |
| S-08 | Tim Proyek | Chat, Stand-up, Retro | Collaborative, Open | < 4 jam |
| S-09 | IT Corporate | Email, Technical Meeting | Technical, Formal | < 24 jam |
| S-14 | Finance | Email, Report | Formal, Structured | < 24 jam |
| S-16 | End Users | Email, Training, Support | Instructional, Supportive | < 24 jam |
| S-17 | Vendors | Email, Portal | Formal, Transactional | < 24 jam |

### 11.5.2. Escalation Communication

| Level | Issue | Communication | Recipient | Response Time |
| --- | --- | --- | --- | --- |
| Level 1 | Daily operational issues | Chat/Email | Tech Lead | < 4 jam |
| Level 2 | Cross-team coordination issues | Meeting/Email | PM + Tech Lead | < 1 hari |
| Level 3 | Schedule/budget impact issues | Formal Report | Project Sponsor | < 3 hari |
| Level 4 | Critical project issues | Urgent Meeting | Executive Committee | < 1 minggu |
| Emergency | Security breach, system down | Immediate notification | Sponsor + Exec + IT | Immediate |

## 11.6. Stakeholder Satisfaction Measurement

### 11.6.1. Satisfaction Metrics

| No | Metric | Target | Measurement Method | Frequency |
| --- | --- | --- | --- | --- |
| 1 | Sponsor Satisfaction | ≥ 4.5/5.0 | Survey, interview | Per milestone |
| 2 | Key User Satisfaction | ≥ 4.0/5.0 | Survey, UAT feedback | Per sprint, UAT |
| 3 | Team Satisfaction | ≥ 4.0/5.0 | Anonymous survey | Per sprint |
| 4 | Executive Satisfaction | ≥ 4.0/5.0 | Survey, steering committee | Per quarter |
| 5 | Stakeholder Engagement | ≥ 80% | Attendance rate | Per meeting |
| 6 | Issue Resolution | ≥ 90% | Tracking system | Monthly |
| 7 | UAT Success Rate | 100% | UAT sign-off | Pre-go-live |

### 11.6.2. Stakeholder Survey Template

text

--- STAKEHOLDER SATISFACTION SURVEY ---

Project: Intelligence & Decision Platform (P-FNE-07)

Stakeholder Group: [Select one]

Date: [Date]

Please rate the following statements (1 = Strongly Disagree, 5 = Strongly Agree):

1. I understand the project's goals and objectives.

[1] [2] [3] [4] [5]

2. The project communications are timely and relevant.

[1] [2] [3] [4] [5]

3. The project is meeting my expectations.

[1] [2] [3] [4] [5]

4. I am satisfied with the progress of the project.

[1] [2] [3] [4] [5]

5. The project team responds to my feedback effectively.

[1] [2] [3] [4] [5]

6. The project deliverables meet my requirements.

[1] [2] [3] [4] [5]

7. I would recommend this project to others.

[1] [2] [3] [4] [5]

8. Overall, I am satisfied with this project.

[1] [2] [3] [4] [5]

Open-ended Questions:

1. What is the best thing about this project?

[Text response]

2. What can be improved?

[Text response]

3. Any additional comments?

[Text response]

--- END ---

## 11.7. Stakeholder Issue Management

### 11.7.1. Issue Log

| ID | Issue | Reported By | Date | Priority | Assigned To | Status | Resolution Date | Resolution |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I-01 | Dashboard not meeting expectations | Key User (Exec) | 2026-01-15 | High | PM + FE Lead | In Progress |  | Adding more granularity and drill-down features |
| I-02 | Data quality issues in farm module | Farm Manager | 2026-01-20 | Critical | Data Engineer Lead | Resolved | 2026-01-22 | Data cleansing and validation added |
| I-03 | Integration delay with P-FNE-05 | PM | 2026-01-22 | High | Tech Lead | Open |  | Coordinating with P-FNE-05 team for API availability |
| I-04 | Training not sufficient | End User | 2026-01-25 | Medium | BA | Open |  | Additional training sessions scheduled |

### 11.7.2. Issue Resolution Process

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           ISSUE RESOLUTION PROCESS                              │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  STEP 1: ISSUE REPORTING                                                         │

│  - Stakeholder reports issue                                                    │

│  - Issue logged in issue log                                                    │

│  - Priority assigned                                                           │

│                                                                                  │

│  STEP 2: ISSUE ANALYSIS                                                         │

│  - Root cause analysis                                                          │

│  - Impact assessment                                                            │

│  - Potential solutions identified                                               │

│                                                                                  │

│  STEP 3: SOLUTION IMPLEMENTATION                                                │

│  - Assign owner                                                                 │

│  - Implement solution                                                           │

│  - Document resolution                                                          │

│                                                                                  │

│  STEP 4: VERIFICATION                                                           │

│  - Stakeholder verification                                                     │

│  - Solution effectiveness measured                                              │

│                                                                                  │

│  STEP 5: CLOSURE                                                                │

│  - Issue closed                                                                 │

│  - Lessons learned documented                                                   │

│  - Communication to relevant stakeholders                                       │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

## 11.8. Stakeholder Engagement Monitoring

### 11.8.1. Engagement Status Dashboard

| Stakeholder | Current Engagement | Desired Engagement | Gap | Action |
| --- | --- | --- | --- | --- |
| Sponsor | ✅ High | High | None | Continue |
| Steering Committee | ✅ High | High | None | Continue |
| Key Users (Exec) | ✅ High | High | None | Continue |
| Key Users (Mgmt) | ⚠️ Medium | High | Gap | Increase demos and feedback sessions |
| Tim Proyek | ✅ High | High | None | Continue |
| IT Corporate | ✅ High | High | None | Continue |
| Finance | ⚠️ Medium | Medium | None | Continue |
| End Users | ⚠️ Low | Medium | Gap | Start training early, more communication |
| Vendors | ✅ High | High | None | Continue |

### 11.8.2. Engagement Improvement Actions

| Stakeholder Group | Issue | Action | Owner | Timeline |
| --- | --- | --- | --- | --- |
| Key Users (Mgmt) | Medium engagement | - Increase demo frequency - More UAT sessions - Monthly feedback calls | PM + PO | Minggu 4-24 |
| End Users | Low engagement | - Early training materials - Regular communication - Champion program | BA | Minggu 8-24 |

## 11.9. Stakeholder Communication Guidelines

### 11.9.1. Guiding Principles

| No | Principle | Deskripsi |
| --- | --- | --- |
| 1 | Transparency | Be honest and open about project status, risks, and issues |
| 2 | Timeliness | Communicate information as soon as it is available |
| 3 | Relevance | Tailor communication to the audience's needs |
| 4 | Clarity | Use clear, jargon-free language |
| 5 | Consistency | Communicate regularly and consistently |
| 6 | Feedback | Actively seek and respond to stakeholder feedback |
| 7 | Respect | Treat all stakeholders with respect and professionalism |
| 8 | Confidentiality | Protect sensitive information appropriately |

### 11.9.2. Confidentiality & Data Privacy

| Level | Information Type | Handling | Access |
| --- | --- | --- | --- |
| Public | Project name, general description | Can be shared publicly | All |
| Internal | Project status, progress reports | Can be shared within company | Project team + internal stakeholders |
| Confidential | Financial data, strategic plans | Need-to-know basis, secure channels | PM + Sponsor + Key Execs |
| Restricted | Personal data, security information | Strictly controlled access, encryption | Authorized personnel only |

# BAB 12: LAMPIRAN

## 12.1. Pendahuluan

Bab ini berisi semua dokumen pendukung, template, dan informasi tambahan yang diperlukan untuk mendukung pelaksanaan Project Management Plan (PMP) untuk proyek Intelligence & Decision Platform (P-FNE-07). Lampiran-lampiran ini berfungsi sebagai referensi dan panduan praktis bagi seluruh tim proyek dan stakeholder.

## 12.2. Lampiran A: Formulir & Template

### A.1. Change Request Form (CR-XXX)

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           CHANGE REQUEST FORM                                   │

│                          Project: P-FNE-07                                      │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  CHANGE REQUEST ID: CR-XXX                                                      │

│  DATE SUBMITTED: [DD/MM/YYYY]                                                   │

│  SUBMITTED BY: [Name] [Role]                                                    │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  TYPE OF CHANGE:                                                                │

│  ☐ Scope Change          ☐ Schedule Change          ☐ Budget Change            │

│  ☐ Resource Change       ☐ Technical Change         ☐ Other: _________        │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  DESCRIPTION OF CHANGE:                                                         │

│  [Provide detailed description of the proposed change]                          │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  REASON/JUSTIFICATION:                                                          │

│  [Explain why the change is necessary]                                          │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  IMPACT ANALYSIS:                                                               │

│                                                                                  │

│  SCOPE IMPACT:                                                                  │

│  ☐ No impact   ☐ Minor impact   ☐ Moderate impact   ☐ Major impact            │

│  Affected WBS Elements: [List]                                                  │

│                                                                                  │

│  SCHEDULE IMPACT:                                                               │

│  Estimated additional days: [___] days                                          │

│  Milestones affected: [List]                                                    │

│                                                                                  │

│  COST IMPACT:                                                                   │

│  Estimated additional cost: Rp [___________]                                    │

│  Budget line affected: [List]                                                   │

│                                                                                  │

│  RESOURCE IMPACT:                                                               │

│  Additional resources needed: [List]                                            │

│  Skills needed: [List]                                                          │

│                                                                                  │

│  QUALITY IMPACT:                                                                │

│  ☐ No impact   ☐ Minor impact   ☐ Moderate impact   ☐ Major impact            │

│  Quality risk: [Description]                                                    │

│                                                                                  │

│  RISK IMPACT:                                                                   │

│  New risks identified: [List]                                                   │

│  Existing risks affected: [List]                                                │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  APPROVAL:                                                                      │

│                                                                                  │

│  Project Manager: __________________________________ Date: _____________        │

│  Tech Lead:      __________________________________ Date: _____________        │

│  Product Owner:  __________________________________ Date: _____________        │

│  CCB Chair:      __________________________________ Date: _____________        │

│                                                                                  │

│  STATUS:  ☐ Approved  ☐ Rejected  ☐ Deferred  ☐ Pending                       │

│                                                                                  │

│  COMMENTS:                                                                      │

│  [Additional comments or conditions]                                            │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### A.2. Risk Register Form

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           RISK REGISTER FORM                                    │

│                          Project: P-FNE-07                                      │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  RISK ID: R-XXX                                                                 │

│  DATE IDENTIFIED: [DD/MM/YYYY]                                                  │

│  IDENTIFIED BY: [Name] [Role]                                                   │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  RISK CATEGORY:                                                                 │

│  ☐ Technical  ☐ Management  ☐ Organizational  ☐ External  ☐ Data  ☐ Security  │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  RISK DESCRIPTION:                                                               │

│  [Clear description of the risk]                                                │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  RISK TRIGGER:                                                                  │

│  [Conditions that would trigger this risk]                                      │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  PROBABILITY:     ☐ 1 - Very Low   ☐ 2 - Low   ☐ 3 - Medium   ☐ 4 - High   ☐ 5 - Very High │

│  IMPACT:          ☐ 1 - Very Low   ☐ 2 - Low   ☐ 3 - Medium   ☐ 4 - High   ☐ 5 - Very High │

│  RISK SCORE:      [Probability x Impact] = [____]                               │

│  PRIORITY:        ☐ Critical  ☐ High  ☐ Medium  ☐ Low                          │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  RISK OWNER: [Name] [Role]                                                      │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  MITIGATION STRATEGY:                                                           │

│  ☐ Avoid  ☐ Mitigate  ☐ Transfer  ☐ Accept  ☐ Escalate                         │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  MITIGATION ACTIONS:                                                            │

│  [Detailed actions to reduce probability/impact]                                │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  CONTINGENCY PLAN:                                                              │

│  [Actions if risk occurs]                                                       │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  STATUS:                                                                        │

│  ☐ Open  ☐ Monitoring  ☐ Mitigated  ☐ Closed  ☐ Materialized                  │

│                                                                                  │

│  LAST UPDATED: [DD/MM/YYYY]                                                     │

│                                                                                  │

│  COMMENTS:                                                                      │

│  [Updates, changes, or additional notes]                                        │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### A.3. Issue Log Form

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           ISSUE LOG FORM                                        │

│                          Project: P-FNE-07                                      │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  ISSUE ID: I-XXX                                                                │

│  DATE REPORTED: [DD/MM/YYYY]                                                    │

│  REPORTED BY: [Name] [Role]                                                     │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  ISSUE DESCRIPTION:                                                             │

│  [Clear description of the issue]                                               │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  PRIORITY:                                                                      │

│  ☐ Critical  ☐ High  ☐ Medium  ☐ Low                                          │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  AFFECTED AREA:                                                                 │

│  ☐ Scope  ☐ Schedule  ☐ Budget  ☐ Quality  ☐ Resources  ☐ Technical           │

│  ☐ Stakeholder  ☐ Other: _________                                              │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  ASSIGNED TO: [Name] [Role]                                                     │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  ROOT CAUSE ANALYSIS:                                                           │

│  [Analysis of what caused the issue]                                            │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  RESOLUTION ACTION:                                                             │

│  [Actions taken to resolve]                                                     │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  STATUS:                                                                        │

│  ☐ Open  ☐ In Progress  ☐ Resolved  ☐ Closed                                 │

│                                                                                  │

│  RESOLUTION DATE: [DD/MM/YYYY]                                                  │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  VERIFICATION:                                                                  │

│  Verified by: [Name] [Role]                                                     │

│  Date: [DD/MM/YYYY]                                                             │

│  Comments: [Verification comments]                                              │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

### A.4. Lessons Learned Form

text

┌─────────────────────────────────────────────────────────────────────────────────┐

│                           LESSONS LEARNED FORM                                  │

│                          Project: P-FNE-07                                      │

├─────────────────────────────────────────────────────────────────────────────────┤

│                                                                                  │

│  LESSON ID: LL-XXX                                                              │

│  DATE: [DD/MM/YYYY]                                                             │

│  CATEGORY: ☐ Process  ☐ Technical  ☐ Management  ☐ People  ☐ External         │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  LESSON DESCRIPTION:                                                            │

│  [What happened?]                                                               │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  WHAT WENT WELL:                                                                │

│  [Positive aspects to continue]                                                 │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  WHAT WENT WRONG:                                                               │

│  [Challenges and issues encountered]                                            │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  RECOMMENDATIONS:                                                               │

│  [What should be done differently next time?]                                   │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  APPLICABILITY:                                                                 │

│  ☐ Current project  ☐ Future projects  ☐ Both                                  │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  ACTION ITEMS:                                                                  │

│  [Actions to implement recommendations]                                         │

│                                                                                  │

│  ────────────────────────────────────────────────────────────────────────────── │

│                                                                                  │

│  STATUS:                                                                        │

│  ☐ Documented  ☐ Reviewed  ☐ Implemented  ☐ Closed                            │

│                                                                                  │

│  REVIEWED BY: [Name] [Role]                                                     │

│  REVIEW DATE: [DD/MM/YYYY]                                                      │

│                                                                                  │

└─────────────────────────────────────────────────────────────────────────────────┘

## 12.3. Lampiran B: Matriks & Checklist

### B.1. RACI Matrix (Complete)

| Aktivitas / Deliverable | Sponsor | PM | PO | Tech Lead | BE Dev | FE Dev | Data Eng | Data Sci | ML Eng | Knowledge Eng | QA | DevOps | BA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Charter | A | R | C | C | - | - | - | - | - | - | - | - | C |
| PMP | A | R | C | C | - | - | - | - | - | - | - | - | C |
| Requirements | C | C | R | C | C | C | C | C | C | C | C | C | R |
| Architecture Design | C | C | C | R | C | C | C | C | C | C | C | C | C |
| Data Lake Setup | - | C | C | C | - | - | R | - | - | - | - | C | - |
| Data Warehouse Setup | - | C | C | C | - | - | R | - | - | - | - | C | - |
| ETL Pipeline | - | C | C | C | - | - | R | - | - | - | - | C | - |
| CDC Setup | - | C | C | C | - | - | R | - | - | - | - | C | - |
| Data Quality | - | C | C | C | - | - | R | - | - | - | C | C | - |
| Dashboard Framework | - | C | C | C | C | R | - | - | - | - | C | C | - |
| Executive Dashboard | - | C | C | C | C | R | - | - | - | - | C | - | - |
| Farm Dashboard | - | C | C | C | C | R | - | - | - | - | C | - | - |
| Production Dashboard | - | C | C | C | C | R | - | - | - | - | C | - | - |
| Supply Chain Dashboard | - | C | C | C | C | R | - | - | - | - | C | - | - |
| Sales Dashboard | - | C | C | C | C | R | - | - | - | - | C | - | - |
| Financial Dashboard | - | C | C | C | C | R | - | - | - | - | C | - | - |
| HCM Dashboard | - | C | C | C | C | R | - | - | - | - | C | - | - |
| Quality Dashboard | - | C | C | C | C | R | - | - | - | - | C | - | - |
| KPI Definition | - | C | R | C | C | C | - | - | - | - | C | - | C |
| KPI Alert System | - | C | R | C | R | - | - | - | - | - | C | - | - |
| Scheduled Reports | - | C | C | C | R | C | - | - | - | - | C | - | - |
| Ad-Hoc Report Builder | - | C | C | C | R | R | - | - | - | - | C | - | - |
| AI/ML Models | - | C | C | C | - | - | C | R | C | - | C | C | - |
| Model Registry | - | C | C | C | - | - | - | C | R | - | C | C | - |
| Model Monitoring | - | C | C | C | - | - | - | C | R | - | C | C | - |
| Explainable AI | - | C | C | C | - | - | - | R | C | - | C | - | - |
| Feature Store | - | C | C | C | - | - | R | C | - | - | C | C | - |
| Ontology Definition | - | C | C | C | - | - | - | - | - | R | - | - | - |
| Graph Ingestion | - | C | C | C | - | - | - | - | - | R | C | C | - |
| Graph Query Engine | - | C | C | C | R | - | - | - | - | C | C | C | - |
| Graph Visualization | - | C | C | C | - | R | - | - | - | C | C | - | - |
| What-If Analysis | - | C | C | C | R | - | - | C | - | - | C | C | C |
| Optimization Engine | - | C | C | C | R | - | - | C | - | - | C | C | C |
| Decision Log | - | C | C | C | R | C | - | - | - | - | C | - | C |
| Integration (All) | - | C | C | C | R | - | R | - | - | - | C | C | - |
| API Gateway | - | C | C | C | R | - | - | - | - | - | C | C | - |
| Integration Testing | - | C | C | C | C | C | C | C | C | C | R | C | - |
| UAT | C | R | R | C | - | - | - | - | - | - | C | - | C |
| Deployment | C | C | C | C | C | C | C | C | C | C | C | R | - |
| Go-Live | A | R | R | C | - | - | - | - | - | - | C | C | - |
| User Training | C | R | C | - | - | - | - | - | - | - | - | - | R |
| Project Closure | A | R | C | C | - | - | - | - | - | - | - | - | - |

R = Responsible, A = Accountable, C = Consulted, I = Informed

### B.2. Quality Checklist

#### B.2.1. Code Review Checklist

| No | Checklist Item | Status (✓/✗) | Comments |
| --- | --- | --- | --- |
| 1 | Code follows coding standards |  |  |
| 2 | Unit tests written and passing (coverage ≥ 80%) |  |  |
| 3 | Integration tests written (if applicable) |  |  |
| 4 | No security vulnerabilities |  |  |
| 5 | Performance is acceptable |  |  |
| 6 | Documentation updated |  |  |
| 7 | Logging implemented appropriately |  |  |
| 8 | Error handling implemented |  |  |
| 9 | No code duplication |  |  |
| 10 | Follows design patterns |  |  |
| 11 | API documentation updated |  |  |
| 12 | Database migration scripts reviewed |  |  |
| 13 | CI/CD pipeline passes |  |  |
| 14 | PR description complete |  |  |
| 15 | Self-review conducted |  |  |

#### B.2.2. Deployment Checklist

| No | Checklist Item | Status (✓/✗) | Comments |
| --- | --- | --- | --- |
| 1 | All tests passed (unit, integration, system) |  |  |
| 2 | Performance testing passed |  |  |
| 3 | Security testing passed |  |  |
| 4 | Code review approved |  |  |
| 5 | Documentation updated |  |  |
| 6 | Database backup taken |  |  |
| 7 | Rollback plan documented |  |  |
| 8 | Deployment plan documented |  |  |
| 9 | Environment configuration verified |  |  |
| 10 | Dependencies and versions verified |  |  |
| 11 | Monitoring configured |  |  |
| 12 | Alerting configured |  |  |
| 13 | Communication plan ready |  |  |
| 14 | Stakeholders notified |  |  |
| 15 | Hypercare team ready |  |  |

### B.3. WBS Dictionary (Complete Summary)

| WBS Code | Name | Description | Responsible | Duration | Deliverable |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Project Management | Project management activities | PM | 24 weeks | PMP, Reports |
| 1.1 | PMP & Planning | Project planning | PM | 4 weeks | PMP, Charter |
| 1.2 | Communication & Reporting | Communication and reporting | PM | 24 weeks | Status Reports |
| 1.3 | Quality & Risk Management | Quality and risk management | PM + QA | 24 weeks | Quality Plan, Risk Register |
| 2.0 | Data Platform | Data platform development | Data Engineering | 8 weeks | Data Lake, DW, Pipeline |
| 2.1 | Data Lake & Storage | Data lake setup | Data Engineer | 2 weeks | MinIO/S3 Setup |
| 2.2 | Data Warehouse & Data Mart | Data warehouse setup | Data Engineer | 3 weeks | Snowflake Schema |
| 2.3 | Data Ingestion (CDC) | CDC setup | Data Engineer | 2 weeks | CDC Pipeline |
| 2.4 | ETL/ELT Pipeline | ETL pipeline | Data Engineer | 3 weeks | Airflow Pipeline |
| 2.5 | Data Quality & Monitoring | Data quality monitoring | Data Engineer | 2 weeks | Quality Dashboard |
| 2.6 | Metadata & Data Lineage | Metadata management | Data Engineer | 2 weeks | Metadata Repository |
| 3.0 | Business Intelligence | BI development | Frontend + Backend | 8 weeks | 8 Dashboards |
| 3.1 | Dashboard - Executive | Executive dashboard | FE + BE | 2 weeks | Executive Dashboard |
| 3.2 | Dashboard - Farm | Farm dashboard | FE + BE | 2 weeks | Farm Dashboard |
| 3.3 | Dashboard - Production | Production dashboard | FE + BE | 2 weeks | Production Dashboard |
| 3.4 | Dashboard - Supply Chain | Supply chain dashboard | FE + BE | 2 weeks | Supply Chain Dashboard |
| 3.5 | Dashboard - Sales | Sales dashboard | FE + BE | 2 weeks | Sales Dashboard |
| 3.6 | Dashboard - Finance | Finance dashboard | FE + BE | 2 weeks | Finance Dashboard |
| 3.7 | Dashboard - HCM | HCM dashboard | FE + BE | 2 weeks | HCM Dashboard |
| 3.8 | Dashboard - Quality | Quality dashboard | FE + BE | 2 weeks | Quality Dashboard |
| 3.9 | KPI Definition & Management | KPI system | BE + FE | 2 weeks | KPI System |
| 3.10 | KPI Alert System | Alert system | BE | 2 weeks | Alert System |
| 3.11 | Scheduled Report System | Report scheduling | BE | 2 weeks | Report System |
| 3.12 | Ad-Hoc Report Builder | Ad-hoc report builder | FE + BE | 3 weeks | Report Builder |
| 4.0 | AI/ML Platform | AI/ML development | Data Science + ML | 8 weeks | 5 Models |
| 4.1 | Infrastructure & MLOps | MLOps setup | ML Engineer | 2 weeks | MLflow, Kubeflow |
| 4.2 | Model #1: Demand Forecasting | Demand forecasting model | Data Scientist | 3 weeks | Model #1 |
| 4.3 | Model #2: Crop Yield Prediction | Crop yield prediction | Data Scientist | 3 weeks | Model #2 |
| 4.4 | Model #3: Inventory Forecasting | Inventory forecasting | Data Scientist | 2 weeks | Model #3 |
| 4.5 | Model #4: Predictive Maintenance | Predictive maintenance | Data Scientist | 3 weeks | Model #4 |
| 4.6 | Model #5: Anomaly Detection | Anomaly detection | Data Scientist | 2 weeks | Model #5 |
| 4.7 | Model Registry & Versioning | Model registry | ML Engineer | 2 weeks | Model Registry |
| 4.8 | Model Monitoring & Drift | Model monitoring | ML Engineer | 2 weeks | Monitoring |
| 4.9 | Explainable AI | XAI implementation | Data Scientist | 2 weeks | XAI API |
| 4.10 | Feature Store | Feature store | Data Engineer | 2 weeks | Feature Store |
| 5.0 | Knowledge Graph | Knowledge graph development | Knowledge Engineer | 4 weeks | Graph System |
| 5.1 | Ontology Definition | Ontology definition | Knowledge Engineer | 1 week | Ontology |
| 5.2 | Graph Ingestion | Graph ingestion | Knowledge Engineer | 2 weeks | Ingestion |
| 5.3 | Graph Query Engine | Query engine | Backend | 2 weeks | GraphQL API |
| 5.4 | Graph Visualization | Visualization | Frontend | 2 weeks | Visualizer |
| 5.5 | Path Discovery & Impact | Path and impact analysis | Backend | 2 weeks | Analysis Engine |
| 5.6 | Semantic Search | Semantic search | Backend | 2 weeks | Search Engine |
| 5.7 | Provenance Management | Provenance | Knowledge Engineer | 1 week | Provenance |
| 6.0 | Decision Intelligence | Decision intelligence | Backend | 3 weeks | Decision System |
| 6.1 | What-If Analysis | What-if engine | Backend | 2 weeks | What-If Engine |
| 6.2 | Scenario Comparison | Scenario comparison | Backend | 2 weeks | Comparison Engine |
| 6.3 | Optimization Engine | Optimization engine | Backend | 2 weeks | LP Engine |
| 6.4 | Decision Log System | Decision log | Backend + FE | 1 week | Decision Log |
| 6.5 | Outcome Tracking | Outcome tracking | Backend | 1 week | Outcome Tracking |
| 7.0 | Integration & Testing | Integration and testing | All Teams | 6 weeks | Integrated System |
| 7.1 | Integration P-FNE-01 | Foundation integration | Backend + DE | 2 weeks | Integrated |
| 7.2 | Integration P-FNE-02 | Ag Ops integration | Backend + DE | 2 weeks | Integrated |
| 7.3 | Integration P-FNE-03 | Supply Chain integration | Backend + DE | 2 weeks | Integrated |
| 7.4 | Integration P-FNE-04 | Production integration | Backend + DE | 2 weeks | Integrated |
| 7.5 | Integration P-FNE-05 | Commerce integration | Backend + DE | 2 weeks | Integrated |
| 7.6 | Integration P-FNE-06 | Finance/HCM integration | Backend + DE | 2 weeks | Integrated |
| 7.7 | API & BFF Development | API gateway and BFF | Backend | 3 weeks | API Gateway |
| 7.8 | Frontend Development | Web application | Frontend | 6 weeks | Web App |
| 7.9 | System Integration Testing | SIT | QA | 3 weeks | SIT Passed |
| 7.10 | User Acceptance Testing | UAT | QA + Users | 2 weeks | UAT Sign-off |
| 7.11 | Deployment & Go-Live | Production deployment | DevOps | 1 week | Live System |

## 12.4. Lampiran C: Referensi & Regulasi

### C.1. Standar & Regulasi yang Berlaku

| No | Standar/Regulasi | Deskripsi | Relevansi |
| --- | --- | --- | --- |
| 1 | PMBOK Guide | Project Management Body of Knowledge | Project management framework |
| 2 | ISO 27001 | Information Security Management | Data security and privacy |
| 3 | ISO 9001 | Quality Management System | Quality assurance |
| 4 | GDPR | General Data Protection Regulation | Data privacy for EU operations |
| 5 | UU No. 27 Tahun 2022 | Perlindungan Data Pribadi Indonesia | Data privacy compliance |
| 6 | OWASP Top 10 | Web Application Security Risks | Security testing |
| 7 | Agile Manifesto | Agile principles and values | Development methodology |
| 8 | Technology Stack Standards | Company-approved technology stack | Technical consistency |
| 9 | IT Governance Framework | IT governance and compliance | Organizational compliance |

### C.2. Teknologi Stack Detail

| Category | Technology | Version | Purpose |
| --- | --- | --- | --- |
| Frontend | React | 18.x | Web application framework |
|  | Next.js | 14.x | Server-side rendering |
|  | TypeScript | 5.x | Type-safe JavaScript |
|  | D3.js | 7.x | Data visualization |
|  | Chart.js | 4.x | Charts and graphs |
|  | Cytoscape.js | 3.x | Graph visualization |
| Backend | Spring Boot | 3.x | Java microservices |
|  | FastAPI | 0.100+ | Python API services |
|  | Node.js | 20.x | API services |
| Data | PostgreSQL | 15.x | Relational database |
|  | TimescaleDB | 2.x | Time-series database |
|  | Neo4j | 5.x | Graph database |
|  | Snowflake | - | Data warehouse |
|  | MinIO | - | Object storage / Data Lake |
| Big Data | Apache Kafka | 3.x | Event streaming |
|  | Apache Spark | 3.x | Data processing |
|  | Apache Airflow | 2.x | Workflow orchestration |
| ML/AI | Python | 3.11 | ML development |
|  | MLflow | 2.x | ML lifecycle management |
|  | Kubeflow | 1.7 | ML orchestration |
|  | TensorFlow | 2.x | Deep learning |
|  | PyTorch | 2.x | Deep learning |
|  | XGBoost | 2.x | Gradient boosting |
|  | Scikit-learn | 1.x | Classical ML |
|  | SHAP | 0.40+ | Explainable AI |
| Infrastructure | Docker | 24.x | Containerization |
|  | Kubernetes | 1.28 | Container orchestration |
|  | Helm | 3.x | Kubernetes package management |
|  | Istio | 1.20 | Service mesh |
| CI/CD | GitHub Actions | - | CI/CD pipeline |
|  | ArgoCD | 2.x | GitOps deployment |
| Monitoring | Prometheus | 2.x | Metrics monitoring |
|  | Grafana | 10.x | Visualization |
|  | ELK Stack | 8.x | Logging |
|  | Jaeger | 1.x | Distributed tracing |
| Security | Keycloak | 22.x | IAM / SSO |
|  | OWASP ZAP | - | Security scanning |
|  | SonarQube | 10.x | Code quality |

### C.3. Glossary of Terms

| Term | Definition |
| --- | --- |
| Actionable Insights | Wawasan yang dapat langsung ditindaklanjuti untuk perbaikan |
| BI (Business Intelligence) | Proses dan teknologi untuk menganalisis data bisnis |
| BFF (Backend for Frontend) | Layer API yang dioptimalkan untuk kebutuhan frontend tertentu |
| CDC (Change Data Capture) | Teknik untuk menangkap perubahan data secara real-time |
| CI/CD | Continuous Integration / Continuous Deployment |
| Data Lake | Repositori data mentah dalam format asli |
| Data Warehouse | Repositori data terstruktur untuk analisis |
| Digital Twin | Representasi digital dari aset fisik |
| ETL | Extract, Transform, Load - proses pemindahan data |
| Explainable AI | Kemampuan AI untuk menjelaskan prediksinya |
| Feature Store | Repositori terpusat untuk fitur ML |
| GraphQL | Query language untuk API |
| Knowledge Graph | Representasi data sebagai graph dengan node dan relationship |
| MLOps | Praktik untuk mengelola siklus hidup ML |
| OEE (Overall Equipment Effectiveness) | Metrik efisiensi produksi |
| Ontology | Definisi formal tentang entity dan relasi dalam domain |
| Provenance | Asal-usul data/relationship |
| RBAC (Role-Based Access Control) | Kontrol akses berdasarkan peran |
| REST | Architectural style untuk web services |
| SLA (Service Level Agreement) | Perjanjian tingkat layanan |
| SSOT (Single Source of Truth) | Sumber kebenaran tunggal |
| UAT (User Acceptance Testing) | Pengujian penerimaan pengguna |
| WBS (Work Breakdown Structure) | Struktur pemecahan pekerjaan |
| What-If Analysis | Analisis skenario dengan mengubah parameter |

## 12.5. Lampiran D: Communication Templates

### D.1. Meeting Minutes Template

text

--- MEETING MINUTES ---

Meeting: [Meeting Name]

Date: [DD/MM/YYYY]

Time: [Start Time] - [End Time]

Location: [Link/Room]

Chair: [Chairperson]

Attendees: [List of attendees]

Minutes Taker: [Name]

--- AGENDA ---

1. [Item 1]

2. [Item 2]

3. [Item 3]

--- DISCUSSION ---

1. [Topic 1]

- Discussion: [Summary]

- Decisions: [Decisions made]

- Action Items: [Action items]

2. [Topic 2]

- Discussion: [Summary]

- Decisions: [Decisions made]

- Action Items: [Action items]

--- ACTION ITEMS ---

| # | Action | Owner | Deadline | Status |

|---|--------|-------|----------|--------|

| 1 | [Action description] | [Name] | [Date] | [Status] |

| 2 | [Action description] | [Name] | [Date] | [Status] |

--- NEXT MEETING ---

Date: [DD/MM/YYYY]

Time: [Start Time]

Agenda Items: [To be defined]

--- ATTACHMENTS ---

[Links to relevant documents]

--- END ---

### D.2. Weekly Status Report Template

text

--- WEEKLY STATUS REPORT ---

Project: P-FNE-07 - Intelligence & Decision Platform

Period: [Start Date] - [End Date]

Week: [Week Number]

Prepared By: [PM Name]

Date: [DD/MM/YYYY]

--- EXECUTIVE SUMMARY ---

Overall Status: 🟢 On Track / 🟡 At Risk / 🔴 Critical

Key Achievements This Week:

1. [Achievement 1]

2. [Achievement 2]

3. [Achievement 3]

Key Issues/Risks:

1. [Issue 1]

2. [Risk 1]

Next Week Focus:

1. [Focus 1]

2. [Focus 2]

--- PROGRESS DASHBOARD ---

Overall Progress: [XX]% (Planned: [XX]%, Variance: [+/-XX]%)

Sprint Progress: [XX]% (Days remaining: [XX])

Milestones: [XX] of [YY] completed

--- BUDGET STATUS ---

Budget Used: Rp [XXX] of Rp [YYY] ([XX]%)

Variance: Rp [ZZZ] ([+/-XX]%)

Forecast: Rp [YYY]

--- WORK ACCOMPLISHED ---

Completed Tasks:

1. [Task 1] - [Status] - [Owner]

2. [Task 2] - [Status] - [Owner]

Completed User Stories:

1. [Story 1] - [Points] - [Owner]

2. [Story 2] - [Points] - [Owner]

--- WORK PLANNED ---

Next Week Tasks:

1. [Task 1] - [Owner]

2. [Task 2] - [Owner]

Next Sprint Stories:

1. [Story 1] - [Points]

2. [Story 2] - [Points]

--- ISSUES & RISKS ---

Open Issues:

| # | Issue | Priority | Owner | Status |

|---|-------|----------|-------|--------|

| 1 | [Issue] | [P0/P1/P2] | [Name] | [Status] |

Risks:

| # | Risk | Probability | Impact | Mitigation | Status |

|---|------|-------------|--------|------------|--------|

| 1 | [Risk] | [H/M/L] | [H/M/L] | [Action] | [Status] |

--- QUALITY METRICS ---

Code Coverage: [XX]%

SonarQube Rating: [A/B/C/D/E]

Defects: [#] Open, [#] Closed this week

Critical Defects: [#] Open

--- TEAM STATUS ---

Resource Utilization: [XX]%

Team Attendance: [XX]%

Upcoming Leaves: [List]

--- END ---

### D.3. Milestone Completion Report Template

text

--- MILESTONE COMPLETION REPORT ---

Project: P-FNE-07 - Intelligence & Decision Platform

Milestone: [Milestone Name] ([M0] - [M6])

Date: [DD/MM/YYYY]

Prepared By: [PM Name]

--- MILESTONE OVERVIEW ---

Milestone ID: [M0/M1/M2/M3/M4/M5/M6]

Planned Date: [DD/MM/YYYY]

Actual Date: [DD/MM/YYYY]

Status: ✅ Completed / 🟡 Completed with Issues / 🔴 Not Completed

Deliverables:

| # | Deliverable | Status | Notes |

|---|-------------|--------|-------|

| 1 | [Deliverable] | ✅/🟡/🔴 | [Notes] |

| 2 | [Deliverable] | ✅/🟡/🔴 | [Notes] |

--- ACCEPTANCE CRITERIA ---

| # | Criteria | Status | Evidence |

|---|----------|--------|----------|

| 1 | [Criteria] | ✅/🟡/🔴 | [Link/File] |

| 2 | [Criteria] | ✅/🟡/🔴 | [Link/File] |

--- LESSONS LEARNED ---

What Went Well:

1. [Lesson 1]

2. [Lesson 2]

What Went Wrong:

1. [Lesson 1]

2. [Lesson 2]

Recommendations:

1. [Recommendation 1]

2. [Recommendation 2]

--- NEXT STEPS ---

1. [Next Step 1]

2. [Next Step 2]

--- SIGN-OFF ---

Project Manager: __________________________________ Date: _____________

Product Owner: __________________________________ Date: _____________

Project Sponsor: __________________________________ Date: _____________

--- END ---

## 12.6. Lampiran E: Acronyms & Abbreviations

| Acronym | Full Form |
| --- | --- |
| ABC | Activity Based Costing |
| AI | Artificial Intelligence |
| API | Application Programming Interface |
| AR | Account Receivable |
| BA | Business Analyst |
| BE | Backend |
| BFF | Backend for Frontend |
| BI | Business Intelligence |
| BOM | Bill of Materials |
| CAPEX | Capital Expenditure |
| CCB | Change Control Board |
| CDC | Change Data Capture |
| CI/CD | Continuous Integration / Continuous Delivery |
| CRM | Customer Relationship Management |
| DE | Data Engineer |
| DevOps | Development Operations |
| DS | Data Scientist |
| DW | Data Warehouse |
| ELT | Extract, Load, Transform |
| ERP | Enterprise Resource Planning |
| ETL | Extract, Transform, Load |
| FE | Frontend |
| FNE | Farm Nation Enterprise |
| GDPR | General Data Protection Regulation |
| HCM | Human Capital Management |
| IAM | Identity and Access Management |
| IoT | Internet of Things |
| KPI | Key Performance Indicator |
| LP | Linear Programming |
| ML | Machine Learning |
| MLOps | Machine Learning Operations |
| OEE | Overall Equipment Effectiveness |
| PM | Project Manager |
| PMBOK | Project Management Body of Knowledge |
| PMP | Project Management Plan |
| PO | Product Owner |
| QA | Quality Assurance |
| RBAC | Role-Based Access Control |
| RFP | Request for Proposal |
| RFQ | Request for Quotation |
| ROI | Return on Investment |
| RTM | Requirements Traceability Matrix |
| SC | Supply Chain |
| SLA | Service Level Agreement |
| SIT | System Integration Testing |
| SSOT | Single Source of Truth |
| UAT | User Acceptance Testing |
| UI/UX | User Interface / User Experience |
| UOM | Unit of Measure |
| WBS | Work Breakdown Structure |
| XAI | Explainable Artificial Intelligence |

--- BAB 12 SELESAI ---

## 12.7. Penutup

Dengan selesainya Bab 12: Lampiran, maka seluruh Project Management Plan (PMP) untuk proyek Intelligence & Decision Platform (P-FNE-07) telah lengkap.

### Ringkasan Dokumen PMP:

| Bab | Judul | Halaman | Status |
| --- | --- | --- | --- |
| 1 | Pendahuluan | [XX] | ✅ Complete |
| 2 | Manajemen Integrasi Proyek | [XX] | ✅ Complete |
| 3 | Manajemen Lingkup Proyek | [XX] | ✅ Complete |
| 4 | Manajemen Penjadwalan Proyek | [XX] | ✅ Complete |
| 5 | Manajemen Biaya Proyek | [XX] | ✅ Complete |
| 6 | Manajemen Kualitas Proyek | [XX] | ✅ Complete |
| 7 | Manajemen Sumber Daya Proyek | [XX] | ✅ Complete |
| 8 | Manajemen Komunikasi Proyek | [XX] | ✅ Complete |
| 9 | Manajemen Risiko Proyek | [XX] | ✅ Complete |
| 10 | Manajemen Pengadaan Proyek | [XX] | ✅ Complete |
| 11 | Manajemen Pemangku Kepentingan | [XX] | ✅ Complete |
| 12 | Lampiran | [XX] | ✅ Complete |

### Dokumentasi PMP Lengkap terdiri dari:

- Dokumen Utama PMP (Bab 1-11) - 11 bab dengan 10 area manajemen PMBOK

- Lampiran Pendukung (Bab 12) - Formulir, matriks, checklist, template, referensi

### Approval

| Peran | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager | [Nama] |  | [DD/MM/YYYY] |
| Tech Lead | [Nama] |  | [DD/MM/YYYY] |
| Product Owner | [Nama] |  | [DD/MM/YYYY] |
| QA Lead | [Nama] |  | [DD/MM/YYYY] |
| Project Sponsor | [Nama] |  | [DD/MM/YYYY] |