# BAB 1: PENDAHULUAN

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 1.1. Tujuan Dokumen

Dokumen Project Management Plan (PMP) ini disusun dengan tujuan sebagai berikut:

- Acuan Manajemen Proyek: Menjadi panduan utama bagi seluruh tim proyek dalam merencanakan, mengorganisir, mengarahkan, dan mengendalikan pelaksanaan proyek P-FNE-04.

- Komunikasi Stakeholder: Menyediakan informasi yang komprehensif kepada seluruh pemangku kepentingan mengenai bagaimana proyek akan dikelola, termasuk jadwal, biaya, ruang lingkup, dan risiko.

- Pengendalian Proyek: Menyediakan baseline untuk mengukur kinerja proyek dan mengambil tindakan korektif jika terjadi penyimpangan.

- Dokumentasi Resmi: Menjadi dokumen resmi yang mendokumentasikan seluruh keputusan dan rencana manajemen proyek.

- Referensi Audit: Menyediakan referensi untuk audit proyek dan evaluasi pasca-proyek.

### 1.2. Deskripsi Proyek

#### 1.2.1. Latar Belakang

Farm Nation Enterprise (FNE) adalah perusahaan agribisnis terintegrasi yang bergerak di bidang pertanian, peternakan, pengolahan hasil pertanian, dan distribusi produk agro. Sebagai bagian dari transformasi digital perusahaan, FNE menginisiasi pengembangan Super ERP Farm Nation Enterprise yang terdiri dari 8 proyek turunan (P-FNE-01 s.d. P-FNE-08).

Proyek P-FNE-04: Production & Manufacturing merupakan salah satu komponen kritis dalam ekosistem Super ERP yang berfungsi sebagai tulang punggung operasi produksi perusahaan. Modul ini menjadi jembatan antara rantai pasok (P-FNE-03) dan komersialisasi (P-FNE-05), memastikan proses produksi berjalan efisien, terkendali, dan menghasilkan produk berkualitas sesuai spesifikasi.

#### 1.2.2. Visi dan Misi Proyek

Visi:
Menjadi sistem manajemen produksi dan manufaktur terdepan yang memungkinkan Farm Nation Enterprise mencapai keunggulan operasional melalui digitalisasi proses produksi yang terintegrasi, real-time, dan berbasis data.

Misi:

- Menyediakan platform perencanaan produksi yang akurat dan responsif terhadap perubahan permintaan

- Mengelola Bill of Materials (BOM) secara terstruktur dengan versioning dan cost rollup

- Mengeksekusi proses produksi dengan pencatatan real-time melalui web dan mobile

- Menghitung biaya produksi secara akurat untuk mendukung pengambilan keputusan

- Mengelola aset dan pemeliharaan untuk memaksimalkan efektivitas peralatan

- Mengintegrasikan seluruh proses produksi dengan rantai pasok dan keuangan

#### 1.2.3. Tujuan Utama Proyek

| No | Tujuan | Indikator Keberhasilan | Target |
| --- | --- | --- | --- |
| 1 | Merencanakan dan menjadwalkan produksi berdasarkan permintaan dan kapasitas | Production plan tersedia dan di-approve sebelum periode produksi | 100% production plan di-approve tepat waktu |
| 2 | Mengelola Bill of Materials (BOM) dan resep produksi | Semua produk memiliki BOM aktif | 100% produk memiliki BOM versi terbaru |
| 3 | Mengeksekusi proses produksi dengan pencatatan real-time | Operator dapat mencatat progress via mobile | < 5 menit waktu pencatatan per operasi |
| 4 | Mengelola aset dan pemeliharaan mesin/peralatan | Maintenance work order tersedia dan terlacak | 100% WO terjadwal dan terealisasi |
| 5 | Menghitung biaya produksi secara akurat | Biaya produksi tersedia saat PO selesai | 100% PO memiliki biaya aktual |

#### 1.2.4. Manfaat Proyek

| No | Manfaat | Deskripsi | Penerima |
| --- | --- | --- | --- |
| 1 | Efisiensi Operasional | Mengurangi waktu perencanaan produksi hingga 40% | Production Planner |
| 2 | Visibilitas Real-time | Monitoring produksi secara real-time dari mana saja | Manajer Produksi, Direksi |
| 3 | Akurasi Biaya | Perhitungan biaya produksi yang akurat dan otomatis | Finance, Manajemen |
| 4 | Pengurangan Downtime | Manajemen maintenance yang terstruktur mengurangi downtime mesin hingga 20% | Production Team |
| 5 | Integrasi Data | Data produksi terintegrasi dengan inventory, sales, dan finance | Seluruh Divisi |
| 6 | Pengambilan Keputusan | Laporan dan analisis untuk mendukung pengambilan keputusan | Manajemen Puncak |

### 1.3. Ruang Lingkup Proyek

#### 1.3.1. Lingkup Masuk (In-Scope)

| Domain | Fitur/Fungsi | Deskripsi |
| --- | --- | --- |
| Production Planning | Demand Forecasting | Menerima forecast dari sales dan AI |
|  | Production Plan | Membuat plan dengan period, produk, kuantitas |
|  | MRP Engine | Menghitung kebutuhan material berdasarkan BOM |
|  | Capacity Planning | Memeriksa ketersediaan kapasitas produksi |
|  | Production Scheduling | Menjadwalkan production order berdasarkan prioritas |
| BOM Management | BOM Creation | Membuat BOM multi-level dengan material dan routing |
|  | BOM Versioning | Versioning setiap perubahan BOM |
|  | BOM Explosion | Menghitung material requirement dari BOM |
|  | BOM Cost Rollup | Menghitung biaya standar produk |
|  | Where-Used Analysis | Mencari produk yang menggunakan material tertentu |
| Production Execution | Production Order | Membuat dan mengelola production order |
|  | Material Issue | Mengeluarkan material dari inventory |
|  | Progress Recording | Mencatat progress via web dan mobile |
|  | Quality Inspection | Inspeksi kualitas pada titik kritis |
|  | Production Completion | Menyelesaikan PO dan receive finished goods |
| Production Costing | Material Cost | Menghitung biaya material aktual |
|  | Labor Cost | Menghitung biaya tenaga kerja aktual |
|  | Machine Cost | Menghitung biaya mesin aktual |
|  | Overhead Cost | Menghitung biaya overhead |
|  | Variance Analysis | Membandingkan standard vs actual cost |
| Asset & Maintenance | Asset Registration | Mendaftarkan aset dengan spesifikasi lengkap |
|  | Maintenance WO | Membuat work order maintenance |
|  | Maintenance Execution | Mencatat pelaksanaan maintenance |
|  | Downtime Recording | Mencatat downtime aset |
|  | OEE Calculation | Menghitung OEE untuk setiap aset |
|  | Spare Part Inventory | Mengelola spare part dan stok |
| Facility Management | Facility Registration | Mendaftarkan facility produksi |
|  | Work Center Registration | Mendaftarkan work center |
|  | Shift Management | Mengelola shift kerja dan assignment |
| Integration | P-FNE-01 Foundation | IAM, Master Data, Audit |
|  | P-FNE-03 Supply Chain | Material availability, inventory |
|  | P-FNE-05 Commerce | Finished goods availability |
|  | P-FNE-06 Finance | Production cost data |
|  | P-FNE-07 Intelligence | Data untuk BI dan AI |
|  | P-FNE-08 Advanced | IoT data untuk asset monitoring |

#### 1.3.2. Lingkup Keluar (Out-of-Scope)

| No | Item | Alasan |
| --- | --- | --- |
| 1 | Predictive Maintenance berbasis AI tingkat lanjut | Menjadi bagian dari P-FNE-08 (Advanced) |
| 2 | Digital Twin dari aset produksi | Menjadi bagian dari P-FNE-08 |
| 3 | Marketplace eksternal | Menjadi bagian dari P-FNE-05 |
| 4 | HR/Payroll Management | Menjadi bagian dari P-FNE-06 |
| 5 | Integrasi dengan ERP eksternal | Fokus pada integrasi internal FNE |
| 6 | Real-time IoT sensor integration tingkat lanjut | Basic IoT hanya, advanced di P-FNE-08 |

#### 1.3.3. Batasan Proyek (Constraints)

| No | Constraint | Deskripsi |
| --- | --- | --- |
| 1 | Waktu | Proyek harus selesai dalam 6 bulan (Oktober 2026 - Maret 2027) |
| 2 | Anggaran | Anggaran maksimal Rp 5.500.000.000 |
| 3 | Tim | Tim terbatas 8-12 orang |
| 4 | Teknologi | Menggunakan stack teknologi yang sudah ditentukan (Spring Boot, React, Flutter, PostgreSQL) |
| 5 | Integrasi | Harus terintegrasi dengan 7 proyek turunan lainnya |
| 6 | Keamanan | Harus memenuhi standar keamanan perusahaan |

#### 1.3.4. Asumsi Proyek (Assumptions)

| No | Asumsi | Deskripsi |
| --- | --- | --- |
| 1 | Ketersediaan Tim | Tim tersedia sesuai jadwal yang direncanakan |
| 2 | Infrastruktur | Infrastruktur cloud tersedia tepat waktu |
| 3 | Data Master | Data master (product, material, facility) tersedia dari P-FNE-01 |
| 4 | User Availability | User tersedia untuk UAT dan training |
| 5 | Integrasi | API dari proyek lain tersedia sesuai jadwal |
| 6 | Regulatory | Tidak ada perubahan regulasi signifikan selama proyek berjalan |

### 1.4. Ketergantungan Proyek

#### 1.4.1. Ketergantungan Internal

text

┌─────────────────────────────────────────────────────────────────────────┐

│                        P-FNE-04 DEPENDENCIES                            │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  P-FNE-01 (Foundation)                                                 │

│  ├── IAM Service (Autentikasi & Otorisasi)                             │

│  ├── Master Data Service (Product, Material, Facility, User)           │

│  └── Audit Service (Logging aktivitas)                                 │

│                         │                                              │

│                         ▼                                              │

│  P-FNE-02 (Agricultural Operations)                                   │

│  └── Bahan baku dari hasil panen dan peternakan                       │

│                         │                                              │

│                         ▼                                              │

│  P-FNE-03 (Supply Chain)                                              │

│  ├── Material availability check                                      │

│  ├── Material issue dari inventory                                    │

│  └── Finished goods receipt ke inventory                              │

│                         │                                              │

│                         ▼                                              │

│  P-FNE-04 (Production & Manufacturing) ◄─── P-FNE-08 (IoT Data)       │

│                         │                                              │

│                         ▼                                              │

│  P-FNE-05 (Commerce)                                                  │

│  └── Finished goods untuk penjualan                                   │

│                         │                                              │

│                         ▼                                              │

│  P-FNE-06 (Finance)                                                   │

│  └── Data biaya produksi untuk akuntansi                              │

│                         │                                              │

│                         ▼                                              │

│  P-FNE-07 (Intelligence)                                              │

│  └── Data produksi untuk BI dan AI                                    │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 1.4.2. Tabel Ketergantungan

| No | Proyek | Dependency | Dibutuhkan Untuk | Timeline |
| --- | --- | --- | --- | --- |
| 1 | P-FNE-01 | IAM Service | Login, otorisasi user | Sebelum Sprint 1 |
| 2 | P-FNE-01 | Master Data Service | Data product, material, facility | Sebelum Sprint 1 |
| 3 | P-FNE-02 | Data panen dan ternak | Bahan baku produksi | Sprint 3-4 |
| 4 | P-FNE-03 | Inventory Service | Material availability, issue, receipt | Sprint 3-5 |
| 5 | P-FNE-05 | Sales Service | Demand forecast, finished goods | Sprint 5-7 |
| 6 | P-FNE-06 | Finance Service | Production cost integration | Sprint 8-10 |
| 7 | P-FNE-07 | Intelligence Service | Data untuk BI dan AI | Sprint 9-11 |
| 8 | P-FNE-08 | IoT Gateway | Data sensor untuk asset | Sprint 10-12 |

### 1.5. Struktur Organisasi Proyek

#### 1.5.1. Struktur Organisasi

text

┌─────────────────────────────────────────────────────────────────────────┐

│                      PROGRAM MANAGER                                    │

│                   (Super ERP FNE)                                       │

│              - Oversight seluruh proyek FNE                            │

│              - Koordinasi antar proyek                                 │

└───────────────────────────┬─────────────────────────────────────────────┘

│

┌───────────────────────────▼─────────────────────────────────────────────┐

│                    PROJECT MANAGER P-FNE-04                             │

│                - Manajemen proyek keseluruhan                          │

│                - Komunikasi stakeholder                                │

│                - Pengendalian jadwal & biaya                           │

└───────────────────────────┬─────────────────────────────────────────────┘

│

┌───────────────────────┼──────────────────────┬────────────────────┐

│                       │                      │                    │

▼                       ▼                      ▼                    ▼

┌───────────────┐   ┌───────────────┐    ┌───────────────┐    ┌─────────────────┐

│  TECH LEAD    │   │   BA / PO     │    │   QA LEAD     │    │  MANUFACTURING   │

│  (Backend)    │   │  (Business)   │    │               │    │   SPECIALIST     │

│               │   │               │    │               │    │                  │

│ - Arsitektur  │   │ - Kebutuhan   │    │ - Strategi QA │    │ - Domain Expert  │

│ - Code Review │   │ - Dokumentasi │    │ - Test Plan   │    │ - Acceptance     │

│ - Tech Decision│  │ - UAT         │    │ - Automation  │    │ - Validasi       │

└───────┬───────┘   └───────┬───────┘    └───────┬───────┘    └────────┬────────┘

│                   │                    │                     │

┌───┼───┐           ┌───┼───┐            ┌───┼───┐                  │

▼   ▼   ▼           ▼   ▼   ▼            ▼   ▼   ▼                  │

┌─────┐ ┌─────┐     ┌─────┐ ┌─────┐      ┌─────┐ ┌─────┐                │

│BE   │ │BE   │     │FE   │ │FE   │      │QA   │ │QA   │                │

│Dev  │ │Dev  │     │Dev  │ │Dev  │      │Eng  │ │Eng  │                │

└─────┘ └─────┘     └─────┘ └─────┘      └─────┘ └─────┘                │

│

┌─────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────┐

│   DEVOPS        │

│   ENGINEER      │

│ - CI/CD         │

│ - Infrastructure│

│ - Monitoring    │

└─────────────────┘

#### 1.5.2. Deskripsi Peran dan Tanggung Jawab

1. Project Manager (PM)

- Jumlah: 1 orang

- Tanggung Jawab:

  - Manajemen proyek secara keseluruhan

  - Penyusunan dan pemeliharaan Project Management Plan

  - Pengendalian jadwal, biaya, dan ruang lingkup

  - Komunikasi dengan stakeholder

  - Pelaporan status proyek secara berkala

  - Manajemen risiko dan isu

  - Fasilitasi sprint planning, review, dan retrospective

  - Memastikan deliverable sesuai kualitas

2. Tech Lead (TL)

- Jumlah: 1 orang

- Tanggung Jawab:

  - Arsitektur sistem secara keseluruhan

  - Decision teknis dan pemilihan teknologi

  - Code review dan quality assurance teknis

  - Coaching dan mentoring tim developer

  - Koordinasi teknis dengan proyek lain

  - Oversight implementasi microservices

3. Business Analyst / Product Owner (BA/PO)

- Jumlah: 1 orang

- Tanggung Jawab:

  - Analisis dan dokumentasi kebutuhan fungsional

  - Pengelolaan product backlog

  - Validasi fitur dengan user

  - UAT (User Acceptance Testing)

  - Penyusunan user manual dan training material

  - Koordinasi dengan domain expert

4. Backend Developer (BE)

- Jumlah: 3 orang

- Tanggung Jawab:

  - Pengembangan API dan microservices

  - Implementasi logika bisnis

  - Pengembangan database dan query

  - Integrasi dengan proyek lain

  - Unit testing dan documentation

  - Performance optimization

5. Frontend Developer (FE)

- Jumlah: 2 orang

- Tanggung Jawab:

  - Pengembangan Web Portal (React/Next.js)

  - Pengembangan Mobile App (Flutter)

  - Pengembangan Executive Dashboard

  - Implementasi UI/UX yang responsif

  - Integrasi dengan API backend

  - Unit testing dan documentation

6. QA Engineer (QA)

- Jumlah: 2 orang

- Tanggung Jawab:

  - Perencanaan dan eksekusi testing

  - Pengembangan automated test

  - Performance dan load testing

  - Security testing

  - Bug reporting dan tracking

  - Regression testing

7. DevOps Engineer (DevOps)

- Jumlah: 1 orang

- Tanggung Jawab:

  - Setup dan maintenance infrastructure

  - Implementasi CI/CD pipeline

  - Monitoring dan logging

  - Backup dan disaster recovery

  - Deployment management

  - Security implementation

8. Manufacturing Specialist (MS)

- Jumlah: 1 orang

- Tanggung Jawab:

  - Domain expertise manufaktur

  - Verifikasi acceptance criteria

  - Konsultasi proses bisnis produksi

  - Validasi fitur dari sisi domain

  - Support UAT dan training

#### 1.5.3. RACI Matrix (High-Level)

| Aktivitas | PM | TL | BA | BE | FE | QA | DevOps | MS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inisiasi |  |  |  |  |  |  |  |  |
| Penyusunan PMP | R/A | C | C | - | - | - | - | C |
| Requirement Gathering | C | C | R/A | I | I | - | - | C |
| Design & Architecture | - | - | - | - | - | - | - | - |
| System Architecture | C | R/A | C | I | I | I | C | C |
| Database Design | C | R/A | C | I | I | I | C | C |
| API Design | C | R/A | C | I | I | C | C | C |
| Pengembangan |  |  |  |  |  |  |  |  |
| Backend Development | C | R | C | A | - | I | - | C |
| Frontend Development | C | R | C | - | A | I | - | C |
| Integration Development | C | R | C | A | - | - | - | C |
| Mobile Development | C | R | C | - | A | I | - | C |
| Testing |  |  |  |  |  |  |  |  |
| Unit Testing | C | R | - | A | A | I | - | - |
| Integration Testing | C | R | - | C | C | A | C | - |
| UAT | C | I | R/A | I | I | C | - | C |
| Performance Testing | C | C | - | C | C | R/A | C | - |
| Deployment |  |  |  |  |  |  |  |  |
| CI/CD Setup | C | C | - | I | I | I | R/A | - |
| Deployment to Staging | C | C | - | C | C | C | R/A | C |
| Deployment to Production | C | C | - | C | C | C | R/A | C |
| Komunikasi |  |  |  |  |  |  |  |  |
| Stakeholder Communication | R/A | C | C | I | I | I | I | C |
| Progress Reporting | R/A | C | C | I | I | I | I | C |
| Documentation | C | C | R/A | C | C | C | C | C |
| Penutupan |  |  |  |  |  |  |  |  |
| Project Closure | R/A | C | C | I | I | I | I | C |
| Post Implementation Review | R/A | C | C | I | I | I | I | C |

Keterangan:

- R = Responsible (Pelaksana utama)

- A = Accountable (Penanggung jawab akhir)

- C = Consulted (Dikonsultasikan)

- I = Informed (Diberi informasi)

### 1.6. Metodologi Proyek

#### 1.6.1. Metodologi Pengembangan

Proyek P-FNE-04 menggunakan Agile Scrum sebagai metodologi pengembangan.

Alasan Pemilihan Scrum:

- Iteratif: Memungkinkan pengiriman fitur secara bertahap untuk umpan balik awal

- Adaptif: Dapat merespons perubahan kebutuhan dengan cepat

- Kolaboratif: Melibatkan stakeholder secara aktif dalam pengembangan

- Transparan: Visibilitas penuh terhadap progress melalui sprint review

- Risiko Minimal: Risiko dapat diidentifikasi dan dimitigasi lebih awal

#### 1.6.2. Struktur Sprint

| Aspek | Keterangan |
| --- | --- |
| Sprint Duration | 2 minggu (10 hari kerja) |
| Total Sprints | 12 sprint (6 bulan) |
| Sprint Start | Hari Kamis |
| Sprint End | Hari Rabu (2 minggu kemudian) |

Ceremony Schedule:

| Ceremony | Waktu | Durasi | Peserta |
| --- | --- | --- | --- |
| Sprint Planning | Hari Kamis (hari pertama sprint) | 2-3 jam | Tim + PM + BA |
| Daily Standup | Setiap hari 09:00 WIB | 15 menit | Tim |
| Sprint Review | Hari Rabu (hari terakhir sprint) | 1-2 jam | Tim + Stakeholder |
| Sprint Retrospective | Hari Rabu (setelah review) | 1 jam | Tim |
| Backlog Refinement | Hari Senin (minggu ke-2 sprint) | 1 jam | PM + BA + Tech Lead |

#### 1.6.3. Estimation Method

- Unit: Story Points (Fibonacci: 1, 2, 3, 5, 8, 13, 21)

- Method: Planning Poker

- Baseline: 1 Story Point ≈ 4 jam work (1 SP per 1 developer day)

- Velocity Target: 35-45 SP per sprint (dari 12 developer tim)

#### 1.6.4. Definition of Ready (DoR)

Sebuah user story dianggap Siap untuk dimasukkan ke sprint jika:

- Memiliki acceptance criteria yang jelas dan terdefinisi

- Memiliki design/UX yang sudah disetujui

- Memiliki estimasi story points

- Dependencies sudah teridentifikasi

- Tidak ada blocker yang diketahui

#### 1.6.5. Definition of Done (DoD)

Sebuah user story dianggap Selesai jika:

- Kode sudah dikembangkan dan di-commit

- Unit test sudah dibuat dan passing (>80% coverage)

- Integration test sudah dibuat dan passing

- Code review sudah dilakukan dan disetujui

- QA testing sudah dilakukan dan lulus

- Documentation sudah diperbarui

- Deployed ke staging environment

- Demonstrated dalam sprint review

### 1.7. Tools dan Teknologi

#### 1.7.1. Development Tools

| Kategori | Tool | Fungsi |
| --- | --- | --- |
| Project Management | Jira | Task tracking, sprint management, backlog |
| Documentation | Confluence | Dokumentasi, meeting notes, knowledge base |
| Communication | Microsoft Teams | Daily communication, video call |
| Design | Figma | UI/UX design, prototyping |
| Version Control | GitLab / GitHub | Code repository, CI/CD |
| Code Review | GitLab Merge Requests | Code review process |
| Testing | JUnit, Jest, Selenium | Unit and integration testing |
| Performance Testing | k6, JMeter | Load and performance testing |
| API Documentation | Swagger / OpenAPI | API documentation |

#### 1.7.2. Technology Stack

| Lapisan | Teknologi | Versi |
| --- | --- | --- |
| Frontend - Web | React.js / Next.js (TypeScript) | 18.x |
| Frontend - Mobile | Flutter | 3.x |
| Frontend - Dashboard | React.js (D3.js, Chart.js) | 18.x |
| Backend | Spring Boot / Node.js (NestJS) | 3.x / 10.x |
| API Gateway | Kong / Traefik | Latest |
| Message Broker | Apache Kafka | 3.x |
| Database - Relational | PostgreSQL | 15.x |
| Database - Time-Series | TimescaleDB (extension PostgreSQL) | 2.x |
| Database - Graph | Neo4j | 5.x |
| Cache | Redis | 7.x |
| Container | Docker | 24.x |
| Orchestration | Kubernetes | 1.28 |
| CI/CD | GitLab CI / GitHub Actions | Latest |
| Monitoring | Prometheus + Grafana | Latest |
| Logging | ELK Stack (Elasticsearch, Logstash, Kibana) | 8.x |
| Tracing | Jaeger / Zipkin | Latest |
| Security | Keycloak, HashiCorp Vault | Latest |

#### 1.7.3. Environment Setup

| Environment | Fungsi | URL |
| --- | --- | --- |
| Development | Pengembangan lokal developer | localhost |
| Staging | Testing dan UAT | staging.fne.com |
| Production | Live production | prod.fne.com |
| DR (Disaster Recovery) | Backup dan recovery | dr.fne.com |

### 1.8. Deliverables Utama

| No | Deliverable | Deskripsi | Milestone |
| --- | --- | --- | --- |
| 1 | Project Management Plan | Dokumen rencana manajemen proyek lengkap | M1 |
| 2 | System Architecture Document | Dokumen arsitektur sistem | M1 |
| 3 | Database Design Document | Dokumen desain database | M1 |
| 4 | API Specification | Spesifikasi API (OpenAPI) | M1-M2 |
| 5 | Production Planning Module | Modul perencanaan produksi | M2 |
| 6 | BOM Management Module | Modul manajemen BOM | M2 |
| 7 | Production Execution Module | Modul eksekusi produksi | M3 |
| 8 | Production Costing Module | Modul perhitungan biaya | M4 |
| 9 | Asset & Maintenance Module | Modul aset dan maintenance | M4 |
| 10 | Facility Management Module | Modul manajemen facility | M2 |
| 11 | Web Portal | Frontend web untuk admin/manager | M5 |
| 12 | Mobile App | Mobile app untuk operator | M5 |
| 13 | Executive Dashboard | Dashboard untuk direksi | M5 |
| 14 | Integration Complete | Semua integrasi selesai | M5 |
| 15 | UAT Sign-off | UAT disetujui oleh user | M6 |
| 16 | User Manual | Manual pengguna | M6 |
| 17 | Technical Documentation | Dokumentasi teknis lengkap | M6 |
| 18 | Production Deployment | Deploy ke production | M7 |
| 19 | Project Closure Report | Laporan penutupan proyek | M8 |

### 1.9. Milestones

| ID | Milestone | Tanggal | Deliverable | Kriteria Sukses |
| --- | --- | --- | --- | --- |
| M1 | Project Kickoff | 1 Okt 2026 | Project Charter, PMP, Architecture Doc | PMP disetujui sponsor |
| M2 | Planning & BOM Complete | 28 Okt 2026 | Production Plan & BOM Module | Semua fitur core selesai |
| M3 | Execution Module Complete | 23 Des 2026 | Production Order & Progress Module | Mobile app functional |
| M4 | Costing & Asset Complete | 3 Feb 2027 | Costing & Asset Module | Semua fitur costing selesai |
| M5 | Integration Complete | 17 Feb 2027 | All Integrations Done | Semua integrasi berhasil |
| M6 | UAT Complete | 3 Mar 2027 | UAT Sign-off | UAT 100% passed |
| M7 | Deployment & Go-Live | 17 Mar 2027 | Production Ready | System live di production |
| M8 | Project Closure | 31 Mar 2027 | Final Report | Penutupan proyek |

### 1.10. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor (CEO) |  |  |  |

# BAB 2: MANAJEMEN INTEGRASI PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 2.1. Pendahuluan

Manajemen integrasi proyek adalah proses yang memastikan seluruh elemen proyek terkoordinasi dengan baik dan bekerja secara sinergis. Area ini mencakup pengembangan project charter, penyusunan rencana manajemen proyek terintegrasi, direktif dan otorisasi kerja, pengelolaan perubahan, dan penutupan proyek. Manajemen integrasi berfungsi sebagai "payung" yang menyatukan semua area manajemen proyek lainnya.

Dalam konteks P-FNE-04, manajemen integrasi sangat kritis karena proyek ini harus terintegrasi dengan 7 proyek turunan lainnya dalam ekosistem Super ERP FNE. Setiap keputusan yang diambil dalam proyek ini memiliki dampak terhadap proyek lain dan sebaliknya.

### 2.2. Project Charter

#### 2.2.1. Definisi dan Tujuan

Project Charter adalah dokumen resmi yang mengotorisasi proyek untuk dimulai dan memberikan wewenang kepada Project Manager untuk menggunakan sumber daya organisasi dalam aktivitas proyek. Dokumen ini menjadi "kontrak" antara sponsor dan Project Manager.

#### 2.2.2. Project Charter P-FNE-04

PROJECT CHARTER
PROYEK P-FNE-04: PRODUCTION & MANUFACTURING
SUPER ERP FARM NATION ENTERPRISE

| Aspek | Keterangan |
| --- | --- |
| Project Title | P-FNE-04: Production & Manufacturing Module |
| Project Sponsor | [Nama Sponsor] - CEO Farm Nation Enterprise |
| Project Manager | [Nama Project Manager] |
| Date of Issue | 1 Oktober 2026 |
| Project Duration | 6 Bulan (Oktober 2026 - Maret 2027) |
| Project Budget | Rp 3.356.000.000 - Rp 5.500.000.000 |

A. Project Purpose / Business Case

Farm Nation Enterprise (FNE) saat ini mengelola proses produksi secara manual dan terpisah-pisah, menyebabkan:

- Inefisiensi Perencanaan: Perencanaan produksi dilakukan secara manual menggunakan spreadsheet, menyebabkan kesalahan perhitungan dan keterlambatan

- Biaya Produksi Tidak Akurat: Tidak adanya sistem yang menghitung biaya produksi secara real-time

- Visibilitas Rendah: Manajemen tidak memiliki visibilitas real-time terhadap proses produksi

- Downtime Tinggi: Manajemen aset dan maintenance tidak terstruktur

- Integrasi Minim: Data produksi tidak terintegrasi dengan inventory, sales, dan finance

Manfaat Proyek:

| Manfaat | Kuantitatif | Kualitatif |
| --- | --- | --- |
| Efisiensi Perencanaan | 40% waktu lebih cepat | Perencanaan lebih akurat |
| Pengurangan Biaya | 15% biaya produksi | Biaya terukur dan terkendali |
| Visibilitas Produksi | Real-time monitoring | Pengambilan keputusan lebih baik |
| Pengurangan Downtime | 20% downtime berkurang | Produksi lebih lancar |
| Integrasi Data | 100% data terintegrasi | Single source of truth |

B. Project Objectives and Success Criteria

| No | Objective | Success Criteria | Target |
| --- | --- | --- | --- |
| 1 | Merencanakan produksi secara efektif | Production plan tersedia sebelum periode produksi | 100% production plan di-approve tepat waktu |
| 2 | Mengelola BOM secara terstruktur | Semua produk memiliki BOM aktif | 100% produk memiliki BOM versi terbaru |
| 3 | Merekam progress produksi real-time | Operator mencatat progress via mobile | < 5 menit per operasi |
| 4 | Menghitung biaya produksi akurat | Biaya tersedia saat PO selesai | 100% PO memiliki biaya aktual |
| 5 | Mengelola aset dan maintenance | WO terlacak dan terealisasi | 100% WO terjadwal selesai |
| 6 | Integrasi dengan proyek lain | Semua integrasi berfungsi | 100% API integration testing passed |

C. High-Level Scope

In-Scope:

- Production Planning (Demand Forecasting, Production Plan, MRP, Capacity Planning, Scheduling)

- Bill of Materials Management (BOM, Versioning, Cost Rollup, Where-Used)

- Production Execution (Production Order, Progress Recording, Quality Inspection, Completion)

- Production Costing (Material/Labor/Machine/Overhead Cost, Variance Analysis)

- Asset & Maintenance Management (Asset Registration, Work Order, Downtime, OEE, Spare Part)

- Facility Management (Facility/Work Center Registration, Shift Management)

- Integrations (P-FNE-01, P-FNE-03, P-FNE-05, P-FNE-06, P-FNE-07, P-FNE-08)

Out-of-Scope:

- Predictive Maintenance tingkat lanjut (P-FNE-08)

- Digital Twin (P-FNE-08)

- Marketplace Eksternal (P-FNE-05)

- HR/Payroll Management (P-FNE-06)

- Integrasi dengan ERP eksternal

- Real-time IoT sensor tingkat lanjut

D. High-Level Timeline

| Phase | Duration | Start | End |
| --- | --- | --- | --- |
| Inisiasi & Setup | 2 minggu | 1 Okt 2026 | 14 Okt 2026 |
| Pengembangan Sprint 1-4 | 8 minggu | 1 Okt 2026 | 25 Nov 2026 |
| Pengembangan Sprint 5-8 | 8 minggu | 26 Nov 2026 | 20 Jan 2027 |
| Pengembangan Sprint 9-12 | 8 minggu | 21 Jan 2027 | 17 Mar 2027 |
| Deployment & Closure | 2 minggu | 18 Mar 2027 | 31 Mar 2027 |

Key Milestones:

- M1: Project Kickoff (1 Okt 2026)

- M2: Planning & BOM Complete (28 Okt 2026)

- M3: Execution Module Complete (23 Des 2026)

- M4: Costing & Asset Complete (3 Feb 2027)

- M5: Integration Complete (17 Feb 2027)

- M6: UAT Complete (3 Mar 2027)

- M7: Deployment & Go-Live (17 Mar 2027)

- M8: Project Closure (31 Mar 2027)

E. Key Stakeholders

| Stakeholder | Role | Involvement |
| --- | --- | --- |
| CEO / Sponsor | Sponsor | Approval, guidance, monthly review |
| Program Manager | Oversight | Weekly coordination |
| Project Manager | Management | Day-to-day management |
| Project Team | Execution | Development, testing, documentation |
| Manufacturing Director | End User | Requirements, UAT, training |
| Production Managers | End User | Requirements, UAT |
| Operators | End User | Requirements, UAT (Mobile) |
| Finance Director | End User | Costing requirements, UAT |
| P-FNE-03 Team | Dependent | Integration coordination |
| P-FNE-06 Team | Dependent | Costing integration |

F. Project Budget Summary

| Kategori | Biaya (Rp) |
| --- | --- |
| Sumber Daya Manusia | 2.136.000.000 |
| Infrastruktur & Software | 650.000.000 |
| Perangkat Keras & Lainnya | 570.000.000 |
| Total | 3.356.000.000 |

G. Project Assumptions & Constraints

Assumptions:

- Tim tersedia sesuai jadwal yang direncanakan

- Infrastruktur cloud tersedia tepat waktu

- Data master tersedia dari P-FNE-01

- User tersedia untuk UAT dan training

- API dari proyek lain tersedia sesuai jadwal

- Tidak ada perubahan regulasi signifikan selama proyek berjalan

Constraints:

- Waktu: 6 bulan

- Anggaran: Rp 3.356.000.000 - Rp 5.500.000.000

- Tim: 8-12 orang

- Teknologi: Menggunakan stack yang sudah ditentukan

- Integrasi: Harus terintegrasi dengan 7 proyek turunan

H. Project Risks

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Scope creep | High | Medium | Strict change control |
| Integration delay | High | Medium | Early integration, mock services |
| Key resource leaving | Medium | Low | Knowledge sharing, documentation |
| Performance issues | High | Medium | Early performance testing, optimization |
| User adoption | Medium | Medium | Early involvement, training |

I. Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor |  |  |  |
| Project Manager |  |  |  |
| Program Manager |  |  |  |

#### 2.2.3. Project Charter Approval Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                    PROJECT CHARTER APPROVAL PROCESS                     │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Project Manager menyusun Project Charter                           │

│         │                                                              │

│         ▼                                                              │

│  2. Review oleh Program Manager                                        │

│         │                                                              │

│         ▼                                                              │

│  3. Review oleh Sponsor (CEO)                                          │

│         │                                                              │

│         ▼                                                              │

│  4. Revisi (jika diperlukan)                                           │

│         │                                                              │

│         ▼                                                              │

│  5. Penandatanganan oleh Sponsor                                       │

│         │                                                              │

│         ▼                                                              │

│  6. Charter di-upload ke repository proyek                             │

│         │                                                              │

│         ▼                                                              │

│  7. Kick-off meeting                                                   │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 2.3. Rencana Manajemen Proyek Terintegrasi

#### 2.3.1. Definisi

Project Management Plan (PMP) adalah dokumen komprehensif yang mengintegrasikan seluruh rencana manajemen dari 10 area PMBOK. PMP ini merupakan dokumen living document yang dapat diperbarui sepanjang siklus proyek melalui proses change control.

#### 2.3.2. Komponen PMP

| No | Komponen | Status | Referensi |
| --- | --- | --- | --- |
| 1 | Project Charter | ✓ | Bab 2.2 |
| 2 | Scope Management Plan | ✓ | Bab 3 |
| 3 | Schedule Management Plan | ✓ | Bab 4 |
| 4 | Cost Management Plan | ✓ | Bab 5 |
| 5 | Quality Management Plan | ✓ | Bab 6 |
| 6 | Resource Management Plan | ✓ | Bab 7 |
| 7 | Communication Management Plan | ✓ | Bab 8 |
| 8 | Risk Management Plan | ✓ | Bab 9 |
| 9 | Procurement Management Plan | ✓ | Bab 10 |
| 10 | Stakeholder Management Plan | ✓ | Bab 11 |
| 11 | Configuration Management Plan | ✓ | Appendiks |
| 12 | Change Management Plan | ✓ | Bab 2.5 |

#### 2.3.3. PMP Maintenance

PMP Review Schedule:

| Aktivitas | Frekuensi | Owner |
| --- | --- | --- |
| PMP Review | Setiap Sprint | PM |
| PMP Update | Setelah perubahan signifikan | PM |
| PMP Approval | Setiap revisi major | Sponsor/Program Manager |

PMP Version Control:

| Versi | Tanggal | Perubahan | Approval |
| --- | --- | --- | --- |
| 0.1 | 20 Sep 2026 | Draft awal | - |
| 0.2 | 25 Sep 2026 | Setelah review internal | - |
| 1.0 | 30 Sep 2026 | Final disetujui | Sponsor |

### 2.4. Directives dan Work Authorization

#### 2.4.1. Work Authorization System

Sistem otorisasi kerja memastikan bahwa pekerjaan hanya dilakukan jika telah diotorisasi oleh pihak yang berwenang.

Tingkat Otorisasi:

| Level | Tingkat | Deskripsi | Otorisasi Oleh |
| --- | --- | --- | --- |
| 1 | Project Charter | Otorisasi proyek untuk dimulai | Sponsor |
| 2 | Work Package | Otorisasi untuk mengerjakan work package | PM |
| 3 | Task/User Story | Otorisasi untuk mengerjakan task | PM/Tech Lead |
| 4 | Change Request | Otorisasi untuk perubahan scope | CCB |

#### 2.4.2. Work Authorization Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                       WORK AUTHORIZATION PROCESS                        │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  Sprint Planning Meeting                                                │

│         │                                                              │

│         ▼                                                              │

│  Select User Stories based on priority and capacity                    │

│         │                                                              │

│         ▼                                                              │

│  PM Approves Sprint Backlog                                            │

│         │                                                              │

│         ▼                                                              │

│  Create Tasks for each User Story                                      │

│         │                                                              │

│         ▼                                                              │

│  Developer picks task from Sprint Backlog                              │

│         │                                                              │

│         ▼                                                              │

│  Developer moves task to "In Progress"                                 │

│         │                                                              │

│         ▼                                                              │

│  Developer completes task and moves to "Ready for Review"              │

│         │                                                              │

│         ▼                                                              │

│  Tech Lead reviews code                                                │

│         │                                                              │

│         ▼                                                              │

│  QA tests and validates                                                │

│         │                                                              │

│         ▼                                                              │

│  Task moved to "Done"                                                  │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 2.4.3. Daily Work Authorization

Daily Standup Process:

- Setiap developer melaporkan progress dan blocker

- PM/Tech Lead memastikan prioritas tasks tetap sesuai

- Developer dapat mengambil task baru dari sprint backlog

Task Assignment Rules:

- Developer bertanggung jawab untuk mengambil task dari sprint backlog

- Tech Lead membantu dalam assignment jika diperlukan

- Setiap task harus memiliki assignee yang jelas

- Task yang membutuhkan review harus di-assign ke reviewer

### 2.5. Pengelolaan Perubahan (Change Management)

#### 2.5.1. Change Control Board (CCB)

CCB adalah tim yang bertanggung jawab untuk meninjau dan menyetujui atau menolak permintaan perubahan.

Komposisi CCB:

| Anggota | Peran | Keputusan |
| --- | --- | --- |
| Project Manager | Ketua | Mengkoordinasikan, memberikan rekomendasi |
| Tech Lead | Anggota | Menilai dampak teknis |
| Business Analyst | Anggota | Menilai dampak fungsional |
| QA Lead | Anggota | Menilai dampak kualitas |
| Program Manager | Anggota | Menilai dampak terhadap program |
| Sponsor | Anggota (untuk perubahan major) | Final decision |

Kewenangan CCB:

| Tingkat Dampak | Kewenangan |
| --- | --- |
| Minor (biaya < 50 juta) | PM + Tech Lead |
| Medium (biaya 50-200 juta) | CCB (tanpa Sponsor) |
| Major (biaya > 200 juta atau scope) | CCB + Sponsor |

#### 2.5.2. Change Request Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                         CHANGE REQUEST PROCESS                          │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  Step 1: Identifikasi Perubahan                                         │

│  - Siapa pun dapat mengidentifikasi perubahan (stakeholder, tim)       │

│         │                                                              │

│         ▼                                                              │

│  Step 2: Submit Change Request                                          │

│  - Mengisi form Change Request di Jira                                 │

│  - Melampirkan justifikasi dan dampak yang diharapkan                  │

│         │                                                              │

│         ▼                                                              │

│  Step 3: Analisis Dampak                                                │

│  - Tech Lead: Analisis dampak teknis                                   │

│  - BA: Analisis dampak fungsional                                      │

│  - PM: Analisis dampak jadwal, biaya, dan risiko                       │

│         │                                                              │

│         ▼                                                              │

│  Step 4: Review oleh CCB                                                │

│  - Meninjau request dan analisis dampak                               │

│  - Memutuskan Approved, Rejected, atau Deferred                        │

│         │                                                              │

│         ▼                                                              │

│  Step 5: Komunikasi Keputusan                                           │

│  - Menginformasikan hasil kepada pengaju                               │

│  - Jika Approved, update semua dokumen yang terkena dampak             │

│         │                                                              │

│         ▼                                                              │

│  Step 6: Implementasi                                                   │

│  - Menambahkan ke backlog untuk sprint berikutnya                     │

│  - Jika urgent, bisa dilakukan di sprint berjalan (dengan persetujuan) │

│         │                                                              │

│         ▼                                                              │

│  Step 7: Verifikasi                                                     │

│  - Memastikan perubahan berhasil diimplementasikan                     │

│  - Update dokumentasi                                                  │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 2.5.3. Change Request Form

text

FORM PERMINTAAN PERUBAHAN (CHANGE REQUEST)

==========================================

Nomor CR: CR-XXXX

Tanggal: XX/XX/XXXX

Diajukan Oleh: [Nama]

Peran: [Peran]

A. INFORMASI PERUBAHAN

-----------------------------------------------------------------------------

Jenis Perubahan: [ ] Scope  [ ] Schedule  [ ] Cost  [ ] Quality  [ ] Lainnya

Prioritas: [ ] Low  [ ] Medium  [ ] High  [ ] Critical

Deskripsi Perubahan:

-----------------------------------------------------------------------------

[Deskripsi detail perubahan yang diusulkan]

Justifikasi:

-----------------------------------------------------------------------------

[Alasan mengapa perubahan ini diperlukan]

B. ANALISIS DAMPAK

-----------------------------------------------------------------------------

Dampak terhadap Lingkup:

-----------------------------------------------------------------------------

[Dampak terhadap scope proyek]

Dampak terhadap Jadwal:

-----------------------------------------------------------------------------

[Dampak terhadap timeline proyek]

Dampak terhadap Biaya:

-----------------------------------------------------------------------------

[Dampak terhadap budget proyek]

Dampak terhadap Kualitas:

-----------------------------------------------------------------------------

[Dampak terhadap quality deliverables]

Dampak terhadap Risiko:

-----------------------------------------------------------------------------

[Risiko baru atau risiko yang berubah]

C. REKOMENDASI

-----------------------------------------------------------------------------

Rekomendasi: [ ] Approve  [ ] Reject  [ ] Defer

Catatan Rekomendasi:

-----------------------------------------------------------------------------

D. KEPUTUSAN

-----------------------------------------------------------------------------

Keputusan: [ ] Approved  [ ] Rejected  [ ] Deferred

Alasan Keputusan:

-----------------------------------------------------------------------------

Disetujui Oleh: ___________________  Tanggal: ____________

#### 2.5.4. Configuration Management

Configuration Items:

| No | Configuration Item | Lokasi | Version Control |
| --- | --- | --- | --- |
| 1 | Source Code | GitHub/GitLab | Git |
| 2 | Database Schema | Migration Files | Git |
| 3 | API Documentation | Swagger/OpenAPI | Git |
| 4 | Deployment Scripts | GitLab CI | Git |
| 5 | Infrastructure as Code | Terraform/Pulumi | Git |
| 6 | Requirements Documents | Confluence | Versioned |
| 7 | Design Documents | Confluence | Versioned |
| 8 | Test Cases | Jira/Test Management | Versioned |
| 9 | User Manual | Confluence/PDF | Versioned |

Versioning Convention:

| Jenis | Convention | Contoh |
| --- | --- | --- |
| Code | Semantic Versioning (MAJOR.MINOR.PATCH) | 1.2.3 |
| Documents | vX.Y (X=Major, Y=Minor) | v2.1 |
| Database | Migration script dengan timestamp | 20261001_initial_schema.sql |
| API | Semantic Versioning | /api/v1/production-orders |

### 2.6. Pengelolaan Baseline

#### 2.6.1. Scope Baseline

Scope baseline terdiri dari:

- Project Scope Statement (Bab 3.2)

- Work Breakdown Structure (WBS) (Bab 3.3)

- WBS Dictionary (Bab 3.4)

#### 2.6.2. Schedule Baseline

Schedule baseline terdiri dari:

- Project Schedule (Bab 4.3 - Gantt Chart)

- Milestone List (Bab 1.9)

- Sprint Plan (Bab 4.4)

#### 2.6.3. Cost Baseline

Cost baseline terdiri dari:

- Project Budget (Bab 5.2)

- Budget by Phase (Bab 5.3)

- Cost Breakdown Structure (CBS)

#### 2.6.4. Baseline Change Process

Setiap perubahan baseline harus melalui Change Request Process:

text

┌─────────────────────────────────────────────────────────────────────────┐

│                         BASELINE CHANGE PROCESS                         │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Identifikasi kebutuhan perubahan baseline                          │

│         │                                                              │

│         ▼                                                              │

│  2. Submit Change Request dengan justifikasi                           │

│         │                                                              │

│         ▼                                                              │

│  3. Analisis dampak terhadap scope, schedule, cost                     │

│         │                                                              │

│         ▼                                                              │

│  4. Review dan Approval oleh CCB                                       │

│         │                                                              │

│         ▼                                                              │

│  5. Update baseline dan semua dokumen terkait                          │

│         │                                                              │

│         ▼                                                              │

│  6. Komunikasikan perubahan ke semua stakeholder                       │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 2.7. Monitoring dan Pengendalian Proyek

#### 2.7.1. Performance Measurement

Metrik Kinerja Utama:

| Metrik | Deskripsi | Target | Frekuensi |
| --- | --- | --- | --- |
| SPI (Schedule Performance Index) | EV / PV | ≥ 0.9 | Sprint |
| CPI (Cost Performance Index) | EV / AC | ≥ 0.9 | Sprint |
| Velocity | Story points per sprint | 35-45 | Sprint |
| Burndown | Remaining effort | On track | Harian |
| Defect Density | Defects per 100 LOC | < 1 | Sprint |
| Code Coverage | % code covered by tests | > 80% | Sprint |

#### 2.7.2. Earned Value Management (EVM)

EVM Calculation:

| Parameter | Formula | Deskripsi |
| --- | --- | --- |
| PV (Planned Value) | Planned % × BAC | Nilai pekerjaan yang direncanakan |
| EV (Earned Value) | Completed % × BAC | Nilai pekerjaan yang selesai |
| AC (Actual Cost) | Actual cost incurred | Biaya aktual yang dikeluarkan |
| BAC (Budget at Completion) | Total budget | Total anggaran proyek |

Variance:

| Parameter | Formula | Interpretasi |
| --- | --- | --- |
| SV = EV - PV | EV - PV | > 0: Ahead of schedule; < 0: Behind schedule |
| CV = EV - AC | EV - AC | > 0: Under budget; < 0: Over budget |

Indices:

| Parameter | Formula | Interpretasi |
| --- | --- | --- |
| SPI = EV / PV | EV / PV | > 1: Ahead; < 1: Behind |
| CPI = EV / AC | EV / AC | > 1: Under; < 1: Over |

Forecast:

| Parameter | Formula | Deskripsi |
| --- | --- | --- |
| EAC = BAC / CPI | BAC / CPI | Estimated cost at completion |
| ETC = EAC - AC | EAC - AC | Estimated remaining cost |
| VAC = BAC - EAC | BAC - EAC | Variance at completion |

#### 2.7.3. Status Reporting

Jenis Laporan Status:

| Laporan | Audience | Frekuensi | Metode |
| --- | --- | --- | --- |
| Daily Standup Report | Tim | Harian | Lisan/Teams |
| Sprint Report | Tim + Stakeholder | 2 Minggu | Presentasi |
| Weekly Status Report | Program Manager | Mingguan | Email/Dokumen |
| Monthly Status Report | Sponsor + Stakeholder | Bulanan | Presentasi |
| EVM Report | PM + Program Manager | Sprint | Spreadsheet |

Weekly Status Report Template:

text

WEEKLY STATUS REPORT

PROJECT: P-FNE-04 Production & Manufacturing

PERIOD: [Tanggal - Tanggal]

SPRINT: [Sprint X]

1. SUMMARY

- Overall Status: [🟢 On Track / 🟡 At Risk / 🔴 Off Track]

- Sprint Progress: [X% complete]

- Remaining Story Points: [X]

2. KEY METRICS

- Planned vs Actual: [X%]

- Velocity: [X SP]

- SPI: [X.XX]

- CPI: [X.XX]

- Blockers: [X]

3. ACCOMPLISHMENTS

- [Item 1]

- [Item 2]

- [Item 3]

4. CHALLENGES / BLOCKERS

- [Item 1]: [Status] [Action]

- [Item 2]: [Status] [Action]

5. NEXT WEEK PLAN

- [Item 1]

- [Item 2]

- [Item 3]

6. RISKS & ISSUES

- [Risk 1]: [Status] [Mitigation]

- [Issue 1]: [Status] [Resolution]

Reported by: [Name]

Date: [Date]

### 2.8. Penutupan Proyek (Project Closure)

#### 2.8.1. Project Closure Criteria

Proyek dinyatakan SELESAI dan DITERIMA apabila seluruh kondisi berikut terpenuhi:

| No | Kriteria | Status |
| --- | --- | --- |
| 1 | Semua acceptance criteria terpenuhi | [ ] |
| 2 | Semua user stories selesai dan di-test | [ ] |
| 3 | Semua integration testing passed | [ ] |
| 4 | Performance testing passed (sesuai target) | [ ] |
| 5 | Security audit passed | [ ] |
| 6 | UAT sign-off dari user | [ ] |
| 7 | Dokumentasi teknis lengkap | [ ] |
| 8 | User manual dan training selesai | [ ] |
| 9 | Deployment ke production selesai | [ ] |
| 10 | Handover ke tim operasional selesai | [ ] |

#### 2.8.2. Project Closure Checklist

| No | Aktivitas | Owner | Status |
| --- | --- | --- | --- |
| A. Administrative Closure |  |  |  |
| 1 | Finalisasi semua dokumentasi proyek | PM | [ ] |
| 2 | Arsipkan semua dokumen proyek | PM | [ ] |
| 3 | Closure meeting dengan stakeholder | PM | [ ] |
| 4 | Final status report | PM | [ ] |
| 5 | Lessons learned document | PM | [ ] |
| B. Financial Closure |  |  |  |
| 6 | Final budget reconciliation | PM | [ ] |
| 7 | Close semua purchase order | PM | [ ] |
| 8 | Final invoice dan payment | PM | [ ] |
| C. Technical Closure |  |  |  |
| 9 | Code freeze dan tagging | Tech Lead | [ ] |
| 10 | Final security audit | DevOps | [ ] |
| 11 | Performance verification | QA | [ ] |
| 12 | Backup dan archive data | DevOps | [ ] |
| D. Handover |  |  |  |
| 13 | Handover ke support team | PM | [ ] |
| 14 | User training completion | BA | [ ] |
| 15 | User manual delivery | BA | [ ] |
| E. Team Closure |  |  |  |
| 16 | Team performance review | PM | [ ] |
| 17 | Release team members | PM | [ ] |

#### 2.8.3. Lessons Learned Process

Tujuan: Mengidentifikasi apa yang berjalan baik dan apa yang perlu ditingkatkan untuk proyek mendatang.

Proses:

text

┌─────────────────────────────────────────────────────────────────────────┐

│                       LESSONS LEARNED PROCESS                           │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Collect Feedback (Survei/Interview)                                │

│         │                                                              │

│         ▼                                                              │

│  2. Facilitate Lessons Learned Meeting (Retrospective)                 │

│         │                                                              │

│         ▼                                                              │

│  3. Categorize Lessons (Technical, Process, People)                    │

│         │                                                              │

│         ▼                                                              │

│  4. Document Lessons                                                   │

│         │                                                              │

│         ▼                                                              │

│  5. Share dengan Organization                                           │

│         │                                                              │

│         ▼                                                              │

│  6. Action Plan for Improvement                                        │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

Lessons Learned Template:

text

LESSONS LEARNED DOCUMENT

PROJECT: P-FNE-04 Production & Manufacturing

1. WHAT WENT WELL

-----------------------------------------------------------------------------

[Item 1]

[Item 2]

[Item 3]

2. WHAT DID NOT GO WELL

-----------------------------------------------------------------------------

[Item 1]

[Item 2]

[Item 3]

3. WHAT COULD BE IMPROVED

-----------------------------------------------------------------------------

[Item 1]

[Item 2]

[Item 3]

4. RECOMMENDATIONS FOR FUTURE PROJECTS

-----------------------------------------------------------------------------

[Item 1]

[Item 2]

[Item 3]

5. ACTION ITEMS

-----------------------------------------------------------------------------

| No | Action Item | Owner | Due Date | Status |

|----|-------------|-------|----------|--------|

| 1  |             |       |          |        |

| 2  |             |       |          |        |

### 2.9. Integrasi dengan Manajemen Lainnya

Manajemen integrasi proyek terhubung dengan seluruh area manajemen lainnya:

| Area Manajemen | Integrasi |
| --- | --- |
| Scope Management | Scope baseline dikelola melalui change control |
| Schedule Management | Schedule baseline dikelola melalui change control |
| Cost Management | Cost baseline dikelola melalui change control |
| Quality Management | Quality standards dimonitor dan dikontrol |
| Resource Management | Resource allocation sesuai kebutuhan proyek |
| Communication Management | Status reporting dan komunikasi perubahan |
| Risk Management | Risiko dimonitor dan dikelola |
| Procurement Management | Pengadaan sesuai kebutuhan proyek |
| Stakeholder Management | Stakeholder dilibatkan dalam change control |

### 2.10. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |

# BAB 3: MANAJEMEN LINGKUP PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 3.1. Pendahuluan

Manajemen lingkup proyek adalah proses yang memastikan bahwa proyek mencakup semua pekerjaan yang diperlukan—dan hanya pekerjaan yang diperlukan—untuk menyelesaikan proyek dengan sukses. Area ini mencakup perencanaan lingkup, pengumpulan kebutuhan, definisi lingkup, pembuatan Work Breakdown Structure (WBS), verifikasi lingkup, dan pengendalian lingkup.

Dalam konteks P-FNE-04, manajemen lingkup sangat kritis karena proyek ini memiliki banyak fitur dan integrasi dengan 7 proyek turunan lainnya. Lingkup yang tidak dikelola dengan baik dapat menyebabkan scope creep, keterlambatan, dan pembengkakan biaya.

### 3.2. Project Scope Statement

#### 3.2.1. Definisi

Project Scope Statement adalah deskripsi rinci tentang lingkup proyek, termasuk deliverables, fitur, batasan, dan asumsi. Dokumen ini menjadi acuan utama untuk menentukan apa yang termasuk dan tidak termasuk dalam proyek.

#### 3.2.2. Project Scope Statement P-FNE-04

PROJECT SCOPE STATEMENT
PROYEK P-FNE-04: PRODUCTION & MANUFACTURING
SUPER ERP FARM NATION ENTERPRISE

A. Product Scope Description

Modul Production & Manufacturing adalah sistem yang mengelola seluruh proses transformasi bahan baku pertanian menjadi produk bernilai tambah. Modul ini mencakup perencanaan produksi, manajemen Bill of Materials (BOM), eksekusi produksi, perhitungan biaya, manajemen aset dan maintenance, serta manajemen facility. Sistem ini terintegrasi dengan modul lain dalam ekosistem Super ERP FNE.

Karakteristik Produk:

| Karakteristik | Deskripsi |
| --- | --- |
| Platform | Web Portal (Admin/Manager), Mobile App (Operator), Executive Dashboard |
| Arsitektur | Microservices, API-first, Event-driven, Cloud-native |
| Database | PostgreSQL (relational), TimescaleDB (time-series), Neo4j (graph) |
| Integrasi | Terintegrasi dengan P-FNE-01, P-FNE-03, P-FNE-05, P-FNE-06, P-FNE-07, P-FNE-08 |
| Bahasa | Indonesia (UI), Inggris (kode) |
| Pengguna | Production Planner, Manager Produksi, Operator, Teknisi, Finance, Direksi |

B. Product Acceptance Criteria

Modul P-FNE-04 dinyatakan SELESAI dan DITERIMA apabila seluruh kondisi berikut terpenuhi:

1. Production Planning:

- □

Production plan dapat dibuat dan diapprove

- □

Material Requirement Planning (MRP) berfungsi

- □

Capacity planning berfungsi

- □

Production schedule dapat dihasilkan

2. BOM Management:

- □

BOM dapat dibuat dengan multi-level

- □

BOM versioning berfungsi

- □

BOM explosion berfungsi

- □

BOM cost rollup berfungsi

- □

Where-Used analysis berfungsi

3. Production Order Execution:

- □

Production Order dapat dibuat dari production plan

- □

Material issue berfungsi (integrasi dengan inventory)

- □

Production order status berfungsi

- □

Quality inspection pada production order berfungsi

- □

Production completion berfungsi (finished goods receipt ke inventory)

4. Production Costing:

- □

Material cost, labor cost, machine cost, dan overhead cost terhitung

- □

Total production cost dan unit cost terhitung

- □

Standard vs actual cost comparison berfungsi

5. Asset & Maintenance:

- □

Asset registration berfungsi

- □

Preventive maintenance schedule berfungsi

- □

Maintenance work order berfungsi

- □

Maintenance history tersedia

- □

Spare part inventory berfungsi

- □

Downtime recording berfungsi

- □

OEE calculation berfungsi

6. Integration:

- □

Event ProductionCompleted terpublikasi dan diterima oleh inventory

- □

Event MaterialIssued terpublikasi untuk inventory

- □

Integrasi dengan P-FNE-03 (material availability check) berfungsi

- □

Integrasi dengan P-FNE-06 (production cost to finance) berfungsi

- □

Integrasi dengan P-FNE-07 (data to intelligence) berfungsi

7. Performance:

- □

Production order query dalam ≤ 2 detik

- □

MRP computation untuk 100 produk dalam ≤ 10 detik

- □

BOM explosion dalam ≤ 5 detik

8. Security:

- □

User hanya dapat mengakses production data sesuai otorisasi

- □

Audit trail untuk semua transaksi produksi

9. Mobile:

- □

Operator dapat mencatat production progress melalui mobile app

- □

Offline support untuk operator lapangan

C. Deliverables

| No | Deliverable | Deskripsi | Milestone |
| --- | --- | --- | --- |
| 1 | Project Management Plan | Dokumen rencana manajemen proyek lengkap | M1 |
| 2 | System Architecture Document | Dokumen arsitektur sistem | M1 |
| 3 | Database Design Document | Dokumen desain database | M1 |
| 4 | API Specification | Spesifikasi API (OpenAPI) | M1-M2 |
| 5 | Production Planning Module | Modul perencanaan produksi | M2 |
| 6 | BOM Management Module | Modul manajemen BOM | M2 |
| 7 | Production Execution Module | Modul eksekusi produksi | M3 |
| 8 | Production Costing Module | Modul perhitungan biaya | M4 |
| 9 | Asset & Maintenance Module | Modul aset dan maintenance | M4 |
| 10 | Facility Management Module | Modul manajemen facility | M2 |
| 11 | Web Portal | Frontend web untuk admin/manager | M5 |
| 12 | Mobile App | Mobile app untuk operator | M5 |
| 13 | Executive Dashboard | Dashboard untuk direksi | M5 |
| 14 | User Manual | Manual pengguna | M6 |
| 15 | Technical Documentation | Dokumentasi teknis lengkap | M6 |

D. Project Exclusions (Out of Scope)

| No | Item | Alasan |
| --- | --- | --- |
| 1 | Predictive Maintenance berbasis AI tingkat lanjut | Menjadi bagian dari P-FNE-08 (Advanced) |
| 2 | Digital Twin dari aset produksi | Menjadi bagian dari P-FNE-08 |
| 3 | Marketplace eksternal | Menjadi bagian dari P-FNE-05 |
| 4 | HR/Payroll Management | Menjadi bagian dari P-FNE-06 |
| 5 | Integrasi dengan ERP eksternal | Fokus pada integrasi internal FNE |
| 6 | Real-time IoT sensor integration tingkat lanjut | Basic IoT hanya, advanced di P-FNE-08 |
| 7 | Custom reporting tool | Menggunakan BI tool dari P-FNE-07 |
| 8 | Data migration dari sistem lama | Dilakukan oleh tim data migration terpisah |

E. Constraints

| No | Constraint | Deskripsi |
| --- | --- | --- |
| 1 | Waktu | Proyek harus selesai dalam 6 bulan (Oktober 2026 - Maret 2027) |
| 2 | Anggaran | Anggaran maksimal Rp 5.500.000.000 |
| 3 | Tim | Tim terbatas 8-12 orang |
| 4 | Teknologi | Menggunakan stack teknologi yang sudah ditentukan (Spring Boot, React, Flutter, PostgreSQL) |
| 5 | Integrasi | Harus terintegrasi dengan 7 proyek turunan lainnya |
| 6 | Keamanan | Harus memenuhi standar keamanan perusahaan |
| 7 | Kinerja | Harus memenuhi target performa (≤2 detik query, ≤10 detik MRP) |
| 8 | Mobile Support | Mobile app harus support offline |

F. Assumptions

| No | Asumsi | Deskripsi |
| --- | --- | --- |
| 1 | Ketersediaan Tim | Tim tersedia sesuai jadwal yang direncanakan |
| 2 | Infrastruktur | Infrastruktur cloud tersedia tepat waktu |
| 3 | Data Master | Data master (product, material, facility) tersedia dari P-FNE-01 |
| 4 | User Availability | User tersedia untuk UAT dan training |
| 5 | Integrasi | API dari proyek lain tersedia sesuai jadwal |
| 6 | Regulatory | Tidak ada perubahan regulasi signifikan selama proyek berjalan |
| 7 | Data Accuracy | Data yang dimasukkan user akurat |
| 8 | User Competency | User memiliki kompetensi dasar menggunakan aplikasi web dan mobile |

### 3.3. Work Breakdown Structure (WBS)

#### 3.3.1. Definisi

Work Breakdown Structure (WBS) adalah dekomposisi hierarkis dari total lingkup pekerjaan yang harus dilakukan oleh tim proyek untuk menciptakan deliverables proyek. WBS mengorganisir dan mendefinisikan total lingkup proyek.

#### 3.3.2. WBS P-FNE-04

text

┌─────────────────────────────────────────────────────────────────────────┐

│                P-FNE-04: PRODUCTION & MANUFACTURING                     │

│                     Total: 12 Sprints, 6 Bulan                          │

└─────────────────────────────────────────────────────────────────────────┘

│

┌───────────────────────────┼───────────────────────────────────┐

│                           │                                   │

▼                           ▼                                   ▼

┌───────────────────┐   ┌───────────────────┐   ┌───────────────────────────┐

│  1.0 PROJECT      │   │  2.0 BACKEND      │   │  3.0 FRONTEND              │

│  MANAGEMENT       │   │  DEVELOPMENT      │   │  DEVELOPMENT               │

│                   │   │                   │   │                            │

│  WBS 1.1 - 1.4   │   │  WBS 2.1 - 2.6   │   │  WBS 3.1 - 3.3             │

└───────────────────┘   └───────────────────┘   └───────────────────────────┘

│                           │                                   │

▼                           ▼                                   ▼

┌───────────────────┐   ┌───────────────────┐   ┌───────────────────────────┐

│  4.0 TESTING &    │   │  5.0 INTEGRATION  │   │  6.0 DEPLOYMENT &         │

│  QUALITY          │   │                   │   │  CLOSURE                  │

│                   │   │                   │   │                           │

│  WBS 4.1 - 4.4   │   │  WBS 5.1 - 5.5   │   │  WBS 6.1 - 6.4             │

└───────────────────┘   └───────────────────┘   └───────────────────────────┘

#### 3.3.3. Detailed WBS

text

1.0 PROJECT MANAGEMENT

│

├── 1.1 Project Initiation

│   ├── 1.1.1 Project Charter

│   ├── 1.1.2 Project Management Plan

│   └── 1.1.3 Kick-off Meeting

│

├── 1.2 Project Planning

│   ├── 1.2.1 Sprint Planning (x12)

│   ├── 1.2.2 Backlog Refinement

│   └── 1.2.3 Resource Planning

│

├── 1.3 Project Monitoring & Control

│   ├── 1.3.1 Daily Standup (x120)

│   ├── 1.3.2 Sprint Review (x12)

│   ├── 1.3.3 Sprint Retrospective (x12)

│   ├── 1.3.4 Status Reporting

│   ├── 1.3.5 Risk Monitoring

│   └── 1.3.6 Change Management

│

└── 1.4 Project Closure

├── 1.4.1 Lessons Learned

├── 1.4.2 Final Report

└── 1.4.3 Handover

2.0 BACKEND DEVELOPMENT

│

├── 2.1 Foundation & Setup (Sprint 1)

│   ├── 2.1.1 Project Setup & Configuration

│   ├── 2.1.2 Database Schema Design

│   ├── 2.1.3 API Gateway Setup

│   ├── 2.1.4 Kafka Setup

│   └── 2.1.5 IAM Integration

│

├── 2.2 Production Planning Domain (Sprint 1-2)

│   ├── 2.2.1 Production Plan CRUD

│   ├── 2.2.2 MRP Engine

│   ├── 2.2.3 Capacity Planning

│   ├── 2.2.4 Production Scheduling

│   └── 2.2.5 Production Plan Approval Flow

│

├── 2.3 BOM Management Domain (Sprint 1-2)

│   ├── 2.3.1 BOM CRUD

│   ├── 2.3.2 BOM Versioning

│   ├── 2.3.3 BOM Explosion

│   ├── 2.3.4 BOM Cost Rollup

│   ├── 2.3.5 Where-Used Analysis

│   └── 2.3.6 BOM Approval Flow

│

├── 2.4 Production Execution Domain (Sprint 2-4)

│   ├── 2.4.1 Production Order CRUD

│   ├── 2.4.2 Material Issue Integration

│   ├── 2.4.3 Progress Recording API

│   ├── 2.4.4 Quality Inspection API

│   ├── 2.4.5 Production Completion API

│   ├── 2.4.6 By-Product & Waste Recording

│   └── 2.4.7 Production Order Status Management

│

├── 2.5 Production Costing Domain (Sprint 3-4)

│   ├── 2.5.1 Cost Calculation Engine

│   ├── 2.5.2 Material/Labor/Machine Cost

│   ├── 2.5.3 Overhead Cost Allocation

│   ├── 2.5.4 Standard vs Actual Comparison

│   └── 2.5.5 Variance Analysis

│

├── 2.6 Asset & Maintenance Domain (Sprint 3-5)

│   ├── 2.6.1 Asset Registration

│   ├── 2.6.2 Maintenance Work Order CRUD

│   ├── 2.6.3 Maintenance Execution API

│   ├── 2.6.4 Downtime Recording API

│   ├── 2.6.5 OEE Calculation Engine

│   ├── 2.6.6 Spare Part Inventory API

│   └── 2.6.7 Asset Performance Metrics (MTBF/MTTR)

│

├── 2.7 Facility Management Domain (Sprint 1-2)

│   ├── 2.7.1 Facility Registration

│   ├── 2.7.2 Work Center Registration

│   ├── 2.7.3 Shift Management

│   └── 2.7.4 Operator Assignment

│

└── 2.8 Shared Services (Sprint 1-5)

├── 2.8.1 Audit Service Integration

├── 2.8.2 Notification Service Integration

├── 2.8.3 Workflow Service Integration

├── 2.8.4 Document Service Integration

└── 2.8.5 Scheduler Service Integration

3.0 FRONTEND DEVELOPMENT

│

├── 3.1 Web Portal (Sprint 1-5)

│   ├── 3.1.1 Production Planning Pages

│   │   ├── Production Plan List & Detail

│   │   ├── Production Plan Creation & Edit

│   │   ├── MRP Result View

│   │   └── Production Schedule View

│   ├── 3.1.2 BOM Management Pages

│   │   ├── BOM List & Detail

│   │   ├── BOM Creation & Edit

│   │   ├── BOM Version History

│   │   └── Where-Used Search

│   ├── 3.1.3 Production Execution Pages

│   │   ├── Production Order List & Detail

│   │   ├── Production Order Creation & Edit

│   │   ├── Production Order Release

│   │   ├── Quality Inspection Form

│   │   └── Production Order Completion

│   ├── 3.1.4 Production Costing Pages

│   │   ├── Cost View by PO/Product

│   │   └── Variance Analysis View

│   ├── 3.1.5 Asset & Maintenance Pages

│   │   ├── Asset List & Detail

│   │   ├── Asset Registration Form

│   │   ├── Maintenance Work Order List & Detail

│   │   ├── Maintenance WO Creation & Edit

│   │   ├── Downtime Recording Form

│   │   ├── OEE Dashboard

│   │   └── Spare Part Inventory Management

│   └── 3.1.6 Facility Management Pages

│       ├── Facility List & Detail

│       ├── Work Center List & Detail

│       └── Shift Management

│

├── 3.2 Mobile App (Sprint 1-5)

│   ├── 3.2.1 Operator Dashboard

│   ├── 3.2.2 Production Progress Recording

│   │   ├── Scan Barcode PO

│   │   ├── Record Output & Defect

│   │   ├── Record Material Consumption

│   │   └── Record Time & Operator

│   ├── 3.2.3 Quality Inspection (Mobile)

│   ├── 3.2.4 Maintenance Execution (Mobile)

│   ├── 3.2.5 Downtime Recording (Mobile)

│   ├── 3.2.6 Offline Mode Support

│   └── 3.2.7 Sync Status Management

│

└── 3.3 Executive Dashboard (Sprint 3-5)

├── 3.3.1 Production KPI Dashboard

│   ├── Production vs Plan

│   ├── Capacity Utilization

│   └── Production Progress

├── 3.3.2 OEE Dashboard

│   ├── OEE Overall

│   ├── Availability/Performance/Quality

│   └── Asset Comparison

├── 3.3.3 Cost Dashboard

│   ├── Production Cost Trend

│   └── Standard vs Actual Cost

└── 3.3.4 Maintenance Dashboard

├── Open Work Orders

├── Overdue Maintenance

└── Maintenance Cost vs Budget

4.0 TESTING & QUALITY

│

├── 4.1 Test Planning

│   ├── 4.1.1 Test Strategy Document

│   ├── 4.1.2 Test Case Design

│   └── 4.1.3 Test Data Preparation

│

├── 4.2 Unit Testing

│   ├── 4.2.1 Backend Unit Tests

│   └── 4.2.2 Frontend Unit Tests

│

├── 4.3 Integration Testing

│   ├── 4.3.1 API Integration Tests

│   ├── 4.3.2 Event-Driven Integration Tests

│   └── 4.3.3 Cross-Service Integration Tests

│

├── 4.4 Performance Testing

│   ├── 4.4.1 Load Testing

│   ├── 4.4.2 Stress Testing

│   └── 4.4.3 Scalability Testing

│

├── 4.5 Security Testing

│   ├── 4.5.1 Penetration Testing

│   └── 4.5.2 Security Audit

│

├── 4.6 UAT (User Acceptance Testing)

│   ├── 4.6.1 UAT Planning

│   ├── 4.6.2 UAT Execution

│   └── 4.6.3 UAT Sign-off

│

└── 4.7 Regression Testing

└── 4.7.1 Regression Test Suite

5.0 INTEGRATION

│

├── 5.1 P-FNE-01 Integration

│   ├── 5.1.1 IAM Integration (Auth)

│   ├── 5.1.2 Master Data Integration

│   └── 5.1.3 Audit Service Integration

│

├── 5.2 P-FNE-03 Integration

│   ├── 5.2.1 Material Availability Check

│   ├── 5.2.2 Material Issue API

│   ├── 5.2.3 Finished Goods Receipt API

│   └── 5.2.4 Event Listeners

│

├── 5.3 P-FNE-05 Integration

│   ├── 5.3.1 Demand Forecast API

│   └── 5.3.2 Finished Goods Availability API

│

├── 5.4 P-FNE-06 Integration

│   ├── 5.4.1 Production Cost Data API

│   └── 5.4.2 Event Listeners

│

├── 5.5 P-FNE-07 Integration

│   ├── 5.5.1 Production Data API

│   └── 5.5.2 AI/ML Model Integration

│

└── 5.6 P-FNE-08 Integration

├── 5.6.1 IoT Data API

└── 5.6.2 Asset Telemetry Integration

6.0 DEPLOYMENT & CLOSURE

│

├── 6.1 Environment Setup

│   ├── 6.1.1 Development Environment

│   ├── 6.1.2 Staging Environment

│   └── 6.1.3 Production Environment

│

├── 6.2 CI/CD Setup

│   ├── 6.2.1 CI Pipeline

│   ├── 6.2.2 CD Pipeline

│   └── 6.2.3 Automated Testing in Pipeline

│

├── 6.3 Deployment

│   ├── 6.3.1 Staging Deployment

│   ├── 6.3.2 UAT Environment

│   └── 6.3.3 Production Deployment

│

├── 6.4 Monitoring & Support Setup

│   ├── 6.4.1 Monitoring (Prometheus/Grafana)

│   ├── 6.4.2 Logging (ELK Stack)

│   └── 6.4.3 Alerting Setup

│

├── 6.5 Documentation & Training

│   ├── 6.5.1 User Manual

│   ├── 6.5.2 Technical Documentation

│   ├── 6.5.3 API Documentation

│   └── 6.5.4 User Training

│

└── 6.6 Project Closure

├── 6.6.1 Final Report

├── 6.6.2 Lessons Learned

└── 6.6.3 Handover to Operations

### 3.4. WBS Dictionary

WBS Dictionary memberikan deskripsi detail untuk setiap elemen WBS, termasuk deskripsi, deliverable, dan acceptance criteria.

#### 3.4.1. WBS 2.2: Production Planning Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- |
| 2.2.1 | Production Plan CRUD | API untuk create, read, update, delete production plan | 100% CRUD operations functional, API documentation complete |
| 2.2.2 | MRP Engine | Perhitungan material requirement berdasarkan BOM | MRP selesai ≤10 detik untuk 100 produk, hasil akurat |
| 2.2.3 | Capacity Planning | Pengecekan kapasitas produksi | Capacity check accurate, integration with facility data |
| 2.2.4 | Production Scheduling | Penjadwalan production order | Schedule generation complete, Gantt view functional |
| 2.2.5 | Production Plan Approval Flow | Workflow approval production plan | Approval matrix implemented, status tracking complete |

#### 3.4.2. WBS 2.3: BOM Management Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- |
| 2.3.1 | BOM CRUD | API untuk create, read, update, delete BOM | 100% CRUD operations functional, multi-level support |
| 2.3.2 | BOM Versioning | Versioning untuk setiap perubahan BOM | Version tracking complete, history view functional |
| 2.3.3 | BOM Explosion | Perhitungan material requirement dari BOM | BOM explosion ≤5 detik, accurate calculation |
| 2.3.4 | BOM Cost Rollup | Perhitungan biaya standar produk | Cost calculation complete, integration with material price |
| 2.3.5 | Where-Used Analysis | Pencarian produk yang menggunakan material | Search functional, result accurate |
| 2.3.6 | BOM Approval Flow | Workflow approval BOM | Approval matrix implemented, status tracking complete |

#### 3.4.3. WBS 2.4: Production Execution Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- |
| 2.4.1 | Production Order CRUD | API untuk create, read, update, delete PO | 100% CRUD operations functional |
| 2.4.2 | Material Issue Integration | Integrasi untuk mengeluarkan material dari inventory | Integration with P-FNE-03 complete, accurate stock reduction |
| 2.4.3 | Progress Recording API | API untuk mencatat progress produksi | Real-time recording functional, offline support |
| 2.4.4 | Quality Inspection API | API untuk inspeksi kualitas | Inspection record complete, defect rate calculation |
| 2.4.5 | Production Completion API | API untuk menyelesaikan PO | PO completion complete, event published |
| 2.4.6 | By-Product & Waste Recording | API untuk mencatat by-product dan waste | Recording functional, accurate calculation |
| 2.4.7 | Production Order Status Management | Manajemen status PO | Status tracking complete, audit trail |

#### 3.4.4. WBS 2.5: Production Costing Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- |
| 2.5.1 | Cost Calculation Engine | Engine untuk menghitung biaya produksi | Calculation ≤5 detik, accurate |
| 2.5.2 | Material/Labor/Machine Cost | Perhitungan biaya per komponen | Accurate calculation, integration with master data |
| 2.5.3 | Overhead Cost Allocation | Alokasi overhead cost | Accurate allocation, configurable method |
| 2.5.4 | Standard vs Actual Comparison | Perbandingan standar dan aktual | Accurate comparison, visual report |
| 2.5.5 | Variance Analysis | Analisis variance biaya | Detailed variance breakdown, actionable insight |

#### 3.4.5. WBS 2.6: Asset & Maintenance Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- |
| 2.6.1 | Asset Registration | API untuk mendaftarkan aset | Asset registration complete, unique code generation |
| 2.6.2 | Maintenance Work Order CRUD | API untuk create, read, update, delete WO | 100% CRUD operations functional |
| 2.6.3 | Maintenance Execution API | API untuk pelaksanaan maintenance | Execution recording complete, spare part stock update |
| 2.6.4 | Downtime Recording API | API untuk mencatat downtime | Accurate recording, MTBF/MTTR update |
| 2.6.5 | OEE Calculation Engine | Engine untuk menghitung OEE | Accurate calculation, visualization |
| 2.6.6 | Spare Part Inventory API | API untuk mengelola spare part | Stock management complete, reorder alert |
| 2.6.7 | Asset Performance Metrics | API untuk MTBF/MTTR | Accurate calculation, historical tracking |

### 3.5. Scope Verification

#### 3.5.1. Proses Verifikasi Lingkup

Scope verification adalah proses formal untuk menerima deliverables proyek yang telah selesai.

Proses:

text

┌─────────────────────────────────────────────────────────────────────────┐

│                       SCOPE VERIFICATION PROCESS                        │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Sprint Review Meeting                                               │

│     - Tim mendemonstrasikan fitur yang selesai                         │

│     - Stakeholder memberikan feedback                                  │

│         │                                                              │

│         ▼                                                              │

│  2. UAT (User Acceptance Testing)                                      │

│     - User menguji fitur di staging environment                        │

│     - User mencatat issues/feedback                                    │

│         │                                                              │

│         ▼                                                              │

│  3. Acceptance Sign-off                                                │

│     - User menandatangani acceptance form                              │

│     - Fitur dianggap "Done"                                            │

│         │                                                              │

│         ▼                                                              │

│  4. Formal Acceptance                                                  │

│     - Project Manager mencatat acceptance                              │

│     - Update status di Jira                                            │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 3.5.2. Acceptance Sign-off Form

text

ACCEPTANCE SIGN-OFF FORM

========================

Project: P-FNE-04 Production & Manufacturing

Sprint: [Sprint X]

Feature/Module: [Feature Name]

A. FEATURE DETAILS

-----------------------------------------------------------------------------

Feature ID: [Feature ID]

Feature Name: [Feature Name]

Description: [Description]

B. ACCEPTANCE CRITERIA CHECKLIST

-----------------------------------------------------------------------------

| No | Criteria | Status | Notes |

|----|----------|--------|-------|

| 1  |          | [ ]    |       |

| 2  |          | [ ]    |       |

| 3  |          | [ ]    |       |

C. TESTING SUMMARY

-----------------------------------------------------------------------------

- Unit Tests: [X] passed, [X] failed

- Integration Tests: [X] passed, [X] failed

- UAT Tests: [X] passed, [X] failed

- Known Issues: [List]

D. SIGN-OFF

-----------------------------------------------------------------------------

User: [Name] - [Role] - [Signature] - [Date]

QA: [Name] - [Role] - [Signature] - [Date]

PM: [Name] - [Role] - [Signature] - [Date]

### 3.6. Scope Control

#### 3.6.1. Proses Pengendalian Lingkup

Scope control adalah proses memonitor status proyek dan produk untuk memastikan bahwa perubahan tidak menyebabkan scope creep.

Proses:

text

┌─────────────────────────────────────────────────────────────────────────┐

│                       SCOPE CONTROL PROCESS                             │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Monitor Progress                                                    │

│     - Tracking progress terhadap scope baseline                         │

│     - Identifikasi penyimpangan                                         │

│         │                                                              │

│         ▼                                                              │

│  2. Identify Scope Creep                                               │

│     - Identifikasi pekerjaan di luar scope                             │

│     - Identifikasi perubahan yang tidak terotorisasi                   │

│         │                                                              │

│         ▼                                                              │

│  3. Evaluate Change Request                                            │

│     - Setiap perubahan melalui Change Request Process                  │

│     - Analisis dampak terhadap scope, schedule, cost                   │

│         │                                                              │

│         ▼                                                              │

│  4. Approved Change Implementation                                     │

│     - Hanya perubahan yang disetujui yang diimplementasikan            │

│     - Update semua dokumen terkait                                     │

│         │                                                              │

│         ▼                                                              │

│  5. Update Baseline                                                    │

│     - Jika diperlukan, update scope baseline                           │

│     - Komunikasikan perubahan ke stakeholder                           │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 3.6.2. Scope Change Prevention Strategy

| Strategi | Deskripsi | Owner |
| --- | --- | --- |
| Detailed Requirements | Kebutuhan didokumentasikan secara detail sejak awal | BA |
| Stakeholder Involvement | Stakeholder dilibatkan sejak awal | PM |
| Sprint Reviews | Sprint review untuk validasi fitur | PM |
| Change Control | Setiap perubahan melalui change control | PM/CCB |
| Communication | Komunikasi yang jelas tentang scope | PM |
| Training | Training stakeholder tentang dampak scope creep | BA |

#### 3.6.3. Scope Creep Warning Signs

| Warning Sign | Action |
| --- | --- |
| Ada fitur baru yang tidak di backlog | Submit change request |
| User meminta perubahan di tengah sprint | Defer ke sprint berikutnya |
| Diskusi melebar ke fitur di luar scope | Re-fokus ke scope utama |
| Estimasi terus bertambah tanpa alasan jelas | Review scope dan perubahan |
| Stakholder mengubah prioritas terus-menerus | Komunikasikan dampak |

### 3.7. Scope Management Tools

| Tool | Fungsi |
| --- | --- |
| Jira | User story management, backlog, sprint tracking |
| Confluence | Requirements documentation, scope statement |
| Figma | UI/UX design, prototype |
| Lucidchart | WBS diagram, process flow |
| Google Sheets | Scope checklist, acceptance criteria |

### 3.8. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |

# BAB 4: MANAJEMEN PENJADWALAN PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 4.1. Pendahuluan

Manajemen penjadwalan proyek adalah proses yang memastikan bahwa proyek diselesaikan tepat waktu melalui perencanaan, estimasi, pengurutan aktivitas, pengembangan jadwal, dan pengendalian jadwal. Area ini mencakup identifikasi aktivitas, estimasi durasi, pengembangan jadwal, dan pengendalian jadwal.

Dalam konteks P-FNE-04, manajemen penjadwalan sangat kritis karena proyek ini memiliki durasi 6 bulan yang harus diselesaikan sesuai dengan milestone yang telah ditetapkan. Keterlambatan dalam satu modul dapat berdampak pada modul lainnya dan integrasi dengan proyek turunan.

### 4.2. Metodologi Penjadwalan

#### 4.2.1. Pendekatan Agile (Scrum)

Proyek P-FNE-04 menggunakan metodologi Agile Scrum dengan pendekatan iterative dan incremental.

| Aspek | Keterangan |
| --- | --- |
| Metodologi | Agile Scrum |
| Sprint Duration | 2 minggu (10 hari kerja) |
| Total Sprints | 12 sprint (6 bulan) |
| Sprint Start | Hari Kamis |
| Sprint End | Hari Rabu (2 minggu kemudian) |
| Estimation | Story Points (Fibonacci: 1,2,3,5,8,13,21) |
| Velocity Target | 35-45 SP per sprint |

#### 4.2.2. Sprint Ceremonies Schedule

| Ceremony | Waktu | Durasi | Peserta | Deskripsi |
| --- | --- | --- | --- | --- |
| Sprint Planning | Hari Kamis (hari pertama sprint) | 2-3 jam | Tim + PM + BA | Menentukan sprint backlog untuk sprint berikutnya |
| Daily Standup | Setiap hari 09:00 WIB | 15 menit | Tim | Report progress, blocker, plan hari ini |
| Sprint Review | Hari Rabu (hari terakhir sprint) | 1-2 jam | Tim + Stakeholder | Demo fitur yang selesai, dapat feedback |
| Sprint Retrospective | Hari Rabu (setelah review) | 1 jam | Tim | Evaluasi proses sprint, improvement plan |
| Backlog Refinement | Hari Senin (minggu ke-2 sprint) | 1 jam | PM + BA + Tech Lead | Grooming backlog untuk sprint berikutnya |

#### 4.2.3. Estimation Method

Planning Poker Process:

text

┌─────────────────────────────────────────────────────────────────────────┐

│                       PLANNING POKER PROCESS                            │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Product Owner menjelaskan user story                                │

│         │                                                              │

│         ▼                                                              │

│  2. Tim berdiskusi untuk klarifikasi                                    │

│         │                                                              │

│         ▼                                                              │

│  3. Setiap anggota memilih card secara rahasia                         │

│         │                                                              │

│         ▼                                                              │

│  4. Semua card dibuka secara bersamaan                                  │

│         │                                                              │

│         ▼                                                              │

│  5. Jika semua setuju → estimasi final                                 │

│         │                                                              │

│         ▼ (jika tidak setuju)                                          │

│  6. Diskusi alasan perbedaan estimasi                                  │

│         │                                                              │

│         ▼                                                              │

│  7. Ulangi proses sampai konsensus tercapai                            │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

Story Point Baseline:

| Story Points | Deskripsi | Estimasi Waktu |
| --- | --- | --- |
| 1 | Sangat sederhana, perubahan kecil | 0.5 - 1 jam |
| 2 | Sederhana, fitur minor | 2 - 4 jam |
| 3 | Sedang, fitur standar | 4 - 8 jam |
| 5 | Cukup kompleks, fitur utama | 1 - 2 hari |
| 8 | Kompleks, fitur besar | 2 - 3 hari |
| 13 | Sangat kompleks, membutuhkan breakdown | 3 - 5 hari |
| 21 | Terlalu besar, harus dipecah | > 5 hari |

### 4.3. Work Breakdown Structure with Estimasi

#### 4.3.1. Level 1 WBS with Estimasi

| WBS | Deskripsi | Story Points | Sprint | Tim |
| --- | --- | --- | --- | --- |
| 1.0 | Project Management | 120 | S1-S12 | PM |
| 2.0 | Backend Development | 520 | S1-S10 | BE Team |
| 3.0 | Frontend Development | 440 | S1-S10 | FE Team |
| 4.0 | Testing & Quality | 240 | S1-S12 | QA Team |
| 5.0 | Integration | 200 | S3-S10 | BE + FE |
| 6.0 | Deployment & Closure | 80 | S10-S12 | DevOps + All |
| Total |  | 1.600 | S1-S12 |  |

#### 4.3.2. Detailed WBS with Estimasi

1.0 PROJECT MANAGEMENT (120 SP)

| WBS | Deskripsi | SP | Sprint | Owner |
| --- | --- | --- | --- | --- |
| 1.1 | Project Initiation | 20 | S1 | PM |
| 1.2 | Project Planning | 20 | S1-S12 | PM |
| 1.3 | Project Monitoring & Control | 60 | S1-S12 | PM |
| 1.4 | Project Closure | 20 | S11-S12 | PM |

2.0 BACKEND DEVELOPMENT (520 SP)

| WBS | Deskripsi | SP | Sprint | Owner |
| --- | --- | --- | --- | --- |
| 2.1 | Foundation & Setup | 40 | S1 | BE Team |
| 2.2 | Production Planning Domain | 80 | S1-S2 | BE Team |
| 2.3 | BOM Management Domain | 80 | S1-S2 | BE Team |
| 2.4 | Production Execution Domain | 120 | S2-S4 | BE Team |
| 2.5 | Production Costing Domain | 60 | S3-S4 | BE Team |
| 2.6 | Asset & Maintenance Domain | 100 | S3-S5 | BE Team |
| 2.7 | Facility Management Domain | 40 | S1-S2 | BE Team |
| 2.8 | Shared Services | 40 | S1-S5 | BE Team |

3.0 FRONTEND DEVELOPMENT (440 SP)

| WBS | Deskripsi | SP | Sprint | Owner |
| --- | --- | --- | --- | --- |
| 3.1 | Web Portal | 200 | S1-S8 | FE Team |
| 3.2 | Mobile App | 160 | S2-S9 | FE Team |
| 3.3 | Executive Dashboard | 80 | S4-S9 | FE Team |

4.0 TESTING & QUALITY (240 SP)

| WBS | Deskripsi | SP | Sprint | Owner |
| --- | --- | --- | --- | --- |
| 4.1 | Test Planning | 20 | S1 | QA |
| 4.2 | Unit Testing | 40 | S1-S10 | Dev + QA |
| 4.3 | Integration Testing | 60 | S3-S10 | QA |
| 4.4 | Performance Testing | 40 | S5-S11 | QA |
| 4.5 | Security Testing | 20 | S9-S11 | QA + DevOps |
| 4.6 | UAT | 40 | S7-S11 | QA + BA |
| 4.7 | Regression Testing | 20 | S8-S12 | QA |

5.0 INTEGRATION (200 SP)

| WBS | Deskripsi | SP | Sprint | Owner |
| --- | --- | --- | --- | --- |
| 5.1 | P-FNE-01 Integration | 20 | S1-S2 | BE |
| 5.2 | P-FNE-03 Integration | 60 | S3-S5 | BE |
| 5.3 | P-FNE-05 Integration | 20 | S5-S7 | BE |
| 5.4 | P-FNE-06 Integration | 40 | S7-S9 | BE |
| 5.5 | P-FNE-07 Integration | 30 | S7-S9 | BE |
| 5.6 | P-FNE-08 Integration | 30 | S9-S10 | BE |

6.0 DEPLOYMENT & CLOSURE (80 SP)

| WBS | Deskripsi | SP | Sprint | Owner |
| --- | --- | --- | --- | --- |
| 6.1 | Environment Setup | 15 | S1 | DevOps |
| 6.2 | CI/CD Setup | 15 | S1-S2 | DevOps |
| 6.3 | Deployment | 15 | S10-S11 | DevOps |
| 6.4 | Monitoring & Support Setup | 15 | S5-S10 | DevOps |
| 6.5 | Documentation & Training | 20 | S10-S12 | BA + All |

### 4.4. Sprint Planning Detail

#### 4.4.1. Sprint 1 - S12 Detailed Plan

Sprint 1: Foundation & Setup (1-14 Oktober 2026)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.1.1 | Project Setup & Configuration | 8 | BE1, BE2 |
| 2.1.2 | Database Schema Design | 13 | BE1, BE2 |
| 2.1.3 | API Gateway Setup | 5 | BE1 |
| 2.1.4 | Kafka Setup | 5 | BE2 |
| 2.1.5 | IAM Integration | 8 | BE1 |
| 3.1.1 | Web Portal - Base Layout | 13 | FE1, FE2 |
| 4.1 | Test Planning | 8 | QA1 |
| 5.1 | P-FNE-01 Integration | 13 | BE1, BE2 |
| 6.1 | Environment Setup | 8 | DevOps |
| 6.2.1 | CI Pipeline | 5 | DevOps |
| Total |  | 86 |  |

Sprint 2: Planning & BOM (15-28 Oktober 2026)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.2.1 | Production Plan CRUD | 13 | BE1 |
| 2.2.3 | Capacity Planning | 8 | BE2 |
| 2.3.1 | BOM CRUD | 13 | BE1 |
| 2.3.2 | BOM Versioning | 8 | BE2 |
| 2.7.1 | Facility Registration | 5 | BE1 |
| 2.7.2 | Work Center Registration | 5 | BE2 |
| 3.1.1 | Web Portal - Planning Pages | 13 | FE1 |
| 3.1.2 | Web Portal - BOM Pages | 13 | FE2 |
| Total |  | 78 |  |

Sprint 3: MRP & Execution Start (29 Okt - 11 Nov 2026)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.2.2 | MRP Engine | 13 | BE1, BE2 |
| 2.3.3 | BOM Explosion | 8 | BE1 |
| 2.3.4 | BOM Cost Rollup | 8 | BE2 |
| 2.4.1 | Production Order CRUD | 13 | BE1 |
| 3.1.3 | Web Portal - PO Pages | 13 | FE1 |
| 3.2.1 | Mobile App - Operator Dashboard | 8 | FE2 |
| Total |  | 63 |  |

Sprint 4: Scheduling & Execution (12-25 Nov 2026)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.2.4 | Production Scheduling | 13 | BE1 |
| 2.4.2 | Material Issue Integration | 13 | BE1, BE2 |
| 2.4.4 | Quality Inspection API | 8 | BE2 |
| 3.1.3 | Web Portal - PO Release | 8 | FE1 |
| 3.2.2 | Mobile App - Progress Recording | 13 | FE2 |
| Total |  | 55 |  |

Sprint 5: Execution & Progress (26 Nov - 9 Des 2026)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.4.3 | Progress Recording API | 13 | BE1, BE2 |
| 2.4.6 | By-Product & Waste Recording | 8 | BE1 |
| 2.4.7 | PO Status Management | 5 | BE2 |
| 2.8.1 | Audit Service Integration | 8 | BE1 |
| 3.2.2 | Mobile App - Progress Recording (cont) | 13 | FE2 |
| 5.2.1 | P-FNE-03 - Material Availability | 13 | BE1, BE2 |
| Total |  | 60 |  |

Sprint 6: Completion & Costing (10-23 Des 2026)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.4.5 | Production Completion API | 13 | BE1 |
| 2.5.1 | Cost Calculation Engine | 13 | BE1, BE2 |
| 2.5.2 | Material/Labor/Machine Cost | 8 | BE2 |
| 3.1.3 | Web Portal - Completion | 8 | FE1 |
| 5.2.2 | P-FNE-03 - Material Issue | 13 | BE1, BE2 |
| Total |  | 55 |  |

Sprint 7: Asset & Maintenance (24 Des 2026 - 6 Jan 2027)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.6.1 | Asset Registration | 8 | BE1 |
| 2.6.2 | Maintenance Work Order CRUD | 13 | BE2 |
| 2.6.4 | Downtime Recording API | 8 | BE1 |
| 3.1.5 | Web Portal - Asset Pages | 13 | FE1 |
| 3.2.5 | Mobile App - Downtime Recording | 8 | FE2 |
| Total |  | 50 |  |

Sprint 8: Maintenance & OEE (7-20 Jan 2027)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.6.3 | Maintenance Execution API | 13 | BE1 |
| 2.6.5 | OEE Calculation Engine | 13 | BE2 |
| 2.6.6 | Spare Part Inventory API | 8 | BE1 |
| 3.1.5 | Web Portal - Maintenance Pages | 13 | FE1 |
| 3.3.2 | Executive Dashboard - OEE | 13 | FE2 |
| Total |  | 60 |  |

Sprint 9: Costing & Dashboard (21 Jan - 3 Feb 2027)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 2.5.3 | Overhead Cost Allocation | 8 | BE1 |
| 2.5.4 | Standard vs Actual Comparison | 13 | BE2 |
| 2.5.5 | Variance Analysis | 8 | BE1 |
| 3.1.4 | Web Portal - Cost Pages | 13 | FE1 |
| 3.3.1 | Executive Dashboard - KPI | 13 | FE2 |
| 5.4.1 | P-FNE-06 - Cost Data API | 13 | BE1, BE2 |
| Total |  | 68 |  |

Sprint 10: Integration & Finalization (4-17 Feb 2027)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 5.3.1 | P-FNE-05 - Demand Forecast API | 8 | BE1 |
| 5.5.1 | P-FNE-07 - Production Data API | 13 | BE2 |
| 5.6.1 | P-FNE-08 - IoT Data API | 8 | BE1 |
| 3.3.3 | Executive Dashboard - Cost | 8 | FE1 |
| 6.3.1 | Staging Deployment | 5 | DevOps |
| 6.5.1 | User Manual Draft | 5 | BA |
| Total |  | 47 |  |

Sprint 11: UAT & Bug Fixes (18 Feb - 3 Mar 2027)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 4.6 | UAT Execution | 13 | QA, BA |
| 4.4 | Performance Testing | 13 | QA |
| 4.5 | Security Testing | 8 | QA, DevOps |
| 6.3.2 | Production Deployment | 8 | DevOps |
| 6.5.2 | Technical Documentation | 8 | All |
| Bug Fixes | Issues from UAT | 13 | BE, FE |
| Total |  | 63 |  |

Sprint 12: Closure & Handover (4-17 Mar 2027)

| WBS | Deskripsi | SP | Owner |
| --- | --- | --- | --- |
| 1.4 | Project Closure | 8 | PM |
| 4.7 | Regression Testing | 8 | QA |
| 6.5.3 | User Training | 13 | BA |
| 6.6 | Final Report & Handover | 8 | PM + All |
| Total |  | 37 |  |

### 4.5. Milestones

#### 4.5.1. Milestone Schedule

| ID | Milestone | Tanggal | Sprint | Deliverable | Kriteria Sukses |
| --- | --- | --- | --- | --- | --- |
| M1 | Project Kickoff | 1 Okt 2026 | S1 | Project Charter, PMP, Architecture Doc | PMP disetujui sponsor |
| M2 | Planning & BOM Complete | 28 Okt 2026 | S2 | Production Plan & BOM Module | Semua fitur core selesai, API ready |
| M3 | Execution Module Complete | 23 Des 2026 | S6 | Production Order & Progress Module | Mobile app functional, PO complete |
| M4 | Costing & Asset Complete | 3 Feb 2027 | S9 | Costing & Asset Module | Semua fitur costing selesai |
| M5 | Integration Complete | 17 Feb 2027 | S10 | All Integrations Done | Semua integrasi berhasil |
| M6 | UAT Complete | 3 Mar 2027 | S11 | UAT Sign-off | UAT 100% passed |
| M7 | Deployment & Go-Live | 17 Mar 2027 | S12 | Production Ready | System live di production |
| M8 | Project Closure | 31 Mar 2027 | S12 | Final Report | Penutupan proyek resmi |

#### 4.5.2. Milestone Gantt Chart

text

MILESTONE                    | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 |

-----------------------------|----|----|----|----|----|----|----|----|----|-----|-----|-----|

M1: Project Kickoff          | ★  |    |    |    |    |    |    |    |    |     |     |     |

M2: Planning & BOM Complete  |    | ★  |    |    |    |    |    |    |    |     |     |     |

M3: Execution Module Complete|    |    |    |    |    | ★  |    |    |    |     |     |     |

M4: Costing & Asset Complete |    |    |    |    |    |    |    |    | ★  |     |     |     |

M5: Integration Complete     |    |    |    |    |    |    |    |    |    |  ★  |     |     |

M6: UAT Complete             |    |    |    |    |    |    |    |    |    |     |  ★  |     |

M7: Deployment & Go-Live     |    |    |    |    |    |    |    |    |    |     |     |  ★  |

M8: Project Closure          |    |    |    |    |    |    |    |    |    |     |     |  ★  |

### 4.6. Dependency Management

#### 4.6.1. Internal Dependencies

| Dependency | From | To | Impact |
| --- | --- | --- | --- |
| D1 | Database Schema | All Backend Modules | Blocked tanpa database schema |
| D2 | IAM Integration | All Features | Blocked tanpa auth |
| D3 | Master Data Integration | BOM, Production Order | Blocked tanpa product/material data |
| D4 | BOM Service | MRP Engine | MRP membutuhkan BOM |
| D5 | Production Plan | Production Order | PO dibuat dari production plan |
| D6 | BOM Service | Cost Calculation | Costing membutuhkan BOM data |

#### 4.6.2. External Dependencies

| Dependency | From | To | Timeline | Owner |
| --- | --- | --- | --- | --- |
| D7 | P-FNE-01 IAM | Auth Service | S1 | P-FNE-01 Team |
| D8 | P-FNE-01 Master Data | Product/Material Data | S1 | P-FNE-01 Team |
| D9 | P-FNE-03 Inventory | Material Availability | S3 | P-FNE-03 Team |
| D10 | P-FNE-03 Inventory | Material Issue/Receipt | S3 | P-FNE-03 Team |
| D11 | P-FNE-05 Sales | Demand Forecast | S5 | P-FNE-05 Team |
| D12 | P-FNE-06 Finance | Costing Integration | S7 | P-FNE-06 Team |

#### 4.6.3. Dependency Tracking

text

┌─────────────────────────────────────────────────────────────────────────┐

│                      DEPENDENCY TRACKING TABLE                          │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  Dependency ID: D9                                                     │

│  Description: P-FNE-03 Inventory Service API for Material Availability  │

│  From: P-FNE-04 (Production Execution)                                │

│  To: P-FNE-03 (Supply Chain)                                           │

│  Due Date: 11 November 2026 (Sprint 3)                                 │

│  Status: [🟡 In Progress]                                              │

│  Owner: P-FNE-03 Team                                                  │

│  Action: Weekly sync meeting                                           │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 4.7. Resource Capacity Planning

#### 4.7.1. Team Capacity per Sprint

| Sprint | BE Dev 1 | BE Dev 2 | BE Dev 3 | FE Dev 1 | FE Dev 2 | QA | DevOps | Total Capacity (SP) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S1 | 8 | 8 | - | 8 | 8 | 8 | 8 | 48 |
| S2 | 8 | 8 | - | 8 | 8 | 8 | 4 | 44 |
| S3 | 8 | 8 | - | 8 | 8 | 8 | 4 | 44 |
| S4 | 8 | 8 | - | 8 | 8 | 8 | 4 | 44 |
| S5 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 52 |
| S6 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 52 |
| S7 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 52 |
| S8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 52 |
| S9 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 52 |
| S10 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 52 |
| S11 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 52 |
| S12 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 26 |

Keterangan:

- 1 developer capacity = 1 SP per hari (dengan asumsi 80% produktif dari 8 jam kerja)

- 1 sprint (10 hari kerja) = 10 SP per developer

- Nilai di atas adalah SP capacity berdasarkan sprint yang direncanakan

#### 4.7.2. Sprint Velocity Tracking

| Sprint | Committed SP | Completed SP | Velocity | On Track? |
| --- | --- | --- | --- | --- |
| S1 | 86 | 80 | 80 | 🟡 (Adjusted) |
| S2 | 78 | 75 | 75 | 🟡 (Adjusted) |
| S3 | 63 | 60 | 60 | 🟡 (Adjusted) |
| S4 | 55 | 52 | 52 | 🟡 (Adjusted) |
| S5 | 60 | 55 | 55 | 🟡 (Adjusted) |
| S6 | 55 | 50 | 50 | 🟡 (Adjusted) |
| S7 | 50 | 48 | 48 | 🟡 (Adjusted) |
| S8 | 60 | 55 | 55 | 🟡 (Adjusted) |
| S9 | 68 | 60 | 60 | 🟡 (Adjusted) |
| S10 | 47 | 45 | 45 | 🟡 (Adjusted) |
| S11 | 63 | 55 | 55 | 🟡 (Adjusted) |
| S12 | 37 | 35 | 35 | 🟡 (Adjusted) |

### 4.8. Schedule Control

#### 4.8.1. Monitoring Process

| Aktivitas | Frekuensi | Owner | Output |
| --- | --- | --- | --- |
| Burndown Chart Update | Harian | PM | Burndown Chart |
| Sprint Progress | 2 minggu | PM | Sprint Report |
| Velocity Tracking | 2 minggu | PM | Velocity Report |
| Milestone Status | Bulanan | PM | Status Report |
| Schedule Variance | 2 minggu | PM | EVM Report |
| Risk Impact Review | 2 minggu | PM | Risk Register |

#### 4.8.2. Schedule Variance Management

EVM (Earned Value Management) Metrics:

| Parameter | Formula | Deskripsi |
| --- | --- | --- |
| PV (Planned Value) | Planned % × BAC | Nilai pekerjaan yang direncanakan |
| EV (Earned Value) | Completed % × BAC | Nilai pekerjaan yang selesai |
| AC (Actual Cost) | Actual cost incurred | Biaya aktual yang dikeluarkan |
| SV (Schedule Variance) | EV - PV | >0 = Ahead, <0 = Behind |
| SPI (Schedule Performance Index) | EV / PV | >1 = Ahead, <1 = Behind |

Tindakan Korektif:

| Kondisi | Tindakan |
| --- | --- |
| SPI < 0.8 (Behind schedule) | • Tambah resource (jika memungkinkan) • Scope reduction (prioritas) • Crashing / fast-tracking |
| SPI 0.8 - 0.9 (Slightly behind) | • Review dan perbaikan proses • Overtime (jika diperlukan) • Re-prioritasi backlog |
| SPI > 1.0 (Ahead of schedule) | • Ambil story dari backlog berikutnya • Fokus pada quality improvement |

#### 4.8.3. Schedule Baseline Change Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                  SCHEDULE BASELINE CHANGE PROCESS                       │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Identifikasi kebutuhan perubahan jadwal                            │

│         │                                                              │

│         ▼                                                              │

│  2. Submit Change Request dengan justifikasi                           │

│         │                                                              │

│         ▼                                                              │

│  3. Analisis dampak terhadap:                                          │

│     - Scope                                                           │

│     - Cost                                                            │

│     - Quality                                                         │

│     - Other dependencies                                              │

│         │                                                              │

│         ▼                                                              │

│  4. Review dan Approval oleh CCB                                       │

│         │                                                              │

│         ▼                                                              │

│  5. Update baseline dan semua dokumen terkait                          │

│         │                                                              │

│         ▼                                                              │

│  6. Komunikasikan perubahan ke semua stakeholder                       │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 4.9. Schedule Communication

| Komunikasi | Audience | Metode | Frekuensi |
| --- | --- | --- | --- |
| Daily Standup Report | Tim | Lisan/Teams | Harian |
| Sprint Report | Tim + Stakeholder | Presentasi | 2 minggu |
| Weekly Status | Program Manager | Email/Dokumen | Mingguan |
| Milestone Report | Sponsor + Stakeholder | Presentasi | Bulanan |
| EVM Report | PM + Program Manager | Spreadsheet | Sprint |

### 4.10. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |

# BAB 5: MANAJEMEN BIAYA PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 5.1. Pendahuluan

Manajemen biaya proyek adalah proses yang memastikan bahwa proyek diselesaikan sesuai dengan anggaran yang telah disetujui melalui perencanaan, estimasi, budgeting, dan pengendalian biaya. Area ini mencakup estimasi biaya, penentuan anggaran, dan pengendalian biaya.

Dalam konteks P-FNE-04, manajemen biaya sangat kritis karena proyek ini memiliki anggaran yang terbatas dan harus dialokasikan secara efisien untuk mencapai deliverables yang ditargetkan. Proyek ini menggunakan Activity Based Costing (ABC) untuk menghitung biaya secara akurat berdasarkan aktivitas yang dilakukan, serta memperhatikan tarif personil sesuai dengan standar Inkindo 2026.

### 5.2. Metodologi Estimasi Biaya

#### 5.2.1. Activity Based Costing (ABC)

Proyek P-FNE-04 menggunakan metodologi Activity Based Costing (ABC) untuk estimasi biaya. ABC mengalokasikan biaya berdasarkan aktivitas yang dilakukan, bukan hanya berdasarkan sumber daya yang digunakan.

Prinsip ABC pada Proyek P-FNE-04:

text

┌─────────────────────────────────────────────────────────────────────────┐

│                    ACTIVITY BASED COSTING (ABC)                         │

│                      PROYEK P-FNE-04                                   │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  RESOURCES ──────────► ACTIVITIES ──────────► COST OBJECTS             │

│                                                                         │

│  • Personil          • Requirement Gathering  • Production Planning    │

│  • Infrastruktur     • System Design          • BOM Management         │

│  • Software          • Backend Development    • Production Execution   │

│  • Hardware          • Frontend Development   • Production Costing     │

│  • Perangkat Lain    • Testing & QA           • Asset & Maintenance    │

│                      • Integration            • Facility Management     │

│                      • Deployment             • Web Portal             │

│                      • Project Management     • Mobile App             │

│                      • Training               • Executive Dashboard    │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 5.2.2. Tarif Personil Inkindo 2026

Berdasarkan standar Inkindo (Ikatan Nasional Konsultan Indonesia) 2026, berikut adalah tarif personil yang digunakan dalam estimasi biaya proyek:

Tabel Tarif Personil (Inkindo 2026):

| No | Jabatan / Kualifikasi | Tingkat | Tarif per Jam (Rp) | Tarif per Hari (Rp) | Tarif per Bulan (Rp) |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Manager / Senior Consultant | Senior | 350.000 | 2.800.000 | 56.000.000 |
| 2 | Tech Lead / Senior Software Architect | Senior | 325.000 | 2.600.000 | 52.000.000 |
| 3 | Business Analyst / System Analyst | Senior | 275.000 | 2.200.000 | 44.000.000 |
| 4 | Senior Backend Developer | Senior | 250.000 | 2.000.000 | 40.000.000 |
| 5 | Backend Developer | Middle | 200.000 | 1.600.000 | 32.000.000 |
| 6 | Senior Frontend Developer | Senior | 250.000 | 2.000.000 | 40.000.000 |
| 7 | Frontend Developer | Middle | 200.000 | 1.600.000 | 32.000.000 |
| 8 | Senior QA Engineer | Senior | 200.000 | 1.600.000 | 32.000.000 |
| 9 | QA Engineer | Middle | 150.000 | 1.200.000 | 24.000.000 |
| 10 | DevOps Engineer | Middle | 225.000 | 1.800.000 | 36.000.000 |
| 11 | Manufacturing Specialist | Senior | 275.000 | 2.200.000 | 44.000.000 |
| 12 | Junior Developer / Trainee | Junior | 125.000 | 1.000.000 | 20.000.000 |

Catatan:

- Tarif berdasarkan standar Inkindo 2026 untuk proyek IT/Software Development

- Tarif per hari = Tarif per jam × 8 jam (1 hari kerja)

- Tarif per bulan = Tarif per hari × 20 hari kerja (1 bulan)

- Sudah termasuk overhead dan keuntungan konsultan

### 5.3. Estimasi Biaya dengan ABC

#### 5.3.1. Identifikasi Aktivitas dan Cost Driver

Aktivitas Utama Proyek:

| No | Aktivitas | Cost Driver | Unit |
| --- | --- | --- | --- |
| A1 | Project Initiation | Jumlah dokumen | Dokumen |
| A2 | Requirement Gathering | Jumlah sesi | Sesi |
| A3 | System Design | Jumlah modul | Modul |
| A4 | Database Design | Jumlah tabel | Tabel |
| A5 | Backend Development | Jumlah story points | SP |
| A6 | Frontend Development | Jumlah story points | SP |
| A7 | Mobile Development | Jumlah story points | SP |
| A8 | Dashboard Development | Jumlah widget | Widget |
| A9 | Testing & QA | Jumlah test cases | Kasus |
| A10 | Integration | Jumlah API endpoint | Endpoint |
| A11 | Deployment | Jumlah environment | Env |
| A12 | Project Management | Jumlah sprint | Sprint |
| A13 | Training & Documentation | Jumlah sesi | Sesi |

#### 5.3.2. Activity Cost Rate Calculation

Perhitungan Tarif per Cost Driver:

| Aktivitas | Total Cost (Rp) | Cost Driver | Total Unit | Rate per Unit (Rp) |
| --- | --- | --- | --- | --- |
| A1: Project Initiation | 14.000.000 | Dokumen | 3 | 4.666.667 |
| A2: Requirement Gathering | 44.000.000 | Sesi | 10 | 4.400.000 |
| A3: System Design | 52.000.000 | Modul | 6 | 8.666.667 |
| A4: Database Design | 40.000.000 | Tabel | 24 | 1.666.667 |
| A5: Backend Development | 640.000.000 | SP | 520 | 1.230.769 |
| A6: Frontend Development | 320.000.000 | SP | 200 | 1.600.000 |
| A7: Mobile Development | 160.000.000 | SP | 160 | 1.000.000 |
| A8: Dashboard Development | 80.000.000 | Widget | 20 | 4.000.000 |
| A9: Testing & QA | 288.000.000 | Kasus | 500 | 576.000 |
| A10: Integration | 192.000.000 | Endpoint | 50 | 3.840.000 |
| A11: Deployment | 96.000.000 | Env | 3 | 32.000.000 |
| A12: Project Management | 240.000.000 | Sprint | 12 | 20.000.000 |
| A13: Training & Documentation | 120.000.000 | Sesi | 8 | 15.000.000 |

#### 5.3.3. Activity Based Cost Calculation

Perhitungan Biaya Berdasarkan Aktivitas:

| No | Aktivitas | Cost Driver | Unit | Rate (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| A. PROJECT INITIATION |  |  |  |  |  |
| A1.1 | Project Charter | Dokumen | 1 | 4.666.667 | 4.666.667 |
| A1.2 | PMP Document | Dokumen | 1 | 4.666.667 | 4.666.667 |
| A1.3 | Kick-off Meeting | Dokumen | 1 | 4.666.667 | 4.666.667 |
|  | Subtotal Project Initiation |  |  |  | 14.000.000 |
| B. REQUIREMENT GATHERING |  |  |  |  |  |
| A2.1 | User Interview | Sesi | 6 | 4.400.000 | 26.400.000 |
| A2.2 | Workshop | Sesi | 4 | 4.400.000 | 17.600.000 |
|  | Subtotal Requirement Gathering |  |  |  | 44.000.000 |
| C. SYSTEM DESIGN |  |  |  |  |  |
| A3.1 | Architecture Design | Modul | 1 | 8.666.667 | 8.666.667 |
| A3.2 | API Design | Modul | 6 | 8.666.667 | 52.000.000 |
| A3.3 | Security Design | Modul | 1 | 8.666.667 | 8.666.667 |
|  | Subtotal System Design |  |  |  | 69.333.334 |
| D. DATABASE DESIGN |  |  |  |  |  |
| A4.1 | ERD Creation | Tabel | 24 | 1.666.667 | 40.000.000 |
|  | Subtotal Database Design |  |  |  | 40.000.000 |
| E. BACKEND DEVELOPMENT |  |  |  |  |  |
| A5.1 | Foundation & Setup | SP | 40 | 1.230.769 | 49.230.769 |
| A5.2 | Production Planning | SP | 80 | 1.230.769 | 98.461.538 |
| A5.3 | BOM Management | SP | 80 | 1.230.769 | 98.461.538 |
| A5.4 | Production Execution | SP | 120 | 1.230.769 | 147.692.308 |
| A5.5 | Production Costing | SP | 60 | 1.230.769 | 73.846.154 |
| A5.6 | Asset & Maintenance | SP | 100 | 1.230.769 | 123.076.923 |
| A5.7 | Facility Management | SP | 40 | 1.230.769 | 49.230.769 |
|  | Subtotal Backend Development |  | 520 |  | 640.000.000 |
| F. FRONTEND DEVELOPMENT |  |  |  |  |  |
| A6.1 | Web Portal - Planning | SP | 50 | 1.600.000 | 80.000.000 |
| A6.2 | Web Portal - BOM | SP | 40 | 1.600.000 | 64.000.000 |
| A6.3 | Web Portal - Execution | SP | 50 | 1.600.000 | 80.000.000 |
| A6.4 | Web Portal - Costing | SP | 30 | 1.600.000 | 48.000.000 |
| A6.5 | Web Portal - Asset | SP | 30 | 1.600.000 | 48.000.000 |
|  | Subtotal Web Portal |  | 200 |  | 320.000.000 |
| G. MOBILE DEVELOPMENT |  |  |  |  |  |
| A7.1 | Mobile App - Core | SP | 80 | 1.000.000 | 80.000.000 |
| A7.2 | Mobile App - Features | SP | 80 | 1.000.000 | 80.000.000 |
|  | Subtotal Mobile Development |  | 160 |  | 160.000.000 |
| H. DASHBOARD DEVELOPMENT |  |  |  |  |  |
| A8.1 | Production Dashboard | Widget | 8 | 4.000.000 | 32.000.000 |
| A8.2 | OEE Dashboard | Widget | 6 | 4.000.000 | 24.000.000 |
| A8.3 | Cost Dashboard | Widget | 6 | 4.000.000 | 24.000.000 |
|  | Subtotal Dashboard Development |  | 20 |  | 80.000.000 |
| I. TESTING & QA |  |  |  |  |  |
| A9.1 | Test Planning & Design | Kasus | 80 | 576.000 | 46.080.000 |
| A9.2 | Unit Testing | Kasus | 150 | 576.000 | 86.400.000 |
| A9.3 | Integration Testing | Kasus | 100 | 576.000 | 57.600.000 |
| A9.4 | Performance Testing | Kasus | 50 | 576.000 | 28.800.000 |
| A9.5 | UAT & Regression | Kasus | 120 | 576.000 | 69.120.000 |
|  | Subtotal Testing & QA |  | 500 |  | 288.000.000 |
| J. INTEGRATION |  |  |  |  |  |
| A10.1 | P-FNE-01 Integration | Endpoint | 6 | 3.840.000 | 23.040.000 |
| A10.2 | P-FNE-03 Integration | Endpoint | 15 | 3.840.000 | 57.600.000 |
| A10.3 | P-FNE-05 Integration | Endpoint | 5 | 3.840.000 | 19.200.000 |
| A10.4 | P-FNE-06 Integration | Endpoint | 12 | 3.840.000 | 46.080.000 |
| A10.5 | P-FNE-07 Integration | Endpoint | 8 | 3.840.000 | 30.720.000 |
| A10.6 | P-FNE-08 Integration | Endpoint | 4 | 3.840.000 | 15.360.000 |
|  | Subtotal Integration |  | 50 |  | 192.000.000 |
| K. DEPLOYMENT |  |  |  |  |  |
| A11.1 | Dev Environment | Env | 1 | 32.000.000 | 32.000.000 |
| A11.2 | Staging Environment | Env | 1 | 32.000.000 | 32.000.000 |
| A11.3 | Production Environment | Env | 1 | 32.000.000 | 32.000.000 |
|  | Subtotal Deployment |  | 3 |  | 96.000.000 |
| L. PROJECT MANAGEMENT |  |  |  |  |  |
| A12.1 | Sprint Management (x12) | Sprint | 12 | 20.000.000 | 240.000.000 |
|  | Subtotal Project Management |  | 12 |  | 240.000.000 |
| M. TRAINING & DOCUMENTATION |  |  |  |  |  |
| A13.1 | User Training | Sesi | 5 | 15.000.000 | 75.000.000 |
| A13.2 | Technical Documentation | Sesi | 3 | 15.000.000 | 45.000.000 |
|  | Subtotal Training & Doc |  | 8 |  | 120.000.000 |
| TOTAL BIAYA AKTIVITAS |  |  |  |  | 2.483.333.334 |

#### 5.3.4. Rekapitulasi Biaya per Aktivitas

| No | Aktivitas | Biaya (Rp) | Persentase |
| --- | --- | --- | --- |
| 1 | Project Initiation | 14.000.000 | 0,6% |
| 2 | Requirement Gathering | 44.000.000 | 1,8% |
| 3 | System Design | 69.333.334 | 2,8% |
| 4 | Database Design | 40.000.000 | 1,6% |
| 5 | Backend Development | 640.000.000 | 25,8% |
| 6 | Frontend Development | 320.000.000 | 12,9% |
| 7 | Mobile Development | 160.000.000 | 6,4% |
| 8 | Dashboard Development | 80.000.000 | 3,2% |
| 9 | Testing & QA | 288.000.000 | 11,6% |
| 10 | Integration | 192.000.000 | 7,7% |
| 11 | Deployment | 96.000.000 | 3,9% |
| 12 | Project Management | 240.000.000 | 9,7% |
| 13 | Training & Documentation | 120.000.000 | 4,8% |
| Total |  | 2.303.333.334 | 100,0% |

### 5.4. Detail Biaya Personil (Inkindo 2026)

#### 5.4.1. Personil per Aktivitas

Berikut adalah alokasi personil per aktivitas dengan tarif sesuai Inkindo 2026:

| No | Aktivitas | Personil | Jam | Tarif/Jam (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- | --- |
| A. PROJECT INITIATION |  |  |  |  |  |
| A1.1 | Project Charter | PM | 16 | 350.000 | 5.600.000 |
| A1.2 | PMP Document | PM | 16 | 350.000 | 5.600.000 |
| A1.3 | Kick-off Meeting | PM + TL + BA | 8 | 350.000 + 325.000 + 275.000 | 7.600.000 |
| B. REQUIREMENT GATHERING |  |  |  |  |  |
| A2.1 | User Interview (6 sesi) | BA | 48 | 275.000 | 13.200.000 |
|  |  | PM | 24 | 350.000 | 8.400.000 |
| A2.2 | Workshop (4 sesi) | BA | 32 | 275.000 | 8.800.000 |
|  |  | PM | 16 | 350.000 | 5.600.000 |
|  |  | MS | 16 | 275.000 | 4.400.000 |
| C. SYSTEM DESIGN |  |  |  |  |  |
| A3.1 | Architecture Design | TL | 40 | 325.000 | 13.000.000 |
| A3.2 | API Design | TL | 40 | 325.000 | 13.000.000 |
|  |  | BE (3 org) | 120 | 250.000 | 30.000.000 |
| A3.3 | Security Design | TL | 24 | 325.000 | 7.800.000 |
|  |  | DevOps | 16 | 225.000 | 3.600.000 |
| D. DATABASE DESIGN |  |  |  |  |  |
| A4.1 | ERD Creation | TL | 40 | 325.000 | 13.000.000 |
|  |  | BE (2 org) | 120 | 225.000 | 27.000.000 |
| E. BACKEND DEVELOPMENT |  |  |  |  |  |
| A5.1 | Foundation & Setup | BE (2 org) | 320 | 225.000 | 72.000.000 |
| A5.2 | Production Planning | BE (2 org) | 480 | 225.000 | 108.000.000 |
| A5.3 | BOM Management | BE (2 org) | 480 | 225.000 | 108.000.000 |
| A5.4 | Production Execution | BE (3 org) | 960 | 225.000 | 216.000.000 |
| A5.5 | Production Costing | BE (2 org) | 480 | 225.000 | 108.000.000 |
| A5.6 | Asset & Maintenance | BE (2 org) | 640 | 225.000 | 144.000.000 |
| A5.7 | Facility Management | BE (2 org) | 320 | 225.000 | 72.000.000 |
| F. FRONTEND DEVELOPMENT |  |  |  |  |  |
| A6.1 | Web Portal - Planning | FE (2 org) | 400 | 225.000 | 90.000.000 |
| A6.2 | Web Portal - BOM | FE (2 org) | 320 | 225.000 | 72.000.000 |
| A6.3 | Web Portal - Execution | FE (2 org) | 400 | 225.000 | 90.000.000 |
| A6.4 | Web Portal - Costing | FE (2 org) | 240 | 225.000 | 54.000.000 |
| A6.5 | Web Portal - Asset | FE (2 org) | 240 | 225.000 | 54.000.000 |
| G. MOBILE DEVELOPMENT |  |  |  |  |  |
| A7.1 | Mobile App - Core | FE (2 org) | 640 | 225.000 | 144.000.000 |
| A7.2 | Mobile App - Features | FE (2 org) | 640 | 225.000 | 144.000.000 |
| H. DASHBOARD DEVELOPMENT |  |  |  |  |  |
| A8.1 | Production Dashboard | FE (1 org) | 160 | 225.000 | 36.000.000 |
| A8.2 | OEE Dashboard | FE (1 org) | 120 | 225.000 | 27.000.000 |
| A8.3 | Cost Dashboard | FE (1 org) | 120 | 225.000 | 27.000.000 |
| I. TESTING & QA |  |  |  |  |  |
| A9.1 | Test Planning & Design | QA (2 org) | 160 | 175.000 | 28.000.000 |
| A9.2 | Unit Testing | QA (2 org) | 320 | 175.000 | 56.000.000 |
| A9.3 | Integration Testing | QA (2 org) | 240 | 175.000 | 42.000.000 |
| A9.4 | Performance Testing | QA (1 org) | 120 | 175.000 | 21.000.000 |
| A9.5 | UAT & Regression | QA (2 org) | 320 | 175.000 | 56.000.000 |
| J. INTEGRATION |  |  |  |  |  |
| A10.1 | P-FNE-01 Integration | BE (1 org) | 64 | 225.000 | 14.400.000 |
| A10.2 | P-FNE-03 Integration | BE (2 org) | 192 | 225.000 | 43.200.000 |
| A10.3 | P-FNE-05 Integration | BE (1 org) | 64 | 225.000 | 14.400.000 |
| A10.4 | P-FNE-06 Integration | BE (2 org) | 160 | 225.000 | 36.000.000 |
| A10.5 | P-FNE-07 Integration | BE (1 org) | 80 | 225.000 | 18.000.000 |
| A10.6 | P-FNE-08 Integration | BE (1 org) | 64 | 225.000 | 14.400.000 |
| K. DEPLOYMENT |  |  |  |  |  |
| A11.1 | Dev Environment | DevOps | 32 | 225.000 | 7.200.000 |
| A11.2 | Staging Environment | DevOps | 40 | 225.000 | 9.000.000 |
| A11.3 | Production Environment | DevOps | 48 | 225.000 | 10.800.000 |
| L. PROJECT MANAGEMENT |  |  |  |  |  |
| A12.1 | Sprint Management (x12) | PM | 960 | 350.000 | 336.000.000 |
| M. TRAINING & DOCUMENTATION |  |  |  |  |  |
| A13.1 | User Training | BA | 80 | 275.000 | 22.000.000 |
|  |  | MS | 40 | 275.000 | 11.000.000 |
| A13.2 | Technical Documentation | All | 120 | 250.000 | 30.000.000 |
| TOTAL BIAYA PERSONIL |  |  |  |  | 3.162.000.000 |

#### 5.4.2. Rekapitulasi Biaya Personil per Peran

| No | Peran | Total Jam | Tarif/Jam (Rp) | Total Biaya (Rp) |
| --- | --- | --- | --- | --- |
| 1 | Project Manager (PM) | 1.000 | 350.000 | 350.000.000 |
| 2 | Tech Lead (TL) | 200 | 325.000 | 65.000.000 |
| 3 | Business Analyst (BA) | 200 | 275.000 | 55.000.000 |
| 4 | Manufacturing Specialist (MS) | 80 | 275.000 | 22.000.000 |
| 5 | Backend Developer (BE) - Senior | 960 | 250.000 | 240.000.000 |
| 6 | Backend Developer (BE) - Middle (3 org) | 2.880 | 225.000 | 648.000.000 |
| 7 | Frontend Developer (FE) - Senior (1 org) | 480 | 250.000 | 120.000.000 |
| 8 | Frontend Developer (FE) - Middle (2 org) | 1.920 | 225.000 | 432.000.000 |
| 9 | QA Engineer - Senior (1 org) | 160 | 200.000 | 32.000.000 |
| 10 | QA Engineer - Middle (2 org) | 1.120 | 175.000 | 196.000.000 |
| 11 | DevOps Engineer | 120 | 225.000 | 27.000.000 |
| Total |  | 9.120 |  | 3.162.000.000 |

### 5.5. Biaya Infrastruktur dan Perangkat Lainnya

#### 5.5.1. Infrastruktur Cloud

| No | Komponen | Deskripsi | Biaya (Rp) |
| --- | --- | --- | --- |
| 1 | Cloud Infrastructure | AWS/GCP (Dev, Staging, Production) - 6 bulan | 300.000.000 |
| 2 | Database License | PostgreSQL, TimescaleDB, Neo4j - 6 bulan | 150.000.000 |
| 3 | Monitoring Tools | Prometheus, Grafana, ELK Stack - 6 bulan | 80.000.000 |
| 4 | CI/CD Tools | GitLab CI / GitHub Actions - 6 bulan | 40.000.000 |
| 5 | API Gateway | Kong / Traefik - 6 bulan | 50.000.000 |
| 6 | Testing Tools | Test Automation Licenses - 6 bulan | 30.000.000 |
| Total Infrastruktur |  |  | 650.000.000 |

#### 5.5.2. Perangkat Keras dan Lainnya

| No | Komponen | Deskripsi | Biaya (Rp) |
| --- | --- | --- | --- |
| 1 | Development Workstations | Laptop/PC untuk 12 orang | 180.000.000 |
| 2 | Mobile Testing Devices | Berbagai perangkat mobile | 50.000.000 |
| 3 | Training & Workshop | Biaya pelatihan dan workshop | 80.000.000 |
| 4 | Documentation & Printing | Biaya cetak dokumen dan manual | 20.000.000 |
| 5 | Meeting & Travel | Biaya pertemuan dan perjalanan | 30.000.000 |
| Total Perangkat Lain |  |  | 360.000.000 |

### 5.6. Rekapitulasi Total Biaya Proyek

#### 5.6.1. Total Biaya

| Kategori | Biaya (Rp) | Persentase |
| --- | --- | --- |
| 1. Biaya Personil | 3.162.000.000 | 64,7% |
| 2. Biaya Infrastruktur | 650.000.000 | 13,3% |
| 3. Biaya Perangkat Keras | 230.000.000 | 4,7% |
| 4. Biaya Training & Workshop | 80.000.000 | 1,6% |
| 5. Biaya Dokumentasi & Lainnya | 50.000.000 | 1,0% |
| Subtotal | 4.172.000.000 | 85,3% |
| 6. Biaya Overhead (10%) | 417.200.000 | 8,5% |
| 7. Biaya Kontingensi (10%) | 417.200.000 | 8,5% |
| Total Anggaran | 5.006.400.000 | 100,0% |

#### 5.6.2. Rekapitulasi per Sprint

| Sprint | Personil | Infrastruktur | Lainnya | Total |
| --- | --- | --- | --- | --- |
| S1 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S2 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S3 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S4 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S5 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S6 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S7 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S8 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S9 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S10 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S11 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| S12 | 263.500.000 | 25.000.000 | 10.000.000 | 298.500.000 |
| Subtotal | 3.162.000.000 | 300.000.000 | 120.000.000 | 3.582.000.000 |
| Overhead (10%) | - | - | - | 358.200.000 |
| Kontingensi (10%) | - | - | - | 358.200.000 |
| Infrastruktur Tambahan | - | - | - | 650.000.000 |
| Total |  |  |  | 5.006.400.000 |

### 5.7. Budget Baseline

#### 5.7.1. Baseline Anggaran per Bulan

| Bulan | Sprint | Biaya (Rp) | Cumulative (Rp) |
| --- | --- | --- | --- |
| Oktober 2026 | S1-S2 | 597.000.000 | 597.000.000 |
| November 2026 | S3-S4 | 597.000.000 | 1.194.000.000 |
| Desember 2026 | S5-S6 | 597.000.000 | 1.791.000.000 |
| Januari 2027 | S7-S8 | 597.000.000 | 2.388.000.000 |
| Februari 2027 | S9-S10 | 597.000.000 | 2.985.000.000 |
| Maret 2027 | S11-S12 | 597.000.000 | 3.582.000.000 |
| Subtotal Personil & Operasional |  | 3.582.000.000 |  |
| Overhead (10%) |  | 358.200.000 | 3.940.200.000 |
| Kontingensi (10%) |  | 358.200.000 | 4.298.400.000 |
| Infrastruktur Tambahan |  | 650.000.000 | 4.948.400.000 |
| Perangkat Keras |  | 58.000.000 | 5.006.400.000 |
| Total |  |  | 5.006.400.000 |

#### 5.7.2. S-Curve Budget

| Bulan | Cumulative Biaya (Rp) | Persentase |
| --- | --- | --- |
| Oktober 2026 | 597.000.000 | 12,0% |
| November 2026 | 1.194.000.000 | 23,9% |
| Desember 2026 | 1.791.000.000 | 35,8% |
| Januari 2027 | 2.388.000.000 | 47,7% |
| Februari 2027 | 2.985.000.000 | 59,6% |
| Maret 2027 | 5.006.400.000 | 100,0% |

### 5.8. Cost Control

#### 5.8.1. Earned Value Management (EVM)

Parameter EVM:

| Parameter | Formula | Deskripsi |
| --- | --- | --- |
| PV (Planned Value) | Planned % × BAC | Nilai pekerjaan yang direncanakan |
| EV (Earned Value) | Completed % × BAC | Nilai pekerjaan yang selesai |
| AC (Actual Cost) | Actual cost incurred | Biaya aktual yang dikeluarkan |
| BAC (Budget at Completion) | Total budget | Total anggaran proyek = Rp 5.006.400.000 |

Variance:

| Parameter | Formula | Interpretasi |
| --- | --- | --- |
| CV = EV - AC | EV - AC | > 0: Under budget; < 0: Over budget |
| SV = EV - PV | EV - PV | > 0: Ahead of schedule; < 0: Behind schedule |

Indices:

| Parameter | Formula | Interpretasi |
| --- | --- | --- |
| CPI = EV / AC | EV / AC | > 1: Under; < 1: Over |
| SPI = EV / PV | EV / PV | > 1: Ahead; < 1: Behind |

Forecast:

| Parameter | Formula | Deskripsi |
| --- | --- | --- |
| EAC = BAC / CPI | BAC / CPI | Estimated cost at completion |
| ETC = EAC - AC | EAC - AC | Estimated remaining cost |
| VAC = BAC - EAC | BAC - EAC | Variance at completion |

#### 5.8.2. Cost Control Actions

| Kondisi | Tindakan |
| --- | --- |
| CPI < 0.8 (Over budget) | • Review pengeluaran • Identifikasi pemborosan • Scope reduction • Negosiasi vendor |
| CPI 0.8 - 0.9 (Slightly over) | • Review budget per aktivitas • Optimasi penggunaan resource • Menunda pembelian tidak penting |
| CPI > 1.0 (Under budget) | • Reallocate budget ke area lain • Tambah fitur prioritas tinggi • Simpan untuk contingency |

### 5.9. Cost Reporting

| Laporan | Audience | Frekuensi | Metode |
| --- | --- | --- | --- |
| Budget vs Actual | Tim Manajemen | Bulanan | Spreadsheet |
| EVM Report | PM + Program Manager | Sprint | Dashboard |
| Expense Report | Finance | Bulanan | Laporan Formal |
| Cost Forecast | PM | Bulanan | Spreadsheet |
| Variance Report | Sponsor | Bulanan | Presentasi |

### 5.10. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |
| Finance |  |  |  |

# BAB 6: MANAJEMEN KUALITAS PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 6.1. Pendahuluan

Manajemen kualitas proyek adalah proses yang memastikan bahwa deliverable proyek memenuhi standar kualitas yang ditetapkan dan memuaskan kebutuhan pengguna. Area ini mencakup perencanaan kualitas, jaminan kualitas (Quality Assurance), dan pengendalian kualitas (Quality Control).

Dalam konteks P-FNE-04, manajemen kualitas sangat kritis karena modul Production & Manufacturing adalah sistem yang kompleks dengan banyak fitur kritis yang memengaruhi operasional perusahaan. Kegagalan kualitas pada sistem ini dapat menyebabkan kerugian finansial, inefisiensi operasional, dan hilangnya kepercayaan pengguna.

### 6.2. Quality Policy

#### 6.2.1. Pernyataan Kebijakan Kualitas

Kebijakan Kualitas Proyek P-FNE-04:

Kami berkomitmen untuk menghasilkan produk perangkat lunak yang:

- Fungsional: Memenuhi semua kebutuhan fungsional yang telah ditentukan

- Handal: Berjalan dengan stabil dan minim error

- Efisien: Memiliki performa yang optimal sesuai target

- Aman: Melindungi data dan privasi pengguna

- Usability: Mudah digunakan oleh seluruh pengguna

- Terintegrasi: Terintegrasi dengan baik dengan sistem lain

- Terpelihara: Mudah dipelihara dan dikembangkan di masa depan

#### 6.2.2. Quality Objectives

| No | Objective | Target | Metode Pengukuran |
| --- | --- | --- | --- |
| 1 | Defect-free delivery | 0 critical bugs di production | UAT, Production monitoring |
| 2 | Code quality | Technical debt < 10% | SonarQube |
| 3 | Test coverage | > 80% | JUnit/Jest coverage report |
| 4 | User satisfaction | > 90% | UAT Survey |
| 5 | Performance | Sesuai NFR target | Performance testing |
| 6 | Integration | 100% integration tests passed | Integration testing |
| 7 | Security | 0 high-severity vulnerabilities | Security audit |

### 6.3. Quality Standards

#### 6.3.1. Standar Kode

| Standar | Deskripsi | Alat |
| --- | --- | --- |
| Coding Standard | Mengikuti standar kode yang telah ditentukan | ESLint (JS/TS), Checkstyle (Java) |
| Naming Convention | Mengikuti convention yang konsisten | ESLint, Checkstyle |
| Code Documentation | Dokumentasi kode dengan Javadoc/JSDoc | Javadoc, JSDoc |
| Code Review | Setiap PR harus di-review minimal 1 orang | GitLab Merge Request |
| Branching Strategy | Menggunakan Git Flow | Git |
| Commit Convention | Conventional Commits | Git |

#### 6.3.2. Standar Arsitektur

| Standar | Deskripsi |
| --- | --- |
| Microservices | Setiap domain diimplementasikan sebagai microservice |
| API-First | Semua komunikasi melalui API yang terdefinisi |
| Event-Driven | Komunikasi async menggunakan Kafka |
| Cloud-Native | Dirancang untuk dijalankan di cloud |
| Security by Design | Keamanan diterapkan di setiap lapisan |
| Polyglot Persistence | Menggunakan database yang sesuai untuk setiap jenis data |

#### 6.3.3. Standar Testing

| Standar | Deskripsi | Target |
| --- | --- | --- |
| Unit Testing | Menguji setiap unit kode secara terisolasi | 100% coverage untuk critical path |
| Integration Testing | Menguji integrasi antar komponen | 100% API endpoints teruji |
| Performance Testing | Menguji kinerja sistem | Sesuai NFR target |
| Security Testing | Menguji keamanan sistem | 0 high-severity vulnerabilities |
| UAT | Pengujian oleh pengguna akhir | 100% acceptance criteria terpenuhi |
| Regression Testing | Memastikan perubahan tidak merusak fitur existing | 100% test case passing |

### 6.4. Quality Assurance (QA) Plan

#### 6.4.1. QA Activities by Phase

| Phase | QA Activity | Owner | Deliverable |
| --- | --- | --- | --- |
| Planning | Test Strategy Document | QA Lead | Test Strategy |
|  | Test Case Design | QA Team | Test Cases |
|  | Test Data Preparation | QA Team | Test Data |
| Development | Unit Testing | Developer | Unit Test Report |
|  | Code Review | Tech Lead | Review Comments |
|  | Static Code Analysis | QA | SonarQube Report |
| Integration | Integration Testing | QA | Integration Test Report |
|  | API Testing | QA | API Test Report |
|  | Event-Driven Testing | QA | Event Test Report |
| System | System Testing | QA | System Test Report |
|  | Performance Testing | QA | Performance Report |
|  | Security Testing | QA + DevOps | Security Report |
| UAT | UAT Execution | BA + User | UAT Sign-off |
|  | User Feedback Collection | BA | Feedback Report |
| Deployment | Smoke Testing | QA | Smoke Test Report |
|  | Regression Testing | QA | Regression Test Report |
| Post-Deployment | Production Monitoring | DevOps | Monitoring Report |
|  | User Support | Support Team | Support Log |

#### 6.4.2. Automated Testing Strategy

| Tipe Test | Alat | Coverage Target | Frekuensi |
| --- | --- | --- | --- |
| Unit Test (Backend) | JUnit | > 80% | Setiap commit |
| Unit Test (Frontend) | Jest | > 80% | Setiap commit |
| Integration Test | Postman/Newman, RestAssured | 100% critical flows | Setiap PR |
| API Contract Test | Pact | 100% API contracts | Setiap PR |
| E2E Test | Cypress | 100% critical user flows | Setiap sprint |
| Performance Test | k6 | 100% critical endpoints | Setiap sprint |
| Security Scan | OWASP ZAP | 100% critical endpoints | Bulanan |
| Static Code Analysis | SonarQube | 100% | Setiap commit |

#### 6.4.3. Testing Tools

| Kategori | Tool | Fungsi |
| --- | --- | --- |
| Unit Testing | JUnit, Jest, Mocha | Unit testing |
| Integration Testing | RestAssured, Postman | API testing |
| E2E Testing | Cypress, Selenium | End-to-end testing |
| Performance Testing | k6, JMeter | Load testing |
| Security Testing | OWASP ZAP, SonarQube | Security scanning |
| Test Management | Jira X-Ray | Test case management |
| Code Coverage | JaCoCo, Istanbul | Coverage reporting |

### 6.5. Quality Control (QC) Plan

#### 6.5.1. QC Activities

| No | QC Activity | Frequency | Owner | Output |
| --- | --- | --- | --- | --- |
| 1 | Code Review | Setiap PR | Tech Lead | Review Comments |
| 2 | Static Code Analysis | Setiap commit | QA | SonarQube Report |
| 3 | Unit Test Execution | Setiap commit | Developer | Test Report |
| 4 | Integration Test | Setiap PR | QA | Test Report |
| 5 | Regression Test | Setiap sprint | QA | Test Report |
| 6 | Performance Test | Setiap sprint | QA | Performance Report |
| 7 | Security Scan | Bulanan | QA + DevOps | Security Report |
| 8 | UAT | Setiap major release | BA + User | UAT Sign-off |
| 9 | Production Monitoring | Setiap hari | DevOps | Monitoring Report |
| 10 | Defect Management | Setiap hari | QA + Dev | Defect Report |

#### 6.5.2. Defect Management Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                      DEFECT MANAGEMENT PROCESS                          │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Defect Discovery                                                    │

│     - QA menemukan bug saat testing                                    │

│     - User melaporkan bug saat UAT                                     │

│     - Monitoring menemukan issue di production                         │

│         │                                                              │

│         ▼                                                              │

│  2. Defect Logging                                                      │

│     - Log di Jira dengan severity (Critical/Major/Minor/Trivial)       │

│     - Attachment: Screenshot, logs, steps to reproduce                 │

│         │                                                              │

│         ▼                                                              │

│  3. Defect Triage                                                      │

│     - Tech Lead melakukan triage                                       │

│     - Menentukan priority dan assignment                               │

│         │                                                              │

│         ▼                                                              │

│  4. Defect Fix                                                         │

│     - Developer memperbaiki bug                                        │

│     - Unit test untuk bug tersebut                                     │

│         │                                                              │

│         ▼                                                              │

│  5. Defect Verification                                                │

│     - QA melakukan verification                                        │

│     - Regression testing                                               │

│         │                                                              │

│         ▼                                                              │

│  6. Defect Closure                                                     │

│     - Jika verified, close ticket                                      │

│     - Jika belum, reopen untuk perbaikan                               │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 6.5.3. Defect Severity & Priority Matrix

| Severity | Deskripsi | Contoh | Response Time |
| --- | --- | --- | --- |
| Critical | Sistem tidak berfungsi, data hilang | Crash, data loss, security breach | < 4 jam |
| Major | Fitur utama tidak berfungsi | MRP tidak jalan, PO tidak bisa dibuat | < 1 hari |
| Minor | Fitur tidak berfungsi tapi ada workaround | Validasi tidak jalan, UI error | < 3 hari |
| Trivial | Masalah kosmetik atau minor | Typo, warna salah | Backlog |

### 6.6. Performance Quality Targets

#### 6.6.1. Performance Targets

| No | Requirement | Target | Test Method |
| --- | --- | --- | --- |
| 1 | Production Order Query | ≤ 2 detik | Load Testing |
| 2 | MRP Computation (100 produk) | ≤ 10 detik | Performance Testing |
| 3 | BOM Explosion | ≤ 5 detik | Performance Testing |
| 4 | Production Cost Calculation | ≤ 5 detik | Performance Testing |
| 5 | API Response Time (95th percentile) | ≤ 500 ms | Load Testing |
| 6 | Concurrent Users | ≥ 1.000 | Load Testing |
| 7 | System Availability | 99,5% | Monitoring |
| 8 | Data Accuracy | ≥ 99% | Audit Testing |

#### 6.6.2. Performance Testing Plan

| Test Type | Description | Scenario | Tool |
| --- | --- | --- | --- |
| Load Test | Menguji performa di bawah beban normal | 100 concurrent users, normal operations | k6 |
| Stress Test | Menguji batas maksimum sistem | Progressive load hingga breaking point | k6 |
| Endurance Test | Menguji performa dalam jangka panjang | 1 jam dengan beban 50% capacity | k6 |
| Spike Test | Menguji respons terhadap lonjakan beban | Spike dari 10 ke 200 users | k6 |

### 6.7. Security Quality Targets

#### 6.7.1. Security Requirements

| No | Requirement | Target | Test Method |
| --- | --- | --- | --- |
| 1 | Authentication | Semua endpoint harus terautentikasi | Security Audit |
| 2 | Authorization | RBAC untuk setiap fitur | Security Audit |
| 3 | Data Encryption | Data sensitif dienkripsi (at-rest & in-transit) | Security Audit |
| 4 | Audit Trail | Semua transaksi tercatat | Security Audit |
| 5 | Input Validation | Semua input divalidasi | Penetration Testing |
| 6 | OWASP Top 10 | 0 high-severity vulnerabilities | OWASP ZAP |

#### 6.7.2. Security Testing Plan

| Test Type | Description | Frequency | Tool |
| --- | --- | --- | --- |
| SAST | Static Application Security Testing | Setiap commit | SonarQube |
| DAST | Dynamic Application Security Testing | Bulanan | OWASP ZAP |
| Penetration Testing | Manual security testing | Bulanan | Manual |
| Dependency Scan | Cek library vulnerabilities | Setiap commit | Snyk |
| Secret Scan | Cek hardcoded secrets | Setiap commit | GitLeaks |

### 6.8. Quality Metrics & Reporting

#### 6.8.1. Quality Metrics Dashboard

| Metric | Target | Actual | Status | Trend |
| --- | --- | --- | --- | --- |
| Defect Density | < 1 per 100 LOC |  | 🟡 | 📈 |
| Code Coverage | > 80% |  | 🟡 | 📈 |
| Technical Debt | < 10% |  | 🟡 | 📈 |
| UAT Pass Rate | 100% |  | 🟡 | 📈 |
| Performance Test Pass | 100% |  | 🟡 | 📈 |
| Security Audit Pass | 100% |  | 🟡 | 📈 |
| User Satisfaction | > 90% |  | 🟡 | 📈 |

#### 6.8.2. Quality Reporting Schedule

| Report | Frequency | Audience | Method |
| --- | --- | --- | --- |
| Test Execution Report | Setiap sprint | PM + QA Lead | Jira Dashboard |
| Defect Report | Setiap hari | PM + Tech Lead | Jira Dashboard |
| Code Quality Report | Setiap commit | Tech Lead | SonarQube |
| Performance Report | Setiap sprint | PM + Tech Lead | Grafana |
| Security Report | Bulanan | PM + DevOps | Laporan |
| UAT Report | Setiap major release | PM + Stakeholder | Laporan |

### 6.9. Quality Improvement Plan

#### 6.9.1. Continuous Improvement Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                     CONTINUOUS IMPROVEMENT PROCESS                      │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Measure                                                            │

│     - Collect quality metrics                                          │

│     - Identify areas for improvement                                   │

│         │                                                              │

│         ▼                                                              │

│  2. Analyze                                                           │

│     - Analyze root cause of issues                                    │

│     - Identify patterns and trends                                     │

│         │                                                              │

│         ▼                                                              │

│  3. Plan                                                              │

│     - Develop improvement plan                                        │

│     - Set improvement targets                                          │

│         │                                                              │

│         ▼                                                              │

│  4. Implement                                                         │

│     - Execute improvement plan                                        │

│     - Monitor progress                                                 │

│         │                                                              │

│         ▼                                                              │

│  5. Review                                                            │

│     - Review effectiveness of improvements                            │

│     - Adjust plan if needed                                            │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 6.9.2. Quality Improvement Initiatives

| Inisiatif | Deskripsi | Owner | Timeline |
| --- | --- | --- | --- |
| Automated Testing Enhancement | Meningkatkan coverage automated testing | QA Lead | S1-S12 |
| Code Review Improvement | Meningkatkan efektivitas code review | Tech Lead | S1-S12 |
| Performance Optimization | Optimasi performa secara kontinu | BE Team | S3-S12 |
| Security Hardening | Meningkatkan keamanan sistem | DevOps | S5-S12 |
| User Feedback Integration | Mengintegrasikan feedback user ke development | BA | S1-S12 |
| Defect Prevention | Mencegah defect melalui root cause analysis | QA + Dev | S1-S12 |

### 6.10. Quality Roles and Responsibilities

| Role | Quality Responsibilities |
| --- | --- |
| Project Manager | • Overall quality accountability • Resource allocation for testing • Quality reporting to stakeholders |
| Tech Lead | • Code quality oversight • Technical standards enforcement • Code review process |
| Business Analyst | • Requirement quality • UAT coordination • User feedback collection |
| QA Lead | • Test strategy and planning • Test automation framework • Quality metrics reporting |
| Backend Developer | • Unit testing • Code quality • Performance optimization |
| Frontend Developer | • Unit testing • UI/UX quality • Cross-browser compatibility |
| QA Engineer | • Test execution • Defect reporting • Regression testing |
| DevOps Engineer | • CI/CD quality • Monitoring quality • Security implementation |

### 6.11. Quality Audit

#### 6.11.1. Internal Quality Audit

| Audit Area | Frequency | Auditor | Scope |
| --- | --- | --- | --- |
| Code Quality | Bulanan | Tech Lead | Code standards, coverage |
| Testing Process | Bulanan | QA Lead | Test coverage, automation |
| Security | Bulanan | DevOps | Security controls |
| Process Compliance | 2 minggu | PM | Process adherence |

#### 6.11.2. External Quality Audit

| Audit Area | Frequency | Auditor | Scope |
| --- | --- | --- | --- |
| Security Audit | Setiap milestone | External Security Team | System security |
| Performance Audit | Setiap milestone | External Performance Team | System performance |
| ISO Compliance | Setiap tahun | External Auditor | Process compliance |

### 6.12. Quality Tools

| Category | Tool | Function |
| --- | --- | --- |
| Static Analysis | SonarQube | Code quality, technical debt |
| Unit Testing | JUnit, Jest | Unit testing |
| Integration Testing | RestAssured, Postman | API testing |
| E2E Testing | Cypress | End-to-end testing |
| Performance Testing | k6, JMeter | Load testing |
| Security Testing | OWASP ZAP | Security scanning |
| Test Management | Jira X-Ray | Test case management |
| Code Coverage | JaCoCo, Istanbul | Coverage reporting |
| Monitoring | Prometheus/Grafana | Production monitoring |
| Logging | ELK Stack | Log aggregation and analysis |

### 6.13. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| QA Lead |  |  |  |
| Sponsor |  |  |  |

# BAB 7: MANAJEMEN SUMBER DAYA PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 7.1. Pendahuluan

Manajemen sumber daya proyek adalah proses yang memastikan bahwa sumber daya yang diperlukan untuk proyek tersedia, dioptimalkan, dan dikelola dengan efektif. Area ini mencakup perencanaan sumber daya, estimasi sumber daya, akuisisi sumber daya, pengembangan tim, dan pengendalian sumber daya.

Dalam konteks P-FNE-04, manajemen sumber daya sangat kritis karena proyek ini membutuhkan tim dengan keahlian spesifik di bidang manufaktur dan pengembangan perangkat lunak, serta infrastruktur yang memadai untuk mendukung pengembangan dan deployment.

### 7.2. Resource Management Plan

#### 7.2.1. Organisasi Proyek

Struktur Organisasi Proyek:

text

┌─────────────────────────────────────────────────────────────────────────┐

│                      PROGRAM MANAGER                                    │

│                   (Super ERP FNE)                                       │

│              - Oversight seluruh proyek FNE                            │

│              - Koordinasi antar proyek                                 │

└───────────────────────────┬─────────────────────────────────────────────┘

│

┌───────────────────────────▼─────────────────────────────────────────────┐

│                    PROJECT MANAGER P-FNE-04                             │

│                - Manajemen proyek keseluruhan                          │

│                - Komunikasi stakeholder                                │

│                - Pengendalian jadwal & biaya                           │

└───────────────────────────┬─────────────────────────────────────────────┘

│

┌───────────────────────┼──────────────────────┬────────────────────┐

│                       │                      │                    │

▼                       ▼                      ▼                    ▼

┌───────────────┐   ┌───────────────┐    ┌───────────────┐    ┌─────────────────┐

│  TECH LEAD    │   │   BA / PO     │    │   QA LEAD     │    │  DEVOPS          │

│  (Backend)    │   │  (Business)   │    │               │    │  ENGINEER        │

│               │   │               │    │               │    │                  │

│ - Arsitektur  │   │ - Kebutuhan   │    │ - Strategi QA │    │ - CI/CD          │

│ - Code Review │   │ - Dokumentasi │    │ - Test Plan   │    │ - Infrastructure │

│ - Tech Decision│  │ - UAT         │    │ - Automation  │    │ - Monitoring     │

└───────┬───────┘   └───────┬───────┘    └───────┬───────┘    └────────┬────────┘

│                   │                    │                     │

┌───┼───┐           ┌───┼───┐            ┌───┼───┐                  │

▼   ▼   ▼           ▼   ▼   ▼            ▼   ▼   ▼                  │

┌─────┐ ┌─────┐     ┌─────┐ ┌─────┐      ┌─────┐ ┌─────┐                │

│BE   │ │BE   │     │FE   │ │FE   │      │QA   │ │QA   │                │

│Dev  │ │Dev  │     │Dev  │ │Dev  │      │Eng  │ │Eng  │                │

└─────┘ └─────┘     └─────┘ └─────┘      └─────┘ └─────┘                │

│

┌─────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────┐

│                      MANUFACTURING SPECIALIST                          │

│                  - Domain Expert Manufaktur                             │

│                  - Verifikasi Acceptance Criteria                      │

└─────────────────────────────────────────────────────────────────────────┘

#### 7.2.2. Deskripsi Peran dan Tanggung Jawab

1. Project Manager (PM)

| Aspek | Keterangan |
| --- | --- |
| Kualifikasi | • Pengalaman manajemen proyek IT > 5 tahun • Sertifikasi PMP/PRINCE2 • Pengalaman proyek ERP > 3 tahun • Kemampuan komunikasi dan negosiasi yang baik |
| Tanggung Jawab | • Manajemen proyek secara keseluruhan • Penyusunan dan pemeliharaan Project Management Plan • Pengendalian jadwal, biaya, dan ruang lingkup • Komunikasi dengan stakeholder • Pelaporan status proyek secara berkala • Manajemen risiko dan isu • Fasilitasi sprint planning, review, dan retrospective • Memastikan deliverable sesuai kualitas |
| Waktu | 100% (Full-time) |
| Lokasi | Kantor Pusat / Hybrid |

2. Tech Lead (TL)

| Aspek | Keterangan |
| --- | --- |
| Kualifikasi | • Pengalaman software architecture > 7 tahun • Keahlian Spring Boot, Microservices, Cloud • Pengalaman memimpin tim > 3 tahun • Pemahaman domain manufaktur |
| Tanggung Jawab | • Arsitektur sistem secara keseluruhan • Decision teknis dan pemilihan teknologi • Code review dan quality assurance teknis • Coaching dan mentoring tim developer • Koordinasi teknis dengan proyek lain • Oversight implementasi microservices |
| Waktu | 100% (Full-time) |
| Lokasi | Kantor Pusat / Hybrid |

3. Business Analyst / Product Owner (BA/PO)

| Aspek | Keterangan |
| --- | --- |
| Kualifikasi | • Pengalaman business analysis > 5 tahun • Pemahaman domain manufaktur/ERP • Kemampuan analisis dan dokumentasi yang baik • Kemampuan komunikasi dengan user |
| Tanggung Jawab | • Analisis dan dokumentasi kebutuhan fungsional • Pengelolaan product backlog • Validasi fitur dengan user • UAT (User Acceptance Testing) • Penyusunan user manual dan training material • Koordinasi dengan domain expert |
| Waktu | 80% (Hampir Full-time) |
| Lokasi | Kantor Pusat / Hybrid |

4. Backend Developer (BE) - 3 orang

| Aspek | Keterangan |
| --- | --- |
| Kualifikasi | • Pengalaman backend development > 3 tahun • Keahlian Spring Boot / Node.js • Pengalaman microservices dan database • Pemahaman RESTful API dan Kafka |
| Tanggung Jawab | • Pengembangan API dan microservices • Implementasi logika bisnis • Pengembangan database dan query • Integrasi dengan proyek lain • Unit testing dan documentation • Performance optimization |
| Waktu | 100% (Full-time) |
| Lokasi | Kantor Pusat / Hybrid / Remote |

5. Frontend Developer (FE) - 2 orang

| Aspek | Keterangan |
| --- | --- |
| Kualifikasi | • Pengalaman frontend development > 3 tahun • Keahlian React/Next.js, TypeScript • Pemahaman mobile development (Flutter) • Pemahaman UI/UX design |
| Tanggung Jawab | • Pengembangan Web Portal (React/Next.js) • Pengembangan Mobile App (Flutter) • Pengembangan Executive Dashboard • Implementasi UI/UX yang responsif • Integrasi dengan API backend • Unit testing dan documentation |
| Waktu | 100% (Full-time) |
| Lokasi | Kantor Pusat / Hybrid / Remote |

6. QA Engineer - 2 orang

| Aspek | Keterangan |
| --- | --- |
| Kualifikasi | • Pengalaman QA > 3 tahun • Keahlian test automation (Selenium, Cypress) • Pengalaman performance testing (k6/JMeter) • Pemahaman security testing |
| Tanggung Jawab | • Perencanaan dan eksekusi testing • Pengembangan automated test • Performance dan load testing • Security testing • Bug reporting dan tracking • Regression testing |
| Waktu | 100% (Full-time) |
| Lokasi | Kantor Pusat / Hybrid / Remote |

7. DevOps Engineer - 1 orang

| Aspek | Keterangan |
| --- | --- |
| Kualifikasi | • Pengalaman DevOps > 3 tahun • Keahlian Kubernetes, Docker • Pengalaman CI/CD (GitLab CI/Jenkins) • Pemahaman monitoring (Prometheus/Grafana) |
| Tanggung Jawab | • Setup dan maintenance infrastructure • Implementasi CI/CD pipeline • Monitoring dan logging • Backup dan disaster recovery • Deployment management • Security implementation |
| Waktu | 80% (Hampir Full-time) |
| Lokasi | Kantor Pusat / Hybrid |

8. Manufacturing Specialist (MS) - 1 orang

| Aspek | Keterangan |
| --- | --- |
| Kualifikasi | • Pengalaman di bidang manufaktur/produksi > 7 tahun • Pemahaman production planning, BOM, costing • Pengalaman implementasi ERP manufaktur • Kemampuan komunikasi dengan tim IT |
| Tanggung Jawab | • Domain expertise manufaktur • Verifikasi acceptance criteria • Konsultasi proses bisnis produksi • Validasi fitur dari sisi domain • Support UAT dan training |
| Waktu | 50% (Paruh waktu) |
| Lokasi | Kantor Pusat / Hybrid |

### 7.3. Resource Planning

#### 7.3.1. Resource Allocation by Phase

| Fase | Sprint | PM | TL | BA | BE | FE | QA | DevOps | MS | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inisiasi & Setup | S1 | 100% | 100% | 100% | 50% | 50% | 50% | 100% | 50% | 9 |
| Pengembangan Awal | S2-S4 | 100% | 100% | 50% | 100% | 100% | 75% | 50% | 50% | 11 |
| Pengembangan Inti | S5-S8 | 100% | 100% | 50% | 100% | 100% | 100% | 50% | 50% | 12 |
| Pengembangan Akhir | S9-S10 | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 100% | 12 |
| Testing & UAT | S11 | 100% | 75% | 100% | 50% | 50% | 100% | 75% | 100% | 11 |
| Deployment & Closure | S12 | 100% | 75% | 100% | 25% | 25% | 50% | 100% | 50% | 10 |

#### 7.3.2. Resource Schedule (Sprint Detail)

| Sprint | BE Dev 1 | BE Dev 2 | BE Dev 3 | FE Dev 1 | FE Dev 2 | QA 1 | QA 2 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S1 | IAM, Master, API Gateway | Kafka, Database | - | Web - Layout | Web - Setup | Test Plan | - |
| S2 | Plan, BOM, Facility | Plan, BOM, Work Center | - | Web - Plan | Web - BOM | Test Cases | - |
| S3 | MRP, BOM Explosion | Cost Rollup, PO | - | Web - PO | Mobile - Dashboard | Test Execution | - |
| S4 | Scheduling, Material Issue | Quality, Integration | - | Web - Release | Mobile - Progress | Test Cases | Integration Test |
| S5 | Progress API, Audit | By-Product, Status | Material Availability | Web - Progress | Mobile - Progress | Test Execution | Automation |
| S6 | Completion API | Cost Engine | Material Issue | Web - Cost | Mobile - Complete | Test Cases | Performance Test |
| S7 | Asset, Downtime | Work Order, Spare | - | Web - Asset | Mobile - Downtime | Test Execution | Automation |
| S8 | Maintenance, OEE | Execution, OEE | Integration | Web - Maintenance | Dashboard - OEE | Test Cases | Performance Test |
| S9 | Overhead, Variance | Standard vs Actual | P-FNE-06 | Web - Cost | Dashboard - KPI | Integration Test | UAT Prep |
| S10 | P-FNE-05 | P-FNE-07 | P-FNE-08 | Dashboard - Cost | Web - Fix | UAT | UAT |
| S11 | Bug Fixes | Bug Fixes | Bug Fixes | Bug Fixes | Bug Fixes | UAT | Performance |
| S12 | Deployment | Deployment | Documentation | Deployment | Deployment | Regression | Regression |

### 7.4. Resource Acquisition

#### 7.4.1. Recruitment Plan

| Peran | Jumlah | Sumber | Target Start | Status |
| --- | --- | --- | --- | --- |
| Project Manager | 1 | Internal Transfer | 1 Okt 2026 | ✅ |
| Tech Lead | 1 | Internal Transfer | 1 Okt 2026 | ✅ |
| Business Analyst | 1 | Internal Transfer | 1 Okt 2026 | ✅ |
| Backend Developer | 3 | External Recruitment | 1 Okt 2026 | 🟡 In Progress |
| Frontend Developer | 2 | External Recruitment | 1 Okt 2026 | 🟡 In Progress |
| QA Engineer | 2 | Internal + External | 1 Okt 2026 | 🟡 In Progress |
| DevOps Engineer | 1 | Internal Transfer | 1 Okt 2026 | ✅ |
| Manufacturing Specialist | 1 | Internal Transfer | 1 Okt 2026 | ✅ |

#### 7.4.2. Resource Onboarding

| Aktivitas | Durasi | Owner |
| --- | --- | --- |
| Administrative Setup (User, Email, Tools) | 1 hari | HR + IT |
| Project Kick-off | 1 hari | PM |
| Domain Training | 2 hari | BA + MS |
| Technical Training | 2 hari | TL |
| Development Environment Setup | 1 hari | DevOps |
| First Sprint Planning | 1 hari | PM |

### 7.5. Team Development

#### 7.5.1. Training Plan

| Pelatihan | Tim | Durasi | Waktu | Metode |
| --- | --- | --- | --- | --- |
| Domain Manufacturing | All | 2 hari | Pra-proyek | Workshop |
| Spring Boot Advanced | BE | 3 hari | Minggu 1 | Training |
| React/Flutter Advanced | FE | 3 hari | Minggu 1 | Training |
| Microservices Architecture | BE/DevOps | 2 hari | Minggu 2 | Workshop |
| Event-Driven Design | BE | 2 hari | Minggu 3 | Workshop |
| Performance Testing | QA | 2 hari | Minggu 4 | Training |
| Security Best Practices | All | 1 hari | Minggu 5 | Workshop |
| Agile & Scrum | All | 1 hari | Pra-proyek | Workshop |

#### 7.5.2. Team Building

| Aktivitas | Frekuensi | Deskripsi |
| --- | --- | --- |
| Sprint Retrospective | Setiap sprint | Evaluasi dan perbaikan proses |
| Team Lunch | Bulanan | Social gathering |
| Knowledge Sharing | 2 minggu | Technical sharing session |
| Pair Programming | Sesuai kebutuhan | Collaborative coding |
| Mentoring | Berkelanjutan | Senior mentoring junior |

### 7.6. Resource Management Tools

| Tool | Fungsi |
| --- | --- |
| Jira | Task assignment, sprint management, resource allocation |
| Confluence | Dokumentasi, knowledge base |
| GitLab | Code repository, code review |
| Microsoft Teams | Communication, daily standup |
| Google Workspace | Document sharing, collaboration |
| Lucidchart | Organization chart, process flow |

### 7.7. Resource Control

#### 7.7.1. Resource Utilization Tracking

| Metrik | Deskripsi | Target | Frekuensi |
| --- | --- | --- | --- |
| Resource Utilization | % jam kerja produktif | > 80% | Mingguan |
| Allocation Accuracy | % alokasi sesuai plan | > 90% | Sprint |
| Overtime | Jam lembur per personil | < 10% | Bulanan |
| Turnover | % pergantian personil | < 10% | Proyek |

#### 7.7.2. Resource Issue Management

| Issue | Tindakan | Owner |
| --- | --- | --- |
| Resource tidak tersedia | • Cari alternatif internal • Rekrutmen darurat • Adjust scope | PM |
| Resource overload | • Redistribusi work • Tambah resource • Re-prioritasi | PM |
| Skill gap | • Training cepat • Pendampingan senior • External consultant | TL |
| Conflict dalam tim | • Mediasi • Team building • Re-assignment | PM |

### 7.8. Resource Cost Summary

| Peran | Jumlah | Rate/Jam (Rp) | Total Jam | Total Biaya (Rp) |
| --- | --- | --- | --- | --- |
| Project Manager | 1 | 350.000 | 1.000 | 350.000.000 |
| Tech Lead | 1 | 325.000 | 700 | 227.500.000 |
| Business Analyst | 1 | 275.000 | 600 | 165.000.000 |
| Backend Developer | 3 | 225.000 | 2.880 | 648.000.000 |
| Frontend Developer | 2 | 225.000 | 1.920 | 432.000.000 |
| QA Engineer | 2 | 175.000 | 1.280 | 224.000.000 |
| DevOps Engineer | 1 | 225.000 | 450 | 101.250.000 |
| Manufacturing Specialist | 1 | 275.000 | 320 | 88.000.000 |
| Total | 12 |  | 9.150 | 2.235.750.000 |

### 7.9. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| HR |  |  |  |
| Sponsor |  |  |  |

# BAB 8: MANAJEMEN KOMUNIKASI PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 8.1. Pendahuluan

Manajemen komunikasi proyek adalah proses yang memastikan bahwa informasi yang tepat disampaikan kepada pemangku kepentingan yang tepat pada waktu yang tepat, melalui metode yang tepat, dan dengan dampak yang diharapkan. Area ini mencakup perencanaan komunikasi, pengelolaan komunikasi, dan pemantauan komunikasi.

Dalam konteks P-FNE-04, manajemen komunikasi sangat kritis karena proyek ini:

- Melibatkan banyak stakeholder dengan kepentingan berbeda

- Berintegrasi dengan 7 proyek turunan lainnya

- Memiliki tim yang tersebar (hybrid/remote)

- Memiliki kompleksitas teknis dan domain yang tinggi

### 8.2. Communication Management Plan

#### 8.2.1. Communication Matrix

| Stakeholder | Informasi | Metode | Frekuensi | Owner | Format |
| --- | --- | --- | --- | --- | --- |
| Sponsor (CEO) | • Status proyek • Milestone achievement • Risiko utama • Keputusan strategis | • Presentasi • Laporan Formal • Meeting | Bulanan | PM | • PowerPoint • Executive Summary |
| Program Manager | • Status proyek • Integrasi dengan proyek lain • Blocker dan risiko • Keputusan | • Meeting • Laporan Status • Email | Mingguan | PM | • Status Report • Dashboard |
| Project Team | • Task assignment • Progress update • Blocker • Sprint planning/review/retro | • Daily Standup • Sprint Ceremonies • Jira • Teams | Harian | PM | • Jira Board • Meeting |
| Manufacturing Director | • Fitur produksi • UAT schedule • Feedback | • Meeting • Demo • UAT Session | 2 Mingguan | BA | • Demo Session • UAT Report |
| Production Managers | • Fitur produksi • UAT schedule • Training schedule | • Meeting • Demo • UAT Session | 2 Mingguan | BA | • Demo Session • UAT Report |
| Operators | • Mobile app features • Training schedule • User guides | • Training • User Manual • Demo | Sesuai Kebutuhan | BA | • Training Session • User Manual |
| Finance Director | • Costing features • Integration with finance | • Meeting • Demo | Bulanan | BA | • Demo Session • Integration Report |
| P-FNE-03 Team | • API integration • Integration schedule • Issues | • Meeting • Technical Discussion • API Doc | 2 Mingguan | Tech Lead | • API Documentation • Meeting Notes |
| P-FNE-06 Team | • Costing integration • Integration schedule | • Meeting • Technical Discussion | 2 Mingguan | Tech Lead | • API Documentation • Meeting Notes |
| P-FNE-07 Team | • Data integration • BI/AI requirements | • Meeting • Technical Discussion | 2 Mingguan | Tech Lead | • API Documentation • Meeting Notes |
| QA Team | • Test plan • Test results • Defects | • Jira • Test Report • Meeting | Harian | QA Lead | • Jira Dashboard • Test Report |
| DevOps Team | • Deployment status • Infrastructure status • Monitoring | • Meeting • Dashboard • Report | Harian | DevOps | • Grafana Dashboard • Deployment Log |

### 8.3. Communication Methods and Tools

#### 8.3.1. Communication Methods

| Metode | Tujuan | Contoh Penggunaan |
| --- | --- | --- |
| Face-to-Face Meeting | Diskusi kompleks, decision making | Sprint Planning, Sprint Review |
| Video Conference | Tim jarak jauh, meeting dengan stakeholder | Daily Standup, Status Meeting |
| Email | Formal communication, dokumentasi | Status Report, Change Request |
| Instant Messaging | Komunikasi cepat, pertanyaan singkat | Daily Standup, pertanyaan teknis |
| Project Management Tool | Task tracking, progress monitoring | Jira, Sprint Backlog |
| Documentation | Penyimpanan informasi formal | Confluence, Technical Doc |
| Dashboard | Visualisasi status dan metrik | Jira Dashboard, Grafana |

#### 8.3.2. Communication Tools

| Tool | Fungsi | Pengguna |
| --- | --- | --- |
| Microsoft Teams | Instant messaging, video call, file sharing | Tim Proyek |
| Jira | Task management, sprint tracking, reporting | Tim Proyek |
| Confluence | Documentation, meeting notes, knowledge base | Tim Proyek |
| GitLab | Code repository, code review, CI/CD | Developer |
| Google Workspace | Email, document, presentation | Tim Proyek |
| Figma | UI/UX design, prototyping | FE Developer |
| Miro | Whiteboard, brainstorming, retrospective | Tim Proyek |
| Prometheus/Grafana | Monitoring dashboard | DevOps |
| Power BI | Executive dashboard | PM, BA |

### 8.4. Communication Schedule

#### 8.4.1. Regular Communication Events

| Event | Waktu | Durasi | Peserta | Agenda |
| --- | --- | --- | --- | --- |
| Daily Standup | 09:00 WIB (Harian) | 15 menit | Tim Proyek | • Progress kemarin • Plan hari ini • Blocker |
| Sprint Planning | Hari Kamis (Awal Sprint) | 2-3 jam | Tim + PM + BA | • Sprint goal • Sprint backlog • Estimasi |
| Sprint Review | Hari Rabu (Akhir Sprint) | 1-2 jam | Tim + Stakeholder | • Demo fitur • Feedback • UAT result |
| Sprint Retrospective | Hari Rabu (Setelah Review) | 1 jam | Tim | • What went well • What went wrong • Improvement plan |
| Backlog Refinement | Hari Senin (Minggu ke-2) | 1 jam | PM + BA + Tech Lead | • Grooming backlog • Estimasi user stories |
| Weekly Sync | Jumat 14:00 WIB | 30 menit | Tim + Program Manager | • Status update • Integration status • Issues |
| Monthly Steering | Akhir Bulan | 1 jam | PM + Sponsor + Program Manager | • Status proyek • Milestone • Risiko • Keputusan strategis |

#### 8.4.2. Ad-hoc Communication

| Situasi | Metode | Owner | Response Time |
| --- | --- | --- | --- |
| Blocker / Issue | Teams / Meeting | Tim | < 1 jam |
| Emergency / Critical Issue | Teams + Email | PM | < 30 menit |
| Change Request | Jira / Email | PM | < 1 hari |
| Technical Question | Teams / GitLab | Developer | < 2 jam |
| Decision Needed | Teams / Meeting | PM | < 1 hari |

### 8.5. Communication Content

#### 8.5.1. Status Report Template

text

STATUS REPORT

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

REPORT PERIODE: [Tanggal - Tanggal]

SPRINT: [Sprint X]

DISUSUN OLEH: [Nama PM]

TANGGAL: [Tanggal]

1. EXECUTIVE SUMMARY

================================================================================

Status: [🟢 On Track / 🟡 At Risk / 🔴 Off Track]

Sprint Progress: [X% complete]

Overall Project Progress: [X% complete]

2. ACHIEVEMENTS

================================================================================

✅ [Item 1]

✅ [Item 2]

✅ [Item 3]

3. KEY METRICS

================================================================================

• Planned vs Actual: [X%]

• Velocity: [X SP]

• SPI: [X.XX]

• CPI: [X.XX]

• Defect Density: [X per 100 LOC]

• Code Coverage: [X%]

4. SPRINT BACKLOG STATUS

================================================================================

| Story | Status | SP | Owner |

|-------|--------|----|-------|

|       |        |    |       |

|       |        |    |       |

5. CHALLENGES / BLOCKERS

================================================================================

| No | Challenge | Impact | Action | Owner | Status |

|----|-----------|--------|--------|-------|--------|

| 1  |           |        |        |       |        |

| 2  |           |        |        |       |        |

6. INTEGRATION STATUS

================================================================================

| Integration | Status | Issues | Action |

|-------------|--------|--------|--------|

| P-FNE-03    | 🟢     | -      | -      |

| P-FNE-06    | 🟡     | API delay | Meeting with team |

7. RISKS

================================================================================

| Risk | Probability | Impact | Mitigation | Status |

|------|-------------|--------|------------|--------|

|      |             |        |            |        |

8. NEXT STEPS

================================================================================

• [Action 1]

• [Action 2]

• [Action 3]

================================================================================

Reported by: [Nama PM]

Approved by: [Nama Program Manager]

================================================================================

#### 8.5.2. Sprint Review Deck Template

text

SPRINT REVIEW

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

SPRINT: [Sprint X]

PERIODE: [Tanggal - Tanggal]

1. SPRINT GOAL

================================================================================

[Deskripsi sprint goal]

2. COMPLETED STORIES

================================================================================

| Story ID | Story Name | SP | Demo |

|----------|------------|----|------|

|          |            |    |      |

3. LIVE DEMO

================================================================================

[Feature 1] - [Demo video/live]

[Feature 2] - [Demo video/live]

[Feature 3] - [Demo video/live]

4. UAT RESULT

================================================================================

• Total UAT Cases: [X]

• Passed: [X] ([X%])

• Failed: [X] ([X%])

• Pending: [X] ([X%])

5. FEEDBACK

================================================================================

• Feedback 1

• Feedback 2

• Feedback 3

6. NEXT SPRINT PLAN

================================================================================

| Story ID | Story Name | SP | Priority |

|----------|------------|----|----------|

|          |            |    |          |

7. IMPEDIMENTS

================================================================================

• [Impediment 1] - [Resolution]

• [Impediment 2] - [Resolution]

================================================================================

Presented by: [Nama PM]

================================================================================

#### 8.5.3. Change Request Form

text

CHANGE REQUEST

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

CR NUMBER: CR-XXXX

TANGGAL: XX/XX/XXXX

DIAJUKAN OLEH: [Nama]

PERAN: [Peran]

A. INFORMASI PERUBAHAN

================================================================================

Jenis Perubahan: [ ] Scope [ ] Schedule [ ] Cost [ ] Quality [ ] Lainnya

Prioritas: [ ] Low [ ] Medium [ ] High [ ] Critical

Deskripsi Perubahan:

[Deskripsi detail perubahan yang diusulkan]

Justifikasi:

[Alasan mengapa perubahan ini diperlukan]

B. ANALISIS DAMPAK

================================================================================

Dampak terhadap Lingkup:

[Dampak terhadap scope proyek]

Dampak terhadap Jadwal:

[Dampak terhadap timeline proyek]

Dampak terhadap Biaya:

[Dampak terhadap budget proyek]

Dampak terhadap Kualitas:

[Dampak terhadap quality deliverables]

Dampak terhadap Risiko:

[Risiko baru atau risiko yang berubah]

C. REKOMENDASI

================================================================================

Rekomendasi: [ ] Approve [ ] Reject [ ] Defer

Catatan Rekomendasi:

D. KEPUTUSAN

================================================================================

Keputusan: [ ] Approved [ ] Rejected [ ] Deferred

Alasan Keputusan:

Disetujui Oleh: ___________________ Tanggal: ____________

### 8.6. Communication with Integration Teams

#### 8.6.1. Integration Communication Plan

| Proyek | PIC | Meeting Schedule | Informasi yang Dibahas |
| --- | --- | --- | --- |
| P-FNE-01 | Tech Lead | Mingguan | IAM, Master Data, Audit |
| P-FNE-03 | Tech Lead + BE | 2 Mingguan | Inventory, Material Availability |
| P-FNE-05 | Tech Lead + BE | 2 Mingguan | Demand Forecast, Sales |
| P-FNE-06 | Tech Lead + BE | 2 Mingguan | Costing Integration |
| P-FNE-07 | Tech Lead + BE | 2 Mingguan | Data Integration, BI/AI |
| P-FNE-08 | Tech Lead + BE | 2 Mingguan | IoT Data, Asset Telemetry |

#### 8.6.2. Integration Communication Template

text

INTEGRATION COMMUNICATION

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

INTEGRATION WITH: [P-FNE-XX]

TANGGAL: [Tanggal]

1. API STATUS

================================================================================

| Endpoint | Status | Issues | Resolution |

|----------|--------|--------|------------|

|          |        |        |            |

2. DATA MAPPING

================================================================================

| P-FNE-04 Field | P-FNE-XX Field | Status | Issues |

|----------------|----------------|--------|--------|

|                |                |        |        |

3. EVENT STATUS

================================================================================

| Event | Publisher | Subscriber | Status | Issues |

|-------|-----------|------------|--------|--------|

|       |           |            |        |        |

4. ISSUES / BLOCKERS

================================================================================

| Issue | Owner | Resolution | Due Date |

|-------|-------|------------|----------|

|       |       |            |          |

5. NEXT STEPS

================================================================================

• [Action 1]

• [Action 2]

• [Action 3]

================================================================================

P-FNE-04 Representative: [Nama]

P-FNE-XX Representative: [Nama]

================================================================================

### 8.7. Communication with Users

#### 8.7.1. User Communication Plan

| User Group | Communication | Method | Frequency | Owner |
| --- | --- | --- | --- | --- |
| Manufacturing Director | • Fitur baru • UAT schedule • Project status | • Meeting • Demo | 2 Mingguan | BA |
| Production Managers | • Fitur baru • UAT schedule • Training schedule | • Meeting • Demo • Email | 2 Mingguan | BA |
| Operators | • Mobile app features • Training schedule • User guides | • Training • User Manual • Demo | Sesuai Kebutuhan | BA |
| Finance Team | • Costing features • Integration status | • Meeting • Demo | Bulanan | BA |

#### 8.7.2. User Training Plan

| Training Module | Audience | Duration | Method | Schedule |
| --- | --- | --- | --- | --- |
| Production Planning | Production Planner | 1 hari | Workshop + Hands-on | S11-S12 |
| BOM Management | Production Planner, Engineer | 1 hari | Workshop + Hands-on | S11-S12 |
| Production Execution | Supervisor, Operator | 2 hari | Workshop + Hands-on | S11-S12 |
| Mobile App | Operator | 1 hari | Hands-on | S11-S12 |
| Production Costing | Finance Team | 1 hari | Workshop | S11-S12 |
| Asset & Maintenance | Maintenance Team | 1 hari | Workshop | S11-S12 |
| Executive Dashboard | Direksi, Management | 0.5 hari | Demo + Briefing | S12 |

### 8.8. Communication Escalation

#### 8.8.1. Escalation Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                         ESCALATION PROCESS                              │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  Level 1: Tim Proyek                                                    │

│  - Daily Standup - 09:00 WIB                                            │

│  - Teams: Komunikasi harian                                             │

│  - Jira: Task update                                                   │

│         │                                                              │

│         ▼ (Issue tidak terselesaikan dalam 24 jam)                     │

│                                                                         │

│  Level 2: Tech Lead / PM                                                │

│  - Koordinasi antar tim                                                │

│  - Pengambilan keputusan teknis                                        │

│  - Penentuan prioritas                                                 │

│         │                                                              │

│         ▼ (Issue tidak terselesaikan dalam 48 jam)                     │

│                                                                         │

│  Level 3: Program Manager                                               │

│  - Koordinasi antar proyek                                             │

│  - Keputusan strategis                                                 │

│  - Alokasi resource antar proyek                                       │

│         │                                                              │

│         ▼ (Issue tidak terselesaikan dalam 72 jam)                     │

│                                                                         │

│  Level 4: Sponsor (CEO)                                                │

│  - Keputusan kritis                                                    │

│  - Perubahan scope / budget                                            │

│  - Intervensi eksternal                                                │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 8.8.2. Escalation Thresholds

| Issue Type | Level 1 | Level 2 | Level 3 | Level 4 |
| --- | --- | --- | --- | --- |
| Technical Issue | Tim Developer | Tech Lead | Program Manager | Sponsor |
| Schedule Delay | PM + Tim | PM + Program Manager | Program Manager | Sponsor |
| Integration Issue | Tim Developer | Tech Lead | Program Manager | Sponsor |
| Resource Issue | PM | Program Manager | Sponsor | Sponsor |
| Scope Change | PM | Program Manager + CCB | Sponsor | Sponsor |
| Budget Issue | PM | Program Manager | Sponsor | Sponsor |

### 8.9. Communication Performance Measurement

#### 8.9.1. Communication Metrics

| Metric | Target | Measurement Method | Frequency |
| --- | --- | --- | --- |
| Team Satisfaction | > 80% | Survey | Bulanan |
| Stakeholder Satisfaction | > 85% | Survey | Bulanan |
| Meeting Effectiveness | > 80% | Survey | Sprint |
| Response Time (Critical) | < 30 min | Measurement | Harian |
| Response Time (Normal) | < 4 hours | Measurement | Harian |
| Issue Resolution Time | < 48 hours | Measurement | Harian |
| Status Report Timeliness | 100% | Measurement | Mingguan |

#### 8.9.2. Communication Audit

| Audit Area | Frequency | Auditor | Scope |
| --- | --- | --- | --- |
| Communication Process | Bulanan | PM | Process adherence |
| Stakeholder Feedback | Bulanan | BA | Feedback collection |
| Meeting Effectiveness | Sprint | PM | Meeting evaluation |
| Documentation Quality | Bulanan | BA | Documentation review |

### 8.10. Stakeholder Communication Strategy

#### 8.10.1. Stakeholder Communication Matrix

| Stakeholder | Current | Desired | Strategy |
| --- | --- | --- | --- |
| Sponsor (CEO) | Supportive | Supportive | Monthly report, milestone demo |
| Program Manager | Supportive | Supportive | Weekly meeting, status report |
| Manufacturing Director | Resistant | Supportive | Early involvement, demo, benefits communication |
| Production Managers | Neutral | Supportive | Requirement workshop, training |
| Operators | Unaware | Supportive | Training, user-friendly design |
| Finance Director | Supportive | Supportive | Cost data validation |
| P-FNE-03 Team | Supportive | Supportive | Integration planning, regular sync |
| P-FNE-06 Team | Supportive | Supportive | Integration planning, regular sync |

#### 8.10.2. Conflict Resolution

| Conflict Type | Resolution Method | Owner |
| --- | --- | --- |
| Technical Disagreement | • Technical discussion • Prototyping • Decision by Tech Lead | Tech Lead |
| Priority Disagreement | • Backlog refinement • Stakeholder alignment • Decision by PM | PM |
| Resource Conflict | • Resource planning • Re-prioritization • Decision by Program Manager | PM |
| Stakeholder Disagreement | • Meeting with stakeholders • Compromise • Escalation | PM |

### 8.11. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |

# BAB 9: MANAJEMEN RISIKO PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 9.1. Pendahuluan

Manajemen risiko proyek adalah proses yang memastikan bahwa risiko proyek diidentifikasi, dianalisis, dan ditangani secara proaktif untuk meminimalkan dampak negatif terhadap proyek. Area ini mencakup perencanaan risiko, identifikasi risiko, analisis risiko (kualitatif dan kuantitatif), perencanaan respons risiko, dan pemantauan serta pengendalian risiko.

Dalam konteks P-FNE-04, manajemen risiko sangat kritis karena proyek ini:

- Memiliki kompleksitas teknis yang tinggi (microservices, event-driven, cloud-native)

- Berintegrasi dengan 7 proyek turunan lainnya

- Memiliki ketergantungan pada sistem eksternal

- Melibatkan data sensitif produksi dan biaya

- Memiliki jadwal yang ketat (6 bulan)

### 9.2. Risk Management Plan

#### 9.2.1. Risk Management Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                        RISK MANAGEMENT PROCESS                          │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. IDENTIFIKASI RISIKO                                                 │

│     - Brainstorming dengan tim                                         │

│     - Review dokumen proyek                                            │

│     - Wawancara stakeholder                                            │

│     - Checklist risiko                                                 │

│         │                                                              │

│         ▼                                                              │

│  2. ANALISIS RISIKO                                                     │

│     - Kualitatif: Probability x Impact                                 │

│     - Kuantitatif: Expected Monetary Value (EMV)                      │

│     - Prioritas risiko                                                 │

│         │                                                              │

│         ▼                                                              │

│  3. PERENCANAAN RESPONS                                                 │

│     - Mitigate: Mengurangi probabilitas/dampak                        │

│     - Transfer: Mengalihkan risiko (asuransi, vendor)                  │

│     - Avoid: Menghindari risiko (ubah scope)                          │

│     - Accept: Menerima risiko (contingency)                           │

│         │                                                              │

│         ▼                                                              │

│  4. MONITORING & KONTROL                                                │

│     - Risk review setiap sprint                                        │

│     - Update risk register                                             │

│     - Risk audit                                                       │

│     - Trigger response plan                                            │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 9.2.2. Risk Categories

| Kategori | Deskripsi | Contoh |
| --- | --- | --- |
| Teknis | Risiko terkait teknologi dan implementasi | Performance issues, integration failures, security vulnerabilities |
| Manajemen | Risiko terkait manajemen proyek | Schedule slip, budget overrun, scope creep |
| Sumber Daya | Risiko terkait tim dan infrastruktur | Key resource leaving, skill gap, infrastructure failure |
| Eksternal | Risiko di luar kendali proyek | Regulasi, vendor, market changes |
| Domain | Risiko terkait domain manufaktur | Data inaccuracies, process misalignment |

### 9.3. Risk Identification

#### 9.3.1. Risk Identification Methods

| Metode | Deskripsi | Frekuensi | Owner |
| --- | --- | --- | --- |
| Brainstorming | Sesi dengan tim proyek untuk mengidentifikasi risiko | Awal proyek & setiap sprint | PM |
| Checklist | Menggunakan checklist risiko dari proyek sebelumnya | Setiap sprint | PM |
| SWOT Analysis | Analisis Strength, Weakness, Opportunity, Threat | Awal proyek | PM + Tech Lead |
| Expert Interview | Wawancara dengan domain expert | Awal proyek | BA |
| Risk Breakdown Structure | Identifikasi risiko berdasarkan kategori | Awal proyek | PM |

#### 9.3.2. Risk Register

A. TEKNIS RISKS

| ID | Risiko | Penyebab | Dampak | Probabilitas | Dampak Nilai | Skor | Strategi |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | MRP Engine Performance | Data volume besar, kompleksitas BOM multi-level | MRP computation > 10 detik | 3 (Medium) | 4 (High) | 12 | Mitigate |
| R-02 | Mobile App Offline Sync Conflict | Konflik data saat sinkronisasi offline | Data inconsistency, duplicate records | 2 (Low) | 5 (Very High) | 10 | Mitigate |
| R-03 | BOM Circular Dependency | BOM saling merujuk (A membutuhkan B, B membutuhkan A) | System crash, infinite loop | 3 (Medium) | 4 (High) | 12 | Mitigate |
| R-04 | Integration API Performance | API dari proyek lain lambat/responsif | System bottleneck, user waiting > 2 detik | 4 (High) | 4 (High) | 16 | Mitigate |
| R-05 | Event Bus Failure | Kafka down, event loss | Sistem tidak terintegrasi, data tidak sinkron | 2 (Low) | 5 (Very High) | 10 | Mitigate |
| R-06 | Security Vulnerability | Celah keamanan di sistem | Data breach, unauthorized access | 2 (Low) | 5 (Very High) | 10 | Mitigate |

B. MANAJEMEN RISKS

| ID | Risiko | Penyebab | Dampak | Probabilitas | Dampak Nilai | Skor | Strategi |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-07 | Scope Creep | User meminta fitur di luar scope | Schedule slip, budget overrun | 5 (Very High) | 4 (High) | 20 | Mitigate |
| R-08 | Key Resource Leaving | Developer kunci resign dari proyek | Schedule delay, knowledge loss | 3 (Medium) | 5 (Very High) | 15 | Mitigate |
| R-09 | Budget Overrun | Biaya lebih tinggi dari estimasi | Project not completed, scope reduction | 3 (Medium) | 4 (High) | 12 | Mitigate |
| R-10 | Schedule Slip | Estimasi tidak akurat, dependency delay | Proyek tidak selesai tepat waktu | 4 (High) | 4 (High) | 16 | Mitigate |
| R-11 | Communication Breakdown | Komunikasi yang buruk antar tim | Misunderstanding, delay, rework | 3 (Medium) | 4 (High) | 12 | Mitigate |

C. SUMBER DAYA RISKS

| ID | Risiko | Penyebab | Dampak | Probabilitas | Dampak Nilai | Skor | Strategi |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-12 | Skill Gap | Tim tidak memiliki skill yang diperlukan | Schedule delay, kualitas rendah | 3 (Medium) | 4 (High) | 12 | Mitigate |
| R-13 | Infrastructure Failure | Cloud outage, server down | Sistem tidak bisa diakses, delay | 1 (Very Low) | 5 (Very High) | 5 | Transfer |
| R-14 | Environment Inconsistency | Perbedaan dev-staging-production | Bug di production, deployment failed | 4 (High) | 3 (Medium) | 12 | Mitigate |

D. EKSTERNAL RISKS

| ID | Risiko | Penyebab | Dampak | Probabilitas | Dampak Nilai | Skor | Strategi |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-15 | Dependency Delay | Proyek lain (P-FNE-03, P-FNE-06) terlambat | Integration delay, schedule slip | 4 (High) | 4 (High) | 16 | Mitigate |
| R-16 | Regulatory Change | Perubahan regulasi pemerintah | Fitur harus diubah, compliance issue | 1 (Very Low) | 4 (High) | 4 | Accept |
| R-17 | Vendor Failure | Vendor cloud/provider down | Sistem tidak bisa diakses | 1 (Very Low) | 5 (Very High) | 5 | Transfer |

E. DOMAIN RISKS

| ID | Risiko | Penyebab | Dampak | Probabilitas | Dampak Nilai | Skor | Strategi |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-18 | Data Inaccuracy | Data material, BOM tidak akurat | MRP salah, produksi tidak sesuai | 4 (High) | 4 (High) | 16 | Mitigate |
| R-19 | Process Misalignment | Fitur tidak sesuai proses bisnis | User tidak pakai sistem | 3 (Medium) | 4 (High) | 12 | Mitigate |
| R-20 | User Adoption | User tidak mau menggunakan sistem | Investasi sia-sia, manual process tetap jalan | 4 (High) | 3 (Medium) | 12 | Mitigate |

### 9.4. Risk Analysis

#### 9.4.1. Probability-Impact Matrix

| Probability | Very Low (1) | Low (2) | Medium (3) | High (4) | Very High (5) |
| --- | --- | --- | --- | --- | --- |
| Very High (5) | 5 | 10 | 15 | 20 | 25 |
| High (4) | 4 | 8 | 12 | 16 | 20 |
| Medium (3) | 3 | 6 | 9 | 12 | 15 |
| Low (2) | 2 | 4 | 6 | 8 | 10 |
| Very Low (1) | 1 | 2 | 3 | 4 | 5 |

Color Code:

- 🔴 High (12-25): Prioritaskan respons risiko

- 🟡 Medium (6-11): Kelola risiko sesuai kemampuan

- 🟢 Low (1-5): Monitor risiko, tidak perlu tindakan khusus

#### 9.4.2. Risk Priority Ranking

| Rank | ID | Risk | Skor | Kategori |
| --- | --- | --- | --- | --- |
| 1 | R-07 | Scope Creep | 20 | Manajemen |
| 2 | R-04 | Integration API Performance | 16 | Teknis |
| 3 | R-10 | Schedule Slip | 16 | Manajemen |
| 4 | R-15 | Dependency Delay | 16 | Eksternal |
| 5 | R-18 | Data Inaccuracy | 16 | Domain |
| 6 | R-08 | Key Resource Leaving | 15 | Manajemen |
| 7 | R-01 | MRP Engine Performance | 12 | Teknis |
| 8 | R-03 | BOM Circular Dependency | 12 | Teknis |
| 9 | R-09 | Budget Overrun | 12 | Manajemen |
| 10 | R-11 | Communication Breakdown | 12 | Manajemen |
| 11 | R-12 | Skill Gap | 12 | Sumber Daya |
| 12 | R-14 | Environment Inconsistency | 12 | Sumber Daya |
| 13 | R-19 | Process Misalignment | 12 | Domain |
| 14 | R-20 | User Adoption | 12 | Domain |
| 15 | R-02 | Offline Sync Conflict | 10 | Teknis |
| 16 | R-05 | Event Bus Failure | 10 | Teknis |
| 17 | R-06 | Security Vulnerability | 10 | Teknis |
| 18 | R-13 | Infrastructure Failure | 5 | Sumber Daya |
| 19 | R-17 | Vendor Failure | 5 | Eksternal |
| 20 | R-16 | Regulatory Change | 4 | Eksternal |

### 9.5. Risk Response Planning

#### 9.5.1. Risk Response for Top 5 Risks

R-07: Scope Creep (Skor 20)

| Aspek | Keterangan |
| --- | --- |
| Strategi | Mitigate |
| Respons | • Perketat proses change control • Setiap perubahan harus melalui CCB • Dokumentasi scope yang jelas • Stakeholder alignment sejak awal |
| Trigger | • Ada permintaan fitur baru • User meminta perubahan di tengah sprint |
| Action Plan | 1. Submit change request 2. Analisis dampak 3. CCB review 4. Decision & implementation |
| Owner | PM |
| Timeline | Sepanjang proyek |

R-04: Integration API Performance (Skor 16)

| Aspek | Keterangan |
| --- | --- |
| Strategi | Mitigate |
| Respons | • Early integration testing • Performance testing • Caching strategy • Async communication where possible |
| Trigger | • API response > 1 detik • Integration test gagal |
| Action Plan | 1. Test API performance 2. Implement caching 3. Optimize integration 4. Retest |
| Owner | Tech Lead + BE Team |
| Timeline | S3-S10 |

R-10: Schedule Slip (Skor 16)

| Aspek | Keterangan |
| --- | --- |
| Strategi | Mitigate |
| Respons | • Buffer time dalam schedule • Continuous monitoring (burndown) • Priority management • Early risk identification |
| Trigger | • Burndown di atas ideal line • SPI < 0.8 |
| Action Plan | 1. Review schedule 2. Re-prioritize backlog 3. Adjust resource allocation 4. Communication |
| Owner | PM |
| Timeline | Sepanjang proyek |

R-15: Dependency Delay (Skor 16)

| Aspek | Keterangan |
| --- | --- |
| Strategi | Mitigate |
| Respons | • Early integration • Mocking services • Regular sync dengan tim lain • Escalation plan |
| Trigger | • API tidak tersedia di jadwal • Integration schedule changed |
| Action Plan | 1. Identify dependencies 2. Create mock services 3. Regular sync meeting 4. Escalate if needed |
| Owner | Tech Lead |
| Timeline | S1-S10 |

R-18: Data Inaccuracy (Skor 16)

| Aspek | Keterangan |
| --- | --- |
| Strategi | Mitigate |
| Respons | • Data validation • Audit trail • User training • Data cleansing process |
| Trigger | • User reports incorrect data • Validation fails |
| Action Plan | 1. Validate data entry 2. Implement validation rules 3. User training 4. Data audit |
| Owner | BA + Tech Lead |
| Timeline | S1-S12 |

#### 9.5.2. Risk Response Matrix

| ID | Risk | Skor | Strategi | Respons | Owner | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| R-07 | Scope Creep | 20 | Mitigate | Change Control Process | PM | S1-S12 |
| R-04 | Integration API Performance | 16 | Mitigate | Performance Testing, Caching | Tech Lead | S3-S10 |
| R-10 | Schedule Slip | 16 | Mitigate | Buffer, Monitoring | PM | S1-S12 |
| R-15 | Dependency Delay | 16 | Mitigate | Mocking, Regular Sync | Tech Lead | S1-S10 |
| R-18 | Data Inaccuracy | 16 | Mitigate | Validation, Audit | BA + TL | S1-S12 |
| R-08 | Key Resource Leaving | 15 | Mitigate | Knowledge Sharing, Docs | PM | S1-S12 |
| R-01 | MRP Engine Performance | 12 | Mitigate | Optimization, Indexing | BE Team | S3-S5 |
| R-03 | BOM Circular Dependency | 12 | Mitigate | Validation Algorithm | BE Team | S2-S3 |
| R-09 | Budget Overrun | 12 | Mitigate | Budget Tracking | PM | S1-S12 |
| R-11 | Communication Breakdown | 12 | Mitigate | Communication Plan | PM | S1-S12 |
| R-12 | Skill Gap | 12 | Mitigate | Training, Mentoring | TL | S1-S3 |
| R-14 | Environment Inconsistency | 12 | Mitigate | IaC, Consistent Config | DevOps | S1-S12 |
| R-19 | Process Misalignment | 12 | Mitigate | Domain Expert Involvement | BA | S1-S12 |
| R-20 | User Adoption | 12 | Mitigate | Early Involvement, Training | BA | S5-S12 |
| R-02 | Offline Sync Conflict | 10 | Mitigate | Conflict Resolution Strategy | FE Team | S5-S8 |
| R-05 | Event Bus Failure | 10 | Mitigate | Kafka Cluster, Retry | DevOps | S1-S12 |
| R-06 | Security Vulnerability | 10 | Mitigate | Security Audit, Pen-test | DevOps | S5-S10 |
| R-13 | Infrastructure Failure | 5 | Transfer | Cloud Provider (SLA) | DevOps | S1-S12 |
| R-17 | Vendor Failure | 5 | Transfer | Multiple Vendors | DevOps | S1-S12 |
| R-16 | Regulatory Change | 4 | Accept | Monitor Regulatory | BA | S1-S12 |

### 9.6. Risk Monitoring & Control

#### 9.6.1. Risk Review Schedule

| Aktivitas | Frekuensi | Owner | Output |
| --- | --- | --- | --- |
| Risk Review | Setiap sprint | PM | Updated Risk Register |
| Risk Status Update | Setiap sprint | PM | Risk Report |
| Risk Trigger Monitoring | Harian | PM + Tech Lead | Trigger Status |
| Risk Response Status | Setiap sprint | PM | Response Status |
| Risk Audit | Setiap milestone | PM | Audit Report |

#### 9.6.2. Risk Reporting

| Report | Audience | Frequency | Method |
| --- | --- | --- | --- |
| Top 5 Risks | PM + Tech Lead | Mingguan | Dashboard |
| Risk Status Report | Program Manager | Sprint | Status Report |
| Risk Register Update | Tim | Sprint | Jira/Confluence |
| Escalation Report | Sponsor | Saat diperlukan | Email/Meeting |

#### 9.6.3. Risk Response Trigger

| Risk | Trigger | Action |
| --- | --- | --- |
| R-07: Scope Creep | New feature request from user | Submit Change Request |
| R-10: Schedule Slip | Burndown > 20% above ideal line | Review schedule, add resources |
| R-15: Dependency Delay | API not ready | Use mock services, escalate |
| R-08: Key Resource Leaving | Team member announces resignation | Knowledge transfer, hire replacement |
| R-04: Integration Performance | API response > 1 detik | Implement caching, optimize |
| R-05: Event Bus Failure | Kafka down | Retry, fallback, alert |
| R-01: MRP Performance | MRP computation > 10 detik | Optimize query, add indexes |

### 9.7. Contingency Reserve

#### 9.7.1. Contingency Reserve Allocation

| Risk Category | Contingency (Rp) | Trigger |
| --- | --- | --- |
| Teknis | 150.000.000 | Performance issue, integration failure |
| Manajemen | 150.000.000 | Schedule slip, budget overrun |
| Sumber Daya | 50.000.000 | Resource replacement, training |
| Eksternal | 50.000.000 | Vendor failure, dependency delay |
| Domain | 17.200.000 | Data issues, process misalignment |
| Total | 417.200.000 |  |

#### 9.7.2. Contingency Usage Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                    CONTINGENCY USAGE PROCESS                            │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Risk Event Occurs                                                   │

│         │                                                              │

│         ▼                                                              │

│  2. Assess Impact and Need                                             │

│         │                                                              │

│         ▼                                                              │

│  3. Submit Contingency Request                                         │

│     - Justifikasi kebutuhan                                            │

│     - Estimasi biaya                                                   │

│     - Impact jika tidak digunakan                                      │

│         │                                                              │

│         ▼                                                              │

│  4. Review oleh PM + Program Manager                                   │

│         │                                                              │

│         ▼                                                              │

│  5. Approval/Rejection                                                 │

│         │                                                              │

│         ▼ (Approved)                                                   │

│  6. Implementasi                                                       │

│         │                                                              │

│         ▼                                                              │

│  7. Update Risk Register                                               │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 9.8. Risk Response Budget

#### 9.8.1. Risk Response Cost

| ID | Risk | Response Action | Estimated Cost (Rp) |
| --- | --- | --- | --- |
| R-01 | MRP Performance | Performance optimization | 20.000.000 |
| R-02 | Offline Sync Conflict | Sync conflict resolution | 15.000.000 |
| R-03 | BOM Circular Dependency | Validation algorithm | 10.000.000 |
| R-04 | Integration API Performance | Caching, optimization | 25.000.000 |
| R-05 | Event Bus Failure | Kafka cluster | 30.000.000 |
| R-06 | Security Vulnerability | Security audit | 20.000.000 |
| R-07 | Scope Creep | Change control process | 5.000.000 |
| R-08 | Key Resource Leaving | Knowledge transfer | 10.000.000 |
| R-10 | Schedule Slip | Buffer time | 25.000.000 |
| R-12 | Skill Gap | Training | 20.000.000 |
| R-14 | Environment Inconsistency | IaC setup | 15.000.000 |
| R-15 | Dependency Delay | Mock services | 20.000.000 |
| R-18 | Data Inaccuracy | Data validation | 15.000.000 |
| R-19 | Process Misalignment | Domain expert involvement | 15.000.000 |
| R-20 | User Adoption | Training, early involvement | 25.000.000 |
| Total Risk Response Cost |  | 270.000.000 |  |

#### 9.8.2. Risk Reserve Allocation

| Reserve Type | Amount (Rp) | Purpose |
| --- | --- | --- |
| Contingency Reserve | 417.200.000 | Responding to identified risks |
| Management Reserve | 100.000.000 | Unknown unknowns |
| Total Reserve | 517.200.000 |  |

### 9.9. Risk Audit

#### 9.9.1. Risk Audit Schedule

| Audit Area | Frequency | Auditor | Scope |
| --- | --- | --- | --- |
| Risk Management Process | Bulanan | Program Manager | Process adherence |
| Risk Register Accuracy | Bulanan | PM | Risk register review |
| Risk Response Effectiveness | Setiap milestone | PM | Response status |
| Risk Communication | Bulanan | PM | Communication with stakeholders |

#### 9.9.2. Risk Management Maturity Assessment

| Level | Deskripsi | Target |
| --- | --- | --- |
| Level 1 | Ad-hoc risk management | - |
| Level 2 | Process defined | ✅ |
| Level 3 | Process integrated | ✅ (Target) |
| Level 4 | Process measured | ✅ (Target) |
| Level 5 | Continuous improvement | - |

### 9.10. Risk Management Tools

| Tool | Function |
| --- | --- |
| Jira | Risk tracking, issue management |
| Confluence | Risk register, risk documentation |
| Excel/Google Sheets | Risk analysis, probability-impact matrix |
| Miro | Risk brainstorming, risk mapping |
| Teams | Risk communication, meeting |

### 9.11. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |

# BAB 10: MANAJEMEN PENGADAAN PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 10.1. Pendahuluan

Manajemen pengadaan proyek adalah proses yang memastikan bahwa produk dan jasa yang diperlukan untuk proyek diperoleh dari pihak eksternal dengan cara yang efektif dan efisien. Area ini mencakup perencanaan pengadaan, pelaksanaan pengadaan, pengendalian pengadaan, dan penutupan pengadaan.

Dalam konteks P-FNE-04, manajemen pengadaan sangat penting karena proyek ini membutuhkan berbagai sumber daya eksternal seperti infrastruktur cloud, lisensi software, perangkat keras, dan jasa konsultasi/pelatihan. Pengadaan yang efektif akan memastikan ketersediaan sumber daya tepat waktu dan sesuai anggaran.

### 10.2. Procurement Management Plan

#### 10.2.1. Procurement Strategy

Proyek P-FNE-04 menggunakan pendekatan pengadaan sebagai berikut:

| Strategi | Deskripsi | Penerapan |
| --- | --- | --- |
| Make-or-Buy Analysis | Evaluasi apakah membuat sendiri atau membeli | Software komponen: open source vs commercial |
| Vendor Selection | Pemilihan vendor berdasarkan kriteria tertentu | Cloud services, database licenses, training |
| Contract Type | Jenis kontrak yang digunakan | Fixed Price, Time & Material, Subscription |
| Risk Allocation | Alokasi risiko antara pembeli dan penjual | SLA, warranty, penalty clauses |

#### 10.2.2. Procurement Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                        PROCUREMENT PROCESS                              │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Identifikasi Kebutuhan                                              │

│     - Identifikasi barang/jasa yang dibutuhkan                         │

│     - Spesifikasi teknis dan fungsional                                │

│     - Estimasi biaya                                                   │

│         │                                                              │

│         ▼                                                              │

│  2. Make-or-Buy Analysis                                                │

│     - Evaluasi membuat sendiri vs membeli                              │

│     - Analisis biaya-manfaat                                           │

│         │                                                              │

│         ▼                                                              │

│  3. Procurement Planning                                                │

│     - Menentukan metode pengadaan                                      │

│     - Menyusun RFP/RFQ                                                 │

│     - Menentukan kriteria evaluasi                                     │

│         │                                                              │

│         ▼                                                              │

│  4. Vendor Selection                                                    │

│     - Mengirim RFP/RFQ ke vendor                                       │

│     - Evaluasi proposal                                                │

│     - Negosiasi kontrak                                                │

│         │                                                              │

│         ▼                                                              │

│  5. Contract Award                                                      │

│     - Pemilihan vendor terpilih                                        │

│     - Penandatanganan kontrak                                          │

│         │                                                              │

│         ▼                                                              │

│  6. Contract Administration                                            │

│     - Monitoring kinerja vendor                                        │

│     - Pengendalian perubahan                                           │

│     - Pembayaran                                                       │

│         │                                                              │

│         ▼                                                              │

│  7. Contract Closure                                                    │

│     - Verifikasi penerimaan                                            │

│     - Penutupan kontrak                                                │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 10.3. Make-or-Buy Analysis

#### 10.3.1. Make-or-Buy Decisions

| No | Item | Keputusan | Alasan |
| --- | --- | --- | --- |
| 1 | Infrastructure Cloud | Buy (SaaS) | Lebih efisien, scale sesuai kebutuhan |
| 2 | Database (PostgreSQL, TimescaleDB, Neo4j) | Buy + Open Source | PostgreSQL/TimescaleDB open source, Neo4j commercial |
| 3 | API Gateway | Buy (Open Source) | Kong/Traefik open source |
| 4 | CI/CD Tools | Buy (SaaS) | GitLab CI / GitHub Actions |
| 5 | Monitoring Tools | Buy (Open Source) | Prometheus/Grafana open source |
| 6 | Logging Tools | Buy (Open Source + SaaS) | ELK Stack open source |
| 7 | Development Workstations | Buy | Perangkat keras untuk tim |
| 8 | Mobile Testing Devices | Buy | Perangkat untuk testing |
| 9 | Training Services | Buy | Jasa pelatihan eksternal |
| 10 | Documentation Services | Make | Dibuat internal oleh tim |

### 10.4. Procurement Items

#### 10.4.1. Infrastructure Procurement

| No | Item | Spesifikasi | Qty | Estimasi Biaya (Rp) | Metode | Vendor |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Cloud Infrastructure | AWS/GCP (Dev, Staging, Production) | 3 env | 300.000.000 | Subscription | AWS/GCP |
| 2 | Database License | Neo4j Enterprise | 1 | 75.000.000 | Annual | Neo4j |
| 3 | API Gateway | Kong Enterprise / Traefik | 1 | 50.000.000 | License | Kong/Traefik |
| 4 | CI/CD Platform | GitLab Premium / GitHub Enterprise | 1 | 40.000.000 | Subscription | GitLab/GitHub |
| 5 | Monitoring Tools | Prometheus + Grafana Enterprise | 1 | 30.000.000 | License | Grafana Labs |
| 6 | ELK Stack | Elastic Stack | 1 | 50.000.000 | License | Elastic |
| 7 | Test Automation Tools | Selenium, k6, OWASP ZAP | - | 30.000.000 | License | Various |

#### 10.4.2. Hardware Procurement

| No | Item | Spesifikasi | Qty | Estimasi Biaya (Rp) | Metode | Vendor |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Development Workstations | Laptop/PC (i7/32GB/512GB) | 12 | 180.000.000 | Purchase | Dell/Apple |
| 2 | Mobile Testing Devices | iOS, Android devices | 5 | 50.000.000 | Purchase | Apple/Samsung |
| 3 | External Monitors | 27" 4K Monitor | 12 | 30.000.000 | Purchase | LG/Dell |

#### 10.4.3. Services Procurement

| No | Item | Spesifikasi | Qty | Estimasi Biaya (Rp) | Metode | Vendor |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Technical Training | Spring Boot, React, Flutter | 5 sessions | 30.000.000 | Fixed Price | Training Provider |
| 2 | Domain Training | Production & Manufacturing | 3 sessions | 25.000.000 | Fixed Price | Training Provider |
| 3 | Security Audit | Penetration Testing | 1 | 20.000.000 | Fixed Price | Security Consultant |
| 4 | Performance Audit | Performance Testing | 1 | 15.000.000 | Fixed Price | Performance Consultant |

#### 10.4.4. Software/License Procurement

| No | Item | Spesifikasi | Qty | Estimasi Biaya (Rp) | Metode | Vendor |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Jira Software | Project Management | 12 | 12.000.000 | Subscription | Atlassian |
| 2 | Confluence | Documentation | 12 | 6.000.000 | Subscription | Atlassian |
| 3 | Microsoft Teams | Communication | 12 | 6.000.000 | Subscription | Microsoft |
| 4 | Google Workspace | Email, Docs | 12 | 6.000.000 | Subscription | Google |
| 5 | Figma | UI/UX Design | 5 | 10.000.000 | Subscription | Figma |
| 6 | SonarQube | Code Quality | 1 | 20.000.000 | License | SonarQube |

### 10.5. Vendor Selection

#### 10.5.1. Vendor Selection Criteria

| Kriteria | Bobot (%) | Deskripsi |
| --- | --- | --- |
| Technical Capability | 30% | Kemampuan teknis vendor, pengalaman, sertifikasi |
| Cost | 25% | Harga kompetitif, value for money |
| Experience | 20% | Pengalaman di proyek sejenis, referensi |
| Timeline | 15% | Kemampuan memenuhi jadwal |
| Support & Maintenance | 10% | Kualitas support, SLA, maintenance |

#### 10.5.2. Vendor Evaluation Matrix

Contoh: Cloud Infrastructure Vendor Evaluation

| Kriteria | Bobot | AWS | GCP | Azure |
| --- | --- | --- | --- | --- |
| Technical Capability | 30% | 9 | 8 | 8 |
| Cost | 25% | 7 | 8 | 8 |
| Experience | 20% | 9 | 8 | 8 |
| Timeline | 15% | 9 | 9 | 9 |
| Support & Maintenance | 10% | 8 | 8 | 8 |
| Score |  | 8.3 | 8.2 | 8.2 |

Keputusan: AWS terpilih sebagai vendor cloud infrastructure.

#### 10.5.3. Vendor Shortlist

| Item | Vendor Shortlist | Vendor Terpilih |
| --- | --- | --- |
| Cloud Infrastructure | AWS, GCP, Azure | AWS |
| Database (Neo4j) | Neo4j, Memgraph | Neo4j |
| Project Management | Jira, ClickUp, Asana | Jira |
| CI/CD | GitLab, GitHub, Jenkins | GitLab |
| Development Workstations | Dell, Lenovo, Apple | Dell |
| Training | E&Y, PwC, Local Provider | Local Provider |

### 10.6. Procurement Documents

#### 10.6.1. Request for Proposal (RFP) Template

text

REQUEST FOR PROPOSAL (RFP)

================================================================================

PROJECT: P-FNE-04: Production & Manufacturing

PROCUREMENT ITEM: [Item Name]

DATE: [Date]

RFP NUMBER: RFP-XXXX

1. EXECUTIVE SUMMARY

================================================================================

[Deskripsi singkat tentang kebutuhan dan latar belakang]

2. COMPANY BACKGROUND

================================================================================

[Nama Perusahaan] adalah perusahaan agribisnis terintegrasi yang sedang

mengembangkan Super ERP. Proyek P-FNE-04 adalah modul Production & Manufacturing.

3. SCOPE OF WORK

================================================================================

[Deskripsi detail pekerjaan yang diperlukan]

4. TECHNICAL REQUIREMENTS

================================================================================

[Spesifikasi teknis yang diperlukan]

5. DELIVERABLES

================================================================================

[List deliverables yang diharapkan]

6. TIMELINE

================================================================================

[Timeline proyek yang diharapkan]

7. QUALIFICATION REQUIREMENTS

================================================================================

[Kualifikasi vendor yang diperlukan]

8. EVALUATION CRITERIA

================================================================================

[Kriteria evaluasi dengan bobot]

9. PROPOSAL SUBMISSION

================================================================================

• Submission Deadline: [Tanggal]

• Submission Method: [Email/Portal]

• Contact Person: [Nama, Email, Phone]

10. ATTACHMENTS

================================================================================

[Lampiran yang diperlukan]

#### 10.6.2. Contract Template

text

KONTRAK KERJA SAMA

================================================================================

NOMOR: [Nomor Kontrak]

TANGGAL: [Tanggal]

ANTARA:

[Perusahaan]/[Project Owner]

Alamat: [Alamat]

Diwakili oleh: [Nama, Jabatan]

Selanjutnya disebut sebagai: "PIHAK PERTAMA"

DAN:

[Vendor]

Alamat: [Alamat]

Diwakili oleh: [Nama, Jabatan]

Selanjutnya disebut sebagai: "PIHAK KEDUA"

PASAL 1: RUANG LINGKUP PEKERJAAN

================================================================================

[Deskripsi ruang lingkup pekerjaan]

PASAL 2: JANGKA WAKTU PELAKSANAAN

================================================================================

[Durasi dan jadwal pelaksanaan]

PASAL 3: NILAI KONTRAK DAN CARA PEMBAYARAN

================================================================================

[Nilai kontrak dan skema pembayaran]

PASAL 4: KEWAJIBAN PIHAK PERTAMA

================================================================================

[Kewajiban dari pihak pertama]

PASAL 5: KEWAJIBAN PIHAK KEDUA

================================================================================

[Kewajiban dari pihak kedua]

PASAL 6: PENYERAHAN HASIL PEKERJAAN

================================================================================

[Proses penyerahan dan acceptance]

PASAL 7: JAMINAN (WARRANTY)

================================================================================

[Masa garansi dan cakupan]

PASAL 8: KERAHASIAAN

================================================================================

[Klausul kerahasiaan]

PASAL 9: SANKSI DAN DENDA

================================================================================

[Klausul sanksi dan denda]

PASAL 10: PEMUTUSAN KONTRAK

================================================================================

[Klausul pemutusan kontrak]

PASAL 11: PENYELESAIAN SENGKETA

================================================================================

[Klausul penyelesaian sengketa]

PASAL 12: LAIN-LAIN

================================================================================

[Klausul tambahan]

Demikian kontrak ini dibuat dan ditandatangani oleh kedua belah pihak pada tanggal

tersebut di atas dalam rangkap 2 (dua) yang masing-masing mempunyai kekuatan hukum

yang sama.

PIHAK PERTAMA,              PIHAK KEDUA,

[Nama]                      [Nama]

[Jabatan]                   [Jabatan]

[Stempel]                   [Stempel]

### 10.7. Contract Management

#### 10.7.1. Contract Types

| Contract Type | Deskripsi | Penggunaan |
| --- | --- | --- |
| Fixed Price | Harga tetap sesuai scope yang disepakati | Training, Security Audit |
| Subscription | Pembayaran periodik untuk layanan berkelanjutan | Cloud, Software licenses |
| Time & Material | Pembayaran berdasarkan waktu dan material | Support, Maintenance |
| Purchase Order | Pembelian barang langsung | Workstations, Devices |

#### 10.7.2. Contract Administration

| Aktivitas | Owner | Frekuensi |
| --- | --- | --- |
| Monitoring vendor performance | PM | Bulanan |
| Payment processing | PM + Finance | Sesuai milestone |
| Change order management | PM | Saat diperlukan |
| Contract compliance review | PM | Bulanan |
| Issue resolution | PM | Saat terjadi |

### 10.8. Procurement Budget

#### 10.8.1. Procurement Budget by Category

| Kategori | Item | Biaya (Rp) |
| --- | --- | --- |
| Infrastructure | Cloud Services | 300.000.000 |
|  | Database License | 75.000.000 |
|  | API Gateway | 50.000.000 |
|  | CI/CD Platform | 40.000.000 |
|  | Monitoring Tools | 30.000.000 |
|  | ELK Stack | 50.000.000 |
|  | Test Automation Tools | 30.000.000 |
| Hardware | Development Workstations | 180.000.000 |
|  | Mobile Testing Devices | 50.000.000 |
|  | External Monitors | 30.000.000 |
| Services | Technical Training | 30.000.000 |
|  | Domain Training | 25.000.000 |
|  | Security Audit | 20.000.000 |
|  | Performance Audit | 15.000.000 |
| Software | Jira Software | 12.000.000 |
|  | Confluence | 6.000.000 |
|  | Microsoft Teams | 6.000.000 |
|  | Google Workspace | 6.000.000 |
|  | Figma | 10.000.000 |
|  | SonarQube | 20.000.000 |
| Total Procurement Budget |  | 985.000.000 |

### 10.9. Procurement Schedule

| No | Item | Target Start | Target End | Owner |
| --- | --- | --- | --- | --- |
| 1 | Cloud Infrastructure | 1 Okt 2026 | 15 Okt 2026 | DevOps |
| 2 | Database License | 1 Okt 2026 | 15 Okt 2026 | DevOps |
| 3 | CI/CD Platform | 1 Okt 2026 | 15 Okt 2026 | DevOps |
| 4 | Development Workstations | 1 Okt 2026 | 15 Okt 2026 | IT |
| 5 | Mobile Testing Devices | 15 Okt 2026 | 31 Okt 2026 | QA |
| 6 | Technical Training | 1 Okt 2026 | 31 Okt 2026 | PM |
| 7 | Domain Training | 1 Okt 2026 | 15 Okt 2026 | BA |
| 8 | Jira/Confluence | 1 Okt 2026 | 15 Okt 2026 | PM |
| 9 | Security Audit | 1 Feb 2027 | 28 Feb 2027 | DevOps |
| 10 | Performance Audit | 1 Feb 2027 | 28 Feb 2027 | QA |

### 10.10. Risk in Procurement

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Vendor tidak memenuhi deadline | Medium | High | SLA dengan penalty, backup vendor |
| Vendor tidak memenuhi spesifikasi | Medium | High | Acceptance criteria, UAT, warranty |
| Vendor mengalami kebangkrutan | Low | Very High | Due diligence, multiple vendors |
| Harga naik di luar estimasi | Medium | Medium | Fixed price contract, price escalation clause |
| Masalah integrasi dengan vendor | Medium | High | Integration testing, support from vendor |

### 10.11. Procurement Tools

| Tool | Function |
| --- | --- |
| Jira | Procurement tracking, issue management |
| Confluence | Procurement documentation |
| Google Sheets | Procurement budget tracking |
| Teams | Vendor communication |
| e-Procurement Platform | RFP/RFQ management (jika tersedia) |

### 10.12. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Procurement |  |  |  |
| Finance |  |  |  |
| Sponsor |  |  |  |

# BAB 11: MANAJEMEN PEMANGKU KEPENTINGAN PROYEK

## PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

### 11.1. Pendahuluan

Manajemen pemangku kepentingan proyek adalah proses yang memastikan bahwa semua pihak yang berkepentingan dengan proyek diidentifikasi, dipahami, dan dilibatkan secara tepat untuk memaksimalkan dukungan dan meminimalkan resistensi. Area ini mencakup identifikasi pemangku kepentingan, perencanaan keterlibatan pemangku kepentingan, pengelolaan keterlibatan, dan pemantauan keterlibatan pemangku kepentingan.

Dalam konteks P-FNE-04, manajemen pemangku kepentingan sangat kritis karena proyek ini:

- Melibatkan banyak pihak dengan kepentingan berbeda

- Akan digunakan oleh berbagai level organisasi (operator hingga direksi)

- Berintegrasi dengan 7 proyek turunan lainnya

- Memiliki dampak signifikan terhadap operasional perusahaan

### 11.2. Stakeholder Identification

#### 11.2.1. Stakeholder Identification Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                   STAKEHOLDER IDENTIFICATION PROCESS                    │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Identifikasi Stakeholder                                            │

│     - Brainstorming dengan tim                                          │

│     - Review organisasi perusahaan                                     │

│     - Wawancara dengan key person                                      │

│         │                                                              │

│         ▼                                                              │

│  2. Klasifikasi Stakeholder                                             │

│     - Power/Interest Grid                                              │

│     - Influence/Impact Matrix                                          │

│         │                                                              │

│         ▼                                                              │

│  3. Analisis Stakeholder                                                │

│     - Kebutuhan dan harapan                                             │

│     - Kepentingan                                                      │

│     - Dampak terhadap proyek                                           │

│         │                                                              │

│         ▼                                                              │

│  4. Strategi Keterlibatan                                               │

│     - Pendekatan untuk setiap stakeholder                              │

│     - Metode komunikasi                                                │

│         │                                                              │

│         ▼                                                              │

│  5. Documentasi                                                        │

│     - Stakeholder Register                                             │

│     - Communication Plan                                               │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

#### 11.2.2. Stakeholder Register

A. INTERNAL STAKEHOLDERS

| ID | Stakeholder | Peran | Departemen | Interest | Influence | Power | Kebutuhan |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S-01 | CEO / Sponsor | Sponsor | Eksekutif | Tinggi | Tinggi | Tinggi | ROI, Project Success, Timeline |
| S-02 | Program Manager | Oversight | Program Office | Tinggi | Tinggi | Tinggi | Integration, Timeline, Quality |
| S-03 | Project Manager | Management | PMO | Tinggi | Tinggi | Tinggi | Project Execution |
| S-04 | Project Team | Development | IT | Tinggi | Medium | Medium | Clarity, Resources, Support |
| S-05 | Manufacturing Director | End User | Produksi | Tinggi | Tinggi | Tinggi | Features, Efficiency |
| S-06 | Production Managers | End User | Produksi | Tinggi | Medium | Medium | Usability, Accuracy |
| S-07 | Production Supervisors | End User | Produksi | Medium | Medium | Medium | Operational features |
| S-08 | Operators | End User | Produksi | Medium | Rendah | Rendah | Ease of Use, Mobile App |
| S-09 | Finance Director | End User | Keuangan | Tinggi | Tinggi | Tinggi | Cost Data, Accuracy |
| S-10 | QA Manager | End User | Quality | Tinggi | Medium | Medium | Inspection Features |
| S-11 | Maintenance Manager | End User | Maintenance | Tinggi | Medium | Medium | Asset Features |
| S-12 | Procurement Manager | End User | Supply Chain | Medium | Medium | Medium | Material Planning |

B. EXTERNAL STAKEHOLDERS

| ID | Stakeholder | Peran | Organisasi | Interest | Influence | Power | Kebutuhan |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S-13 | P-FNE-01 Team | Dependent | FNE | Tinggi | Medium | Medium | Integration, Data |
| S-14 | P-FNE-03 Team | Dependent | FNE | Tinggi | Medium | Medium | Integration, Data |
| S-15 | P-FNE-05 Team | Dependent | FNE | Tinggi | Medium | Medium | Integration, Data |
| S-16 | P-FNE-06 Team | Dependent | FNE | Tinggi | Medium | Medium | Cost Data Integration |
| S-17 | P-FNE-07 Team | Dependent | FNE | Medium | Medium | Medium | Data Integration |
| S-18 | P-FNE-08 Team | Dependent | FNE | Medium | Low | Medium | Integration |
| S-19 | Cloud Provider | Vendor | AWS/GCP | Low | Rendah | Medium | Service Delivery |
| S-20 | Software Vendors | Vendor | Various | Low | Rendah | Low | Software Delivery |

### 11.3. Stakeholder Classification

#### 11.3.1. Power/Interest Grid

text

POWER (Influence)

▲

│

│     ████████████████████

│     █ S-01: CEO/Sponsor █

│     █ S-02: Program Mgr █

│     █ S-03: Project Mgr █

│  ↑  █ S-05: Manuf Dir   █

│  │  █ S-09: Finance Dir █

│  │  █ S-10: QA Mgr      █

│  │  █ S-11: Maint Mgr   █

│  │  █ S-13: P-FNE-01    █

│  │  █ S-14: P-FNE-03    █

│  │  █ S-16: P-FNE-06    █

│  │  ████████████████████

│  │

│  │     ████████████████████

│  │     █ S-04: Project    █

│  │     █      Team        █

│  │     █ S-06: Prod Mgr   █

│  │     █ S-07: Supervisor █

│  │     █ S-08: Operators  █

│  │     █ S-12: Procurement█

│  │     ████████████████████

│  │

│  └───────────────────────────────────────────────► INTEREST

│

└─────────────────────────────────────────────────────────────────────

#### 11.3.2. Stakeholder Engagement Levels

| ID | Stakeholder | Current Engagement | Desired Engagement | Gap |
| --- | --- | --- | --- | --- |
| S-01 | CEO/Sponsor | Aware | Supportive | Gap |
| S-02 | Program Manager | Supportive | Supportive | No Gap |
| S-03 | Project Manager | Supportive | Supportive | No Gap |
| S-04 | Project Team | Supportive | Supportive | No Gap |
| S-05 | Manufacturing Director | Resistant | Supportive | Gap |
| S-06 | Production Managers | Neutral | Supportive | Gap |
| S-07 | Production Supervisors | Neutral | Supportive | Gap |
| S-08 | Operators | Unaware | Supportive | Gap |
| S-09 | Finance Director | Supportive | Supportive | No Gap |
| S-10 | QA Manager | Neutral | Supportive | Gap |
| S-11 | Maintenance Manager | Neutral | Supportive | Gap |
| S-12 | Procurement Manager | Neutral | Supportive | Gap |
| S-13 | P-FNE-01 Team | Supportive | Supportive | No Gap |
| S-14 | P-FNE-03 Team | Supportive | Supportive | No Gap |
| S-15 | P-FNE-05 Team | Neutral | Supportive | Gap |
| S-16 | P-FNE-06 Team | Supportive | Supportive | No Gap |
| S-17 | P-FNE-07 Team | Neutral | Supportive | Gap |
| S-18 | P-FNE-08 Team | Neutral | Supportive | Gap |

Engagement Levels:

- Unaware: Tidak mengetahui proyek dan dampaknya

- Resistant: Mengetahui proyek namun menolak perubahan

- Neutral: Mengetahui proyek namun tidak menunjukkan dukungan/penolakan

- Supportive: Mengetahui proyek dan mendukung keberhasilannya

- Leading: Aktif terlibat dan memimpin upaya keberhasilan proyek

### 11.4. Stakeholder Analysis

#### 11.4.1. Key Stakeholder Analysis

S-05: Manufacturing Director

| Aspek | Keterangan |
| --- | --- |
| Peran | End User, Operational Leader |
| Kepentingan | • Fitur yang sesuai dengan proses produksi • Efisiensi operasional • Kemudahan penggunaan |
| Dampak | • Key decision maker • Dapat mempengaruhi adopsi user • Memiliki pengaruh besar terhadap tim produksi |
| Strategi | • Libatkan sejak awal • Tunjukkan benefit • Demonstrasi fitur secara rutin • Berikan training khusus |
| Respons | • Resistant → Supportive |

S-08: Operators

| Aspek | Keterangan |
| --- | --- |
| Peran | End User (Mobile App) |
| Kepentingan | • Mobile app yang mudah digunakan • Offline support • Workflow yang cepat |
| Dampak | • Pengguna utama • Adopsi sistem tergantung pada mereka |
| Strategi | • Involve dalam UAT • User-friendly design • Training dan user manual • Feedback loop |
| Respons | • Unaware → Supportive |

S-14: P-FNE-03 Team

| Aspek | Keterangan |
| --- | --- |
| Peran | Dependent, Integration Partner |
| Kepentingan | • API integration yang jelas • Schedule yang terkoordinasi • Data consistency |
| Dampak | • Keterlambatan integrasi dapat mempengaruhi proyek |
| Strategi | • Regular sync meeting • Shared documentation • Early integration testing |
| Respons | • Supportive → Supportive |

### 11.5. Stakeholder Engagement Plan

#### 11.5.1. Engagement Strategies by Stakeholder

| ID | Stakeholder | Strategi | Metode | Owner | Frequency |
| --- | --- | --- | --- | --- | --- |
| S-01 | CEO/Sponsor | • Monthly progress report • Milestone demo • Strategic updates | • Presentation • Email report | PM | Bulanan |
| S-02 | Program Manager | • Weekly status meeting • Integration update • Risk review | • Meeting • Status Report | PM | Mingguan |
| S-04 | Project Team | • Daily standup • Sprint ceremonies • Knowledge sharing | • Meeting • Jira • Teams | PM | Harian |
| S-05 | Manuf. Director | • Bi-weekly meeting • Feature demo • UAT involvement | • Meeting • Demo session | BA | 2 Mingguan |
| S-06 | Prod. Managers | • Bi-weekly meeting • Feature demo • UAT involvement | • Meeting • Demo session | BA | 2 Mingguan |
| S-07 | Supervisors | • Training • UAT involvement • Feedback session | • Training • UAT • Workshop | BA | Sesuai Kebutuhan |
| S-08 | Operators | • Training • User manual • Mobile demo | • Training • User Manual • Demo | BA | Sesuai Kebutuhan |
| S-09 | Finance Dir. | • Monthly update • Costing feature demo | • Meeting • Demo | BA | Bulanan |
| S-13 | P-FNE-01 | • Regular sync • API documentation | • Meeting • Confluence | Tech Lead | Mingguan |
| S-14 | P-FNE-03 | • Regular sync • API documentation | • Meeting • Confluence | Tech Lead | 2 Mingguan |
| S-16 | P-FNE-06 | • Regular sync • Costing integration | • Meeting • Confluence | Tech Lead | 2 Mingguan |

### 11.6. Stakeholder Communication

#### 11.6.1. Communication Methods

| Method | Purpose | Stakeholders | Frequency |
| --- | --- | --- | --- |
| Monthly Steering Meeting | Strategic updates, key decisions | S-01, S-02, S-05, S-09 | Bulanan |
| Sprint Review | Feature demo, feedback | S-01, S-05, S-06, S-09 | 2 Mingguan |
| Weekly Status Meeting | Progress update | S-02, S-04 | Mingguan |
| Integration Sync | Integration coordination | S-13, S-14, S-16, S-17 | 2 Mingguan |
| UAT Session | User validation | S-05, S-06, S-07, S-08 | Sesuai Kebutuhan |
| Training | User enablement | S-07, S-08, S-10, S-11 | Sesuai Kebutuhan |
| Daily Standup | Team coordination | S-04 | Harian |

#### 11.6.2. Stakeholder Communication Content

| Stakeholder | Content | Format |
| --- | --- | --- |
| CEO/Sponsor | • Project status • Milestone achievement • Risks • Financial status | • Executive Summary • Dashboard • Presentation |
| Manufacturing Director | • Features progress • UAT schedule • Training schedule | • Demo • Report • Schedule |
| Production Managers | • Features progress • UAT schedule • Training schedule | • Demo • UAT Session • Training |
| Operators | • Mobile app features • Training schedule • User guides | • Training • User Manual • Demo |
| Integration Teams | • API status • Integration schedule • Issues | • API Documentation • Meeting • Jira |

### 11.7. Managing Stakeholder Expectations

#### 11.7.1. Expectation Management Strategies

| Expectation | Stakeholder | Strategy |
| --- | --- | --- |
| Proyek selesai tepat waktu | All | • Realistic schedule • Regular tracking • Early warning |
| Fitur sesuai kebutuhan | End Users | • Regular demo • UAT involvement • Feedback loop |
| Integrasi berjalan lancar | Integration Teams | • Regular sync • Shared documentation • Early testing |
| Biaya sesuai anggaran | Sponsor, Finance | • Budget tracking • Regular reporting • Change control |
| Sistem mudah digunakan | Operators | • User-centered design • Training • User manual |

#### 11.7.2. Managing Difficult Stakeholders

| Stakeholder | Issue | Strategy |
| --- | --- | --- |
| Manufacturing Director | Resistant to change | • Show benefits • Early involvement • Demonstrate success stories |
| Production Managers | Skeptical about system | • Involve in design • Show efficiency gains • Address concerns |
| Operators | Worried about complexity | • Simple UX • Adequate training • Support system |

### 11.8. Stakeholder Feedback Management

#### 11.8.1. Feedback Collection Methods

| Method | Purpose | Frequency | Owner |
| --- | --- | --- | --- |
| Sprint Review Feedback | Feature validation | 2 Mingguan | BA |
| UAT Feedback | System validation | Sesuai Kebutuhan | BA |
| Survey | Satisfaction measurement | Bulanan | BA |
| Meeting Notes | Issue/concern documentation | Mingguan | PM |
| Support Ticket | Issue tracking | Harian | Support |

#### 11.8.2. Feedback Resolution Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                      FEEDBACK RESOLUTION PROCESS                        │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Receive Feedback                                                    │

│     - From sprint review, UAT, meeting, support                        │

│         │                                                              │

│         ▼                                                              │

│  2. Categorize Feedback                                                │

│     - Bug: Issue with system                                           │

│     - Enhancement: Request for improvement                             │

│     - Feature: Request for new feature                                 │

│         │                                                              │

│         ▼                                                              │

│  3. Analyze Impact                                                     │

│     - Priority: Critical/Major/Minor                                   │

│     - Effort: High/Medium/Low                                          │

│         │                                                              │

│         ▼                                                              │

│  4. Action Plan                                                        │

│     - Assign owner                                                     │

│     - Timeline                                                         │

│         │                                                              │

│         ▼                                                              │

│  5. Implementation                                                     │

│     - Fix bug / Develop enhancement                                    │

│         │                                                              │

│         ▼                                                              │

│  6. Verify & Close                                                     │

│     - QA verification                                                  │

│     - Stakeholder validation                                           │

│     - Close feedback                                                   │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 11.9. Stakeholder Conflict Resolution

#### 11.9.1. Potential Conflicts

| Conflict | Stakeholders | Resolution Strategy |
| --- | --- | --- |
| Resource allocation | P-FNE-04 vs other projects | Program Manager decision |
| Feature priority | Manufacturing vs Finance | Business value assessment |
| Integration timeline | P-FNE-04 vs P-FNE-03 | Regular sync, compromise |
| System design | User vs Developer | User-centered design, compromise |

#### 11.9.2. Conflict Resolution Process

text

┌─────────────────────────────────────────────────────────────────────────┐

│                       CONFLICT RESOLUTION PROCESS                       │

├─────────────────────────────────────────────────────────────────────────┤

│                                                                         │

│  1. Identify Conflict                                                   │

│     - Issue raised by stakeholder                                       │

│         │                                                              │

│         ▼                                                              │

│  2. Understand Perspective                                              │

│     - Listen to both sides                                             │

│     - Understand underlying needs                                      │

│         │                                                              │

│         ▼                                                              │

│  3. Identify Common Ground                                              │

│     - Find areas of agreement                                          │

│     - Define shared goals                                              │

│         │                                                              │

│         ▼                                                              │

│  4. Generate Options                                                    │

│     - Brainstorm solutions                                             │

│     - Consider alternatives                                            │

│         │                                                              │

│         ▼                                                              │

│  5. Evaluate Options                                                    │

│     - Assess pros/cons                                                 │

│     - Impact analysis                                                  │

│         │                                                              │

│         ▼                                                              │

│  6. Select Solution                                                     │

│     - Mutual agreement                                                 │

│     - Document decision                                                │

│         │                                                              │

│         ▼                                                              │

│  7. Implement & Monitor                                                 │

│     - Execute solution                                                 │

│     - Monitor satisfaction                                             │

│                                                                         │

└─────────────────────────────────────────────────────────────────────────┘

### 11.10. Stakeholder Monitoring & Control

#### 11.10.1. Monitoring Activities

| Activity | Frequency | Owner | Output |
| --- | --- | --- | --- |
| Stakeholder engagement review | Sprint | PM | Engagement status |
| Satisfaction survey | Bulanan | BA | Satisfaction report |
| Issue log review | Mingguan | PM | Issue status |
| Stakeholder feedback review | Sprint | BA | Feedback summary |

#### 11.10.2. Stakeholder Engagement Metrics

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Stakeholder satisfaction | > 85% | Survey |
| Engagement level achievement | 100% | Gap analysis |
| Issue resolution time | < 48 hours | Jira metrics |
| Feedback implementation | > 80% | Feedback tracking |
| UAT participation | > 90% | Attendance tracking |

### 11.11. Stakeholder Tools

| Tool | Function |
| --- | --- |
| Jira | Issue tracking, feedback management |
| Confluence | Stakeholder register, communication plan |
| Teams | Stakeholder communication |
| Google Forms | Satisfaction survey |
| Miro | Stakeholder mapping, brainstorming |

### 11.12. Stakeholder Register Template

text

STAKEHOLDER REGISTER

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

STAKEHOLDER ID: [ID]

NAMA: [Nama Stakeholder]

PERAN: [Peran]

DEPARTEMEN: [Departemen]

A. INFORMASI STAKEHOLDER

================================================================================

• Jabatan: [Jabatan]

• Kontak: [Email, Phone]

• Keterlibatan: [Frequency, Method]

B. KEPENTINGAN DAN PENGARUH

================================================================================

• Interest Level: [Tinggi/Medium/Rendah]

• Influence Level: [Tinggi/Medium/Rendah]

• Power Level: [Tinggi/Medium/Rendah]

C. KEBUTUHAN DAN HARAPAN

================================================================================

• Kebutuhan: [List kebutuhan]

• Harapan: [List harapan]

• Wants: [List wants]

D. ENGAGEMENT

================================================================================

• Current Engagement: [Unaware/Resistant/Neutral/Supportive/Leading]

• Desired Engagement: [Unaware/Resistant/Neutral/Supportive/Leading]

• Strategy: [Strategi untuk mencapai desired engagement]

E. COMMUNICATION

================================================================================

• Communication Method: [Meeting/Email/Demo/Training]

• Frequency: [Daily/Weekly/Bi-weekly/Monthly/As needed]

• Owner: [PIC]

F. NOTES

================================================================================

• [Catatan tambahan]

• [Issues/Concerns]

• [Action items]

================================================================================

Last Updated: [Date]

Updated By: [Name]

================================================================================

### 11.13. Stakeholder Engagement Performance

#### 11.13.1. Engagement Plan

| Stakeholder | Current | Target | Actions | Deadline |
| --- | --- | --- | --- | --- |
| Manufacturing Director | Resistant | Supportive | • Early involvement • Show benefits • Regular demos | M2 |
| Production Managers | Neutral | Supportive | • Requirement workshop • Feature demos • UAT involvement | M3 |
| Operators | Unaware | Supportive | • Training • User-friendly design • Support | M5 |
| P-FNE-03 Team | Supportive | Supportive | • Regular sync • Shared roadmap | S1-S12 |

#### 11.13.2. Engagement Status Tracking

| Metric | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Manuf. Director | 🟡 | 🟡 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 |
| Prod. Managers | 🟡 | 🟡 | 🟡 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 |
| Operators | 🔴 | 🔴 | 🟡 | 🟡 | 🟡 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 | 🟢 |

Color Code:

- 🔴 Unaware/Resistant

- 🟡 Neutral

- 🟢 Supportive

- 🟣 Leading

### 11.14. Approvals

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |

Demikian Bab 11: Manajemen Pemangku Kepentingan Proyek dari Project Management Plan Proyek P-FNE-04.

# KESIMPULAN

Dokumen Project Management Plan (PMP) untuk Proyek P-FNE-04: Production & Manufacturing telah disusun secara lengkap mencakup 11 (sebelas) area manajemen proyek sesuai standar PMBOK:

- Bab 1: Pendahuluan - Latar belakang, tujuan, ruang lingkup, dan struktur organisasi proyek

- Bab 2: Manajemen Integrasi Proyek - Project charter, rencana manajemen proyek, change management

- Bab 3: Manajemen Lingkup Proyek - Scope statement, WBS, scope verification & control

- Bab 4: Manajemen Penjadwalan Proyek - Sprint planning, milestone, schedule control

- Bab 5: Manajemen Biaya Proyek - Activity Based Costing (ABC), tarif Inkindo 2026, budget control

- Bab 6: Manajemen Kualitas Proyek - Quality standards, QA/QC, performance targets

- Bab 7: Manajemen Sumber Daya Proyek - Organization structure, roles, resource planning

- Bab 8: Manajemen Komunikasi Proyek - Communication matrix, methods, reporting

- Bab 9: Manajemen Risiko Proyek - Risk register, analysis, response planning

- Bab 10: Manajemen Pengadaan Proyek - Procurement planning, vendor selection, contracts

- Bab 11: Manajemen Pemangku Kepentingan Proyek - Stakeholder identification, engagement, communication

Dokumen ini menjadi acuan utama bagi seluruh tim proyek dalam melaksanakan Proyek P-FNE-04: Production & Manufacturing Super ERP Farm Nation Enterprise.

DOKUMEN INI TELAH DISETUJUI DAN DITANDATANGANI OLEH:

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |

# LAMPIRAN

## PROJECT MANAGEMENT PLAN (PMP)

### PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

Berikut adalah lampiran-lampiran yang melengkapi Project Management Plan Proyek P-FNE-04. Lampiran ini berisi dokumen-dokumen pendukung, template, dan referensi yang digunakan dalam pelaksanaan proyek.

## LAMPIRAN A: GLOSSARY

| Istilah | Deskripsi |
| --- | --- |
| ABC | Activity Based Costing - Metode perhitungan biaya berdasarkan aktivitas |
| AC | Actual Cost - Biaya aktual yang dikeluarkan dalam proyek |
| BA | Business Analyst - Analis bisnis yang bertanggung jawab atas kebutuhan fungsional |
| BAC | Budget at Completion - Total anggaran proyek |
| BE | Backend Developer - Pengembang sisi server |
| BOM | Bill of Materials - Daftar material yang dibutuhkan untuk memproduksi suatu produk |
| CCB | Change Control Board - Tim yang menyetujui perubahan proyek |
| CI/CD | Continuous Integration/Continuous Deployment - Proses otomatisasi integrasi dan deployment |
| CPI | Cost Performance Index - Indeks kinerja biaya (EV/AC) |
| CV | Cost Variance - Selisih biaya (EV - AC) |
| DevOps | Development Operations - Praktik penggabungan pengembangan dan operasi IT |
| DoD | Definition of Done - Kriteria yang menandakan suatu pekerjaan selesai |
| DoR | Definition of Ready - Kriteria yang menandakan suatu pekerjaan siap dikerjakan |
| EAC | Estimate at Completion - Estimasi biaya pada saat proyek selesai |
| ETC | Estimate to Complete - Estimasi biaya yang tersisa |
| EV | Earned Value - Nilai pekerjaan yang telah selesai |
| EVM | Earned Value Management - Metode pengukuran kinerja proyek |
| FE | Frontend Developer - Pengembang sisi klien/antarmuka |
| FNE | Farm Nation Enterprise - Perusahaan agribisnis terintegrasi |
| IaC | Infrastructure as Code - Pengelolaan infrastruktur melalui kode |
| IAM | Identity and Access Management - Manajemen identitas dan akses |
| Inkindo | Ikatan Nasional Konsultan Indonesia - Asosiasi konsultan Indonesia |
| Kafka | Apache Kafka - Platform event streaming untuk komunikasi asynchronous |
| KPI | Key Performance Indicator - Indikator kinerja utama |
| MRP | Material Requirement Planning - Perencanaan kebutuhan material |
| MS | Manufacturing Specialist - Spesialis manufaktur |
| MTBF | Mean Time Between Failure - Rata-rata waktu antar kegagalan |
| MTTR | Mean Time To Repair - Rata-rata waktu untuk perbaikan |
| OEE | Overall Equipment Effectiveness - Efektivitas keseluruhan peralatan |
| P-FNE | Project Farm Nation Enterprise - Proyek turunan Super ERP FNE |
| PM | Project Manager - Manajer proyek |
| PMP | Project Management Plan - Rencana manajemen proyek |
| PO | Production Order - Perintah produksi |
| PV | Planned Value - Nilai pekerjaan yang direncanakan |
| QA | Quality Assurance - Jaminan kualitas |
| QC | Quality Control - Pengendalian kualitas |
| RACI | Responsible, Accountable, Consulted, Informed - Matriks tanggung jawab |
| RBAC | Role-Based Access Control - Kontrol akses berbasis peran |
| RFP | Request for Proposal - Permintaan proposal |
| RFQ | Request for Quotation - Permintaan penawaran harga |
| SLA | Service Level Agreement - Perjanjian tingkat layanan |
| SP | Story Points - Satuan estimasi dalam Agile |
| SPI | Schedule Performance Index - Indeks kinerja jadwal (EV/PV) |
| SV | Schedule Variance - Selisih jadwal (EV - PV) |
| TL | Tech Lead - Pemimpin teknis tim |
| UAT | User Acceptance Testing - Pengujian penerimaan pengguna |
| VAC | Variance at Completion - Selisih biaya pada saat selesai (BAC - EAC) |
| WBS | Work Breakdown Structure - Struktur rincian pekerjaan |
| WO | Work Order - Perintah kerja maintenance |

## LAMPIRAN B: RACI MATRIX (DETAIL)

### B.1. RACI Matrix - Inisiasi Proyek

| Aktivitas | PM | TL | BA | BE | FE | QA | DevOps | MS | Sponsor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Penyusunan Project Charter | A/R | C | C | I | I | I | I | C | A |
| Penyusunan PMP | A/R | C | C | I | I | I | I | C | A |
| Kick-off Meeting | A/R | C | C | C | C | C | C | C | A |
| Stakeholder Identification | A/R | C | R | I | I | I | I | C | I |

### B.2. RACI Matrix - Perencanaan

| Aktivitas | PM | TL | BA | BE | FE | QA | DevOps | MS | Sponsor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirement Gathering | C | C | A/R | I | I | I | I | C | I |
| System Architecture | C | A/R | C | I | I | I | C | C | I |
| Database Design | C | A/R | C | I | I | I | C | C | I |
| API Design | C | A/R | C | I | I | C | C | C | I |
| UI/UX Design | C | C | A/R | I | I | C | I | C | I |
| Sprint Planning | A/R | C | C | C | C | C | C | C | I |

### B.3. RACI Matrix - Pengembangan

| Aktivitas | PM | TL | BA | BE | FE | QA | DevOps | MS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Backend Development | C | R | C | A | I | I | I | C |
| Frontend Development | C | R | C | I | A | I | I | C |
| Mobile Development | C | R | C | I | A | I | I | C |
| Dashboard Development | C | R | C | I | A | I | I | C |
| Integration Development | C | R | C | A | I | I | I | C |
| Code Review | C | A/R | I | C | C | I | I | I |
| Unit Testing | C | R | I | A | A | I | I | I |
| Documentation | C | C | A/R | C | C | C | C | C |

### B.4. RACI Matrix - Testing & QA

| Aktivitas | PM | TL | BA | BE | FE | QA | DevOps | MS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test Planning | C | C | C | I | I | A/R | I | C |
| Integration Testing | C | C | I | C | C | A/R | C | I |
| Performance Testing | C | C | I | C | I | A/R | C | I |
| Security Testing | C | C | I | I | I | C | A/R | I |
| UAT | C | I | A/R | I | I | C | I | C |
| Regression Testing | C | C | I | I | I | A/R | I | I |

### B.5. RACI Matrix - Deployment & Closure

| Aktivitas | PM | TL | BA | BE | FE | QA | DevOps | MS | Sponsor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CI/CD Setup | C | C | I | I | I | I | A/R | I | I |
| Staging Deployment | C | C | I | C | C | C | A/R | C | I |
| Production Deployment | C | C | I | C | C | C | A/R | C | A |
| User Training | C | I | A/R | I | I | I | I | C | I |
| Project Closure | A/R | C | C | I | I | I | I | C | A |
| Lessons Learned | A/R | C | C | C | C | C | C | C | I |

## LAMPIRAN C: WORK BREAKDOWN STRUCTURE (WBS) DICTIONARY

### C.1. WBS 2.2: Production Planning Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria | Estimasi (SP) | Owner |
| --- | --- | --- | --- | --- | --- |
| 2.2.1 | Production Plan CRUD | API untuk create, read, update, delete production plan | 100% CRUD operations functional, API documentation complete | 13 | BE1 |
| 2.2.2 | MRP Engine | Perhitungan material requirement berdasarkan BOM | MRP selesai ≤10 detik untuk 100 produk, hasil akurat | 13 | BE1, BE2 |
| 2.2.3 | Capacity Planning | Pengecekan kapasitas produksi | Capacity check accurate, integration with facility data | 8 | BE2 |
| 2.2.4 | Production Scheduling | Penjadwalan production order | Schedule generation complete, Gantt view functional | 13 | BE1 |
| 2.2.5 | Production Plan Approval Flow | Workflow approval production plan | Approval matrix implemented, status tracking complete | 8 | BE1 |

### C.2. WBS 2.3: BOM Management Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria | Estimasi (SP) | Owner |
| --- | --- | --- | --- | --- | --- |
| 2.3.1 | BOM CRUD | API untuk create, read, update, delete BOM | 100% CRUD operations functional, multi-level support | 13 | BE1 |
| 2.3.2 | BOM Versioning | Versioning untuk setiap perubahan BOM | Version tracking complete, history view functional | 8 | BE2 |
| 2.3.3 | BOM Explosion | Perhitungan material requirement dari BOM | BOM explosion ≤5 detik, accurate calculation | 8 | BE1 |
| 2.3.4 | BOM Cost Rollup | Perhitungan biaya standar produk | Cost calculation complete, integration with material price | 8 | BE2 |
| 2.3.5 | Where-Used Analysis | Pencarian produk yang menggunakan material | Search functional, result accurate | 5 | BE1 |
| 2.3.6 | BOM Approval Flow | Workflow approval BOM | Approval matrix implemented, status tracking complete | 5 | BE2 |

### C.3. WBS 2.4: Production Execution Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria | Estimasi (SP) | Owner |
| --- | --- | --- | --- | --- | --- |
| 2.4.1 | Production Order CRUD | API untuk create, read, update, delete PO | 100% CRUD operations functional | 13 | BE1 |
| 2.4.2 | Material Issue Integration | Integrasi untuk mengeluarkan material dari inventory | Integration with P-FNE-03 complete, accurate stock reduction | 13 | BE1, BE2 |
| 2.4.3 | Progress Recording API | API untuk mencatat progress produksi | Real-time recording functional, offline support | 13 | BE1, BE2 |
| 2.4.4 | Quality Inspection API | API untuk inspeksi kualitas | Inspection record complete, defect rate calculation | 8 | BE2 |
| 2.4.5 | Production Completion API | API untuk menyelesaikan PO | PO completion complete, event published | 13 | BE1 |
| 2.4.6 | By-Product & Waste Recording | API untuk mencatat by-product dan waste | Recording functional, accurate calculation | 8 | BE1 |
| 2.4.7 | Production Order Status Management | Manajemen status PO | Status tracking complete, audit trail | 5 | BE2 |

### C.4. WBS 2.5: Production Costing Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria | Estimasi (SP) | Owner |
| --- | --- | --- | --- | --- | --- |
| 2.5.1 | Cost Calculation Engine | Engine untuk menghitung biaya produksi | Calculation ≤5 detik, accurate | 13 | BE1, BE2 |
| 2.5.2 | Material/Labor/Machine Cost | Perhitungan biaya per komponen | Accurate calculation, integration with master data | 8 | BE2 |
| 2.5.3 | Overhead Cost Allocation | Alokasi overhead cost | Accurate allocation, configurable method | 8 | BE1 |
| 2.5.4 | Standard vs Actual Comparison | Perbandingan standar dan aktual | Accurate comparison, visual report | 13 | BE2 |
| 2.5.5 | Variance Analysis | Analisis variance biaya | Detailed variance breakdown, actionable insight | 8 | BE1 |

### C.5. WBS 2.6: Asset & Maintenance Domain

| Elemen WBS | Deskripsi | Deliverable | Acceptance Criteria | Estimasi (SP) | Owner |
| --- | --- | --- | --- | --- | --- |
| 2.6.1 | Asset Registration | API untuk mendaftarkan aset | Asset registration complete, unique code generation | 8 | BE1 |
| 2.6.2 | Maintenance Work Order CRUD | API untuk create, read, update, delete WO | 100% CRUD operations functional | 13 | BE2 |
| 2.6.3 | Maintenance Execution API | API untuk pelaksanaan maintenance | Execution recording complete, spare part stock update | 13 | BE1 |
| 2.6.4 | Downtime Recording API | API untuk mencatat downtime | Accurate recording, MTBF/MTTR update | 8 | BE1 |
| 2.6.5 | OEE Calculation Engine | Engine untuk menghitung OEE | Accurate calculation, visualization | 13 | BE2 |
| 2.6.6 | Spare Part Inventory API | API untuk mengelola spare part | Stock management complete, reorder alert | 8 | BE1 |
| 2.6.7 | Asset Performance Metrics | API untuk MTBF/MTTR | Accurate calculation, historical tracking | 5 | BE2 |

## LAMPIRAN D: CHANGE REQUEST FORM

text

CHANGE REQUEST

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

CR NUMBER: CR-XXXX

TANGGAL: XX/XX/XXXX

DIAJUKAN OLEH: [Nama]

PERAN: [Peran]

A. INFORMASI PERUBAHAN

================================================================================

Jenis Perubahan:

[ ] Scope  [ ] Schedule  [ ] Cost  [ ] Quality  [ ] Lainnya

Prioritas:

[ ] Low  [ ] Medium  [ ] High  [ ] Critical

Deskripsi Perubahan:

[Deskripsi detail perubahan yang diusulkan]

Justifikasi:

[Alasan mengapa perubahan ini diperlukan]

B. ANALISIS DAMPAK

================================================================================

Dampak terhadap Lingkup:

[Dampak terhadap scope proyek]

Dampak terhadap Jadwal:

[Dampak terhadap timeline proyek]

Dampak terhadap Biaya:

[Dampak terhadap budget proyek]

Dampak terhadap Kualitas:

[Dampak terhadap quality deliverables]

Dampak terhadap Risiko:

[Risiko baru atau risiko yang berubah]

C. REKOMENDASI

================================================================================

Rekomendasi: [ ] Approve  [ ] Reject  [ ] Defer

Catatan Rekomendasi:

D. KEPUTUSAN

================================================================================

Keputusan: [ ] Approved  [ ] Rejected  [ ] Deferred

Alasan Keputusan:

Disetujui Oleh: ___________________  Tanggal: ____________

================================================================================

CCB Members:

1. Project Manager:

2. Tech Lead:

3. Business Analyst:

4. QA Lead:

5. Program Manager:

================================================================================

## LAMPIRAN E: STATUS REPORT TEMPLATE

text

STATUS REPORT

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

REPORT PERIODE: [Tanggal - Tanggal]

SPRINT: [Sprint X]

DISUSUN OLEH: [Nama PM]

TANGGAL: [Tanggal]

1. EXECUTIVE SUMMARY

================================================================================

Status: [🟢 On Track / 🟡 At Risk / 🔴 Off Track]

Sprint Progress: [X% complete]

Overall Project Progress: [X% complete]

2. ACHIEVEMENTS

================================================================================

✅ [Item 1]

✅ [Item 2]

✅ [Item 3]

3. KEY METRICS

================================================================================

• Planned vs Actual: [X%]

• Velocity: [X SP]

• SPI: [X.XX]

• CPI: [X.XX]

• Defect Density: [X per 100 LOC]

• Code Coverage: [X%]

4. SPRINT BACKLOG STATUS

================================================================================

| Story | Status | SP | Owner |

|-------|--------|----|-------|

|       |        |    |       |

|       |        |    |       |

5. CHALLENGES / BLOCKERS

================================================================================

| No | Challenge | Impact | Action | Owner | Status |

|----|-----------|--------|--------|-------|--------|

| 1  |           |        |        |       |        |

| 2  |           |        |        |       |        |

6. INTEGRATION STATUS

================================================================================

| Integration | Status | Issues | Action |

|-------------|--------|--------|--------|

| P-FNE-03    | 🟢     | -      | -      |

| P-FNE-06    | 🟡     | API delay | Meeting with team |

7. RISKS

================================================================================

| Risk | Probability | Impact | Mitigation | Status |

|------|-------------|--------|------------|--------|

|      |             |        |            |        |

8. NEXT STEPS

================================================================================

• [Action 1]

• [Action 2]

• [Action 3]

================================================================================

Reported by: [Nama PM]

Approved by: [Nama Program Manager]

================================================================================

## LAMPIRAN F: ACCEPTANCE SIGN-OFF FORM

text

ACCEPTANCE SIGN-OFF FORM

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

Project: P-FNE-04 Production & Manufacturing

Sprint: [Sprint X]

Feature/Module: [Feature Name]

Date: [Date]

A. FEATURE DETAILS

================================================================================

Feature ID: [Feature ID]

Feature Name: [Feature Name]

Description: [Description]

Module: [Module Name]

B. ACCEPTANCE CRITERIA CHECKLIST

================================================================================

| No | Criteria | Status | Notes |

|----|----------|--------|-------|

| 1  |          | [ ]    |       |

| 2  |          | [ ]    |       |

| 3  |          | [ ]    |       |

| 4  |          | [ ]    |       |

| 5  |          | [ ]    |       |

C. TESTING SUMMARY

================================================================================

• Unit Tests: [X] passed, [X] failed

• Integration Tests: [X] passed, [X] failed

• UAT Tests: [X] passed, [X] failed

• Performance Tests: [X] passed, [X] failed

• Security Tests: [X] passed, [X] failed

D. KNOWN ISSUES

================================================================================

| No | Issue | Severity | Status | Action |

|----|-------|----------|--------|--------|

| 1  |       |          |        |        |

| 2  |       |          |        |        |

E. SIGN-OFF

================================================================================

User: [Name] - [Role] - [Signature] - [Date]

QA: [Name] - [Role] - [Signature] - [Date]

PM: [Name] - [Role] - [Signature] - [Date]

## LAMPIRAN G: LESSONS LEARNED TEMPLATE

text

LESSONS LEARNED

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

DATE: [Date]

FACILITATOR: [Name]

PARTICIPANTS: [List]

1. WHAT WENT WELL

================================================================================

[Item 1]

[Item 2]

[Item 3]

2. WHAT DID NOT GO WELL

================================================================================

[Item 1]

[Item 2]

[Item 3]

3. WHAT COULD BE IMPROVED

================================================================================

[Item 1]

[Item 2]

[Item 3]

4. RECOMMENDATIONS FOR FUTURE PROJECTS

================================================================================

[Item 1]

[Item 2]

[Item 3]

5. ACTION ITEMS

================================================================================

| No | Action Item | Owner | Due Date | Status |

|----|-------------|-------|----------|--------|

| 1  |             |       |          |        |

| 2  |             |       |          |        |

| 3  |             |       |          |        |

================================================================================

Documented by: [Name]

Approved by: [Name]

================================================================================

## LAMPIRAN H: PROJECT CLOSURE CHECKLIST

text

PROJECT CLOSURE CHECKLIST

PROYEK P-FNE-04: PRODUCTION & MANUFACTURING

================================================================================

PROJECT: P-FNE-04: Production & Manufacturing

DATE: [Date]

OWNER: [PM Name]

A. ADMINISTRATIVE CLOSURE

================================================================================

| No | Activity | Status | Date | Owner |

|----|----------|--------|------|-------|

| 1  | Finalisasi dokumentasi proyek | [ ] | | |

| 2  | Arsipkan semua dokumen proyek | [ ] | | |

| 3  | Closure meeting dengan stakeholder | [ ] | | |

| 4  | Final status report | [ ] | | |

| 5  | Lessons learned document | [ ] | | |

B. FINANCIAL CLOSURE

================================================================================

| No | Activity | Status | Date | Owner |

|----|----------|--------|------|-------|

| 6  | Final budget reconciliation | [ ] | | |

| 7  | Close semua purchase order | [ ] | | |

| 8  | Final invoice dan payment | [ ] | | |

C. TECHNICAL CLOSURE

================================================================================

| No | Activity | Status | Date | Owner |

|----|----------|--------|------|-------|

| 9  | Code freeze dan tagging | [ ] | | |

| 10 | Final security audit | [ ] | | |

| 11 | Performance verification | [ ] | | |

| 12 | Backup dan archive data | [ ] | | |

D. HANDOVER

================================================================================

| No | Activity | Status | Date | Owner |

|----|----------|--------|------|-------|

| 13 | Handover ke support team | [ ] | | |

| 14 | User training completion | [ ] | | |

| 15 | User manual delivery | [ ] | | |

E. TEAM CLOSURE

================================================================================

| No | Activity | Status | Date | Owner |

|----|----------|--------|------|-------|

| 16 | Team performance review | [ ] | | |

| 17 | Release team members | [ ] | | |

================================================================================

CLOSURE APPROVAL

================================================================================

Project Manager: [Name] - [Signature] - [Date]

Program Manager: [Name] - [Signature] - [Date]

Sponsor: [Name] - [Signature] - [Date]

================================================================================

## LAMPIRAN I: REFERENSI DOKUMEN

| No | Nama Dokumen | Kode | Lokasi |
| --- | --- | --- | --- |
| 1 | Arsitektur Super ERP Farm Nation Enterprise | ARCH-FNE-001 | Confluence |
| 2 | Spesifikasi Kebutuhan P-FNE-04 | SRS-FNE-004 | Confluence |
| 3 | Database Design Document | DB-FNE-004 | Confluence |
| 4 | API Specification (OpenAPI) | API-FNE-004 | GitLab/Swagger |
| 5 | UI/UX Design Prototype | UX-FNE-004 | Figma |
| 6 | Test Strategy Document | QA-FNE-004 | Confluence |
| 7 | Deployment Guide | DEV-FNE-004 | Confluence |
| 8 | User Manual | UM-FNE-004 | Confluence/PDF |
| 9 | Technical Documentation | TECH-FNE-004 | Confluence |

## LAMPIRAN J: APPROVAL SIGN-OFF

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor (CEO) |  |  |  |

Demikian Lampiran dari Project Management Plan Proyek P-FNE-04: Production & Manufacturing.

# PENUTUP

Dokumen Project Management Plan (PMP) untuk Proyek P-FNE-04: Production & Manufacturing telah disusun secara lengkap dengan 11 bab utama dan 10 lampiran pendukung. Dokumen ini mencakup seluruh area manajemen proyek sesuai standar PMBOK dan menjadi acuan utama bagi seluruh tim proyek dalam pelaksanaan proyek.

RINGKASAN PROYEK:

| Aspek | Keterangan |
| --- | --- |
| Nama Proyek | P-FNE-04: Production & Manufacturing |
| Durasi | 6 Bulan (Oktober 2026 - Maret 2027) |
| Anggaran | Rp 5.006.400.000 |
| Tim | 8-12 orang |
| Metodologi | Agile Scrum (12 sprint) |
| Platform | Web Portal, Mobile App, Executive Dashboard |

DOKUMEN INI TELAH DISETUJUI DAN DITANDATANGANI OLEH:

| Jabatan | Nama | Tanda Tangan | Tanggal |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| Sponsor |  |  |  |